| WORLD METEOROLOGICAL ORGANIZATION __________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION CIMO MANAGEMENT GROUP Ninth Session Geneva, Switzerland 5 - 8 April 2011 |  | CIMO/MG-9/Doc. 4.3(5) (15.III.2011) _______ ITEM: 4.3 Original: ENGLISH |
| --- | --- | --- |

# OPAG CAPACITY BUILDING

# Workplan for the Theme Leader on Surface-based Instrument Performance Monitoring

(Submitted by PEI Chong)

Summary and purpose of document This document provides the proposed workplan for the Theme Leader on Surface-based Instrument Performance Monitoring developed by PEI Chong.

# Action proposed

The Meeting is invited to review the draft work and make a necessary change taking into account CIMO priorities before approving it.

________________

# DRAFT WORKPLAN

C5: CIMO Theme Leader on Surface-based Instrument Performance Monitoring

(2011-2014)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Establishment of a working group on surface-based instrument performance monitoring from members of WMO | PEI Chong | to develop Terms of Reference, tasks, objectives and draft work plans of the working group to establish a working group (composed of about 5 experts) on surface-based instrument performance monitoring from members of WMO | Terms of reference of the working group submitted to CIMO MG Identification of experts | 2012 |  |  |
| 2. | Development of basic requirements and configuration for Real-time monitoring of surface-based operational instrument performances. | PEI Chong | to develop a framework of guidance on how to conduct the monitoring, including requirements and structure for the basic information systems etc | Document identifying requirements and proposal of basic structure (methods, criteria, standards and procedures) for the monitoring system (possibly to be published as IOM report) | 2013 |  |  |
| 3. | Development of working mechanisms between the monitoring system and other Capacity Building facilities, such as Regional Instrument Centers, etc | PEI Chong | to exchange experiences among Members, especially with RICs, through expert visits, workshops, etc. to verify requirements and structures for the basic monitoring system. | Document with comments and suggestions on strengthening Capacity Building inputs to Technical Documents | 2013 2014 |  |  |
| 4. | Follow-up on identified performance issues | PEI Chong | to liaison with CIMO and HMEI on instrument performance and development | Reports to CIMO-MG, HMEI and relevant Members | 2014 |  |  |