## Slide 1: WMO SPICE Caribou Creek (Canada)
Site Configuration Update
Oct 10, 2012
Information from Craig Smith
Prepared by Rodica Nitu

## Slide 2: Caribou Creek: Site Layout
Distance between instruments: 10 m

## Slide 3: Caribou Creek: References
R2 reference:
  DFIR fence;
  Geonor 600 mm, 3 transducers + CRN heating + single Alter;
  DRD11
  Sampling Frequency: 6 seconds (1500 cycles)
R3 reference:
  Geonor 600 mm, 3 transducers + CRN heating + single Alter;
  Geonor 600 mm, 3 transducers + CRN heating + no shield;
  DRD11 (the same instrument as for the R2)
  Sampling frequency: 6 seconds (1500 cycles)

## Slide 4: Caribou Creek: Instruments Under Test
Instrument Type | Instrument Make and Model | Configuration |  | Number of instruments in the same configuration
 |  | Shield type (if applicable) | Other configuration information | 
Weighing Gauge | Geonor T-200B3 | Bush\Single Alter | Heated | 1
Weighing Gauge | Geonor T-200B3 1500mm* | Single Alter | Heated | 1
Weighing Gauge | Pluvio2 | Bush\Single Alter | Heated | 1

## Slide 5: Caribou Creek: Ancillary Measurements
Parameter | Instruments Used | Data available | Reporting Interval
Air Temperature | Scientific HMP45, 1.5 m | ASCII | 1-minute
Relative Humidity | Scientific HMP45C, 1.5m | ASCII | 1-minute
Atmospheric Pressure | Campbell Scientific, CS105, surface pressure | ACII | 1-minute
Wind Speed 6 m | RMY 05103 | ASCII | 1-minute
Wind Direction 6 m | As above | ASCII | 1-minute
Wind Speed at the gauge orifice (specify height) | MetOne 014A, 2m MetOne 014A, 3m | ASCII | 1-minute
Precipitation Detector (Y/N output) | Vaisala DRD11A | ASCII | 1-minute
Precipitation type | Parsivel | ASCII | 1-minute
Snow Depth | Scientific SR50, 2m | ASCII | 1-minute

## Slide 6: Caribou Creek: Site Commissioning
Anticipated date of commissioning: December 1, 2012
Expected status on commissioning:
References (where applicable):
  R0’: Weighing Gauges in the bush area
  R2: November 15, 2012; DFIR is nearly complete, instrument mounts need to be finished and gauge needs to be installed and tested
  R3: November 15, 2012; gauges and heaters need to be installed and tested
Instruments under test:
  Provided by the host: Nov 15, 2012; installed Bush gauge needs to be heated, 2nd Bush gauge needs to be installed
  From Instrument Providers: Nov 30, 2012; shipping of gauges has been delayed, expected arrival mid- to late-October; if we get an early onset of cold temperatures, installation may not be possible before Spring 2013.
Instruments for Ancillary Measurements: unknown;
  have a learning process to go through for some of this instrumentation and some technical issues to resolve with installing some instrumentation on site. It is probable that some of this instrumentation will not be installed prior to Summer 2013.
Expected status on Nov 15th:
  50-75% functional.
  Real-time communications may not be completely functional before Nov 15.
  Data flow protocols remain to be put in place.

## Slide 7: Caribou Creek: Site Update
Gaps for the winter 2012/2013:
  the intended SPICE test/activities which may not take place, as anticipated during the 2012/13 season; gauge intercomparisons of instruments provided by instrument manufacturers
  reasons: late shipping, no time for testing before onset of cold temperatures
  activities postponed for 2013: intercomparisons of instruments provided by manufacturers, extensive testing (with all ancillary instrumentation functioning properly) of reference intercomparisons.
Data archive;
  Existing or planned: Data archiving at this site is still in the planning stage as communications at this site have not yet been installed. We are hoping to use protocols established during previous research projects but equipment still needs to be installed and tested and protocols put into place
  Frequency of data transmission from the site to an archive (if any): unkown, probably daily but could be more frequent, archiving onsite will take place.
Have you sent data to NCAR for pre-SPICE? (new site, data not yet available)
  Do you have to change data format for transfer to NCAR: yes
  How difficult is the process? Not difficult but will take time
  Any risks if format is changed: Not if done correctly
  Which is the reasonable frequency of data transfer to NCAR/SPICE archive to be expected during the experiment: Daily
Additional Information:
  This is a new site and as of October 1st, installation is only about 50% completed.
  Because of the time of year, bad weather could delay the completion of installation into Spring 2013.
  It would have been desirable to have 2 months of warm season testing of new, repaired, and updated instrumentation prior to commissioning this site. This will not be possible before the start of the project.
  It is anticipated that some issues will not be resolved until Spring of 2013. Because of winter conditions at this site, it will be difficult to install instrumentation or diagnose problems after the onset of winter. This applies to both gauges under test and ancillary instrumentation. Access to the site will become more difficult after snowfall.