| No. | ToR | Task Description | Person Responsible | Action | Deliverables / Outcome | Commence | Deadline for Delivery | Status (%) | Comments | 2013 Budget Expend | 2014 Budget Estimate | 2015 Budget Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | (a) | Coordinate with CBS ET-ABO on Work Plan & Budget | Ch-TT-AO, SO/ARO | Rep. of TT to attend ET-ABO meetings; Work Plan & Budget for 2014-15 to be compiled & approved. Regular Work Plan WebEx sessions to be held. | Harmonised Work Plan & Budget for the ABO Program. Report to TT-AO | Q3 2013 | Ongoing | 50 | May require TF funding for member of TT to attend ET-ABO-1 Chair attended ET-ABO-1 | 2.1K |  | 2.3K |
| 2 | (a) | Meeting of TT-AO | Ch-TT-AO, SO/ARO | Meeting of TT-AO, Feb 2014 | Work Program advanced; Report to CIMO | Q3 2013 | Q3 2014 | 10 | Meeting to be held 18-20 Feb 2014. |  | 15K |  |
| 3 | (b) | Investigate AMDAR Temperature Bias | S.d.Haan | Review of relevant reference material Consultation with avionics/sensor experts | Report to TT-AO and CIMO | Q1 2014 | TBD | 5 | May require funding to complete a study on onboard issues, such as deicing. Ref: WMO AMDAR Panel Aircraft Observing System Data Management Workshop, Section 5.1, |  |  |  |
| 4 | (b) | AMDAR and water vapor measurement (WVM) integration into existing avionics and airframes | A.Hoff, SO/ARO | Drafting and review of plan. Finalise plan as part of the ABOP Strategy & Implementation Plan (A-SIP) | Strategic Plan | 2012 | Q2 2014 | 25 | This needs to be harmonized with the the A-SIP. Ref: WMO AMDAR Panel Session 15 Fin. Rep. 4.2.1. Incorporate: Ownership of STCs Collaboration on STC costs Integration into airframes AMDAR Software requirements |  |  |  |
| 5 | (b) | AMDAR and water vapor measurement (WVM) as standard accessory on commercial aircraft | A. Hoff | Drafting and review of plan. Finalise plan as part of the ABOP Strategy & Implementation Plan (A-SiP) | Strategic Plan | 2012 | Q4 2014 | 10 | Incorporate: Formulation of IP into WMO Project in collaboration with ICAO Ref: WMO AMDAR Panel Session 15 Fin. Rep 4.2.1. |  |  |  |
| 6 | (b) | Turbulence (EDR ) Implement. in AMDAR - Develop IP for EDR | G Meymaris, TT-AO as required | Drafting and review of plan. Teleconferencing of collaborators. Liaise with NCAR on software requirements; Identify possible airline partner for trial. | EDR IP | Q3 2013 | Q2 2014 | 10 | Possibly include: A trial program with a European airline (the E-AMDAR Team are discussing possibility with Air France). Ref: WMO AMDAR Panel Session 15 Fin. Rep 4.2.2. |  |  |  |
| 7 | (b) | Review & approve EDR spec. in AMDAR Onboard Software Functional Requirements Specification (AOSFRS) | S.Taylor, A.Hoff, G.Fournier, J.Xu | Review EDR algorithms within the AOSFRS. | EDR spec. in AOSFRS | Q1 2013 | Q3 2013 | 100 | Linked to Task 9. AOSFRS pub. as IOM Report 114. |  |  |  |
| 8 | (b) | Study on Current & Future Comms & Technology Impact on AMDAR | SO/ARO, S.Taylor | Write Statement of Work Identify consultants SSA in place Monitor progress | Study and recommendations produced | Q3 2013 | 2014 | 0 | Ref: WMO AMDAR Panel Session 15 Fin. Rep 4.3.2. | 0K (15K) | 35K |  |
| 9 | (c) | Finalise and publish AOSFRS | S.Taylor, A.Hoff, G.Fournier, J.Xu | Conduct final review of AOSFRS; Publish AOSFRS as approp. | AOSFRS Published | 2012 | Q2 2013 | 100 | In combination with ET-ABO; Final review of spec.; Publication of spec; AOSFRS pub. as IOM Report 114? | 22.7K (23K) |  |  |
| 10 | (c) | Approach to avionics manufac. re AOSFRS implem. | S.Taylor, SO/ARO | Approach Teledyne Controls re AOSFRS implementation; Approach other avionics vendors | Integration of AMDAR into avionics systems. | Q3 2013 | Q4 2014 | 10 | Work towards availability of AMDAR software as a catalogue item of delivery for avionics systems. |  |  |  |
| 11 | (c) | Boeing 777 AMDR Software Dev. | Ch-TT-AO, Ch/ET-ABO, SO/ARO, | Finalise negotiations with AFR and KLM in consult. with E-AMDAR & Meteo-France Review quotation; Provide advice on specifications and requirements. | B777 AMDAR Software application | 2012 | Q4 2014 (delayed – next AFR-KLM meeting to be finalized) | 20 | Combined action with ET-ABO Project has been delayed Ref: WMO AMDAR Panel Session 15 Fin. Rep 4.4.7. | 0K (20K) | 20K |  |
| 12 | (c) | Develop and specify standard for AMDAR Data Optimisation System | S.Taylor, A Hoff | Determine requirements (consult with FPs); Draft specification; Conduct review; Publish spec. | Addition to CIMO Guide (spec of ADOS). | Q3 2013 | Q4 2014 | 0 | The aim is to develop a functional specification that can be included in the Manual on WIGOS or in CIMO Guide |  |  |  |
| 13 | (d) | Monitor & Review reports from WVSS testing | A.Hoff | Review reports. Report to TT-AO-1 | Report to CIMO | Q3 2013 | Q4 2013 | Ong. | Ref: WMO AMDAR Panel Session 15 Fin. Rep 4.2.1. |  |  |  |
| 14 | (d) | Monitor & report on impact assessment results of TAMDAR humidity & other parameters by UKMO | G.Fournier, G Meymaris | Review reports and analyse results. Report to TT-AO-1 | Report to CIMO | Q3 2013 | Q4 2014 | 0 |  |  |  |  |
| 15 | (e) | Develop plans for AMDAR & WVSS inter-comparison | S.d.Haan | Determine requirements; Analyse options; Draft Plan. | WVSS Inter-comparisons Plan | Q4 2013 | Q1 2014 | 0 |  |  |  |  |
| 16 | (e) | Prepare a paper on the status of WVSS-II validation | B. Ford & Collaborators | Prepare outline and scope Identify contributors Research and draft Review Publish | IOM Report | Q3 2013 | Q2 2014 | 50 | Provide a summary on all scientific and operational aspects of the WVSS-II sensor and prepare a paper to be published as an IOM report. |  |  |  |
| 17 | (f) | Review & Update Aircraft-based Obs Reg. Mat. In CIMO Guide | G.Fournier, J.Xu S.Taylor, SO/ARO | Review current status of material and identify requirements for update; Coordinate & undertake update; Review and complete; Provide to WMO Reg. Mat. Board. | CIMO Guide on Aicraft-based Observations updated. | Q1 2014 | Q4 2014 | 90 | Chapter has been submitted to CIMO Ed. Board |  |  |  |
| 18 | (g) | Attend meetings of relevance to AMDAR Technical Dev. | TT-AO, SO/ARO |  | Meetings attended. Reports produced for CIMO and Secretariat | Q2 2013 | Ongoing | N/A | This may include: Meeting with avionics vendors; Others. SO/ARO & S.Taylor to meet Dec in Offenbach for Task 19. | 2.5K(est) (15K) | 15K | 15K |
| 19 | (c) | Update of AEEC ARINC 620 Specification | S.Taylor, SO/ARO, A. Hoff | Work with AEEC DataLink Systems Sub-Committee to updated the Met. Report in the ARINC 620 standard to version 6. | Met. Report V6 defined in the AEEC ARINC 620 spec. | Q4 2013 | Q4 2014 | 20 | Will require travel support for work team and to attend AEEC meetings | See Item 18 (Cost of Dec 17/18th meeting) | Item 18 | Item 18 |

# TASK TEAM ON AIRCRAFT-BASED OBSERVATIONS, TT-AO, Terms of Reference

- Develop and manage the workplan and associated activities of the TT-AO, as well as the budget for the corresponding expenditure of the AMDAR Trust Fund in line with the Trust Fund’s Terms of Reference, in collaboration with CBS ET-Aircraft-Based Observations;

- Oversee the scientific and technical development and maintenance of aircraft-based observing systems, from a point of view of instruments and methods of observation, and inform the Commission of latest developments;

- Work closely with ET-A1 in conducting the development and maintenance of technical standards associated with aircraft-based observations, and provision of related specifications to meet user requirements; and,

- Provide the technical review of approved aircraft-based humidity capabilities,

- Liaise closely with ET-A3 for testing and validation of the AMDAR system and aircraft based humidity sensors.

- Provide input for updates of the CIMO Guide relevant to aircraft-based observations, including identification of standards for inclusion in the CIMO Guide and other WMO regulatory documents

- Assist and provide support for training and outreach activities to support the use of aircraft-based observations

# Footnotes

AMDAR Onboard Software Functional Requirements Specification, see : WMO AMDAR Panel Session 15 Fin. Rep 4.4.7.