| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION TASK TEAM ON REVISION OF THE INTERNATIONAL CLOUD ATLAS (TT-ICA) Geneva, Switzerland, 18-22 November 2013 | CIMO/TT-ICA/Doc. 12(2) (08.XI.2013) _________ ITEM: 12.2 Original: ENGLISH ONLY |
| --- | --- |

REVIEW OF TERMS OF REFERENCE AND REFINEMENT OF WORK PLAN

Work Plan of WMO CIMO Task Team on Revision of the International Cloud Atlas

(Submitted by the Secretariat)

Summary and purpose of document This document provides information on the revised draft Work Plan of WMO CIMO Task Team on Revision of the International Cloud Atlas

Action proposed

The Meeting is invited to take into account the information provided in the document when discussing the relevant agenda items

________________

(Revised 08 August 2013)

WorkPlan of WMO CIMO Task Team on Revision of the International Cloud Atlas

(2013)

| No. | Task description | Person responsible | Action | Deliverable | Deadline for deliv. | Status [%] | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Review the current ICA, in its digital form. Assess its current suitability, or shortcomings as a web-based ICA. Consider desirable features if revised (e.g. modular design, structures that facilitate multiple uses, etc.) | ELIANE, plus ALL participate; (CA experts, ETR, ITD, Pubs, …) | Fast-start: Brainstorm as a smaller group (email) Lead TT discussion Summarize findings Revise short report in the light of outcomes of Tasks 3 and 4 | Dot point list of options Dot point list of preferences Prelim short report on requirements. Revised report on requirements. | 22 Aug 2013 22 Aug 2013 28 Aug 2013 30 Oct 2013 |  | ToR 1 Webex 2: 22 Aug Action 4 a joint effort between sub-groups 1, 3, 4 |
| 2. | Ascertain the suitability / need for revision of the graphical decision aid currently contained in Vol. I, Part II (II.8.3) (page 97-102 of Vol 1.) | COLLEEN (lead) ERNEST, MIKE, ELIANE, MARINES, and others | Discuss current suitability. Brainstorm possible improvements. Prepare short report on recommendations. Lead TT discussion. Revise short report in light of TT discussion | Short report on recommendations | 22 Aug 2013 22 Aug 2013 4 Sep 2013 4 Sep 2013 11 Sep 2013 |  | ToR 2 Involvement of WMO ETR specialists? Webex 3: 4 Sep |
| 3. | Survey WMO Members on their requirements for revision of the ICA (basic needs, desired features) | ERNEST plus CLAIRE/SYLVIE, COLLEEN, (help from WMO/CIMO/CPA area) | Fast-start: discuss and summarize objectives and questions. Lead TT discussion Prepare and release survey Collect and analyze results Prepare report on Member requirements Lead TT discussion Finalize report | List of key items of info to be obtained. Finalized survey Short report on Member requirements | 22 Aug 2013 22 Aug 2013 4 Sep 2013 9 Oct 2013 16 Oct 2013 16 Oct 2013 23 Oct 2013 |  | ToR 4 Entrain survey expertise at WMO/HQ (CPA? CIMO?) Webex 2: 22 Aug Webex 3: 4 Sep Include question on need for additional/new cloud types. (T5) Webex 5: 16 Oct Include question on need for more imagery. (T5) |
| 4. | Perform a web-survey of alternative existing (web-based) forms of cloud atlas, and briefly summarize their key features, strengths and weaknesses. | MIKE. JIM, IGOR, (input encouraged from ALL) familiarity with what is required in an ICA. | Perform survey Prepare short report Lead TT discussion Revise short report in light of TT discussion | Draft short report on findings and recommendations Finalized short report on findings and recommendations | 11 Sep 2013 18 Sep 2013 18 Sep 2013 25 Sep 2013 |  | ToR 3 Webex 4: 18 Sep May result in recommending particular external experts (web site authors) be coopted for 2014 work. |
| 5. | Specify meta-data and design a template to describe each cloud image i. Specify the metadata that should accompany each image in a new CA. ii. Design a template for an individual cloud image (format, accompanying description, metadata, etc) | JIM, GEORGE, MIKE (+input from Tasks 3 and 4 | Discuss requirements Prepare short report on requirements Lead TT discussion Finalize report on requirements for metadata Design template | Draft report on metadata reqs and ICA Image template. Final report on metadata reqs and ICA Image template. | 11 Sep 2013 18 Sep 2013 18 Sep 2013 30 Oct 2013 30 Oct 2013 |  | ToR 5c/d Use reports from T3 and T4 as input. Webex 4: 18 Sep Template design will require involvement of CPA, ITD, Pubs. May be better left to next TT. |
| 6. | Assess opportunities for enhancement of the WMO Cloud Atlas afforded by publication in digital form: a) determine the need for additional new cloud classifications to be included in the CA (such as asperatus and anthropo- ) and the feasibility of reporting these. b) assess opportunities afforded for inclusion of more imagery, allowance for clouds appearing differently, etc. | GEORGE, COLLEEN, ERNEST, MIKE, MARINES | Initial discussion of each topic (a and b). Await survey results and prepare paper with discussion and recommendations each topic. Lead TT discussion Finalize report | Short paper on considerations and preliminary conclusions/recommendations. Short report on TT recommendations. | 16 Oct 2013 30 Oct 2013 30 Oct 2013 06 Nov 2013 |  | ToR 5a/b Webex 6: 30 Oct |
| 7. | Report on activity | STEVE plus ALL members | Prepare a project proposal for follow-on work (include resource requirements and timeline) Prepare draft final report of the TT once all Tasks are complete. Discuss and refine report Finalize report and submit to CIMO MG | Final report delivered to CIMO MG | 13 Nov 2013 22 Nov 2013 31 Jan 2014 |  | ToR 6 TT meeting in Geneva tentatively planned for 18-22 Nov 2013. Deadline for submission of input documents to CIMO MG expected to be 31 January 2014. |