WORK PLAN (updated)

Expert Team on Meteorological Radiation and Atmospheric Composition Measurements

(2003-2006)

| No. | Task description | Person responsible | Action | Deadline | Deliverables | Deadline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Facilitate further activities related to meteorological radiation measurements: |  |  |  |  |  |
| 1 a) | IPC-X, 2005, WRC, Switzerland | I. RÜEDI W. FINSTERLE in co-operation with the ad hoc group of the IPC | Assist in the preparations and participate in the IPC-X Analyze results of IPC-X | Jan. 04 Dec. 05 | Concept for IPC-X comparison Published results of the IPC-X | Sep. 04 Feb. 06 |
| 1 b) | RPCs, 2004-2006, either in conjunction with IPC-X or at RPCs concerned | I. RÜEDI W. FINSTERLE in co-operation with the ad hoc group of the IPC | Assist in the preparations and participate in the RPCs Analyze results of RPCs | Jan. 04 Jan. 06 | Concept for RPC comparisons Published results of the RPC comparisons | Sep. 04 Feb. 06 |
| 1 c) | Liaise with the World Climate Research Programme on matters related to Baseline Surface Radiation Network and inform Members of developments | K. BEHRENS | Identify the role of CIMO in further development of BSRN Liaise with WCRP on identified matters | Jan. 06 Jan. 06 | Report to Members on BSRN | May 06 |
| 1 d) | Review the operational practice associated with total ozone measurements | O. M. BARTUREN | Study of present and emerging technologies to determine the mot suitable method maintaining long-term, cost-effective, total ozone measurements | Jan. 06 | IOM Report on Recommendations for a standard automated ozone observational site | May 06 |
| 1 e) | Review operational practice associated with UV and, aerosol optical depth measurements | UV: L.J.B. McARTHUR Aerosol: K. BEHRENS | Develop recommendations for practices associated with UV and, aerosol optical depth measurements | Jan. 06 | IOM Report on Recommendations for operational practice associated with UV and, aerosol optical depth measurements | May 06 |
| 1 f) | Monitor the efforts of the CAS Scientific Steering Committee on UV Measurements | L.J. B. McARTHUR J. GRÖBNER | Collaborate with CAS on matters related to UV Measurements | Jan. 06 | Report to Members | May 06 |
| 1 g) | Update the CIMO Guide | All members | Develop proposals for update of Ch 7, "Measurement of radiation", of the CIMO Guide | Jan. 06 | Updated Ch 7, "Measurement of radiation", of the CIMO Guide | May 06 |
| 1 h) | Develop further the establishment of a World Standard Group of absolute long-wave radiometers | W. SCHMUTZ & N. FOX (Representatives of BIPM) | Collaborate with PMOD/WRC on the establishment of a World Standard Group of absolute long-wave radiometers | Jan. 05 | A World Standard Group of absolute long-wave radiometers established | Mar.06 |
| 1 i) | Coordinate the dissemination of World Radiometric Reference (WRR) factors to regional and national radiation standards | W. SCHMUTZ & N. FOX (Representatives of BIPM) | Develop proposal for the dissemination of IR factors to regional and national radiation standards | Jan. 06 | Report to Members | May 06 |
| 1 j) | Provide technical/scientific guidance in the establishment and continuing quality assurance of WIRCC Davos | W. SCHMUTZ & N. FOX (Representatives of BIPM) | Collaborate with PMOD/WRC on the establishment of a WIRCC | Jan. 06 | A World Infrared Radiometer Calibration Center established and QA guaranteed | May 06 |
| 1 k) | Initiate activities so that high quality solar radiation measurements may be widely guaranteed in all national radiation networks through training courses and in the establishment of networks in areas with a low density of radiation stations | A. TSVETKOV (Act. 1) W. FINSTERLE (Act. 2) | Review the quality of solar radiation measurements in national networks Assist NRC by developing proposals for improvements in quality of solar radiation measurements Develop proposal for training courses in solar radiation measurements | Jan. 06 Jan.06 Jan. 06 | IOM Report on the quality of solar radiation measurements Support provided and documented to National Radiation Centers (NRCs) Syllabus and lecture notes for training in solar radiation measurements | May 06 May 06 May 06 |