| WORLD METEOROLOGICAL ORGANIZATION _________________________ INTER-COMMISSION COORDINATION GROUP ON THE WMO INFORMATION SYSTEM SIXTH SESSION Seoul, Korea, 22-26 February 2009 |  | ICG-WIS VI/Doc. 4.3(1) (16.II.2010) ___________ ITEM 4.3 ENGLISH only |
| --- | --- | --- |

Progress Report from

Expert Team on WIS-GTS Communication Techniques and Structure (ET-CTS)

(Submitted by Hiroyuki ICHIJO and Remy GIRAUD)

Summary and Purpose of Document

This document is to report the progress status of ET-CTS including its working plan.

ACTION PROPOSED

The meeting is invited to review this report and make appropriate comments on further ET-CTS work.

Attachment :  ET-CTS Membership

- Working arrangement

  - Membership

The CBS designated Hiroyuki ICHIJO and Remy GIRAUD as co-chairpersons of ET-CTS at its Fourteenth session (Dubrovnik, 25 March–2 April 2009).  Subsequently, CBS Management Group approved 7 core members and 20 associate experts as team members.  The list of the members is shown in Attachment 1.

  - Key Deliverables and tasks

Four key deliverables are expected toward CBS-ext 2010.

- Confirm arrangements for consolidation of two IMTN clouds (migration of the current “cloud 1” to the RMDCN)  [Target : Oct 2009]

- Guidance on “push” and “pull” technologies for use in WIS (taking account of standards that have been developed for the web, such as RSS, ATOM), including recommendations on handling of high priority information to support hazard warning  [Target : May 2010]

- Publication for consultation on recommendations for changes to TCP/IP practices, including advice on adoption of IPv6  [Target : Jun 2010]

- Guidance on  administrative and contractual aspects of data communication services for WIS implementation  [Target : Jul 2010]

To achieve the deliverables, 20 tasks are allocated to task groups within the team.  Each task group consists of one or two task leader(s) and a few task members.

  - Tentative schedule

(1) mid-March 2010	:  Distribution of drafts developed by task groups within the ET-CTS

(2) late April 2010	:  Physical meeting of the ET-CTS and review of the drafts

(3) May 2010		:  Pre-coordination with other OPAG-ISS teams

(4) May to July 2010	:  Finalize the ET-CTS report including Recommendations

(5) July 2010		:  Submission of the report to ICT-ISS and ICG-WIS

(6) after CBS-ext.2010:  Start of another working cycle with refined TORs

- Progress of prioritized tasks

  - Confirmation of arrangements for consolidation of two IMTN clouds

All Frame Relay links on the Improved MTN (IMTN) Network I have migrated to MPLS links on the IMTN Network II by the end of 2009.  Currently all MTN circuits except ones in RAs I and III are operating on a single coordinate IMTN cloud using the MPLS network service under the extended contract of RMDCN in RA VI.

Figure 1 shows the evolutional migration of IMTN configuration.

  - Study of GISC network bandwidth requirements

(1)  Backgrounds

Since a WIS core network will be established on the IMTN, it is easy to realize the full-mesh GISC topology.  However it is expected that traffic on the WIS core network handled by GISCs will considerably increase. To support future-oriented WIS operation, network capacity of each GISC will have to be expanded in collaboration with others.

In connection with the issue, appropriate maximum number of GISCs has come up for discussion repeatedly since the initial stage called as FWIS:

[Extraction from the final report of CBS-ext.02, Annex IV]

Several (perhaps four to 10) centres would serve as GISCs. Each GISC would have a defined area of responsibility. GISCs would usually be located within or closely associated with a centre running a global data assimilation system or having some other global commitment, such as a WMC.

[Extraction from ET-CTS outcome reported to ICG-WIS-3 in 2006]

Correlation between the number of GISCs and reasonableness of full-mesh topology of a WIS core network: 	From the practical and relative evaluation, the full-mesh can be appropriate on the assumption that the number of GISCs would be less than 7 inclusive.  In case of more GISCs, the full-mesh should be avoided.

However 13 GISCs candidates have been identified as of the end of November 2009.

(2)  Tasks

In this situation, ET-CTS set a task group the following tasks:

[Main task]

Required GISC bandwidth on the core network should be considered carefully considering not only bulk but also peak traffic.  In addition, it is important to study smooth evolution process in gradual participation of operational GISCs.

[Additional task on a possible basis]

Further study is desired to clarify the appropriate maximum number of GISCs from the practical view of network bandwidth requirements.

(3)  Progress

The task group devised an unbalanced model on the assumption that GISC network topology is full-meshed on a unicast based core network to find out required GISC bandwidth practically.  The unbalanced model is to simulate the traffic condition that there is difference in data volume between incoming and outgoing, considering the pragmatic case of different data volumes from individual responsible areas.  The model is shown in Figure 2.

Furthermore the group developed a convenient tool for trial calculation for the bandwidth based on the unbalanced model.  The tool is able to calculate the required bandwidth corresponding to an input value of total daily traffic for global exchange, adjusting parameters such as protocol overhead, duplicated rate, the number of GISCs, unbalanced ratio, and operational upper limit.   The tool in spreadsheet form is available at

http://spreadsheets.google.com/ccc?key=0AsDEZG6XKnasdG9MNWlRYXUzeVJJRkJsWFppWlI0UEE&hl=fr

The sheet “Comments and History” is used for collecting comments and suggestions to improve the tool.

Practical required bandwidth will be found as long as the daily volume is accurately estimated.  It is expected that ET-OI will estimate the daily volumes at present and in five years.

Regarding the maximum number of GISCs, the group will challenge the issue to find an appropriate number from the practical view in the process of the study on the required bandwidth, but it will be on a possible basis.

|  | Incoming daily volume | Outgoing daily volume | Necessary port speed |
| --- | --- | --- | --- |
| GISC #1 | 3 GB | 15 GB | Bandwidth appropriate for 15 GB/day |
| GISC #2 | 7 GB | 3 GB | Bandwidth appropriate for 7 GB/day |
| GISC #3 | ditto | ditto | ditto |
| GISC #4 | ditto | ditto | ditto |

  - Investigation of blog technologies

Japan (JMA) has been investigating usability of blog-based technologies for notification of priority messages and also GISC synchronization of global data/products in cooperation with Brazil (INPE) and China (CMA).  The following items have already been tested.

- File synchronization like podcast using a pull-based protocol for getting web feed of Atom and RSS

- Notification of priority messages using a push-based protocol of the Atom Publishing Protocol (AtomPub) for posting blog

The following empirical outcome was reported at the ET-WISC meeting (Geneva, 2-5 Feb 2010).

- Blog technologies are not appropriate for WIS part A because it would be difficult to introduce sharply new technologies into the existing GTS.  Also the blog technologies would be not necessarily appropriate for GISC synchronization.  The reasons are as follows:

- The file synchronization has a polling delay;

- The notification of priority messages is not suitable for sending a lot of messages.

- On the other hand, they are very useful for WIS Part B. The reasons are as follows:

- The file synchronization enables data providers to provide unspecified number of users with data without managing data distribution tables;

- Posting priority message to data provider’s blog server enables data providers to publish the priority data to unspecified number of users, and the users can easily get the priority data by using feed reader;

- Combinations of increasing blog software and related services on the Internet enable data providers to bring the most value to users.

- The following usage are desirable:

- Data providers provide users with data on a near-real-time basis over the Internet;

- Data providers provide users with data at intervals over the Internet;

- Data providers receive a priority message from the GTS, and then post it to their blog server on the Internet;

- Timely delivery service can also be implemented by “pull” mechanism using the file synchronization of blog technologies.

Regarding the notification of priority message, there is a problem of the password sharing between poster and blog server owner.  Japan will continue the investigation to find a possible solution of the problem.

  - Development of a list of synchronisation protocols among GISCs

ET-CTS will develop a list of protocols for GISC synchronisation considering requirements from ET-WISC.

Attachment

ET-CTS Membership

| Family name | First name | Nominated by | RA | Membership function within CBS |
| --- | --- | --- | --- | --- |
| ICHIJO | Hiroyuki | Japan | II | Co-chair |
| GIRAUD | Remy | ECMWF | VI | Co-chair |
| AYINA | Hugues | ASECNA | I | core member |
| LANG | Hongliang | China | II | core member |
| GIANNI | Jose Luis | Argentina | III | core member |
| GAGNON | Jean-Francois | Canada | IV | core member |
| DARLING | Alan | USA | IV | core member |
| SENIOR | Ian | Australia | V | core member |
| GLASER | Ilona | Germany | VI | core member |
| ALDER | Kevin | New Zealand | V | Associate Expert |
| FAVENNEC | Erwan | France | VI | Associate Expert |
| JEFFERY | Duncan | UK | VI | Associate Expert |
| KARANJA | Henry N. | Kenya | I | Associate Expert |
| MACHUA | Samuel | Kenya | I | Associate Expert |
| OLOTU | Jane | Tanzania | I | Associate Expert |
| LEMKHENTER | Abderrazak | Morocco | I | Associate Expert |
| LEE | Okki | Korea Rep. | II | Associate Expert |
| TORSKY | Mikhail | Uzbekistan | II | Associate Expert |
| TSUNODA | Kenji | Japan | II | Associate Expert |
| HUSSAIN | Assif | Pakistan | II | Associate Expert |
| REZENDE | Jose Mauro | Brazil | III | Associate Expert |
| TUEL | Jason | USA | IV | Associate Expert |
| HODGE | Bryan | Australia | V | Associate Expert |
| MOLLOY | Geoffrey | Australia | V | Associate Expert |
| OKTAR | Cemal | Turkey | VI | Associate Expert |
| ALBAYRAK | Omer Hudai | Turkey | VI | Associate Expert |
| OSTATNICKY | Karel | Czech Rep. | VI | Associate Expert |
| AKHTIAMOV | Jalil | Russia F. | II,VI | Associate Expert |
| BEZROUK | Leonid | Russia F. | II,VI | Associate Expert |

# Text boxes

1GB

1GB

5GB

1GB

1GB

1GB

5GB

5GB

5GB

1GB

1GB

1GB

1GB

1GB

GISC #4

AMDCN #4

Responsible area #4

GISC #3

AMDCN #3

Responsible area #3

Figure 1  Evolutional migration of IMTN configuration

Network II

Moscow

New Delhi

Cairo

Brasilia

Offenbach

Algiers

Dakar

Toulouse

Prague

Jeddah

Network I

Washington

Nairobi

Beijing

Tokyo

Buenos Aires

Melbourne

Sofia

Exeter

1GB

GISC #2

AMDCN #2

Responsible area #2

5GB

GISC #1

AMDCN #1

Responsible area #1

WIS core network

(Full-meshed topology)

Figure 3  Test sites for blog-based technologies

Figure 2  Unbalanced model of 4 GISCs (example case of total daily volume of 8GB)