| WORLD METEOROLOGICAL ORGANIZATION _________________________ IMPLEMENTATION COORDINATION MEETING ON THE IMPROVED MAIN TELECOMMUNICATION NETWORK (CLOUD I) WASHINGTON, 27-29 NOVEMBER 2007 |  | ICM-IMTN (CLOUD I)/Doc. 2.3(1) (10.XI.2007) ____________ ITEM 2.3 ENGLISH only |
| --- | --- | --- |

Lessons learned from the RA VI RMDCN & IMTN (Cloud II) migration to MPLS

(Submitted by ECMWF)

Summary and purpose of document This document describes the migration process of the RMDCN from Frame-Relay to MPLS and the lessons learned

ACTION PROPOSED:

The meeting is invited to review the document.

TABLE OF CONTENT

1.	Why migrating to MPLS?	2

2.	From Frame-Relay to MPLS, a technical comparison	5

The Frame-Relay technology	5

The MPLS technology (Multi-Protocol Label Switching)	5

The new MPLS-based RMDCN network	6

3.	Technical solutions	6

4.	The Implementation	7

Validation of the new network	7

Migration of operational traffic	8

5.	Performance and Reliability	8

6.	ECWMF Role and lessons learned	10

7.	What comes next ?	11

IPSEC Backup	11

Beyond 2010	11

# Why migrating to MPLS?

The RMDCN has been in operation since March 2000. It provides a network infrastructure for both the connections between ECMWF and its Member States and most of the GTS connections for WMO Regional Association VI. Over time it has expanded to encompass the Far East with connections to Japan, China and India. Currently there are 42 User Sites connected to it. Orange Business Services (OBS), formerly known as EQUANT, is the provider of this network. ECMWF manages the project and monitors the network on behalf of the connected User Sites following an agreement with WMO.

The initial network was based on a Frame Relay infrastructure using Permanent Virtual Circuits (PVC) between User Sites. There have been regular reviews of the contract which concentrated on pricing issues and also looked at the technology used for the network infrastructure. It was found that networks using Multi Protocol Label Switching (MPLS) were becoming more and more the norm. The RMDCN Operations Committee (ROC) and the ECMWF Technical Advisory Committee (TAC) were regularly updated on the progress of these types of networks, both in terms of reach and reliability and in terms of commercial viability. In 2004 OBS made an offer for a migration of the RMDCN from Frame Relay to an MPLS-based IPVPN (Internet Protocol Virtual Private Network) solution. The main features of the offer from OBS were as follows.

- A doubling of the bandwidth for the network connection for the same charge.

- An improved backup service with the effect that OBS were able to offer improved availability figures (the majority of sites now have 99.9% availability, while Mission Critical sites have 100%). A pre-condition for these improved figures is that the access circuits for both the primary and the backup connection are diversely routed from User Site to OBS Point of Presence.

- The provision of Class of Service (CoS) to allow traffic prioritization.

- Any-to-any connectivity.

- The ability of sites to choose a reduced service type (Silver service versus Gold).

However some technical trade-offs were made.

- Frame Relay networks provide site-to-site bandwidth guarantees by default, while MPLS-based networks only provide a bandwidth guarantee on the access into the MPLS distributed router (referred to as the cloud).

- In a Frame Relay network the traffic is automatically partitioned by the PVC infrastructure, whereas in an MPLS network the infrastructure is a shared resource and therefore allows for better utilization of the available bandwidth.

- The CoS feature in MPLS networks allows for traffic prioritization and substitutes the end-to-end bandwidth guarantees. Also the network management overhead in a Frame Relay network is quite significant. For an MPLS network this is greatly simplified.

Figure 1 and 2 shows the differences between the two network infrastructures, before and after the migration to the MPLS infrastructure.

Figure 1 - Frame Relay based RMDCN

Figure 2 - MPLS Based RMDCN (May 2007)

The proposal from OBS for the migration of the network was approved by the ECMWF Council in December 2004 and this was also accepted by the other WMO members connected to the RMDCN. Since the new network infrastructure was significantly different the Service Level Agreement had to be revised. Also the implementation plan required detailed discussion with OBS. In order to guarantee an uninterrupted service on the existing Frame Relay network it was decided to implement the new network in parallel with the old network. Following intense negotiations Supplement 4 to the RMDCN contract was signed on 8 May 2006.

The new MPLS based network went operational on 18 June 2007.

# From Frame-Relay to MPLS, a technical comparison

The MPLS technology used by the new RMDCN network is different from that of the previous Frame Relay technology. We now consider the differences and the improvements that are provided by the new network.

## The Frame-Relay technology

Frame Relay is a relatively old technology which has the following two major characteristics.

- Link-based Network: In order to be able to exchange data, two sites must share a common dedicated point-to-point circuit. This circuit is deployed by the provider and is called a Permanent Virtual Circuit (PVC). Typically, a site shares several PVCs with all the sites with which it needs to exchange traffic.

- Dedicated bandwidth between two sites: When a PVC is deployed between two sites, it provides a dedicated bandwidth. This also highlights a limitation, as unused PVC bandwidth can not be (re)used by other PVCs.

For example Figure 3 shows a simplified Frame Relay network. Note that sites B and D cannot exchange data as they do not share a PVC.

## The MPLS technology (Multi-Protocol Label Switching)

MPLS is an IP-centric solution that includes significant new features such as CoS (Class of Service) and VPN (Virtual Private Network). It is “Multi Protocol” as it can utilise different network technologies (FR, Ethernet etc.). It performs "Label Switching" since the data packets are switched through the network by virtue of an attached label. The following features characterize an MPLS-based solution.

- One access circuit per site: In order to exchange data with any of the other sites that are connected to the network, a site needs only one access circuit to the MPLS "cloud".

- Dedicated bandwidth to the network: The bandwidth value of the access circuit is the only guaranteed bandwidth for a site.

- Traffic prioritisation and CoS (Class of Service): Through its traffic engineering mechanisms, MPLS provides a granular way of distinguishing the different traffic flows that cross the network and assign them the appropriate priority. Critical traffic can therefore be allocated a higher bandwidth.

Typically with MPLS a site can exchange data with all of the sites that are connected to the network. In essence, the network acts as a private Internet-like topology. This is known as any-to-any setup (see Figure 4). The lack of dedicated bandwidth between sites is compensated by the CoS configuration that allocates a higher priority the more critical the traffic is.

Figure 3								Figure 4

## The new MPLS-based RMDCN network

For the RMDCN community, the two main benefits of an MPLS-based RMDCN network over one based on Frame Relay are the following.

- Any-to-any connectivity: Without further changes to the existing network, any pair of RMDCN sites can exchange data as soon as they have implemented the necessary routing changes locally.

- Class of Service: Taking into account that there is no dedicated bandwidth between the different RMDCN sites, the emphasis is on the traffic prioritisation and CoS. It is important that each RMDCN site classifies its traffic properly.

# Technical solutions

During the specification phase of the project each site had to decide what kind of connection was needed.

For the connection, OBS offered:

- Mission Critical : Dual connection (to two different POP), Dual CPE (the second is a backup)

- Extra enhanced : Dual Connection (to two different POP), One CPE

- Enhanced : Dual CPE, one with ISDN access to another POP

For the Class of Service, OBS offered:

|  | D1 | D2 | D3 |
| --- | --- | --- | --- |
| SILVER | N/A | 100% of IP bandwidth | N/A |
| GOLD | 75% of IP bandwidth | 20% of IP bandwidth | 5% of IP bandwidth |

Note : The COS function only kicks in when there is congestion on  the access line

# The Implementation

The actual migration project commenced following the signature of Supplement 4 of the RMDCN contract on 8 May 2006.

| Date | Task |
| --- | --- |
| 8 May 2006 | Signature of Supplement 4 of the RMDCN contract |
| 11 September 2006 | Start of installation – roll-out |
| 16 April 2006 | Ready for Trial Date – OBS handed over the network |
|  | Start of the User Site Acceptance Tests |
| 19 May 2007 | Start of the Reliability Acceptance Test |
| 4 June 2007 | Start of the migration of all operational traffic |
| 18 June 2007 | Final acceptance of the new network |

Table 1 - The major milestones during the migration project.

The following phases for the implementation were identified.

Specification of the configuration for each User Site

During this period the final configuration details such as access speed, mission critical setup, backup method, etc. were agreed with all RMDCN Members and the information was passed on to OBS.

Installation of the network

OBS rolled out the new MPLS-based network in parallel with the existing Frame Relay network. ECMWF gathered from all of the RMDCN members the detailed technical information (CoS classification, IP network addresses etc.) which OBS required to configure the network equipment.

## Validation of the new network

In order to be confident that the new network was able to meet the operational requirements it had to be validated. This validation was split into two parts.

Firstly there would be a two week User Site Acceptance period during which tests were run to identify any configuration or deployment issues for each User Site on the network. This phase was also used to validate whether or not the traffic on the network was properly classified according to the CoS specifications and that the expected performance levels could be attained. To achieve this, all User Sites were provided with a common set of test software that had been developed by ECMWF.

The second phase of the validation was the Reliability Acceptance Test. Before running any real operational traffic on the network it was necessary to validate the service provided by OBS. During this phase ECMWF duplicated its dissemination traffic that was using the operational network and transmitted this duplicated data over the new network to systems that had been set up for testing by some member sites. Some Regional Telecommunications Hubs did similar tests by transmitting a copy of their operational GTS traffic over the new network to some of their partner sites.

## Migration of operational traffic

In order to migrate the 91 PVCs in a controlled manner a detailed time schedule for migrating the operational traffic flows (i.e. PVC) was agreed by all RMDCN Members.

# Performance and Reliability

The figure 5 shows the performance improvement for ECMWF dissemination to a particular country between the Frame Relay and the MPLS network.

The pictures above prove that the network delivers the expected performance and meet the Service Level Agreement over the last months. This was also true for the Frame Relay network over the years.

# ECWMF Role and lessons learned

As already mentioned ECMWF manages the project and monitors the network on behalf of the connected User Sites following an agreement with WMO.

This type of organization is rather uncommon for the provider. The final decision on what to do and how to do it is taken by the connected User Sites and not by ECMWF. OBS, and it is probably the same for others Telcos, is used to deal with one customer Centre responsible for all the connected sites. This is not our case, and this has proved to be a rather difficult situation to manage for OBS.

For such a large network, with so many different countries (very different level of technical knowledge, language barriers, number of staff involved…), ECMWF’s role can be seen as:

- presenting a “unified” interface to the provider. For this to be successful, and the way the migration was done is a proof of that success, two key factors can be identified: a very good technical knowledge of networking, and a deep understanding of the meteorological community. Thanks to its position and to the people involved, ECMWF can provide both.

- supporting the connected countries with the daily activity of the network and with changes. This, for example, covers: providing statistics on the links, supervising the network 24x7, following the trouble tickets, checking SLA, checking invoices, dealing with modifications…

Obviously, such a migration is a major milestone in the life of the network. In particular, the change of the technology (from Frame Relay to MPLS) implied a lot of coordination between OBS, ECMWF and the User Sites. In order to minimize the risks and to keep the migration phase as short as possible, it was decided to use a “Big Bang” approach.

With this solution, the new network was built by the provider in parallel to the existing network (all routers configured, all leased lines in place…). Once everything was in place, the network was “delivered” to the community. During this phase, the Frame Relay network was still the operational network, OBS did not charge for the new infrastructure during that period. Though difficult to accept by OBS, it would have been impossible to proceed this way (a free of charge parallel network) if at the same time a different provider was used for the new network.

The “Big Bang” method proved its efficiency in terms of operation (almost no traffic disruption during the migration phase), however the 4.5 months delay in the project was related to this method. For the RMDCN migration this was not a major issue but might be one in some cases. We clearly set the priority on minimizing operational impacts and accepted the risk of delays.

Dealing with a lot of countries during this migration was really challenging in terms of the time schedule. On a day to day basis, there was obviously the issue of the time difference between countries. We also saw that there are always holidays somewhere! Summer break in Nordic countries starts as early as mid-June, May is a month of public holidays more or less everywhere, Easter is not at the same period, and even week-ends are not on the same days in some Islamic countries… So, scheduling operations and following multiple actions with all the countries was a real challenge.

However, the organisation established for this migration was quite scalable. Each analyst at ECMWF was the main contact point for a subset of countries and at the same time, each analyst was responsible for a particular subset of tasks (Project Management, Development of the assessment software, collection of configurations…).  Should the RMDCN grow larger, this would easily be expandable to a larger team.

# What comes next ?

## IPSEC Backup

At the last ROC the ISDN backup method for the new IPVPN MPLS network was also discussed and, although it was seen as a big improvement over the ISDN backup method in the Frame Relay-based network, there was still some doubt about the overall functionality. In particular, the speed of the ISDN backup, which is much lower than that of the access line, was seen as a weak point. It was agreed that ECMWF would investigate a new backup method via the Internet, based on Internet Protocol security (IPsec) VPN and using ECMWF as a gateway into the IPVPN MPLS cloud. These tests are now going to start. A limited number of sites will participate in these tests. The outcome will be presented during the next ROC meeting (June 2008) to potentially decide to extend this method, of course, on a voluntary basis only.

## Beyond 2010

Following ECMWF Council’s agreement (December 2004) and signature of Supplement 4 to the RMDCN contract, the RMDCN contract with OBS covers the period to March 2009 and will be extended automatically, on a rolling basis, for successive terms of 12 months (see figure 9). The next Biennial Contract Review (BCR) is scheduled for April 2008. Taking into account that the original contract dates from 1998, the need for an ITT for the provision of the RMDCN service beyond 2010 will be assessed in 2008.

Both the ECMWF Council and the WMO RA VI RMDCN Steering Committee will need to approve a possible Invitation To Tender.

It is expected that the procurement and implementation of such a network service would need considerable time: from writing the Specification of Requirements to making the final decision and negotiating a complex contract can take in the order of 18 to 24 months. Experience has shown that there are often delays of several months during implementation.  Hence, any new network service could be implemented in 2010 at the earliest.

Based on the contractual issues and time constraints mentioned above, ECMWF proposes to the RMDCN community that:

- the future of the RMDCN be discussed at the next WMO RA VI RMDCN Steering Committee

- the need of an ITT for the provision of the RMDCN service beyond 2010 be assessed during 2008.

The anticipated timeline for the above proposals is:

| 2008 | January to March: | Market Survey |
| --- | --- | --- |
|  | April: | Annual Price Review with OBS |
|  | Late spring: | Session of the RMDCN RA VI Steering Committee |
|  | Summer: | Session of the ECMWF TAC Subgroup on the RMDCN |
|  | Autumn: | Report to ECMWF TAC and to ECMWF Council |

If it is decided to go for an ITT at the end of 2008, the estimated timescale for the next steps will be:

| 2009 | March: | Issue of the ITT |
| --- | --- | --- |
|  | May: | Closing date |
|  | Summer: | Evaluation and contract negotiation |
|  | Autumn: | Report to ECMWF committees, WMO RA VI Steering Committee and ECMWF Council |
| 2010 | Spring: | Start of the migration to the new network |

At its recent session in Oct. 07, the ECMWF Technical Advisory Committee has decided to establish a subgroup to plan for the provision of the RMDCN service beyond 2010 and agreed on the following Terms of Reference for the RMDCN Subgroup:

i to review the scope and methodology of the planned networking market survey;

ii to examine the outcome of the market survey and make recommendations;

iii to involve WMO/RA VI, WMO Secretariat and EUMETSAT as observers in the subgroup, as appropriate;

iv to consider the consequences of any further expansion of the RMDCN to non-RA VI countries.

The RMDCN IPVPN MPLS Configuration.

| Country/Site | Access Speed | IPVPN Port Speed | Resiliency | CoS | Load Balancing | NAS Backup Speed |
| --- | --- | --- | --- | --- | --- | --- |
| ECMWF Member States |
| Austria | 2M | 1M | enhanced | Gold | NO | 512 |
| Belgium | 2M | 2M | enhanced | Gold | NO | 384 |
| Denmark | 2M | 2M | mission critical | Gold | NO | N/A |
| Finland | 2M | 768 | enhanced | Gold | NO | 256 |
| France | 4M | 3M | mission critical | Gold | NO | N/A |
| Germany | 2M | 2M | mission critical | Gold | NO | N/A |
| Greece | 1M | 768 | enhanced | Gold | NO | 384 |
| Ireland | 1M | 1M | enhanced | Gold | NO | 512 |
| Italy | 2M | 2M | mission critical | Gold | NO | N/A |
| Luxembourg * | 2M | 768 | enhanced | Gold | NO | N/A |
| Netherlands | 2M | 768 | enhanced | Gold | NO | 384 |
| Norway | 2M | 2M | enhanced | Gold | NO | 1M |
| Portugal | 768 | 768 | enhanced | Gold | NO | 384 |
| Spain | 2M | 2M | enhanced | Gold | NO | 512 |
| Sweden | 4M | 3M | mission critical | Gold | NO | N/A |
| Switzerland | 2M | 768 | enhanced | Gold | NO | 384 |
| Turkey ** | 768 | 768 | extra enhanced | Gold | NO | N/A |
| United Kingdom | 2M | 2M | mission critical | Gold | NO | N/A |
| ECMWF | 50M | 50M | mission critical | Gold | YES | N/A |
| ECMWF Co-operating States |
| Croatia | 512 | 512 | enhanced | Gold | NO | 256 |
| Czech Republic | 2M | 2M | enhanced | Gold | NO | 1M |
| Estonia | 64 | 64 | enhanced | Silver | NO | 64 |
| EUMETSAT | 2M | 2M | mission critical | Gold | NO | N/A |
| Hungary | 1M | 1M | enhanced | Gold | NO | 256 |
| Iceland | 128 | 128 | enhanced | Gold | NO | 128 |
| Lithuania | 128 | 128 | enhanced | Silver | NO | 128 |
| Romania | 2M | 256 | enhanced | Gold | NO | 128 |
| Serbia | 512 | 512 | enhanced | Gold | NO | 256 |
| Slovenia | 256 | 256 | enhanced | Gold | NO | 256 |
| Other RMDCN Member States |
| Bulgaria | 512 | 512 | enhanced | Gold | NO | 128 |
| China | 2M | 2M | mission critical | Gold | NO | N/A |
| India | 128 | 128 | enhanced | Gold | NO | 128 |
| Japan | 1M | 1M | mission critical | Gold | YES | N/A |
| Jordan | 128 | 128 | enhanced | Gold | NO | 128 |
| Latvia | 128 | 128 | enhanced | Gold | NO | 128 |
| Lebanon | 128 | 128 | enhanced | Gold | NO | 128 |
| FYR Macedonia | 128 | 128 | enhanced | Gold | NO | 128 |
| Poland | 128 | 128 | enhanced | Gold | NO | 128 |
| Russian Federation | 512 | 512 | mission critical | Gold | NO | N/A |
| Saudi Arabia * | 512 | 128 | enhanced | Silver | NO | N/A |
| Slovakia | 256 | 256 | enhanced | Silver | NO | 128 |
| United Arab Emirates | 128 | 128 | enhanced | Gold | NO | 64 |
| *) Luxembourg and Saudi Arabia do not have a secondary (backup) connection |  |  |
| **) Turkey has got a secondary connection with a speed of 384 kbps |  |  |

# Text boxes

Figure 9: Contract Term RMDCN

Suppl. 4    12-months
extension

BCR

Effective

Date

Automatic

12-month extension

Automatic

12-month extension

BCR

Effective

Date

Initial contract period

BCR

Effective

Date

PR

Effective

Date

BCR

Effective

Date

Contract

Review

2010

2009

2008

2007

2006

2005

2004

Figure 8: Trouble Tickets with SLA breach

Figure 7: Trouble Ticket distribution (red: End User problems; blue: OBS problems; yellow: Duplicate tickets for same incident)

Figure 6: RMDCN availability according to the SLA

Figure 5: Example showing the reduction in transfer times for ECMWF dissemination products. The blue bars denote the amount of data transferred (in kBytes). The red line denotes the duration of the dissemination (in minutes).