| WORLD METEOROLOGICAL ORGANIZATION _______________________________ Joint meeting: CBS Expert Team on Aircraft Based Observations (Second Session) and AMDAR Panel (Thirteenth session) (GENEVA, SWITZERLAND, 5-7 OCTOBER 2010) |  | ET-AIR-2 and AMDAR Panel-13/Doc.3.4.1 (21.IX.2009) __________ ITEM: 3.4 Original: ENGLISH ONLY |
| --- | --- | --- |

AIRCRAFT AND AMDAR DEVELOPMENTS

Progress Achieved for the WIGOS Pilot Project for AMDAR

(Submitted by WMO Secretariat)

Summary and purpose of document This document provides information on the implementation of WIGOS Pilot Project III as defined by Cg-XV.

## Action Proposed

The Panel is invited to note the information contained in the document.

_______________

Annexes:	1.	The WIGOS Pilot project for AMDAR

2.	The WIGOS Pilot Project for AMDAR – Sub Projects

PILOT PROJECT III

INTEGRATION OF AMDAR INTO THE WMO GLOBAL OBSERVING SYSTEM

1.	Introduction

Within the WMO Integrated Global Observing Systems (WIGOS) a Pilot Project specifically for AMDAR was initiated. To progress this Pilot Project and see the realisation of the benefits it required the participation from a number of operational AMDAR Programs, including the EUCOS (E-AMDAR) and USA AMDAR Programs. The initial development phase of the project was instigated by an Ad-hoc Steering Group, consisting of members from the AMDAR Panel, WMO Secretariat and the CIMO Vice President and the Ad-hoc Steering Group had its first session on 2-3 July 2008 in Geneva, Switzerland. The WIGOS Pilot Project for AMDAR has been designed with a focus on the practices impacting AMDAR data collection, processing, archiving and dissemination.

2.	Integration of AMDAR into WIGOS

2.1	Governance Issues

2.1.1	One of the key issues that would ultimately see success of the WIGOS Pilot Project for AMDAR was the overall governance structure of the AMDAR Programme. The first major step that addressed the governance of WMO AMDAR Panel was the successful transfer of the AMDAR Technical Coordinator’s responsibility into WMO and the WMO Secretariat structural. This also included an organization change that saw the creation of a new Aircraft Observation Unit (AIR) within the Observing and Information Systems Department (OBS) and its Observing Systems Division (OSD). The AMDAR Technical Coordinator is the Secretariat lead for the Aircraft Observation Unit, with the responsibility for aeronautical observations.

2.1.2	The second step that addressed the governance was a resolution of CBS XIV, Dubrovnik, Croatia 25 March to 2 April 2009 to establish a CBS Expert Team on Airborne Observations (ET-AIR) as an anchor of the WMO AMDAR Panel to CBS. This proposal was approved at the 11th AMDAR Panel (Malaysia, 17-21 November 2008) and first successful Joint meeting of ET-AIR and the AMDAR Panel was held in Toulouse, France, in November 2009. Further information on the governance for the AMDAR Programme can been found in Doc 4.6 Future governance for the AMDAR Programme.

2.2	Technical Issues

2.2.1	The AMDAR Panel and ET-AIR have both identified that there are several key components to the AMDAR system that require immediate attention, such as the standardization of AMDAR BUFR code, the essential updates to the AMDAR Reference Manual and the Standardization of AMDAR Software that should be included under the WIGOS Structure.

    - At the first ad-hoc Steering Group Meeting on WIGOS Pilot Project for AMDAR, 2 to 3 July 2008 Geneva, Switzerland, the issues relevant to all three levels of WIGOS integration were discussed, namely: the standardization of AMDAR BUFR Template, standardization of QC/QA requirements for AMDAR data, standardized specification for instruments, standardized Generation of data from all types of aircraft. Based on the information provided by the participating experts, the Meeting developed a set project goals and objectives for the WIGOS Pilot Project for AMDAR, to assist with the integration of AMDAR into WIGOS.  The AMDAR Pilot Project and the objectives are contained in Annex I.

    - The six Pilot Project aims and objectives were developed to assist with the integration of AMDAR into WIGOS (see Annex II).  Over the past few years a number of business cases, developed individually by operational AMDAR Programs, have been explored. Ideally a comprehensive business case, covering requirements for all operational and potential AMDAR Programs, taking into account all the requirements from all application areas should be developed together with the airline industry. This potentially will allow for a more coordinated development of a standardized AMDAR software package, based on the generic software specification.

2.3	Funding of the Pilot Project and the Sub Projects

  - The AMDAR Ad-hoc Steering Group believed that sufficient funding should be made available so that the potential of the WIGOS Pilot Project and Sub Projects could be fully realized. The Chairman of the AMDAR Panel expressed his concern at the Executive Council Working Group on the WIGOS and WIS (EC WG on WIGOS and WIS) and the Subgroup on the WIGOS (SG-WIGOS) that the AMDAR Pilot Project that if sufficient funding was not made available it would be difficult to achieve all their expected results.  It was also agreed that the success of the AMDAR Pilot Project could only be guaranteed if some of the activities could be accomplished through a short term contract with appropriate experts. For further information on the key deliverables, expected benefits and implementation constrains see Annex III, WIGOS Project Evaluation Template submitted to Executive Council Working Group on WIGOS-WIS, 12-14 October 2010, Geneva Switzerland.

3.	AMDAR PILOT PROJECT ACTVITIES

3.1	The second session for the WIGOS Pilot Project for AMDAR was held at KNMI Headquarters in De Bilt, The Netherlands from 10-12 February 2009. The meeting discussed Objective 1, Development of a BUFR Template for AMDAR and Objective 3, the development of standardized procedure for Quality Management of AMDAR data.

3.2	This meeting agreed on a new Standardized BUFR Template for AMDAR, 3 11 010 version 2 and agreed on the inclusion of a number of new elements, including a new AMDAR quality element. The meeting proposed that the new Standardized BUFR Template for AMDAR would be provided to the AMDAR Community and major NWP Centres for review and comment. Following the review and comments of the AMDAR Community and NWP Centres the final version, version 3 of the Standardized AMDAR BUFR Template was made available to the Inter-Programme Expert Team on Data Representation and Codes (IPET-DRC) for approval. IPET-DRC-1 discussed this template, in particular the representation of quality information, and finally  approved 3 11 010 version 4 and the new descriptors, provided that the proposed usage of  an additional descriptor is found feasible to the AMDAR users.  Following the approval from IPET-DRC the new Standardized BUFR Template for AMDAR is being validatated using independant processing centres. The validation procedure being completed, the template would then be again submitted to IPET-DRC. Following the approval of the chairperson of the IPET-DRC, chairperson of the OPAG-ISS and the president of the CBS, the Template will be declared preoperational. The two selected encoding centres, USA and UK, are currently working towards resigning their systems to accommodate the new template, expected completion 4th Quarter 2010.

3.3	The second session for the WIGOS Pilot Project for AMDAR also discussed Objective 3, the development of standardized procedure for Quality Management of AMDAR data. The meeting noted that with the ever increasing amount of AMDAR data on the GTS there is now a real need to improve the overall quality of AMDAR data disseminated on the GTS. In order to achieve this, a better coordinated response to quality control of AMDAR data is required. The meeting agreed that a set of minimum standards, including evaluation criteria and procedures, for AMDAR data monitoring need to be developed. The meeting agreed that it would evaluate the current criteria and procedures used by all national and regional AMDAR programmes and would develop a set of minimum quality standards for AMDAR data.

3.4	The third session for the WIGOS Pilot Project for AMDAR was held at KNMI HQ in De Bilt, The Netherlands, from 1 to 2 July 2009. The meeting discussed the Objective 2, Application of WMO Metadata relevant to AMDAR. The meeting agreed that the proposed AMDAR Metadata would classify components of metadata associated with AMDAR. In particular, the meeting identified metadata needed for describing data and products, metadata needed for usage of data and metadata needed for the operation of the AMDAR observing system.  The meeting examined how metadata could be used for quality control, administration purposes and the issues associated with the sharing and usage of the metadata, data and products. The meeting, using WMO profile of ISO 19115 to ensure appropriate compatibility with WIS and WIGOS developed metadata that would cover both the aircraft and airport. The meeting also agreed that this particular objective would be tested on a single airline in the E-AMDAR Programme before finally being distributed to other operational AMDAR Programmes.

3.5	The AMDAR Panel has also had initial discussions with the WMO Secretariat and the CIMO President regarding the WIGOS Pilot Project for AMDAR Objective 4, Validation and Preparation for Intercomparison of Available Water Vapour Sensor Performance. It was agreed that before any further work on this development progress and before the AMDAR Panel and CIMO define the rules and procedures for an intercomparison of AMDAR (with a water vapour sensor) and other upper-air systems, the WVSS-II water vapour sensor would have to complete USA and European evaluation trials and answer pre-defined quality requirements. It is expected that these field trials should be completed and documented by 4th quarter of 2010.

3.6	In July 2010 the AMDAR Panel presented its future requirements for an upgrade ARINC620 Standard to the Date Link (DLK) Systems Subcommittee in Montreal, Canada. Following this meeting WMO hosted a short meeting in Geneva with key members of the E-AMDAR Programme and Hans-Rudi Sonnabend (Lufthansa Systems Aeronautics GmbH) to discuss and develop the future requirements for an upgrade ARINC620 Standard as well as start the process of initiating an ARINC Project Initiation/Modification (APIM), the standard platform for changing/upgrading an ARINC Standard. This meeting undertook the responsibility of undertaking the initial steps of developing the framework for generic software specification for AMDAR, by further developing and improving on the existing AMDAR ARINC620 Standard to include a number of new meteorological parameters, based on the new standardized AMDAR BUFR Template and to improve upon the current range of meteorological parameters included in the current ARINC620V4 (Sup5) Standard.

3.7	An additional meeting to discuss the outcomes and the future development of all short and long term AMDAR WIGOS Pilot Project objectives did not eventuate in 2010; this was primarily due to the unavailability of key people as well as conflicts with other WMO and other AMDAR related meetings.

______________

THE WIGOS PILOT PROJECT FOR AMDAR

| Project Name: | Integration of AMDAR into WIGOS |
| --- | --- |
| Acronym: | WIGOS-PP-AMDAR |
| Project Type: | Pilot |
| Project Status: | The WIGOS Pilot Project for AMDAR is currently in the advanced stages of collaboration and definition. |
| Project Overview: | This Project will focus on the practices impacting AMDAR data collection, processing, archiving and dissemination. The standard practices used in observing the atmosphere need to be well documented to ensure sufficient detail accompany the observations so that users can interpret measurements correctly. In addition new methods and procedures will be required in preparation for the deployment of new operational instruments, such WVSSII water vapour sensor. |
| Project Aims: | Short-term: (1) Development of a standardised BUFR Template for AMDAR; (2) Application of WMO Metadata relevant to AMDAR; (3) Development of a standardised Quality Management Framework for AMDAR data; and (4) Validation and preparation for intercomparison of available Water Vapour sensor performance. Long-term: (5) Update of the AMDAR Reference Manual WMO-No.958; and (6) Development of the framework for generic software specification for AMDAR. Note: In case of lack of resources provided towards the WIGOS-PP-AMDAR, Project Aims will be prioritized accordingly. |
| Partners / Participants: | AMDAR Panel E-AMDAR and USA AMDAR Programmes WMO Technical Commissions |
| Project Cost: | Estimated costs for meetings, consultants and publication CHF 125K |
| Funding Source(s): | This project will make optimum use of the expertise available from the AMDAR Panel and its WIGOS partners. Financial support shall be required through the WMO AMDAR Panel Trust Fund and WIGOS-WIS Trust Fund. |
| Project Timescale: | Will all be done in parallel and completed by February 2010 (short term aims) |
| Deliverables: | (1) Agreed BUFR Template for AMDAR; (2) Published best metadata practice for AMDAR; (3) Published best practice for Quality Management procedures for AMDAR; (4) Published results from the validation of the available Water Vapour sensors; (5) Updated AMDAR Reference Manual WMO-No. 958; and (6) Agreed framework for generic software specification for AMDAR. Note: In case of lack of resources provided towards the WIGOS-PP-AMDAR, Deliverables will be prioritized accordingly. |
| Project Links: | http://www.wmo.int/amdar/ |
| Project Summary: | With the completion of the project aims, AMDAR will be better integrated into WIGOS by adhering to WMO standards for instrumentation, data exchange and for end products. |
| Date of Last Update: | 08/10/2009 |
| Contact Person: Name: Organization: Address: Telephone: Fax: E-Mail: | AMDAR Technical Co-ordinator Mr Michael Berechree WMO WMO Secretariat 7 bis, avenue de la Paix CH-1211 GENEVE 2, Switzerland +41 (0) 22 730 80 21 +41 (0) 22 730 82 12 |

____________

The WIGOS Pilot Project for AMDAR – Sub Projects

| Sub Project | Objective | Who | Action |
| --- | --- | --- | --- |
| 1. | Development of a BUFR Template for AMDAR | (Frank Grooters) (Jitze v. d. Meulen, Stewart Taylor, Eva Cervena and Dave Helms) in collaboration with the ET-DR&C Validation Centres (to be nominated) | 1. Investigate the various versions of BUFR templates for AMDAR and their elements currently in use by national and regional AMDAR Programs. Provide specification to ET DR&C; 2. Develop a standardised BUFR Template for AMDAR that includes all the new extensions supporting parameters for AMDAR; 3. Validation of the AMDAR BUFR Template; and 4. Approval of the AMDAR BUFR Template. |
| 2. | Application of WMO Metadata relevant to AMDAR | (Frank Grooters) Contractor TBD under the guidance of the AMDAR Panel Chairperson, ad-hoc support from WIS Project Office, IPET-MI | 1. Classify components of metadata associated with AMDAR. In particular, identify metadata needed for describing data and products, metadata needed for usage of data and metadata needed for the operation of the AMDAR observing system; 2. Identify metadata for quality control and administration. Also identify relevant policies for the sharing and usage of the metadata, data and products; 3. Describe the metadata utilising WMO profile of ISO 19115 to ensure appropriate compatibility with WIS and WIGOS; and 4. Create examples and best practice guides for inclusion in the AMDAR Reference Manual and relevant CIMO documents. |
| 3. | Development standardised procedure for Quality Management of AMDAR data | Jitze v. d. Meulen E-AMDAR QEv in coordination with the AMDAR Science Sub Group, other AMDAR Data Monitoring Centres | 1. Examine the requirements for Quality Monitoring and Quality Assurance of AMDAR Data; 2. Develop a Quality Framework and procedure in support of high quality AMDAR Data to users; and 3. Identify potential AMDAR archive centres (DCPCs for WIS). |
| 4. | Validation and preparation for intercomparison of available Water Vapour sensor performance | Dave Helms E-AMDAR Programme in coordination with CIMO ET-UASI | 1. Perform calibration and flight test and report; and, 2. Organize preparatory meeting to define the rules and procedures for the intercomparison of AMDAR and other upper-air data. 3. Take part in the WMO Radiosonde Intercomparison, China, 2010 |

| 5. | Update of the AMDAR Reference Manual, WMO-No.958 | (Frank Grooters) Contractor TBD under the guidance of the AMDAR Science Sub Group, CIMO Rapporteur | 1. Review those sections of the AMDAR Reference Manual as identified (ensure the full suite of water vapour sensors and their measurements are included, turbulence and icing and future requirements for AMDAR; 2. Update to both technical and scientific components of the AMDAR Reference Manual and propose changes to the CIMO Guide; and 3. Incorporate input from other sub projects. 4. Draft new version of AMDAR Reference Manual |
| --- | --- | --- | --- |
| 6. | Development of the framework for generic software specification for AMDAR | (Frank Grooters) Contractor TBD under the supervision of Stewart Taylor in coordination with AMDAR Panel Technical Sub-Group, Aviation Industry Groups. | 1. Review all versions of current software specifications currently in use by operational AMDAR Programs; and 2. Provide framework for the development of the generic software solution for AMDAR. |

___________

WIGOS Project Evaluation Template

- Aims

This WIGOS Pilot Project for AMDAR focuses on developing the practices that are currently impacting AMDAR data collection, processing, archiving and dissemination.  The practices used by AMDAR in observing the atmosphere need to be well documented to ensure sufficient detail accompany the observations so that users can properly interpret measurements. It will develop new methods and procedures in preparation for the deployment of new operational instruments, such WVSSII water vapour sensor.

- Key deliverables and expected benefits

- Development of a standardised BUFR Template for AMDAR;

- Implementation of the application of WMO Metadata relevant to AMDAR;

- Development of a standardised Quality Management Framework for AMDAR data;

- Validation and preparation for inter-comparison of available Water Vapour sensor performance.

- Update the AMDAR Reference Manual WMO-No.958; and

- Develop the framework for generic software specification for AMDAR.

The impacts on existing AMDAR Programs following the WIGOS PP for AMDAR will greatly assist the operations of AMDAR Programs, with improved practices impacting AMDAR data collection, processing, archiving and dissemination of AMDAR data. In particular the use of a single standardized AMDAR BUFR Template, standardized procedure for Quality Management of AMDAR data and the application of WMO Metadata will greatly assist all operational and proposed AMDAR Programs.

- Implementation constrains; problems encountered

The AMDAT Pilot Project has gained so far the following experience and lessons learned:

- The AMDAR community is lacking sufficient experienced personnel that could actively contribute to all the objectives of the Pilot Project.

- The level of funds available has reduced the support to the Pilot Project such that only personnel from the E-AMDAR or the USA AMDAR Programmes have been included in the Pilot Project, where participation from other regions would have provided wider acceptance of the concept and given the Pilot Project a more global perspective.

- Support to the Pilot Project from the NMHSs is suffering from a low priority; most members have very active AMDAR Programme(s) and therefore members find it difficult to secure the appropriate amount time to work on the Pilot Project objectives.

- Due to required upgrades to the water vapour, the availability of a reliable aircraft based water vapour sensor has been delayed, causing the need for additional development, certification and (expensive) laboratory testing and flight trials. Pending issues (as well as reasons, such as lack of resources (budget/staff), etc.)

- Pending issues

There are a number aspects to this project that require further attention, however due to work load of key personnel involved, E-AMDAR and USA AMDAR Programme, and classes with other WMO Meeting/workshops it has been difficult to schedule additional time when all key personnel are available at the same time to discuss the project. As such several key objectives require more time to be regarded as complete.

- Partners involved (internal/external)

Without the close the cooperation of the E-AMDAR and USA AMDAR Programs it would be difficult to further progress the WIGOS Pilot Project AMDAR.

- Management and governance aspects (changes of organizational structure, etc.)

The first step in addressing the governance of the WMO AMDAR Panel was the successful transfer of the AMDAR Technical Coordinator’s responsibility into WMO and the WMO Secretariat structural and organization change that included the creation of a new Aircraft Observation Unit (AIR) within the Observing and Information Systems Department (OBS) and its Observing Systems Division (OSD). The AMDAR Technical Coordinator is the Secretariat lead for the Aircraft Observation Unit, with the responsibility for aircraft observations.  The second step that addressed the governance was a recommendation of the CBS Implementation-Coordination Team (ICT-IOS-5), Geneva, 15-18 September 2008 to CBS-XIV (March 2009) to establish a CBS Expert Team on Aircraft Observations (ET-AIR), with oversight of the WIGOS PP for AMDAR. The new ET on Aircraft Observations now has the oversight of the AMDAR PP for AMDAR.

- Capacity building and Outreach requirements

Capacity and out reach was not addressed in the WIGOS PP for AMDAR. This PP focused on improving the practices impacting on AMDAR data collection, processing, archiving and dissemination.

- Benefits achieved

The benefit of the WIGOS PP for AMDAR would be improved practices impacting AMDAR data collection, processing, archiving and dissemination allow better integration of AMDAR into WIGOS.

- Lessons learned and experiences gained

See point 3.

- Legacy of the Project

The legacy of the WIGOS PP for AMDAR will allow better integration of AMDAR into WIGOS.

- Resources used

Since the beginning of the WIGOS PP for AMDAR the staff resources used to date have included the time and effort of personnel from: WMO (SO/AIR, C/OSD), E-AMDAR and USA AMDAR Programme staff.

WIGOS Planning Office Funds used: CHF 16,500

- Planned Project completion date

There are a number of short term and long term objectives under the WIGOS PP for AMDAR. The completion of the major objectives, both short and long term, will depend on appropriate resources.  The original planned completion date for the WIGOS PP for AMDAR was the 4th quarter 2010.

- Project Focal Point

Contact person: 	Michael Berechree

Position: 		SO/AIR, AMDAR Panel Technical Coordinator

Organization:		WMO

Phone:			+41 (0) 22 730 8212

Fax:			+41 (0) 22 730 8021

Email:			mberechree@wmo.int

- Place and Date

Geneva, Switzerland 17 September 2010