Notes on Status and Progress on 2012 Work Programme from AMPG-4 Review

| M-T Activity | Description | Pty (1-3) | 2012 Activities | Responsibility | Comments |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Study on data coverage and airline capabilities | 1 | Award SSA | APMG | SSA awarded in Mar 2012 |
|  |  |  | Manage SSA | SO/ARO | Commenced |
|  |  |  | Review deliverables. | SO/ARO, A-FPs, (APMG) | TBC |
| 1.1.2 | Development of AMDAR Programmes for: Northern Africa; South and Central America; Southwest Pacific Eastern Europe; Middle East Central Africa. | 1 | Organise finance for AeroMexico programme. | APMG, SO/ARO | Commenced |
|  |  | 2 | Determine potential for data targeting over Africa | APMG | S.Taylor provided a report to APMG-4 on E-AMDAR capabilities; Survey to be conducted of operation programmes (see Appendix VI Action for 4.5) |
|  |  | 2 | Determine what capacity there is to use targeted data in Africa | APMG | Some discussion at Workshop on DM but no other progress. |
|  |  | 2 | 1 or 2 members of the Panel to undertake fact-finding mission to Africa re programme potential | APMG | Address in 2013 |
|  |  | 3 | Investigate approach for Emirates AMDAR Programme commencement – assess possiblities for Bahrain, Oman: Write generic letter to appropriate PRs and contacts through the Secretariat. | F.Grooters | No progress |
|  |  |  | Write to WMO Regional Association I | F.Grooters | No progress |
| 1.1.3 | Improve and extend Targeted Data Activities | 2 | All programmes to identify potential for data targeting within their programs. Request info from A-FPs Submit information Analyse data Report to APMG-4 | SO/ARO A-FPs (Operational) SO/ARO SO/ARO | Survey to be conducted of operational programmes (see Appendix VI Action for 4.5) |
| 1.1.4 | Develop guidelines for programme development | 2 | Write DoW Review and approval Compilation of Guidelines | SO/ARO APMG SSA or A-FPs? | No progress. |
| 1.1.5 | Contribute to the WMO/CBS RRR Process | 1 | Develop a methodology for defining the required capabilites for inclusion in the RRR database. Provide data for input to the RRR Obs Systems Capabilities database | SO/ARO | Work will progress on this through the WIGOS Implementation Plan. |
| 1.2.1 | Develop optimization systems for: United States AMDAR Programme; Asia; Africa; South America. | 2 | Study on optimization for Sth Africa AMDAR Programme Study on optimization for US AMDAR Programme (MDCRS) Report on Australian Data Optimisation System SITA Optimisation Development | SO/ARO, G.Khambule SO/ARO, D. Helms SO/ARO, A-FP-Australia SO/ARO seek Pilot Project proposal from SITA. | Work progressing on 1 through possible SITA development; No update provided on 2; Report to Panel-15 Collaboration with SITA is ongoing. |
| 2.1.1 | Implement water vapour sensing measurement | 1 | Investigate Panel ownership of general STC for Airbus 320 family. | A.Hoff | No progress. |
|  |  | 1 | Investigate Panel ownership of general FAA STCs for Boeing 737 types and conversion to European EU/EASA certification. | A.Hoff/Y. Lemaitre | Status not known. |
|  |  | 1 | Write a letter to PRs seeking interest in international project for WV implementation | SO/ARO | Operational programmes were surveyed on WV IP. |
|  |  | 2 | Request SSI to provide a “dynamic” document on STC status, issues and processes | SO/ARO | Completed by Bryce Ford. |
|  |  | 1 | Draft a strategic plan for WV implementation | SO/ARO, A.Hoff, D.Helms | Commenced. |
|  |  | 2 | Obtain statements of impact of WVSS-II on airline operations from USA airlines. | F. Grooters | Commenced. |
| 2.2.1 | Implement turbulence measurement | 1 | Obtain specification for EDR from FAA | SO/ARO | Completed. |
|  |  | 1 | Obtain EDR software package from FAA for use in E-AMDAR | SO/ARO | Completed. |
| 4.1.1 | WIGOS Pilot Project for AMDAR | 1 | WIGOS-PP-AMDAR-1 Development of BUFR Template: Coordinate validation; Report to Code Group Report to APMG-3; Report to JM-4 | SO/ARO ECMWF/Met Office | Completed. |
|  |  | 1 | WIGOS-PP-AMDAR-2 Metadata Development: AP-FPs and Review Group to review Metadata sets; D..Helms to review and define metadata categories; AP-FPs and Review Group to Review in preparation for AMDAR DM Workshop | PL-IDEQC, SO/ARO, AP-FPs Review Group: SO/ARO, N.Halsey, D.Helms, J.v.d.Meulen, | WIGOS-PP-AMDAR is now no longer maintained as a WIGOS project – roll this project into appropriate areas of the work programme; Addressed at Workshop on AO Data Management; S.Taylor working on a implementation plan. |
|  |  | 1 | WIGOS-PP-AMDAR-3 Develop AMDAR Data Management Procedures: Hold a workshop of AMDAR data management experts in Q2 2012 (Geneva); Develop a strategy for global AMDAR data management; Address data display issues; | J.v.d.Meulen, APMG | Workshop held June 2012; Draft DM Framework skeleton proposed; See App VI, Item 4.1. |
|  |  | 1 | WIGOS-PP-AMDAR-4 Validation and Inter-comparison of WVSS-II: Paper on summary of results and conclusions: DoW Award SSA Manage SSA Seek endorsement by CIMO and CBS as a candidate system for operational deployment by Members; Technique employed by the WVSS-II sensor should be appropriately integrated into the CIMO Guide and CBS guides. Development of AMDAR Panel Statement of Support for WV implementation leading to WMO endorsement. | APMG | Statement of Support drafted; These tasks to be incorporated into the WVM Implementation Plan (Activity 2.1.1.6). |
|  |  | 1 | WIGOS-PP-AMDAR-5: Update of AMDAR Reference Manual: 1. SSA to be compiled for: i) Review of WMO and AMDAR regulatory material ii). Integrate AMDAR RM into WMO regulatory material. I iii). Conduct a regulatory material review process as necessary to finalise item ii. 2. Review and update the CIMO Guide for water vapor sensing developments. | 1. APMG, SO/ARO 2. APMG 3. A.Hoff | No progress. |
|  |  | 1 | WIGOS-PP-AMDAR-6 Generic Software Spec: 1. Manage SSA; 2. Review deliverables. | 1. SO/ARO; 2. Review group: SO/ARO, D.Helms. HR.Sonnabend, A.Hoff. | Good progress via SSA; 3rd draft of chapters 1 to 3 in progress. |
| 4.1.2 | Establishment of National and International Metadata | 2 | Collection of metadata on AMDAR software to be completed | PL-IDEQC, SO/ARO, AP-FPs | Ongoing |
| 4.2.1 | Develop a National and Global Aircraft Observations Data Management Framework | 2 | Re NOAA/ESRL/GSD AMDAR data display determine: Future maintenance of and for this system Possible change to use of national aircraft IDs | D.Helms | No progress. |
| 4.3.1 | Update of ARINC 620 Meteorological Report to Version 5 | 1 | Finalise ARINC 620 Met. Report Version 5 | SO/ARO, A.Hoff, HR.Sonnabend, D.Helms | Completed. |
| 4.3.2 | Standardisation of AMDAR within Aviation | 3 | Commence planning for an Aviation Industry event for 2013 re software implementation in new aircraft. Attend the Airlines Association of South Africa AGM, South Africa | APMG APMG G.Khambule, APMG | No Progress. |
| 4.3.3 | AMDAR Software Development | 2 | B777 Software Development: Proposal of B777 software development to be made to Meteo-France and E-AMDAR at E-TAG (March 2012) Ownership issues to be addressed at E-TAG (March 2012) Chairman to report to Panel-15 (Q4) | F.Grooters APMG | Ongoing. |
| 4.4.1 | Develop strategies for the management of ADS and Mode S data | 2 | Ensure item is addressed under 4.1.1(3): AMDAR Data Management Workshop | SO/ARO, J.v.d.Meulen | Completed. |
| 5.1.1 | Aircraft Observations System Website Maintenance | 2 | Review website. | C.Weiss, SO/ARO, Y.Lemaitre, J.v.d.Meulen | Commenced; Require significant changes to accommodate cessation of Panel and new governance under CBS, CIMO. |
|  |  | 3 | Technical contractor to update website. | SO/ARO | No progress. |
| 5.1.2 | Impacts and Benefits Document for Aviation | 2 | Identify contractors and obtain EoIs and quotations Award and manage SSA Review deliverables Write to USA and Australian airline contacts seeking evidence of AMDAR impacts and benefits. | APMG SO/ARO, B.Ford APMG F.Grooters, SO/ARO | No progress. |
| 5.1.3 | AMDAR COMET Training Module | 3 | Contact COMET re development of a AMDAR course. | APMG(C. Weiss), SO/ARO | See App VI, 4.6. |
| 5.1.4 | Impact Studies Assessment | 3 | Commission a paper summarizing results of AMDAR Impact studies including NWP and other Data Users | APMG, (ESRL, ECMWF, ABoM, MF, CMA,SAWS) | SSA in place; Contractor attended Sedona Workshop; Ongoing. |
| 5.1.5 | Attend Aviation Meetings | 2 | Panel to attend AEEC DLUF Meetings in Europe and USA | APMG | S.Taylor to attend AEEC DLUF in Sep 2012, see App VI, 4.13. |
| 5.2..1 | Aircraft Observations Newsletter production | 2 | Newsletters Q1, Q2, Q3, Q4 | C-TOSG, SO/ARO,APMG, AP-FPs. | Newsletters Vol 1-3 published. |
| N/A | AMDAR Panel Admin | 1 | Update of AMDAR Panel ToR | APMG | Completed. Work now subsumed by governance transition process. |
| N/A | AMDAR Panel Admin | 1 | Manage and finalise the transition of the AMDAR Observing System to WMO | APMG | In progress and ongoing |
| 6.1.1 | Organization of Panel Meetings | 1 | Confirm meeting location and date | APMG | Completed. |
|  |  |  | Venue and meeting logistics | Host | Completed or ongoing. |
|  |  |  | Info for participants | Host | Commenced. |
|  |  |  | Doc Plan draft | APMG | Completed. |
|  |  |  | Doc Plan | APMG, SO/ARO, A-FPs | Completed. |
|  |  |  | 2012 Panel Meeting | SO/ARO, (APMG) | TBC |
| 6.1.2 | Organization of AMDAR Panel Management Group Meetings | 1 | Organise and hold APMG Session 3 | APMG, SO/ARO | Completed. |
|  |  |  | Organise and hold APMG Session 4 | APMG, SO/ARO | Completed. |
| 6.2.1 | Reporting and planning associated with ICT-IOS, CBS and ET-AIR | 1 | Finalisation of ET- Work Plan 2013 - 2016 ET-AIR Report to CBS | APMG ET-AIR Chair | Completed. |
|  |  | 1 | Review of EGOS IP | APMG | Completed. |