Aircraft-Based Observations Programme

Strategy and Implementation Plan to 2025 Including Development and Expansion of AMDAR

Version 2013.1D4

# Contents

Contents	2

Scope	3

Requirements, Justification, Aims and Objectives	3

WMO Aircraft-based Observing System Core Activities	4

Implementation Strategy & Plans	6

General Programmematic Strategy & Principles	6

1 Enhancement of AMDAR Observing System Coverage	7

1.1 Extend global AMDAR coverage, particularly over upper air data sparse and developing areas	7

1.2 Address the requirement for national, regional and global optimization	10

1.3 Extend AMDAR Programme to Regional Airlines and GA aircraft and coverage of regional airports	11

2 Extension of the AMDAR System	12

2.1 Implement water vapour sensing measurement	12

2.2 Implement turbulence measurement	14

2.3 Implement icing indication	15

3 Research and Development of New Aircraft Observation Technologies	16

3.1 Manage risks and opportunities associated with new and developing technologies in avionics, communications and metrology.	16

4.  Development and Maintenance of the Aircraft Observing System Quality Management System	17

4.1 Implement a Quality Management Framework for AMDAR that incorporates standardization across national programmes	17

4.2 Develop a National and Global Aircraft Observations Data Management Framework	19

4.3	Standardize AMDAR software function across avionics systems and optional sensors (e.g. water vapour) across aircraft	20

4.4 Manage the data processing and quality assurance for other sources of aircraft data transmitted on the GTS including data provided through ICAO	21

5. Aircraft Observing System Training and Outreach	22

5.1 Develop methods and material for promoting Aircraft Observations and the AMDAR Programme.	22

5.2  Conduct training and outreach activities in support of Core Activities.	23

6. Management and administration of the Aircraft-based Observations Programme	24

6.1 Conduct meetings of members and stakeholders	24

6.2 Coordinate planning activities	25

6.3 Monitor and evaluate the Aircraft -Based Observations Programme	25

Annex 1 Aircraft-Based Observations Programme Core and Long-term Activities	27

Annex 2: EGOS-IP Aircraft-based Observations Development Actions	35

Annex 3: Proposed Aircraft Observations Global Data Management Framework, Version 0.2	39

# Scope

This document describes the strategy and plan for implementation of the enhanced and expanded WMO aircraft-based observing system as a component of the WMO Integrated Global Observing System and the World Weather Watch Global Observing System (GOS). While this includes the strategy and plan for enhancement and coverage expansion of the WMO AMDAR observing system as the primary aircraft-based observing system, it also incorporates the strategy for development and further access to observations from regional airlines (RA) and smaller general aviation (GA) aircraft operating out of regional airports and for increased access to meteorological data generated by ICAO systems that support aviation and airline flight operations. Enhancement through the wider measurement of parameters such as water vapour, atmospheric turbulence and aircraft icing is also incorporated.

The strategy is relevant to WMO Members and partner organizations that currently, or will in the future operate aircraft-based observing systems or contribute to the generation and delivery of data from such systems through the WMO Information System (WIS).

The implementation of the strategy will be overseen by the WMO Commission for Basic Systems (CBS) and under the responsibility of its Expert-Team on Aircraft-Based Observations (ET-ABO) as well as the Commission for Instruments and Methods of Observation (CIMO) under the responsibility of its Task-Team on Aircraft-Based Observations (TT-AO) , relying on the resource input of WMO Members and partner organizations and coordination through the WMO Regional Associations. The programmematic and governance structure for the teams responsible for this development will be referred to as the Aircraft-Based Observations Programme (ABOP).

The strategy will focus in detail on the shorter-term, 5-year evolution of the aircraft-based observing system and, in line with the CBS planning process, extend to longer-term aims and objectives towards 2025 (see Annex 1).

Further background information on the aircraft-based observing system and the AMDAR system is available at: http://www.wmo.int/pages/prog/www/GOS/ABO/index_en.html

# Requirements, Justification, Aims and Objectives

The justification for the requirement to expand and enhance aircraft-based observing system coverage and capability is primarily based on the CBS Implementation Plan for the Evolution of the Global Observing System (EGOS-IP), which determines and specifies requirements, strategy and actions for the evolution of WMO observing systems. The EGOS-IP is founded on the WMO Rolling Review of Requirements process, which undertakes: an assessment of data user and applications requirements; assessment of observing system impacts and capability; identification of observing system gaps and potential for improvement; and, the specification of national, regional and global actions to implement the evolution and improvement process.

The benefits of aircraft-based observations (ABO) to various meteorological data users and application areas, particularly to and by Numerical Weather Prediction (NWP) systems, have been well demonstrated and utilized within the RRR process to provide the basis and justification for the relevant actions within the EGOS-IP.

The global actions relevant to aircraft-based observing systems, which essentially form the basis for the aims and objectives for the development of these systems are extracted from the EGOS-IP and presented in Annex 2 to this document. These actions are summarized as:

- G19: Improve AMDAR Coverage - especially over and within RA I and RA III.

- G20: Extend coverage of existing programmes outside national boundaries and extend optimization capability.

- G21: Work towards extension of AMDAR into aviation standards and systems (avionics and airframes)

- G22: Validation and implementation of water vapour measurement

- G23: Implementation of turbulence and icing capability

- G24: Extend AMDAR to aircraft operating at the regional scale and regional airports.

Taking into account the requirement to support the technical development and also the development and standardization of the operational framework for observing system and data quality management, the Aircraft-Based Observations Programme developed a set of aims and objectives in the form of the Core Activities given below.

## WMO Aircraft-based Observing System Core Activities

1 Enhancement of AMDAR Observing System Coverage.

1.1 Extend global AMDAR coverage, particularly over upper air data sparse and developing areas.

1.2 Address the requirement for national, regional and global optimization

1.3 Extend AMDAR Programme to regional airlines and GA aircraft and coverage of regional airports.

2 Extension of the AMDAR System.

2.1 Implement water vapour sensing measurement.

2.2 Implement turbulence measurement.

2.3 Implement icing indication.

3 Research and Development of New Aircraft Observation Technologies.

3.1 Manage risks and opportunities associated with new and developing technologies in avionics, communications and metrology.

4 Development and Maintenance of the Aircraft Observing System Quality Management System.

4.1 Implement a Quality Management Framework for AMDAR that incorporates standardization across national programmes, taking into account:

1) Data management;

2) Metadata management;

3) Quality control for metrological systems;

4) Systems and data monitoring and evaluation.

4.2 Develop a National and Global Aircraft Observations Data Management Framework.

4.3 Standardize AMDAR software function across avionics systems and optional sensors (e.g. water vapour) across aircraft.

4.4 Manage the data processing and quality assurance for other sources of aircraft data transmitted on the GTS including data provided through ICAO.

5 Aircraft Observing System Training and Outreach.

5.1 Develop methods and material for promoting Aircraft Observations and the AMDAR Programme.

5.2 Conduct training and outreach activities in support of Core Activities.

6 Management and administration of the Aircraft-Based Observing Programme

6.1 Conduct meetings of members and stakeholders.

6.2 Coordinate planning activities.

6.3 Monitor and evaluate the Aircraft-Based Observations Programme.

The strategy and the implementation plan for the ABOP will be focused on implementing the EGOS-IP actions through the undertaking of the above Core Activities.

# Implementation Strategy & Plans

## General Programmematic Strategy & Principles

- The strategy for aircraft-based observations (ABO) will be developed by the ABOP based on undertaking and accomplishing the actions of the CBS EGOS-IP.

- Primary responsibility for ABO system implementation and operation will lie with WMO Member NMHSs in collaboration with partner airlines and organizations.

- The strategy for development of AMDAR and other ABO systems and the 3rd party observational data that are derived from them, are very reliant upon the continued and expanded contribution and cooperation of the aviation industry and, in particular, partner airlines that provide the aircraft platforms, avionics systems and onboard sensors. For this reason, significant resources must be dedicated to the aspects of the programme that strengthen and develop the relationships, agreements, avionic standards and data exchange protocols that are vital for its ongoing operation.

- It is critical that ABO development and expansion is undertaken with a view to the building and maintenance of an aircraft-based observing system that is both stable over the long-term and meets requirements (WMO RRR) for data quality. Therefore, the ABOP must plan for and dedicate resources to both the development of the quality management system for ABO (as a component system of WIGOS) and the integration and maintenance of the system within the wider aviation infrastructure.

- Where possible, Regional Associations should endeavour to promote and coordinate the implementation of ABO systems so as to take advantage of efficiencies associated with regional or sub-regional collaboration in the requirements for development and operation of data processing and optimization system infrastructure.

- Members should endeavour to develop programmes in accordance with WMO and ABOP manuals, guides and standards.

- As an observing system strongly reliant on 3rd party participation, collaboration and cooperation:

  - Outreach and promotional activities must be a core and ongoing component of the ABOP strategy; and.

  - The ABOP must ensure that the programme maintains knowledge and maintenance of the current and future likely aviation and communications protocols and standards relevant to ABO systems.

## 1 Enhancement of AMDAR Observing System Coverage

### 1.1 Extend global AMDAR coverage, particularly over upper air data sparse and developing areas

#### Background

Despite the fact that the existing AMDAR Programmes together currently produce more than 400,000 observations per day, the geographic distribution is not optimal. Upper-air data-sparse areas exist in several parts of the world and first priority should be given to expanding the observations in RA I and RA III where this problem is most pronounced.

A consultants’ study has identified commercial airlines with great potential for providing AMDAR observations in all RAs.

Well established regional or national AMDAR Programmes may provide support and demonstrate their best practices e.g. by participation in regional workshops or by direct interaction with new programmes. Special emphasis will be placed on those Regional Associations or NMHSs that respond to the challenge of establishing an AMDAR programme or further developing an existing programme. The availability of an AMDAR Development Officer provides a time-limited resource for technical guidance and assistance.

#### Strategy

- Use experience and practice of regional and national AMDAR Programme as a model for global expansion: E-AMDAR and US-AMDAR - The ideal incorporates a regional data processing center with data optimization functionality and is depicted by the data management framework diagram shown in Annex 3.

- The ABOP will attempt to develop and nurture a regional approach to ABO and AMDAR Programme implementation through the WMO Regional Associations but also provide requested support directly to those individual NMHSs that have demonstrated capability and drive to establish AMDAR programmes.

- Given the 50% only capacity of the scientific officer responsible for ABOP coordination within the WMO Secretariat, an AMDAR Development Officer will be employed to work with RAs and NMHSs to: 1) Provide ongoing, dedicated development and technical support; 2) Assist putting in place RA AMDAR Implementation Plans; and 3) Provide assistance to develop business cases to motivate airline cooperation and other plans as needed.

- ET-ABO, SO/ARO and ADO will work towards the development on AMDAR Regional Implementation Plans (A-RIPs) that will be incorporated into the Regional WIGOS Implementation Plans (R-WIPs).

- Investigate and take advantage of new & additional opportunities for derivation of aircraft-based observations from ICAO systems, currently including ADS-C, ADS-B and Mode S.

- Through the Training and Outreach activity, hold workshops and training seminars and develop materials that promote, encourage and enable national and regional programme development and expansion.

#### Recent Activities

- Study on coverage and target airlines was carried out by consultants. Report is available at: http://www.wmo.int/pages/prog/www/GOS/ABO/AMDAR/resources/AMDAR_Coverage_Recruitment_Study.html

- An AMDAR Development Officer, ADO was contracted for 12 months (50% capacity) as consultant and started working 1 July 2013.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 1.1.1 Develop global strategy and implementation planning documents (1) | 1.1.1.a Complete initial draft | July 2013 | 9 Sep 2013 | SO/ARO, ADO, C/ET-ABO |
|  | 1.1.1.b Review and complete final draft and obtain approval to publish. | Sep 2013 | Nov 2013 | SO/ARO, ADO, ET-ABO |
| 1.1.2 Develop regional implementation planning template (1) | 1.1.2.a Complete initial draft for review by ET-ABO | August 2013 | 9 Sep 2013 | SO/ARO, ADO, C/ET-ABO |
|  | 1.1.2.b Complete final version | Sep 2013 | 1 Oct 2013 | SO/ARO, ADO, C/ET-ABO |
| 1.1.3 Develop regional implementation plans (1) | 1.1.3.a Establish leadership expert groups in each WMO Region | Sep 2013 | Dec 2013 | ET-ABO(Region Leads), Region I - VI supported by SO/ARO, ADO |
|  | 1.1.3.b Develop 1st drafts of implementation plans for each WMO Region | Sep 2013 | Dec 2013 | Region I - VI supported by SO/ARO, ADO |
|  | 1.1.3.c Attend upcoming RA Meetings over coming 3 years and promote A-RIP. | Jan 2013 | Ongoing | WMO Secretariat, ET-ABO |
| 1.1.4. Develop guidance material for NMHS for programme initiation (1) |  | Q4 2013 | Q2 2014 | SO/ARO, ADO, ET-ABO, TT-AO |
| 1.1.5. Develop cost/benefit information to support RAs (2) | 1.1.5.a. Complete data impact papers on AMDAR and WVSS | Q1 2012 | Q4 2013 | SO/ARO, ADO, C/ET-ABO |
|  | 1.1.5.b.Complete ABO Benefits to Meteorology and Aviation document | Q2 2013 | Q4 2013 | SO/ARO, ADO, C/ET-ABO |
|  | 1.1.5.c.Complete AMDAR Benefits to Aviation document | Q4 2013 | Q2 2014 | SO/ARO, ADO, C/ET-ABO |
| 1.1.6. Work with Avionics Vendors for software development (2) |  | Q3 2013 | Q4 2014 | TT-AO |
| 1.1.7. Optimise and extend existing programme coverage (1) | 1.1.7.a. Investigate international approach to AMDAR data coverage enhancement from existing programmes. | Q1 2013 | Q2 2014 | ET-ABO , Operational Programme FPs |
|  | 1.1.7.b. Work with AirDat and FlyHt to investigate provision of required data only through elimination of redundant data by optimisation. | Q1 2014 | Q3 2014 | SO/ARO, C/TT-AO |
| 1.1.8. .i Investigate the possibility to collect, and increase, observations over polar regions (3) |  | Q3 2014 | Q2 2015 | ET-ABO |
| 1.1.9. Develop proposals for international development projects for ABO and seek funding. (2) |  | TBD | TBD | SO/ARO, C/ET-ABO |

##### Activity Notes

1.1.2.b The final version will be distributed to the contact persons in each WMO Region.

1.1.3.a Each leadership group should include the regional contact persons and key experts.

1.1.5 The cost/benefit information can support RAs/NMHSs in convincing airlines of the benefit of participating in AMDAR programmes.

1.1.6 Cooperation with Avionics Vendors is essential to facilitate access to of-the-shelf AMDAR software. Negotiation is ongoing concerning software for Boeing B777

### 1.2 Address the requirement for national, regional and global optimization

#### Background

AMDAR Programmes have to pay for all or a major part of the observations they acquire from cooperating airlines. If observation frequency is high redundant data may be produced at high cost to the AMDAR Programme. A well designed optimizer makes it possible to define how, where and when observations should be made by the aircraft, thus reducing the operational costs.

Optimization allows a convenient way to rapidly and easily adjust programme coverage and can enhance global coverage by allowing data to be generated outside of national and regional programme coverage boundaries in support of the global programme. This activity, in conjunction with appropriate agreements and cost recovery activity should be further developed. Combining wider use of optimization and the AMDAR activation of international aircraft fleets will support coverage extension of the global AMDAR programme.

Optimization also allows the targeting of observations for weather-related issues and perhaps even for seasonal cycles. This benefit of optimization needs to be further developed and promoted.

#### Strategy

- Use the experience of existing AMDAR Programmes with optimization systems to assist new programmes to develop or acquire optimization systems.

- Explore what e.g. Data Service Providers (DSPs) can offer as service for optimization.

- Work towards development of a standard specification for optimization functional requirements.

- Work towards developing a better structure and possibly an international (WMO) administration for provision of “Supplementary AMDAR Data” - data produced by AMDAR programmes under international agreements that support global coverage extension.

#### Recent Activities

- The Panel and the WMO Secretariat have been liaising with SITA regarding the development of an AMDAR data processing system that might eventually incorporate an optimization system - this would suit both a national and regional approach to programme management.

- The USA has been collaborating with ARINC re an optimization capability for the USA MDCRS programme.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 1.2.1 Develop a standard specification for AMDAR Optimization System (1) |  | Q3 2013 | Q4 2014 | TT-AO |
| 1.2.2 Work with corporate Data Service Providers to enable data optimization services to be available to NMHSs. (2) |  | Q1 2014 | Q3 2014 | SO/ARO, C/TT-AO |
| 1.2.3 Develop an optimization capability for the USA MDCRS Programme. (1) | 1.2.3.a. Implement the standard for AMDAR Data Optimization System in the USA MDCRS Programme | Q1 2015 | Q4 2015 | US FP |

### 1.3 Extend AMDAR Programme to Regional Airlines and GA aircraft and coverage of regional airports

#### Background

What can be achieved in terms of the production of regular vertical profiles of temperature and wind will also depend on the location of airports used by commercial airlines. In some areas there are very long distances between these airports. It is, therefore, of interest to establish cooperation with general aviation operators using regional airports. In this way the observation network can be improved, particularly for vertical profiles.

#### Strategy

- ABOP will continue to investigate and take advantage of new & additional opportunities for derivation of aircraft-based observations from Regional Airlines and General Aviation (GA) aircraft and regional airports through interaction with relevant 3rd party data providers, currently including AirDat and FlyHt, which work directly with smaller regional airlines and operators of GA aircraft putting in place the TAMDAR and AFIRS avionics systems, which are capable of providing aircraft-based observations similar to AMDAR.

#### Recent Activities

- AirDat is now a member of HMEI and has Associate Membership to ET-ABO

- AirDat made presentations to the Panel management group and the AMDAR Panel with a view to collaboration being extended.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 1.3.1 Monitor the results of TAMDAR impact studies undertaken by UKMO and EUMETNET (1) |  | Q3 2013 | Q4 2014 | TT-AO |
| 1.3.2 Collaborate with 3rd party ABO data providers on provision of data to WMO Members (1) |  | Q3 2013 | Ongoing | ET-ABO |

## 2 Extension of the AMDAR System

### 2.1 Implement water vapour sensing measurement

#### Background

As humidity is an essential parameter for prediction of several weather phenomena it is important to include humidity observations in aircraft-based observations programmes. Extensive testing of the WVSS-II equipment in test chambers, on research aircraft and on commercial aircraft was carried out by the AMDAR programmes in Europe and the USA and was considered by the Panel to be the only currently available sensor that adequately meets scientific and AMDAR operational performance standards. Evaluation of the operational performance of various humidity sensors will continue and results documented.

The US-AMDAR programme currently has the WVSS-II sensor operationally installed on more than 100 aircraft and the E-AMDAR is in the process of installing the equipment on 9 aircraft. Other programmes should be stimulated to follow (in line with the actions of the EGOS-IP). However the chief hurdles to overcome are 1) the cost of certification and integration; and, 2) the unwillingness by some airlines to install the equipment due to issues such as: lack of strong business case justification, lack of technical capability, lack of resources, leasing/ownership of the aircraft and “make-good” issues. It is therefore desirable that aircraft would have the equipment installed as a standard or optional deliverable from the factory floor or by retrofit on request. At least one aircraft manufacturer indicated that they would be willing to supply this as optional equipment but only if there is a demonstrable demand for future orders. The costs and cost-sharing between NMHSs and airlines of installation and maintenance is a significant issue and so development of cost/benefits material for WVSS-II integration and operation is and will be critical.

The AMDAR Panel reviewed an initial draft of an implementation plan for WVSS-II and water vapour measurement at its meeting in 2012 and this work is being continued under the CIMO Task Team on Aircraft-Based Observations (TT-AO). That document will form the detailed implementation plan for WVSS-II implementation.

The other currently known source of humidity data from the aircraft platform is via the Panasonic Avionics (formerly AirDat) TAMDAR system. Data has previously been utilized and assessed for impact by NOAA through the Great Lakes Field Experiment (GLFE) that took place during the last decade. EUMETNET currently has an agreement with Panasonic to receive and utilize TAMDAR data and will make an impact assessment of the data over the USA region and other areas as it becomes available via the extension of the TAMDAR network. The ABOP will continue to assess TAMDAR as a source of ABO data.

#### Strategy

- Continue validation of WVSS-II and document the data impacts and the benefits of water vapour measurement as a component of ABO and AMDAR.

- Implement WVSS in current programmes.

- Work toward integration of WVSS as standard on aircraft platforms.

- Evaluation of TAMDAR (UK and ECMWF data impact studies (see also task 3.1.4)

#### Recent activities:

- Testing of WVSS-II in Europe on FAAM (UK) and DENCHAR (Germany) research aircraft (2 sensors on each aircraft): Report from FAAM at AMDAR Projects & Collaboration Site.

- SSA with University of Wisconsin to complete paper(s?) on impacts of AMDAR and WVSS - II, papers to be delivered in Q4 2013

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 2.1.2 Joint Project with ICAO for roll out of WVSS in developing world (1) |  | Q1 2012 | TBD | SO/ARO, ADO, C/ET-ABO |
| 2.1.3 Continue aircraft testing of WVSS (1) |  | 2011 | TBD | TT-AO |
| 2.1.4 Complete WVSS Impact papers (1) |  | Q1 2012 | Q4 2013 | SO/ARO Ralph Petersen |
| 2.1.5 Develop plan for inter-comparison of AMDAR and WVSS with other measurement systems (1) |  | Q3 2013 | Q2 2014 | TT-AO |
| 2.1.6 Write IOM paper on WVSS validation (1) |  | TBD | TBD | TT-AO |
| 2.1.7 Complete two Implementation Plans for WVSS (1) |  | Commenced | Q4 2013 | TT-AO |

##### Activity Notes

2.1.2  A joint WMO-ICAO Project Proposal has been worked out in support of the widespread implementation of AMDAR, including humidity sensors, in commercial aircraft.

2.1.5 The purpose of the validation is to demonstrate that the WVSS-II sensor meets scientific requirements.

2.1.7 One plan concerns implementation in existing AMDAR Programmes and the other plan describes factory equipping of new aircraft with the WVSS sensor.

### 2.2 Implement turbulence measurement

#### Background

Turbulence causes not only discomfort to passengers and airline crew but personal injuries dooccur and damages to aircraft and equipment is not rare. Therefore, measurement and improved forecasting of turbulence is of interest in the area of NMHS services to aviation and, critically, to airline operations and safety, thus strengthening the case for AMDAR participation. Turbulence is difficult to predict in NWP partly because there are too few reliable observations. Pilots do report during flights about turbulence they encounter but the quantification is subjective and data are difficult to use in NWP. Systematic and quantified observations of turbulence and reporting together with other aircraft-based observations will make it possible to predict turbulence as a service to airlines both for route planning and during flight. Very good progress in this field has been made in the USA. The Eddy Dissipation Rate is the ICAO standard metric for turbulence measurement and will become the preferred standard for AMDAR. The new AMDAR Onboard Software Functional Requirements Specification (AOSFRS) will specify the algorithm for routine and event based reporting of EDR. The ABOP has established key contacts and team membership from the FAA and NCAR that can assist in developing and implementing strategy for EDR measurement and data utilization. Another metric of turbulence the Derived Equivalent Vertical Gust - DEVG - is reported by many operational AMDAR programmes.

#### Strategy

- Follow the FAA/NCAR EDR developments:

  - EDR Standardization Project including Operational trials and Forecast products

- Coordinate implementation of EDR outside of USA and especially in Europe.

- Pilot project(s) on EDR implementation in E-AMDAR

- Interact with NWP to ensure they can use the data.

- Interact with ICAO and aviation to determine their requirements for warnings and other aviation application.

#### Recent Activities

- Turbulence workshop in Boulder, November 2012 with NCAR

- Turbulence EDR algorithm integrated into new WMO AMDAR Onboard Software Functional Requirements Specification (AOSFRS).

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 2.2.1 Develop Turbulence Implementation Plan (2) |  | Q4 2013 | Q1 2014 | TT-AO |
| 2.2.2 Negotiate with an EU partner airline for turbulence trial in Europe (2) |  | Q1 2014 | Q3 2014 | TT-AO |

##### Activity Notes

2.2.2 Air France has discussed EDR with one of their Partner Airlines (Delta) and has indicated its interest to participate in this test.

### 2.3 Implement icing indication

#### Background

AMDAR downlink formats provide for the reporting of both icing accretion (to be reported if the aircraft has a sensor and provides the data to the avionics system) and de-icing activation, however no AMDAR programmes currently report this information.

It is likely that the availability of humidity data from the aircraft platform may lead to the derivation of more direct benefits to airline and airline operations, which would strengthen the case for sensor integration and implementation. Possible and potential applications that should be explored and possibly itemized as benefits to aviation are: 1) contrail detection and avoidance; 2) aircraft icing and de-icing performance and operation; 3) fuel burn efficiency.

#### Strategy

- Determine the requirements for reporting of icing-related parameters from AMDAR and, if required, develop planning for implementation of icing and de-icing reporting from AMDAR.

- The benefits of humidity information directly from sensor to cockpit will be clearly explained in the Benefits document (see Sub-Task 1.1.5).

- Explain the benefits to aviation representatives in various meetings.

- Contact aircraft manufacturers about implementation

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 2.3.1 Inform aviation representatives about the benefit of humidity information directly to cockpit (1) |  | Q3 2014 | Ongoing | SO/ARO, C/ET-ABO, C/TT-AO and AMDAR PMs |
| 2.3.2. Discuss with aircraft manufacturer the implication of arranging humidity information from sensor to cockpit (1) |  | Q3 2014 | Ongoing | SO/ARO, C/ET-ABO, C/TT-AO |

##### Activity Notes

## 3 Research and Development of New Aircraft Observation Technologies

### 3.1 Manage risks and opportunities associated with new and developing technologies in avionics, communications and metrology.

#### Background

The continuing increase of air traffic requires new systems with increased capacity for air traffic control and, therefore, also improved systems for communications. This is very evident in Europe with the evolution of the SESAR concept and in the USA with the Next-Gen concept. The avionics and communications are areas where development is fast and many organizations and companies are involved. Changes in technology can potentially be expensive for AMDAR programmes if they would have to finance development and implementation of software for reporting of weather observations from aircraft. The WMO Secretariat and TT-AO, follows this development e.g by participation in fora like ARINC Data Link Users Forum (DLUF). TT-AO and expert teams in AMDAR programmes follow the development also in observation technologies. Cockpit and cabin broadband communication will be available in near future and it is essential that AMDAR takes advantage of the significantly greater bandwith and lower communication charges.

#### Strategy

- Investigate and take advantage of new and developing technologies for communications and avionics (e.g. satellite TCP/IP communication solutions, data from ADS-Broadcast for GA aircraft and ADS-Contract for international oceanic traffic)

- Investigate and take advantage of new or developing technologies for observation of meteorological parameters.

#### Recent development

- Plan for study on new technologies to be undertaken by consultant (AMDAR Panel 15th Session)).

- Expert on ADS-B/Mode S is member of TT-AO (S. de Haan, Netherlands)

- Expert on TAMDAR is associate member of ET-ABO

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 3.1.1 A SSA for Study of new technologies to be put in place (1) |  | Q4 2013 | Q2 2014 | SO/ARO, C/TT-AO |
| 3.1.2 Work with ICAO to extend ADS-C data on GTS with enhanced quality assurance (1) |  | Q4 2013 | Q4 2014 | ET-ABO |
| 3.1.3 Submit to Aviation bodies the meteorological requirements for ADS-B/Mode-S (1) |  | Q4 2013 | Q4 2013 | TT-AO |
| 3.1.4 Monitor and evaluate TAMDAR data impact on UK and ECMWF NWP (1) |  | Commenced | Q3 2014 | ET-ABO |
| 3.1.5 Attend meetings of relevance to AMDAR Technical Development (1) |  | Q2 2013 | Ongoing | TT-AO, SO/ARO |

##### Activity Notes

## 4.  Development and Maintenance of the Aircraft Observing System Quality Management System

### 4.1 Implement a Quality Management Framework for AMDAR that incorporates standardization across national programmes

#### Background

Observational data must have a defined and known quality. This is essential for the utilization of the data and the products generated from these data so that the products will meet the user requirements.

An expert workshop dedicated to ABO Data Management was held in June 2012, which addressed many issues related to data quality, focusing chiefly on data quality control and quality monitoring. Data monitoring is currently largely based on a monthly cycle and, given the reliance on NWP for ABO data, it will be necessary for the ABOP to work towards support for a (near) real-time monitoring programme.

The description of the data and its quality is based on access to metadata. It should be noted here that aircraft based observation systems are different from most other observation systems in that the equipment (possibly with the exception of humidity sensors) does not belong to the NMHSs but to the participating airlines. Airlines have different policies concerning what information they are willing to share with others. This may limit the access to some categories of metadata as well as the possibility to keep registers of metadata updated.

The ABOP through TT-AO is required to take the lead in investigating any data quality and systems issues that might arise.

#### Strategy

- Integrate existing regulatory material from the AMDAR Panel into reference manuals (WIGOS/GOS and CIMO Guide).

- Refine the ABO Quality Management System and data management concepts developed at the Workshop on Aircraft Observing System Data Management of June 2012.

- Develop, define and implement the AMDAR metadata model through WIGOS.

- Investigate and resolve any data or systems issues, particularly making use of results from data monitoring programmes.

- Work within the frameworks of the WIGOS metadata model to ensure incorporation and adherence of ABO metadata.

- Work towards improvement and update of requirements for ABO data quality control and monitoring based on outcomes and recommendations of the Workshop on Aircraft Observing System Data Management .

#### Recent development

- Update to CIMO guide drafted

- Workshop on Aircraft Observing System Data Management held in June 2012 which also addressed many aspects of data quality control and data monitoring.

- Definition of a AMDAR metadata standard has been approved.

- Metadata Implementation Plan drafted.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 4.1.1 Implement a Quality Management Framework that incorporates standardization across national programmes (1) |  | Commenced | Ongoing | TT-AO |
| 4.1.2 Continue work on regulatory material integration. (1) |  | Commenced | Ongoing | ET-ABO, TT-AO |
| 4.1.3 Develop and Implement a Metadata Management Framework for Aircraft-based Observations including AMDAR (1) | 4.1.3.a Continue and finalize the development of the Implementation Plan for a metadata management framework for ABO | Commenced | Q4 2014 | ET-ABO |
|  | 4.1.3.b Implement the plan described in 4.1.3.a | ? | ? |  |
| 4.1.4 Investigate AMDAR Temperature Bias |  | Q1 2014 | TBD | TT-AO |

##### Activity Notes

4.1.1. This Quality Management Framework should take into account:

1) Data management;

2) Metadata management;

3) Quality control for metrological systems; and,

4) Systems and data monitoring and evaluation.

4.1.2. This task refers to the migration of material from the AMDAR Reference Manual to the GOS and CIMO guides.

4.1.3. E-AMDAR runs a pilot project to transfer metadata from E-AMDAR to WMO

### 4.2 Develop a National and Global Aircraft Observations Data Management Framework

#### Background

The AMDAR data management framework is quite well developed and robust. A significant issue that was raised at the Workshop on Aircraft Observing System Data Management was that of the establishment of a global data center for ABO data.

#### Strategy

- Refine the ABO Quality Management System and data management concepts developed at the Workshop on Aircraft Observing System Data Management of June 2012

- Develop, define and implement the AMDAR metadata model through WIGOS

#### Recent development

- Workshop on on Aircraft Observing System Data Management held in June 2012 which also addressed many aspects of data quality control and data monitoring.

- The new WMO General AMDAR BUFR Template was approved by CIMO 1st May 2012

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 4.2.1 Establish AO Data Centre (1) |  | Q1 2013 | Q4 2014 | SO/ARO, C/ET-ABO |

##### Activity Notes

### 4.3	Standardize AMDAR software function across avionics systems and optional sensors (e.g. water vapour) across aircraft

#### Background

There exists two standard onboard software specifications for automatic weather reporting, ARINC 620 and the AAA and they are implemented in several different versions in various aircraft. Although the two specifications to some extent are similar they do not offer the same options and the same degree of flexibility. Furthermore, they need updating from time to time as the meteorological requirements change e.g. with the introduction of new sensors or new parameters. Clearly there will be future benefits to have one standardized and flexible software with great possibilities for adapting to future needs.

#### Strategy

- Cooperate with consultants as needed for software development

- Cooperate with avionics vendors and DSPs for software development

- Cooperate with airlines for implementation onboard of the improved software

- Determine the strategy and practice in relation to use of the AOSFRS and the AEEC ARINC 620 standard containing the definition of the Met. Report.

#### Recent development

- Meteorology Report updated to version 5 in the AEEC industry standard ARINC 620.

- New WMO AMDAR Onboard Software Functional Requirements Specification - AOSFRS (WMO Special Service Agreement with consultant) completed.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 4.3.1 Final review of AOSFRS and publish as IOM (1) |  | Ongoing | Q2 2014 | TT-AO |
| 4.3.2 Approach Teledyne Controls and Honeywell to implement AOSFRS as a standard catalogue avionics application (1) |  | Q2 2014 | Q4 2014 | TT-AO |
| 4.3.3 Cooperate with airlines for implementation onboard of the improved software (1) |  | Q2 2014 | Ongoing | TT-AO, MDAR PMs |

##### Activity Notes

### 4.4 Manage the data processing and quality assurance for other sources of aircraft data transmitted on the GTS including data provided through ICAO

#### Background

Some aircraft data e.g. those collected according to ICAO regulations are ingested on the GTS by WAFCs  but also – illegitimately - by ATCs/ATMs without any quality control. It is very good that airlines collect these data and that they are made available, but it is not acceptable that the data quality is unknown. Cooperation will have to be established with ICAO and other organization supplying data to the GTS to solve any data quality issue. The management and quality control of ICAO data is currently a significant issue that requires resolution.

#### Strategy

- Work with ICAO to develop data and quality management practices for ADS data sources and in line with the DM Framework in Annex 3.

#### Recent development

- This problem was raised with ICAO at the AMDAR Panel meeting in November 2011.

- The ABOP supported a working paper by IATA putting forward a proposal that a QC system is developed for ADS data - WMO proposed a solution for this issue and the ABOP has commenced dialogue with ICAO relating to this development.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 4.4.1.a Establish cooperation with ICAO (1) |  | Q4 2013 | Q4 2014 | SO/ARO, C/ET-ABO,TT-AO |

##### Activity Notes

## 5. Aircraft Observing System Training and Outreach

### 5.1 Develop methods and material for promoting Aircraft Observations and the AMDAR Programme.

#### Background

WMO presents an update on AMDAR to the aviation industry e.g. at DLUF once or twice every year. Opportunities to do the same in other fora should be utilized by the Secretariat or through representation by national or regional AMDAR programmes e.g in their meetings with cooperating airlines. WMO promotes AMDAR e.g. by publishing the AMDAR Newsletter as well as the monthly statistical reports on the WMO web. Information about this is disseminated to national contact points. However, this requires initiatives to read the material. A more direct way to actively inform NMHSs about benefits of AMDAR use should be found. This is one of several reasons why regional workshops could be held e.g. in conjunction with meetings of ET-ABO and TT-AO in various RAs.

#### Strategy

- Use the WMO website, the AMDAR News & Events site, the email forums and relevant social media to ensure AMDAR and ABO are promoted to NMHSs and the aviation industry.

- Continue the development of business case and benefit documents and materials to ensure NMHSs have, or are given access to, the necessary information to develop their own business cases and airline partnerships.

- Ensure new programmes comply with standards and guidelines (regulations and QMS).

#### Recent activities

- WMO Website revised and updated.

- News & Events site with 5 volumes of the newsletter published.

- AMDAR Projects & Collaboration site for Members established.

- Latest regional workshop for AMDAR held in November 2011 (Mexico)

- Requirements for an online COMET Training module on AMDAR have been defined and the development has been costed

- SSA commenced to produce two papers on AMDAR data impact to be published in AMS

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 5.1.1 Continue to develop online information and resources (1) |  | Commenced | Ongoing | SO/ARO, |
| 5.1.2 Publish Newsletter biannually (1) |  | Commenced | Ongoing | SO/ARO |
| 5.1.3 SSA on Business Case for Airline Participation in AMDAR (1) |  | Q4 2013 | Q2 2014 | ET-ABO |
| 5.1.4 Establish MoU with participating airlines for cross-promotion on websites (3) |  | Q3 2014 | Ongoing | ET-ABO |
| 5.1.5 Further work on Training Module possibly leading to tender process (2) |  | Q4 2013 | Q2 2014 | ET-ABO |

##### Activity Notes

5.1.3  It is very important that the report is described from the aviation perspective and by a person trusted by the aviation community.

5.2.5  The Training Module has been costed but funding is needed.

### 5.2  Conduct training and outreach activities in support of Core Activities.

#### Background

Continuing the work of the AMDAR Panel, the ABOP will provide support for Workshops on AMDAR though input of technical guidance and training.

#### Strategy

- Building on the transfer of AMDAR to WMO, the ABOP should endeavor to make use of the resources and expertise of the WMO Education and Training Department (ETD) for delivery of workshops and training.

- Plan , coordinate and work with WMO ETD  to hold workshops and training seminars on AMDAR and ABO in areas and with stakeholders strategic to AMDAR programme development

#### Recent Activity

- Regional workshop on AMDAR was last held in Mexico City in November 2011.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 5.2.1 Conduct training and outreach activities in support of Core Activities (1) | 5.2.1.a Conduct workshops in Middle East and in RA I | Ongoing | Mid-East workshop Q1 2014 RA I Q2 2014 | SO/ARO, ADO, C/ET-ABO |
|  | 5.2.1.c Representative of ABOP to attend all RA Sessions | Q1 2014 | Ongoing, based on schedules of RA Sessions | SO/ARO, C/ET-ABO C/TT-AO |
|  | 5.2.1.d. Conduct workshops in regions and areas targeted for coverage enhancement. | Ongoing | Ongoing | SO/ARO, ADO, C/ET-ABO |

Activity Notes

## 6. Management and administration of the Aircraft-based Observations Programme

### 6.1 Conduct meetings of members and stakeholders

#### Background

For background on the structure of ABOP, see: http://www.wmo.int/pages/prog/www/GOS/ABO/ABOWorkTeams.html

Keeping the biennial meetings of ET-ABO and TT-AO open not only to official contact points but also to other persons actively working with AMDAR programmes and those who consider starting AMDAR programmes will promote AMDAR and facilitate coordinated planning.

The two teams of the ABOP are obliged to develop and seek approval of their respective work plans and budgets for use of the AMDAR Trust Fund under its ToR.

#### Strategy

- Teams to meet in alternate years.

- Meeting of ET-ABO to be possibly held in location targeted for development and in conjunction with workshops.

- Work plans and budgets for ABOP teams to be revised and updated on an annual basis by the end of December.

- Seek to ensure WMO regular budget supports meetings in future.

#### Recent activities

- Work Team online area established on WMO Website

- ET-ABO Session 1 to be held in Geneva on 10-13 September 2013

- TT-AO Session 1 planned for Q1 2014

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 6.1.1Hold ET-ABO-1 (1) |  |  | 13 Sep 2013 | SO/ARO, ADO, C/ET-ABO |
| 6.1.2 Hold TT-AO in Q1 2014 (1) |  |  | 1 April 2014 | SO/ARO, C/TT-AO |

##### Activity Notes

### 6.2 Coordinate planning activities

#### Background

The ABOP is dependant on an organization that is literally spread out over the world. As new AMDAR Programmes will be started the number of persons involved will increase. It is essential that the WMO Secretariat coordinates the planning process and arranges follow-up meetings. These cannot all be physical meetings and, therefore, meetings by WebEx (or similar systems) and telephone are essential.

#### Strategy

The WMO Secretatiat will:

- Take initiative for the planning process so that plans on different levels are harmonized

- Keep frequent contact with those involved in the planning

- Give feedback on all draft plans

#### Recent activities

- Work Plan ET-ABO approved.

- Work Plan TT-AO approved.

- Budget for 2013-16 developed and approved.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 6.2.1 Regular (monthly) task-focused WebEx meetings (1) |  | Commenced | Ongoing | SO/ARO, C/ET-ABO C/TT-AO |

##### Activity Notes

### 6.3 Monitor and evaluate the Aircraft -Based Observations Programme

#### Background

The WMO Secretariat and the respective leadership of the Technical Commission (TC) teams are responsible for monitoring the performance of the work teams and their progress on achieving the aims and objectives of the ABOP.

#### Strategy

- Each team will have responsibility for reporting to its parent body within the relevant WMO Technical Commission.

- Expenditure from the AMDAR Trust will be monitored and administered by the WMO Secretariat and authorized by the ABO-MG as defined in the ToR for the Trust.

- The annual update of the work plans and the budget should incorporate documentation of progress and actual expenditure versus planned.

#### Recent activities

- Work plans and budgets were developed and approved for each team for 2013-14.

#### Medium-term Implementation Plan [5 years]

| Task (Priority) | Sub-Task | Commence | Complete | Responsibility |
| --- | --- | --- | --- | --- |
| 6.3.1 Regular reporting from ET-ABO (1) | ET-ABO report to ICT-IOS and CBS |  | Q1 2014 | C/ET-ABO |
| 6.3.2 Regular reporting from TT-AO (1) | TT-AO will report to CIMO MG |  | Q1 2014 | C/TT-AO |

##### Activity Notes

# Annex 1 Aircraft-Based Observations Programme Core and Long-term Activities

Core Activity 1: Enhancement of AMDAR Observing System Coverage

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Extend global AMDAR coverage, particularly over upper air data sparse and developing areas. | 1. Regional and national workshops; 2. Training and Outreach; 3. Liaison with NMHSs, Airlines and Avionics service providers; 4. Liaison with stakeholders and data users; 5. Studies on data coverage and airline capabilities; 6.Assessment and use of impact studies; 7. Facilitate, coordinate and promote data provision among and outside AMDAR programmes. | 1. AMDAR Workshops; 2. AMDAR training materials; 3. Extension of AMDAR expertise; 4. Results and reports of studies; 5. AMDAR data provided beyond national AMDAR Programme requirements. | 1. More airlines recruited; 2. More national AMDAR programmes; 3. Better AMDAR global data coverage; 4. Significant, positive impact on applications and for Data Users. | EGOS-IP Action G19 | 1 | Ongoing to 2025 |
| 1.2 | Address the requirement for national, regional and global optimization | 1. Promote the implementation and use of AMDAR Data Optimisation Systems; 2. Specification of AMDAR data requirements; 3. Specification of optimization requirements; 4. Liaison with WMO/CBS/E-EGOS. | 1. Studies and reports 2. Specifications 3. Optimised AMDAR Programmes | 1. More efficient use of Member resources 2. Improved AMDAR data coverage | EGOS-IP Action G20 | 1 | Ongoing to 2025 |
| 1.3 | Extend AMDAR Programme to GA aircraft and coverage of regional airports. | 1. Research, trial and study of new and developing aircraft observing systems, avionics systems, communications systems and sensors appropriate for GA aircraft application 2. Develop standards associated with new aircraft observing systems for GA aircraft 3. Assist Members in the implementation of proven and approved aircraft observing systems for GA aircraft. | 1. Studies and reports 2. Manuals and guides 3. Programmes incorporating GA aircraft | 1. More airlines recruited 2. Better AMDAR global data coverage 3. Significant, positive impact on applications and for Data Users. | EGOS-IP Action G24 | 3 | Ongoing to 2025 |

Core Activity 2: Extension of the AMDAR System

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Implement water vapour measurement | 1. Undertake planning and project coordination in the implementation by Members of WV measurement within the AMDAR Observing System 2. Coordinate negotiations and interactions with sensor manufacturers 3. Coordinate negotiations and develop agreements for standardization with aircraft and avionics manufacturers and aviation standards authorities. 4. Promote the standardization of aircraft equipment by merging the interests of meteorology pilots, airlines, ATM, NMHSs, Environmental control for - better deicing warning, - deicing efficiency, - NWP, - contrail warning. | 1. Studies and reports 2. Business cases for NMHSs and Airlines 3. International WV Project 4. Certificates (STCs) for aircraft 5. Agreements between the relevant stakeholders. | 1. WV capability for AMDAR Programme 2. Significant, positive impact on applications and for Data Users. 3. Ex-works availability AMDAR + humidity + particles. | EGOS-IP Action G22 | 1 | Ongoing to 2025 |
| 2.2 | Implement turbulence measurement. | 1. Undertake planning and project coordination in the implementation by Members of turbulence measurement within the AMDAR Observing System; 2. Coordinate negotiations and interactions with algorithm developers; 3. Coordinate negotiations for standardisation with aircraft and avionics manufacturers and aviation standards authorities. | 1. Specification of turbulence requirements for reporting in software standards. 2. AMDAR Software applications that include reporting of turbulence (EDR). 3. A standard turbulence metric reported from the AMDAR Programme. | 1. Turbulence data produced and used by the aviation, NWP and forecasting communities. 2. Improved monitoring and prediction of turbulence in support of the aviation industry. 3. More acceptance of the AMDAR programme as a contributor and benefit to aviation operations. | EGOS-IP Action G23 | 1 | Ongoing to 2015 |
| 2.3 | Implement icing indication in cockpit. | 1. Undertake planning and project coordination in the implementation by Members of icing measurement within the AMDAR Observing System; 2. Coordinate negotiations for standardisation with aircraft and avionics manufacturers and aviation standards authorities. | 1. Specification of requirements for transferring humidity and temperature data to an icing indication. 2. Decision by at least one aircraft manufacturer to implement icing indication in cockpit | 1. Concrete discussions with aircraft manufacturers will be possible. 2.a. Improved icing indication available in cockpit. 2.b. Installation of WVSS ex-works on airlines’ expense possible | EGOS-IP Action G23 | 2 | Ongoing to 2020 |

Core Activity 3: Research and Development of New Aircraft Observations Technologies

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Manage risks and opportunities associated with new and developing technologies in avionics, communications and metrology. | 1. Research, trial and study of new and developing aircraft observing systems, avionics systems, communications systems and sensors appropriate for aircraft application; 2. Attend and report on appropriate aviation meetings and forums that develop and define standards relating to avionics and communications 3. Develop standards associated with new aircraft observing system technologies; 4. Assist Members in the implementation of proven and approved technologies for aircraft observing systems. | 1. Reports, expert advise and recommendations to Members. 2.a. Insight into the development driven by other stakeholders in aviation, and 2.b. Gives some possibility to influence development by describing the needs from meteorology. 3. Prepararation of new aircraft for AMDAR service. 4. Upgraded or modernized observation system | 1. Increased knowledge, readiness to improve observation systems or routines. 2. Preparedness for future changes or investments 3. and 4. Maintaining or expanding AMDAR fleets | EGOS-IP Action G21 | 1 | Ongoing to 2025 |

Core Activity 4: Development and Maintenance of the Aircraft Observing System Quality Management System

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Implement a Quality Management Framework for AMDAR that incorporates standardization across national programmes, taking into account: 1. Data management; 2. Metadata management; 3. Quality control for metrological systems; 4. Systems and data monitoring and evaluation. | 1. Coordinate (expert) meetings, projects and tasks related to the development of standards; 2.Approve and document standards; 3. Coordinate the implementation of standards by Members. | 1. and 2. New standards as guidance to Members 3. Assistance to Members | 1. and 2. Improved understanding for the need of data management 3. Improved data management, improved data quality | WMO-ER-4 | 1 | Ongoing to 2025 |
| 4.2 | Develop a National and Global Aircraft Observations Data Management Framework. | 1. Coordinate (expert)meetings, projects and tasks related to the development of a DMF; 2. Approve and document the DMF; 3. Coordinate the implementation of the DMF by Members. | 1. and 2. New standards as guidance to Members 3. Assistance to Members | 1. and 2. Improved understanding for the need of data management 3. Improved data management, improved data quality | WMO-ER-4 | 1 | Ongoing to 2015 |
| 4.3 | Standardize AMDAR software function across avionics systems and optional sensors (e.g. water vapour) across aircraft. | 1. Coordinate with and attend meetings with representatives of airlines, avionics manufacturers, and other aviation bodies as appropriate; 2. Coordinate implementation of the establishment of software and sensor standards. | 1. Reports, expert advise and recommendations to Members. 2. AMDAR fleets with upgraded or expanded capabilities. | 1. Increased knowledge, readiness to improve observation systems or routines. 2. More observations, more parameters or observations of improved quality. | EGOS-IP Action G21 | 2 | Ongoing to 2020 |
| 4.4 | Manage the data processing and quality assurance for other sources of aircraft data transmitted on the GTS including data provided through ICAO. | 1. Coordinate with and attend meetings with representatives of data providers (e.g. ICAO); 2. Coordinate the establishment of standards for aircraft data other than AMDAR (ADS, Mode-S). | 1. and 2. Reports and expert advice to Members and data providers | 1. and 2. Access to more aircraft observations and with known, improved, quality. | WMO-ER-4 | 2 | Ongoing to 2025 |

Core Activity 5:  Aircraft Observing System Training and Outreach

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Develop methods and material for promoting and developing Aircraft Observations and the AMDAR Programme. | 1. Define, develop and manage the content of the Aircraft Observing System WMO website; 2. Specify and coordinate the development of promotional material, e.g. flyers, papers, posters, etc; 3. Specify and coordinate the development of training material for Members. | 1. Continuous improvement of the website. 2. More and improved promotional material. 3. New or improved training material. | 1. Increased interaction by Members and inproved service to Members. 2. ABO becomes beter known and attracts more participants. 3. Wider active use of ABO data by Members in addition to the NWP. | EGOS-IP Action G20 | 2 | Ongoing to 2025 |
| 5.2 | Conduct training and outreach activities in support of Core Activities. | 1. Conduct technical workshops for Members; 2. Coordinate and conduct meetings, workshops and conferences with appropriate stakeholders. | 1. Reports, expert advice and increased knowledge to Members 2. Reports, expert advice and increased knowledge to participants. | 1. a. ABO becomes beter known and attracts more participants. 1.b.. Wider active use of ABO data by Members in addition to the NWP. 2. ABO becomes beter known and attracts more participants. | EGOS-IP Action G20 | 2 | Ongoing to 2025 |

Core Activity 6: Management and Administration of the Aircraft Observing System Programme

| Long-term Activity | Description | Activities | Outputs | Outcomes/Impacts | Justification | Priority (1-3) | Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Conduct meetings of members and stakeholders. | 1. Coordinate meetings of ET-ABO; 2. Coordinate meetings of ET-AIR; =TT-AO?? 3. Coordinate meetings of the Aircraft –based Observations Programme Management Group (APMG). | 1. – 3. Reports and recommendations | 1. – 3. Better governance and efficiency | WMO-ER-4 | 1 | Ongoing to 2025 |
| 6.2 | Coordinate planning activities. | 1. Develop plans for extension and enhancement of the AMDAR Observing System. | 1. Plans and recommendations. | 1. Possible extension and enhancement of the existing system | WMO-ER-4 | 1 | Ongoing to 2025 |
| 6.3 | Monitor and evaluate the Aircraft Observations Programme. | 1. Develop and maintain diagnostics and tools for monitoring and evaluating progress of the development of the Aircraft Observations Programme. | 1. Tools for monitoring and evaluation. | 1. Improved quality of ABOP and better use of resources. | WMO-ER-4 | 2 | Ongoing to 2025 |

# Annex 2: EGOS-IP Aircraft-based Observations Development Actions

The fundamental basis for global development of the aircraft-based observing sytem and the AMDAR system is the IMPLEMENTATION PLAN FOR THE EVOLUTION OF GLOBAL OBSERVING SYSTEMS (EGOS-IP) and, in particular, the actions on Aircraft meteorological stations under Recommendations for the evolution of Surface-Based Sub-system of GOS, Section 5.3.1.3:

5.3.1.3. Aircraft meteorological stations

In the northern hemisphere, meteorological data derived from aircraft stations, especially the automatic data produced by the AMDAR system, are an excellent complement to the data derived from the radiosonde network. This system produces vertical profile data in the vicinity of airports and single-level data when aircraft are flying at cruise levels. It has been shown through NWP impact studies that their impact on numerical forecasts has a magnitude similar to the impact of the radiosonde network. In the southern hemisphere and in the tropics the aircraft data coverage is very poor although there is some potential for developing it, preferably in a way that is complementary to existing AMDAR and radiosonde networks.

Extending aircraft observations data coverage is important and can be achieved through the extension of the programme to new airlines and aircraft operating in data-sparse areas. The programme coverage can also be improved greatly through an optimization process. This can be achieved through two general activities. Firstly, existing programmes can be extended so that internationally-operating aircraft are activated for reporting outside the national areas or regions that tend to be restricted by national programme constraints. Secondly, one can enhance the capabilities of programmes to control data output through the wider development and implementation of automated data optimization systems. Such systems, whilst allowing the efficient growth of the programme outside and across international boundaries with appropriate agreements in place, will also offer the potential to utilize the AMDAR system as an adaptive observing network (capability to change the reporting regime to serve the changing purposes of programme areas).

Action G19

Action: Improve AMDAR coverage over areas that currently have poor coverage, especially within Regions I and III, focussing on the provision of data at airports in the tropics and southern hemisphere where vertical profiles are most needed to complement current radiosonde data coverage and its likely evolution.

Who: NMSs, NMHSs in collaboration with commercial and other airlines, RAs. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicators: Number of airports where AMDAR measurements are taken. Amount of vertical profiles and AMDAR data in general, measured by the usual indicators of current AMDAR programmes.

Action G20

Action: Extend the AMDAR programme so as to equip and activate more internationally operating fleets and aircraft (i.e. fleets and aircraft flying to and between international airports outside the country of origin) and extend the use of data optimization systems in support of improved upper-air observations coverage and efficiency, and also the adaptive functionality of the system.

Who: NMSs, NMHSs in collaboration with commercial and other airlines, RAs, CBS and AMDAR Programme Management. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicators: The number of airports where AMDAR measurements are taken and number of vertical profiles per day at each airport. The number of international airlines and aircraft equipped to provide AMDAR observations. The adaptability of the AMDAR programme.

Action G21

Action: Given the nature of the aircraft observing system as an increasingly critical and

basic component of the Global Observing System, seek to establish agreements with airlines and the aviation industry to ensure that the system, infrastructure, data and communications protocols are supported and standardized within relevant aviation industry frameworks so as to ensure continuity and reliability of the system.

Who: NMSs, NMHSs in collaboration with national and other airlines and aviation industry, RAs, CBS and AMDAR Programme Management. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicators: Agreements made with aviation industry partners and organizations. Data produced by humidity sensors are now used operationally from an increasing number of aircraft both in the USA and Europe, and it is critical and strategic to continue this development in order to converge to systems which measure humidity as well as air pressure (pressure altitude), temperature and wind as do radiosondes. Such an extension will provide an increased opportunity to restructure the upper-air observing systems for efficiency and improvement in coverage.

Action G22

Action: Continue the development and operational implementation of humidity sensors as an integrated component of the AMDAR system to ensure that humidity data is, processed and transmitted in the same way as wind and temperature.

Who: NMSs, NMHSs in collaboration with commercial and other airlines and TCs (CBS, CIMO) and AMDAR Programme Management. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicator: A number of aircraft providing humidity data in real-time.The lower cost of aircraft observations in comparison to the radiosonde information as well as the reduced reliance on ground-based systems and infrastructure make it an ideal candidate system for rapid and reliable expansion of upper-air observations for developing countries in support of local, regional and global data users. Such an expansion should be undertaken in parallel with the necessary development action to facilitate the provision and utilization of data. Observations of turbulence and icing are also made on some aircraft and it is desirable to expand this capability of the AMDAR system with these parameters in support of aviation operations and safety as well as other meteorological applications.

Action G23

Action: Enhance and extend the capability to report observations of atmospheric turbulence and icing variables as an integrated component of the AMDAR system and in line with the requirements of the relevant programme areas and data users.

Who: NMSs, NMHSs in collaboration with airlines and TC (CBS, CIMO) and AMDAR Programme Management l, RAs. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicator: A number of aircraft providing atmospheric turbulence and icing data in real-time.

Another source of important potential progress is the research and development actions associated with AMDAR systems for small aircraft, usually referred to as General Aviation (GA) aircraft. These aircraft tend to fly and generate level data in the middle troposphere whilst operating over shorter regional flight legs. This type of observation would be very useful for regional and local purposes and could also contribute to global data coverage. Priority should be placed on equipping aircraft operating on, to and out of isolated islands and remote sites where radiosonde observations are not available, e.g. deserts, islands and the Arctic. The impact of existing data sets (derived from deployment of the commercial communications and sensor system) on high resolution NWP models has been evaluated and compared to other observing systems such as profilers and radars. The results are encouraging: see for example Moninger et al. (2010) and Benjamin et al. (2010). In spite of several technical snags, AMDAR systems for GA aircraft do have potential for contributing to the improvement of data coverage of vertical profiles of AMDAR measurements (wind, temperature, humidity, turbulence and icing) in the lower troposphere and this development should be pursued whilst taking into account the potential associated with new and developing technologies such as ADS-B and Mode S.

Action G24

Action: Develop and implement operational AMDAR systems which are adapted to small aircrafts operating at the regional scale and flying at low altitude in the troposphere.

Who: Airlines operating small aircraft, NMSs, NMHSs in collaboration with RAs, CBS and

AMDAR Programme Management. AMDAR Programme Management to lead the action.

Time-frame: Continuous.

Performance indicator: Number of small aircrafts providing AMDAR observations operationally in real-time.

Atmospheric composition measurements for several species, aerosols and volcanic ash are measured on some aircraft, but more in research than in operational mode. The actions related to atmospheric chemistry are documented in section 5.3.8.4.

# Annex 3: Proposed Aircraft Observations Global Data Management Framework, Version 0.2

# Footnotes

http://www.wmo.int/pages/prog/www/GOS/ABO/ABOWorkTeams.html

http://www.wmo.int/pages/prog/www/OSY/gos-vision.html#egos-ip

AMDAR Coverage & Targeting for Future Airline Recruitment

# Comments

S.Stringer: Should this be reporting rather than measurement?