| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS EXPERT TEAM ON REQUIREMENTS AND IMPLEMENTATION AWS PLATFORMS (ET-AWS) SEVENTH SESSION GENEVA, SWITZERLAND, 16-20 APRIL 2012 | CBS/OPAG-IOS (ET-AWS-7)/Doc.14(1) (12.03.2012) _________ ITEM: 14 Original: ENGLISH ONLY |
| --- | --- |

ET-AWS workplan for the period 2010 to 2012

Submitted by the WMO Secretariat

(RAtkinson@wmo.int)

________________________________________________________________

Summary and Purpose of Document

This document presents the ET-AWS Work Plan as updated at ET-AWS Session 6 (2010).

________________________________________________________________

ACTION PROPOSED

This meeting is invited to update the work plan, taking into account progress made on agreed tasks since ET-AWS-6 and work still to be completed.

__________________

ET-AWS workplan for the period 2010 to 2012

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | To contribute to the development and implementation of concept of WIGOS and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by EC-WG/WIGOS-WIS-2 | ET-AWS-7 Mtg | MONNIK, Karl MERROUCHI Rabia | On-going/ | Focus on the 3 areas of standardization Instruments and methods of observations WIS information exchange and discovery End-product quality assurance |
| 2 | Develop and maintain the requirements and specifications for automated observations networks in collaboration with ET-EGOS and application areas | Monitor and update AWS Functional Specifications (FS) for all WMO-related Programmes Update on request the list of basic set of variables to be reported by a standard AWS for multiple users | ET-AWS-7 | MERROUCHI, Rabia VAN DER MEULEN Jitze |  | Refer to Annex III.1 of Guide on GOS - Request review of relevant parts by other TCs, program areas - Prepare final draft of FS for next meeting Review Annex III.2 of Guide on GOS before ET-AWS-7 and propose updates if necessary |
| 3 | Develop the requirements and standards for a basic, robust AWS suitable for less developed, remote and extreme climate conditions, taking advantage of advances in technology | Prepare recommendations for addressing challenges facing the operation of AWS Networks. Report on advances in AWS technology Review challenges, solutions and advances in liaison with HMEI | ET-AWS-7 | NITU Rodica SEVAKULA Krishnaiah ZHAO Zhiqiang |  | Collect information and report on the challenges and solutions concerning the configuration, operation and maintenance of AWSs in remote and extreme climate conditions, and in terms of sub-system components based on experience of Members. Monitor advances in AWS technology and networks and report in terms of sub-system components. Request HMEI to review and advise of developments which can address the challenges facing member countries. |
| 4 | Develop requirements for the integration between AWS and space-based observations | Identify list of AWS geophysical parameters suitable for validation or integration with satellite observations Develop a proposal for a pilot inter-comparison | ET-AWS-7 | MONNIK, Karl (VAN DER MEULEN Jitze) |  |  |
| 5 | Develop the requirements for automated observations to address the deficiencies of AWS following the migration from manual observations | Collaborate with CIMO ET-ST&MT to publish guidelines and procedures to assist in the transition from manual to automatic surface observing stations Prepare a gap analysis for automated observations following the transition from manual observations. Review with subject area specialists including JCOMM, CAgM, CHy, CCl and GCOS | Dec. 2010 ET-AWS-7 | MOLYNEUX Mike TUTEN, Ozden |  | Include info on new sensor and measurement technologies which can contribute to reducing the gaps. Identify the priority manual observations and justification for the priorities. |
| 7 | Develop AWS metadata catalogues for real-time exchange through WIS | Prepare requirements for AWS metadata for WIS based on BUFR descriptors Liaise with IPET-DRC to implement the metadata in BUFR tables |  | NITU, Rodica CERVENA Eva MONNIK Karl |  | Focus on real-time delivery of metadata as listed in Annex III.3 of Guide on GOS (p.1-2) |
| 8 | Develop guidelines for the siting classification of surface observing stations | In coordination with CIMO and other relevant TCs, finalize the guideline materials for Members |  | LEROY, Michel | Done | Awaiting formal approval by CIMO Once approved, training material for the siting classification will need to be developed. |
| 9 | Review BUFR descriptors related to AWS measurements according to requirements | Review BUFR descriptors and propose new ones as needed. Coordinate implementation with IPET-DRC of BUFR template for SYNOP/AWS reporting. Validate BUFR templates for AWS data from n-minute period and for representation of nominal values. | ET-AWS-7 | LEROY, Michel CERVENA Eva |  |  |
| 10 | Monitor advances in AWS technology and develop guidance for integration into AWS networks | Review progress and advances in AWS technologies Develop guidance to deal with integration of third party AWS networks | ET-AWS-7 | NITU, Rodica SABATINI Francesco ZHAO Zhiqiang |  |  |