| WORLD METEOROLOGICAL ORGANIZATION ______________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS EXPERT TEAM ON EVOLUTION OF THE GLOBAL OBSERVING SYSTEM SECOND SESSION GENEVA, SWITZERLAND, 10 – 14 JULY 2006 |  | CBS/OPAG-IOS/ET-EGOS-2/Doc. 3.1 (12.V.2006) ____________ ITEM: 3.1 Original: ENGLISH |
| --- | --- | --- |

REVIEW OF ACTIONS FROM PREVIOUS MEETING

(Submitted by the Secretariat)

SUMMARY AND PURPOSE OF DOCUMENT To present the Action Items from the previous ET-EGOS, Geneva, 7-9 December 2005, and to report on activities involving these actions.

ACTION PROPOSED

The meeting is invited to review these actions.

_______________

Actions from ET-EGOS, December 2005

1a.	Secretariat to facilitate quarterly contact within ET-EGOS to check progress on workplan and IP next actions (March 2006 and thereafter).

STATUS:  Update provided Sec. to Chair (email from B. Sumner, 30 March)

NEXT:  Update required from all with actions in June 2006, in good time for paper for ET-EGOS.  Suggest request contributions asap.

1b.	WWW Director to be requested to increase resources for the Secretariat to enable pursuit of IP actions regarding ground based sub-component of GOS in similar fashion to WMO SP pursuit of IP recommendations regarding space based sub-component of GOS.  (ET-EGOS chair P. Menzel, Feb. 2006)

STATUS:  Letter from P.Menzel to J. Hayes, 23 January.  Raised in telecon between J. Hayes and J. Eyre, 9 June.

NEXT:  Topic to be raised at ET-EGOS in connection with future updates of the IP and the Integrated WMO Observing System.

1c.	Secretariat to provide acronym list for IP (Feb. 2006).

STATUS:  Acronym list is now a link on the ET-EGOS web page.

2.	Obtain update from CIMO on in situ observation capabilities for characterizing UT and LS temperature and moisture. (R. Stringer, April 2006)

STATUS:  Awaiting input from Russell

3.	Request response from regional rapporteurs on progress with regard to the recommendations in the IP concerning ground based sub component of the GOS as appropriate to their region.  Secretariat will approach the rapporteurs routinely to receive updates.  (Secretariat, Jan. 2006)

STATUS:  Letter sent:  J. Purdom to Regional Rapporteurs, 30 January.

NEXT:  Any replies?

4.	Review and update CEOS/WMO database of ground based component observing system capabilities to assure consistency with recent CBS monitoring statistics (R. Stringer, Jun 2006)

STATUS:  Awaiting input from Russell.

5a.	Study the impact of all AMDAR data over southern and central Africa in Global NWP.  (ET-EGOS chair P. Menzel request NWP centers, Feb. 2006).

STATUS:  email from P. Menzel, 2 Feb “5a has eluded me - I am not sure how to proceed. “

NEXT:  Ask Paul for update.

5b. 	Get feedback from Met Office regarding requirements for vertical resolution in AMDAR observations and in particular layer averaging for humidity (S. Goldstraw, May 2006).

STATUS:  Awaiting input from Stuart.

5c. 	Study the sensitivity to density (spatial and temporal) of in situ sea surface observations (pressure and wind) in an OSSE (ET-EGOS chair P. Menzel request NCEP, Jan. 2006).

STATUS:  Email from P. Menzel, 2 Feb “5c has been brought up via email with Steve Lord (mild positive response attached below could be re-inforced at JCSDA SSC mtg in mid May).”

NEXT:  Ask Paul for update

6.	Complete planning for a CBS/CAS expert meeting on optimized and targeted observations as requested by EC.  Report to OPAG-IOS chair on progress. (S.  Goldstraw, Feb. 2006).

STATUS:  Email from S. Goldstraw, 2 Feb. “Discussed with Jim and Horst at recent Space Terrestrial Study meeting.  Jim is going to Thorpex/CAS science workshop in SA and will sound out one or two others before proposing the plan.”

NEXT:  Request update from Stuart.

7.	Provide a draft letter for Chair OPAG IOS to contact the appropriate commission (that owns the user requirements) for each application area to request that they assume responsibility for the RRR process, confirm or nominate a PoC that will update the user requirements as appropriate, and maintain the SoG for that application area (Secretariat, Jan. 2006).

Global NWP	CBS / J. Eyre

Regional NWP		CBS / F. Rabier

Synoptic Met		CBS / E. Legrand

Nowcasting and VSRF		CBS / (PoC TBD via J. Schmetz)

Atmospheric Chem.		CAS / L. Barrie

Aeronautical Met		CAeM / H. Puempel

SIA Forecast		CBS / (PoC TBD via B. Strauss, chair OPAG DPFS)

Climate Variability		CCl / R. Heino

Climate Change 		CCl / R. Heino

Ocean		JCOMM / H. Kawamura

Hydrology		CHy / W. Grabs

Agro Met		CAgM / M. Sivakumar

STATUS:  Letter from President CBS to Presidents of TCs, 7 Feb.

NEXT:  Any responses?

8.	Establish contact with Chair of IPY Observing Working Group and establish information flow.  (P. Menzel, Jan. 2006)

STATUS:  Email from P. Menzel, 2 Feb. “IPY contact with Wenjian is being pursued through my sending him our polar raob impact papers.”

9.	Contact OSE rapporteurs to start planning next NWP OSE Workshop for 2007 (ET-EGOS chair, Jan. 2006)

STATUS:  Some dialogue between J. Eyre and J. Pailleux to start preparations for next Workshop, probably early 2008.

NEXT:  Planning to be pursued at ET-EGOS, in July, with input in paper from J. Pailleux

10.	Request CAS to look into options for sustaining the AMMA network (J. Eyre, Jan. 2006).

STATUS:  Request sent to Elena Manaenkova, 5 Jan.  No reply yet.  Also informal dialogue with AMMA.  AMMA are writing to President CAS and ask him to write to President CBS about sustaining the AMMA network.

11.	In view of the report that there is a risk of a lack of sustained funding for the ARGO Programme as it moves from the developmental to operational phase, Secretariat to contact JCOMM regarding issues to sustain Argo network (Secretariat, June 2006)

STATUS:  Update needed.