| WORLD METEOROLOGICAL ORGANIZATION ______________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS EXPERT TEAM ON EVOLUTION OF THE GLOBAL OBSERVING SYSTEM Fourth Session GENEVA, SWITZERLAND, 7–11 JULY 2008 |  | CBS/OPAG-IOS/ET-EGOS-4/Doc. 4.2(2) (1.VII.2008) _____ ITEM: 4.2 Original: ENGLISH |
| --- | --- | --- |

WMO HIGH-LEVEL ACTIVITIES RELEVANT TO THE ET-EGOS AND OPAG-IOS

WIGOS

(Submitted by the WMO Secretariat)

SUMMARY AND PURPOSE OF DOCUMENT This document provides information on the implementation of WIGOS Pilot Projects as identified by Cg-XV.

ACTION PROPOSED

The Meeting is invited to note the information contained in this document when considering further role and input of ET-EGOS within WIGOS Pilot Projects.

____________

Appendix:	Status of WIGOS Pilot Projects as identified by Cg-XV

References:	1.	Abridged final report of the EC-LX; and

2.	Final report of the third session of the ET-EGOS

DISCUSSION

1.	EC-LX (Geneva, Switzerland, 18-27 June 2008) endorsed an overarching WIGOS Development and Implementation Plan (WDIP) which foresees, inter-alia, the implementation of 
5 Pilot Projects, as identified by Cg-XV.  Subsequent reviews and updates of WDIP will be done annually as the planning proceeds and experience is gained from the various Pilot Projects and inputs from the Technical Commissions, Regional Associations and the advisory/steering bodies of WMO co-sponsored programmes are received.

2.	Following the guidance given by Congress and the Executive Council, the activities under 5 Pilot Projects (PP) has been initiated.  Updated information on the status of each of Pilot Projects is presented in the appendix to this paragraph.  The ET-EGOS, as one of the leading bodies of CBS responsible for the observational domain, may wish to consider its involvement in the implementation of 5 Pilot Projects as identified by Cg-XV.

____________

Appendix to paragraph 2

Status of implementation of Pilot Projects, as identified by Cg-XV

Pilot Project I:	GOS GAW Pilot Project (PP) Proposal on the Improvement of Dissemination of Ozone (total column, profiles and surface) and Aerosol observations through WIS

| Project Name | Improvement of Dissemination of Ozone (total column, profiles and surface) and Aerosol observations through the WIS |
| --- | --- |
| Acronym | GAW-IDOA |
| Project Type | WIS-WIGOS Pilot |
| Project Status | Planning |
| Project Overview | This pilot will improve availability of ozone and Aerosol Optical Depth (AOD) and surface Particulate Matter (PM) observations to the user community and prepare documentation to help other communities make their observing practices compatible. This pilot project combines activities already proposed by four advisory groups: SAG Ozone, SAG Aerosol, ET-NRT, ET-EGOS. The original proposals as provided to the March 2008 meeting are in annexes to this pilot project document. |
| Project Aims | Improve dissemination of ozone (total column, profiles and surface) and aerosol observations through the WIS (noting that WIS includes the GTS) for: Ingestion into atmospheric models using data assimilation; Support improved forecasts of weather, surface UV and air quality; and, Verification of models by: Dissemination on timescales appropriate to the applications; Instituting a Rolling Review of Requirements (RRR) Process, as prescribed by the Manual on GOS (WMO-No. 544); and, Supporting training and capacity building as necessary. Assist other observing communities to make their observations more widely available by documenting: Benefits, challenges and solutions encountered; Procedures developed for the ozone and AOD communities; |
| Partners / Participants | Key participants: MACC partnership (Monitoring Atmospheric Composition and Climate, led by ECMWF) with collaborating environmental agencies, WDCA (World Data Centre for Aerosols), WOUDC (World Ozone and Ultraviolet Radiation Data Centre), CBS, CAS, CIMO, PMOD/WRC, JMA (WDCGG, World Data Centre for Greenhouse Gases), WMO Secretariat Also contributing: Atmospheric composition community, WMO Members, HMEI (Hydro-Meteorological Equipment Industry Association), Universities |
| Project cost | Estimates to be confirmed Support for meetings of 3 expert groups: CHF50k One meeting of Ad Hoc group: CHF10k Consultants: 6 months: CHF60k |
| Funding Source(s) | WIGOS Trust Fund, Government grants |
| Project Timescale | Report to EC WG on WIGOS / WIS at the end of 2009 on the status of the objectives |
| Expected Key Deliverables | Description of deliverables will be provided by the three CAS groups referenced in the project overview in coordination with CBS, using the three areas of interoperability of WIGOS: measurement, distribution (WIS), quality. Measurement Increase the number of stations delivering observations for use in NWP, air composition forecasting and possibly hazard warning Distribution Increase in ozone and AOD observations received by Numerical Weather Prediction (NWP) and other centres (compared with 2008 baseline) on a time scale determined by the RRR; “quick look” AOD data available (with initial quality control but without finalized quality assurance) to centres executing experimental sand and dust storm models (Task 6.5 of GAW strategy) on timescales determined by the RRR; and, Document the further enhancements needed for WIS Quality Standard procedures for quality control in accordance with GAW strategic plan |
| Project Links | http://need a project web site |
| Project Summary | Ozone and aerosol observations from the GAW network are needed for ingestion into atmospheric models, via data assimilation techniques, in support of improved forecasts of weather, surface UV and air quality. To be useful, the data must be disseminated in near real time, which will benefit in addition such products as the Ozone Bulletins. This project will contribute to the design of activities that enhance the transfer of GAW data in near real time through WIS. A detailed implementation plan is being developed by the three component leads in cooperation with the CBS. The project will be implemented on the basis of current programmes and activities, carried out by Expert Teams of CAS, CBS and CIMO. Other relevant Programmes would be involved. The WMO Secretariat and component leads will facilitate the implementation of the project. The WIGOS GOS-GAW Pilot Project Ad-hoc Group Chairperson will monitor the results and report to the EC SG on WIGOS/WIS. Management outcomes: Identify the benefits and challenges associated with moving to use of the WIS for data dissemination and integration of GAW data into the work of other Programmes, including hazard warnings; and, Document a procedure that could be used to guide interoperability of other atmospheric chemistry components with WIS/WIGOS and propose changes to the Manual on the GOS and other Technical Regulations where appropriate. Common to ozone and AOD: Expand the number of stations submitting ozone and AOD observations to operational users in near real-time via WIS; Increase the availability and use of ozone and AOD observations to NMHS and other user communities; Develop and deliver training and provide capacity-building to support increased provision and use of the data and products created from the data; Update the WMO database of observation requirements to take account of the Rolling Review of Requirements; Promote the measurement of ozone and AOD to a common set of standards; Identify a set of relevant standards as a candidate for an WMO / ISO standard; Standardise on BUFR/CREX format for data distribution; and, Ensure that WIS can distribute the data (including ensuring that telecommunications headers are defined). Total Ozone and Ozone Profiles: Invite NMHSs to make use of the ability of the computer program DOBSON to produce total ozone data in CREX for transmission via WIS on timescales identified by the RRR; Encourage NMHSs using Brewer spectrophotometers to implement the subroutine CX.RTN to prepare total ozone data in CREX for transmission via WIS on timescales identified by the RRR; Initiate distribution of ozone sounding data from NILU using the WIS; Invite producers of sounding systems to upgrade their software to allow production of ozone sounding data in BUFR or CREX; and, Encourage development and implementation of BUFR/CREX encoding programs for other types of instrumentation that measure total ozone or ozone profile observations (e.g., DOAS, lidars, FTIR), Surface Ozone: Demonstrate routine exchange of hourly data in at least one region. Aerosols Develop communications headers for AOD information. |
| Date of Last Update | 27 March 2008 |
| Contact Person | Dr Liisa Jalkanen |

____________

Pilot Project II:  Initiation of a Global Hydrological Network in the context of WIGOS

(To be presented during the session)

____________

Pilot Project III:  Integration of AMDAR into WIGOS

(To be presented during the session)

____________

Pilot Project IV:	The CIMO Pilot Project on WIGOS “Elaboration of the underpinning / crosscutting role and responsibilities of the Instruments and Methods of Observation Programme and CIMO in the context of WIGOS”

| Project Name | Elaboration of the underpinning / crosscutting role and responsibilities of the Instruments and Methods of Observation Programme and CIMO in the context of WIGOS |
| --- | --- |
| Acronym | N/A |
| Project Type | Pilot |
| Project Status | The pilot is currently in its initial stage of collaboration and planning |
| Project Overview | This pilot is directed at defining the CIMO’s role and responsibilities within the WIGOS-WIS framework. Once these proposed role and responsibilities (Terms of Reference (TOR)) are endorsed by the EC-WG-WIGOS/WIS and Sub-group on WIGOS, the proposal will be tested and demonstrated across the remaining WIGOS Pilot and Demonstration Projects to prove the effectiveness of the proposed TOR in addressing the WIGOS needs. |
| Project Aims | Phase 1 of this project is to elaborate the underpinning / crosscutting role of CIMO in WIGOS (TOR for CIMO in the context of WIGOS). Phase 2 of this project is to develop and implement a plan which demonstrates the process by which CIMO fulfils its newly EC-agreed role and responsibilities within the WIGOS framework. |
| Partners/Participants | Phase 1: All WMO Technical Commissions and Co-sponsored Programmes and related International Organizations. Phase 2: Selected WIGOS Pilot & Demonstration Projects relevant to the CIMO-PP. |
| Funding Source(s) | The two phases of this project will, to the maximum extent possible, make use of the expertise to be provided through the working structure of CIMO and its WIGOS partners. Additional support will be required through the WMO budget and / or WIGOS-WIS Trust Fund. |
| Project Timescale | Phase 1: pilot project proposal for the role of CIMO within WIGOS and draft implementation plan development; fourth quarter 2008. Phase 2: Implementation: 2009-2011. |
| Expected Key Deliverables | Phase 1: Proposed CIMO TOR within WIGOS and draft proposal for implementation. Phase 2: Project implementation, periodic evaluation and management, a report with recommendations. |
| Project Links | http:/www.XXXXXXXXXXX |
| Project Summary | The CIMO Pilot Project is in the first stages of development |
| Date of Last Update | 01/02/2008 |
| CIMO Contact Person Name Organization Address Telephone Fax E-Mail | Rainer Dombrowsky NOAA Homeland Security Programme Office National Oceanic and Atmospheric Administration (NOAA) 1315 East-West Highway SSMC3, Room 10846 SILVER SPRING, MD 20910-3283 United States of America +1 202 282 9937 +1 202 282 8782 Rainer.Dombrowsky@noaa.gov |

____________

Pilot Project V:  WIGOS Pilot Project for JCOMM, status as of June 2008

The Pilot Project for the integration of marine and other appropriate observations into the GOS, also named WIGOS Pilot Project for WIGOS has been working pro-actively since WMO 
Cg XV for developing its Project Plan.  The deliverables of the WIGOS Pilot Project for JCOMM are: (i) developing interoperability arrangements between ocean data systems and the WIS while proving for documented and standardized data; (ii) documenting & integrating best practices and standards; and, (iii) Quality Management and implementation of cost effective Quality Management Systems (QMS).  The Pilot Project multi-disciplinary approach will permit the provision of consistent, coherent, more timely, and better quality data and products, while at the same time minimizing duplication.

The cooperation with the ocean community and IOC is key, in particular with the IOC International Oceanographic Data and Information Exchange (IODE) and its system of National Oceanographic Data Centres (NODC).  This will permit to develop appropriate connections between the IODE Ocean Data Portal (ODP) and the WIS for historical and recent data new sources of data for integration in the WIGOS framework (e.g., World Ocean Atlas, Argo, OceanSITES, GHRSST, XBT, Ocean carbon, sea level stations, ICOADS, satellite data).  Access to those ocean data sets through WIS will be facilitated.  The ownership of IOC for some of the components of the Global Ocean Observing System (GOOS), and the WMO and IOC respective data policies will be respected, as well as specific data policies for specific data sets.  SeaDataNET, GHRSST, and the Global Collecting Centres (GCCs – delayed mode VOS data as part of the MCSS) have already been approached in this regard and promising feedback was received from them so far.

The ad hoc planning meeting for the JCOMM Pilot Project for WIGOS was held in Ostend, Belgium, 29 March 2008.  The recommendations from the Executive Council Working Group on WIGOS-WIS were discussed and the Pilot Project plan updated so that it is in line with the WIGOS Concept of Operations (CONOPS).

The Vice-president of CIMO addressed the instrument best practices issues as well as the link with the other pilot projects and the demonstration projects.  The ad hoc planning meeting recognized the need for traceability to agreed standards, and recommended to establish cooperation with the WMO Commission on Instruments and Methods of Observation (CIMO) and to build on its experience with regard to instrument intercomparisons, instrument centres, etc.  The various related publications available via WMO and IOC will be reviewed and updated as required. JCOMM has also recently proposed to compile a catalogue of best practices to be eventually published as a JCOMM Technical Document.  The ad hoc planning meeting proposed to explore establishment of one or more marine and oceanographic instrument centre(s) and reviewed the methodology proposed by CIMO for conducting instrument intercomparisons to ensure homogeneity, and compatibility of the observations. The meeting also agreed to explore how JCOMM and ocean instrument comparisons can profit from the CIMO experience.

Because of the strong potential synergies between the ODP and the JCOMM Pilot Project for WIGOS, the ad hoc planning meeting proposed to establish a joint Steering Group with balanced representation from the IOC and WMO communities.  The Steering group includes representatives from CIMO, IODE, JCOMM Observations and Data Management Programme Areas, the IODE / JCOMM Expert Team on Data Management Practices (ETDMP), the WIS, the US Integrated Ocean Observing System (IOOS), the IODE NODCs, and the MCSS Global Collecting Centres (GCCs).

A meeting of the joint Steering Group is planned Geneva, Switzerland, from 18 to 19 September 2008.  It will review the draft Pilot Project business plan for assisting meteorological and oceanographic services understanding the potential benefits they can gain from the Pilot Project and from participating in its development.  The business plan will be addressing costs related to the implementation plan.  The Meeting will review the project plan and the draft implementation plan. The implementation plan provides for detailed information on actions proposed to implement the plan (e.g., feedback with regard to specific implementation of the E2E, requirements for partners to develop interoperability).

It will discuss quality management, and how appropriate quality management systems could be promoted in the framework of both ODP and WIGOS Pilot Projects.  It will also address capacity-building issues and refine the strategy to facilitate the implementation of both Pilot Projects within developing countries in coordination with the Demonstration Project as appropriate.

____________