| WORLD METEOROLOGICAL ORGANIZATION ______________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS EXPERT TEAM ON EVOLUTION OF THE GLOBAL OBSERVING SYSTEM Fifth Session GENEVA, SWITZERLAND, 30 NOV – 4 DEC 2009 |  | CBS/OPAG-IOS/ET-EGOS-5/Doc.5 (22.VIII.2009) _____ ITEM: 5 Original: ENGLISH |
| --- | --- | --- |

REVIEW OF ACTIONS

(Submitted by the WMO Secretariat)

Summary and Purpose of Document

This document provides status of individual actions agreed by the ET-EGOS-4, Geneva, Switzerland, 7-11 July 2008.

ACTION PROPOSED

The Meeting is invited to update further the Action Sheets and responsible persons will be invited to provide more detailed explanation on individual actions. Information provided should be taken into account when discussion relevant agenda items.

REVIEW OF ACTIONS

  - At its fourth session, the ET-EGOS (Geneva, Switzerland, 7-11 July 2008), agreed on actions resulting from the previous ET-EGOS-3 session as well as those from ET-EGOS-4.  These actions were structured as follows:

(i)	User Requirements (URs) and Statement of Guidance (SoGs);

(ii)	Observing Systems Capabilities (OSCs);

(iii)	Other Terms of Reference (TORs); and

(iv)	Issue from the CBS-Ext.(06) (Seoul, Republic of Korea, 9-16 November 2006).

  - The WMO Secretariat converted agreed actions into the ET-EGOS-4 Action Sheets and requested that the persons responsible regularly update the status of relevant actions. The last update was done in September 2009 (see attached Appendix).

  - The Meeting is invited to update further the actions, close them or forward them to the actions resulting from the ET-EGOS-5, as appropriate.

| ET-EGOS-4 Action Sheets |
| --- |
| TOR Item: | Action Required: | Responsible: | Deadline for action: | Action Status: | Date of Action: |
| I. USER REQUIREMENTS (URs) AND STATEMENTS OF GUIDANCE (SOGs) |
| I (a) | For each application area, confirm or nominate a Point-of-Contact (PoC) for the Rolling Review of Requirements (RRR) process, to update the URs as appropriate, and to maintain the Statement of Guidance (SOG) for that application area |
| I (a) 1 | Other Climate applications - Agree homogeneous application areas | R. Heino | Dec. 08 | Under preparation | New deadline March 09 |
| I (a) 2 | Other Climate applications - Create URs | R. Heino | Dec. 08 | Under preparation | New deadline March 09 |
| I (a) 3 | Other Climate applications - Perform Critical Review | R. Heino | Dec. 08 | Under preparation | New deadline March 09 |
| I (a) 4 | Other Climate applications - Create SOG(s) | R. Heino | Feb. 09 | Under preparation for submission to CCl MG 23-25.3.09 | New deadline March 09 |
| I (a) 5 | Nominate new PoC for "Climate" application area | M. Ondráš | Mar. 09 | Done (R. Heino nominated) | 9.12.2008 |
| I (a) 6 | General actions - Review all revised SoGs | J. Eyre | Jan. 09 | On-going action; status to be reviewed at ET-EGOS-5 | On-going |
| I (a) 7 | General actions - Refer revised SoGs to appropriate “owners” for endorsement | J. Eyre | Mar. 09 | On-going action; to be addressed at ET-EGOS-5 | On-going |
| I (a) 8 | Update UR DB | All PoCs | Dec. 08 | DONE for Global NWP DONE for Reg. NWP REDONE for GNWP PoC requested to update UR DB using supplied excel sheet | 14.1.2009 10.2.2009 10.2.2009 9.12.2008 |
| I (a) 9 | Update SoG | All PoCs | Dec. 08 | DONE for Global NWP DONE for NWC+VSRF DONE for Reg. NWP Ocean apps – some correspondence Update requested (1) SoG for GCOS will only be available early 2010; (2) SoG for SM does not need update; | 14.1.2009 26.1.2009 19.2.2009 26.2.2009 9.12.2008 |
| I (a) 10 | Request resources to support administration and maintenance of UR and OSC DBs | J. Eyre | Aug. 08 | DONE J. Eyre requested at ICT-IOS Emails within Secretariat No action so far by Secretariat | Sept 2009 28.1.2009 9.12.2008 |
| I (a) 11 | New Aeronautical Meteorology SoG for airports | C. M. Shun / H. Puempel | Jun. 09 | Requested and reminded | 9.12.2008 |
| I (a) 12 | Requirements for new “Met-ocean services” application area to be incorporated into DB | A. Soares / J. Lafeuille | Dec. 08 | Requested and reminded | 16.1.09 |
| I (a) 13 | To check if a separate application areas were required for coastal and open ocean, and if so, to proceed accordingly | A. Soares | Dec. 08 | Requested and reminded | 16.1.09 |
| I (a) 14 | Specific variables to describe waves (e.g. 2-D wave spectrum) to be included in the Manual of the CEOS/WMO Database of Observational User Requirements, | A. Soares | Dec. 08 | Requested and reminded | 16.1.09 |
| I (a) 15 | Publish the approved SoG | J. Lafeuille | Aug. 08 | DONE | Jul. 08 |
| I (a) 16 | ET members to provide comments to published SoG | ET Members | Sept. 08 | Requested and reminded | 16.1.09 |
| I (a) 17 | Review Gap Analysis performed by WMO Space Programme and inform WMO Space Programme Office | ET Members | Sept. 08 | Requested and reminded | 16.1.09 |

| II. OBSERVING SYSTEM CAPABILITIES (OSCs) |
| --- |
| II | Noting that OSCs have recently been partly updated (space based components, ocean / marine components), complete the review and update by September 2007 as follows: |
| II (a) | Pursue updates for remaining elements with 1st priority on WIN PROF, RADARs, AMDAT | R. Stringer | Oct. 08 | Requested and reminded | 16.1.09 |
| II (b) | Earth Observation Satellite and their Systems - send to ET members | J. Lafeuille | Jul. 08 | DONE | Jul.08 |
| II (c) | Update of OSCs by Space Agencies - seek ET review | J. Lafeuille | when available | Requested and reminded | 16.1.09 |
| II (d) | Make recommendation to ICT-IOS on establishment of a new ET to support OSCs | J. Eyre | Aug. 08 | DONE (Recommendation made by ICT-IOS-5 to CBS-XIV) | 18.9.2008 |
| II (e) | Promote WMO involvement in Weather Radar intl. Efforts | J. Eyre | 15 Aug. 08 | DONE (Recommendation made by ICT-IOS-5 to CBS-XIV) | 18.9.2008 |
| II (f) | Replace instituting with more appropriate ‘…continuing a Rolling Review of Requirements…’ under Pilot Project Aims | WIGOS PO | Sept. 08 | DONE | May 2009 |
| II (g) | Review the Vision for the GOS for IPY issues | E. Sarukhanian | Aug. 08 | Request sent to Mr Sarukhanian | 27.8.08 |
| II (h) | Encourage establishment of a global AMDAR optimisation solution | AMDAR Panel Chairperson | Nov. 08 | DONE (Recommendation made by ICT-IOS-5 to CBS-XIV) | 18.9.2008 |
| III. OTHER TORs (e, f, g, h) |
| III (a) | Advise on requirements for vertical resolution in AMDAR observations and in particular layer averaging for humidity – to communicate results of completed UK Met Office study to AMDAR Panel | S. Klink / S. Goldstraw | Sep. 08 | Reminder sent to Mr Klink and Goldstraw. Email from Jochen Dibbern | 27.8.08 22.1.2009 |
| III (b) | Report to the CBS ICT-IOS on all ET activities | J. Eyre | 15 Aug. 08 | DONE | Aug.08 |
| III (c) | Review Impact studies Workshop report for issues to go to CBS | J. Eyre / J. Pailleux / L. P. Riishojgaard / E. Andersson | 15 Aug.08 | DONE | Sep.08 |
| III (d) | Consider development of GRUAN Operational Manual through WIGOS Pilot Project | S. Bojinski / M. Menne | Mar. 09 | DONE: GRUAN WPP proposal accepted by WIGOS PO and CBS by August 2009, containing as a major element the development of a GRUAN manual; | Mar.09 |
| III (e) | Resubmit call for nomination of NFP responsible for reporting progress and plan relevant to EGOS-IP | M. Ondráš | Sept. 08 | DONE | Sep.08 |
| III (f) | Request NFP to submit their report | M. Ondráš | Sept. 08 | DONE Draft sent to Mr Stringer for review | 27.8.08 |
| III (g) | Finalize a draft of the new updated implementation plan and send for review and adoption by the chair | E. Andersson | Jul. 08 | DONE | Jul.08 |
| III (h) | Provide comments to draft Work Plan (2009-2012) to ET Chair | ET Members | 10 Aug. 08 | DONE | Sep.08 |
| IV. ISSUE FROM CBS (Nov.06) |
| IV (a) | Analyze information on progress and plans supplied by the Members related to the EGOS-IP, summarize progress, inform NFP | R. Stringer in collaboration with WMO Secretariat | yearly | DONE Provided national reports submitted to R. Stringer for analysis | Sep. 2009 |

___________