| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS EXPERT TEAM ON THE EVOLUTION OF GLOBAL OBSERVING SYSTEMS Sixth Session GENEVA, SWITZERLAND, 14 – 17 JUNE 2011 |  | CBS/OPAG-IOS/ET-EGOS-6/Doc. 4 (05.04.2011) _______ ITEM: 4 Original: ENGLISH |
| --- | --- | --- |

PROGRESS ON ET-EGOS WORK PLAN FOR CBS

(Submitted by  Dr John Eyre, ET-EGOS Chairperson, Met Office, UK)

SUMMARY AND PURPOSE OF DOCUMENT The document provides information on progress on the Work Plan of the Expert Team on Evolution of global observing systems (ET-EGOS).

ACTION PROPOSED

The Meeting is invited to note the information contained in this document when considering its recommendations.

____________

Appendix: 	WMO CBS ET-EGOS: Progress on the Work Plan

DISCUSSION

1.	ET-EGOS is established as an Expert Team under the Open Programme Area Group for Integrated Observing Systems (OPAG/IOS) of the Commission for Basic Systems (CBS) of WMO.  It follows Terms of Reference and a Work Plan approved by CBS.  Appendix 1 provides for the Work Plan with updated actions for ET-EGOS for the 4-year period from CBS-XIV, following adoption by CBS and by the CBS Management Group.

2.	ET-EGOS should note the scope and content of its Work Plan.  A preliminary discussion on progress of the Work Plan is anticipated under agenda item 4, prior to detailed discussion of individual elements of the Work Plan under later agenda items.

__________

Appendix A

UPDATED ET-EGOS workplan for the period 2009 to 2012

(this workplan was presented to the CBS-XIV, approved by the CBS Management Group, then updated by ET-EGOS-5 to assign responsibilities, deadlines, and indicate status)

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | To contribute to the development and implementation of concept of WIGOS and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by EC-WG/WIGOS-WIS-2 | Ongoing | John Eyre | CONOPS and WDIP reviewed at ET-EGOS-5; provided comments to the EC-WG WIGOS WIS |  |
| 2 | Survey and collate user requirements for observations for WMO and WMO-sponsored programmes | Review and update CEOS/WMO database of user requirements for observations, through Points of Contact for application areas. | Ongoing / Annual review | John Eyre | Reviewed at ET-EGOS-5 and recommendations made | Action continuing; to be reviewed at ET-EGOS-6 |
| 3 | Survey and collate observing systems capabilities for surface-based and space-based systems that are candidate components of WIGOS | Review and update CEOS/WMO database of observing system capabilities, in collaboration with other OPAG IOS ETs. | Ongoing / Annual review | John Eyre | Reviewed at ET-EGOS-5 and recommendations made | Action continuing; to be reviewed at ET-EGOS-6 |
| 4 | Maintain Rolling Review of Requirements (RRR) for observations in several application areas, using subject area experts, including appropriate liaison with CAS, JCOMM, CAeM, CAgM, CHy, CCl and GCOS. | Continue RRR process for 12 application areas and expand to new areas as required: review and update as necessary Statements of Guidance on the extent to which present/ planned observing system capabilities meet user requirements, through Points of Contact on application areas. | Ongoing / Annual review | John Eyre | Reviewed at ET-EGOS-5; identified 2 new areas requiring SoGs | Action continuing; to be reviewed at ET-EGOS-6 |
| 5 | Prepare and maintain reviews of OSEs, OSSEs and other studies undertaken by NWP centres and to provide information for consideration by ET-EGOS and OPAG-IOS | Rapporteurs on Impact Studies and NWP experts, review results of impact studies relevant to the evolution of GOS. Organize and hold next NWP Impact Studies Workshop in 2012. | End April 2010 (organization planning) | Erik Andersson | Recent OSEs and OSSEs reviewed at ET-EGOS-5; preliminary plans for next Workshop were initiated at ET-EGOS-5 and discussed at ICT-IOS-6 | Action continuing; to be reviewed at ET-EGOS-6 |
| 6 | Promote CBS activities in support of GCOS goals | Review the implications of the 2010 update of the GCOS Implementation Plan for the activities of CBS Bring relevant issues to the attention of the ET-EGOS | End Jan 2010 (Impl. Plan) July 2010 ( review GRUAN Guide) | Matthew Menne | GCOS-IP reviewed by ET-EGOS following ET-EGOS-5 | Transfer of items from GCOS-IP into EGOS-IP has started; action continuing |
| 7 | Prepare a new version of the Implementation Plan for the Evolution of the global observing systems (EGOS-IP), fully responding to the “Vision for the GOS in 2025” Update current version of the IP during this transition period. | Based upon monitoring of the progress in the Evolution of the GOS and after successful endorsement of the “Vision for the GOS in 2025” by CBS-XIV, that the ET-EGOS prepare a new version of the EGOS-IP that will incorporate the information included in the Vision. | End 2010 (initial version of new EGOS-IP) | John Eyre | ToRs for consultant and guidelines for the new EGOS-IP proposed by ET-EGOS-5; recommendation to rename EGOS-IP to the “Implementation Plan for the Evolution of Global Observing Systems” adopted by CBS.Ext(2010) | Draft of new EGOS-IP prepared; to be reviewed by ET-EGOS-6 |

__________