| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS INTER PROGRAMME EXPERT TEAM ON WIGOS FRAMEWORK IMPLEMENTATION Third Session Exeter, United Kingdom, 1 to 4 September 2015 |  | CBS/OPAG-IOS/IPET-WIFI-3/Doc. 8 (21/08/2015) _______ ITEM: 8 Original: ENGLISH |
| --- | --- | --- |

UPDATE ON PROGRESS AGAINST ASSIGNED TASKS AND FUTURE CONSIDERATIONS:

METADATA SUBGROUP

(Submitted by Karl Monnik, SG-MD Chair)

Summary and purpose of document This document is to update IPET-WIFI on progress against assigned tasks and future considerations for the Sub-Group on Metadata (SG-MD).

Action proposed

It is proposed that IPET-WIFI:

- Note the progress achieved against assigned tasks;

- achieve further progress through the work of this meeting, particularly by the SG-MD;

____________

References:

- Final report of first meeting: Inter-Programme Expert Team on WIGOS Framework Implementation - First Meeting, Geneva, 10-14 June 2013

UPDATE ON PROGRESS AGAINST ASSIGNED TASKS AND FUTURE CONSIDERATIONS FOR WIGOS METADATA

- Introduction

  - The Sub-Group on WIGOS METADATA (SG-MD) was established at the first meeting of IPET-WIFI in June 2013. The Terms of Reference and membership were updated and are listed in the documentation plan for this meeting.

  - The ToRs highlight the collaboration needed with the OPAG-IOS ETs and in particular its Task Team on WIGOS Metadata (TT-WMD).

- Progress

  - The "status" and "comments" have been updated in this extract from the Work Plan to describe progress achieved:

| No. | Task | Deliverable/Activity | Due | Respons -ible | Impact-ed ETs | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8. | 1) Compile and provide input to the development of WIGOS (interpretation) metadata, focusing on the GOS component. 2) Compile and provide input to the development of approaches for gathering, storing and exchanging WIGOS metadata, focusing on the GOS component. This should lead to a number of standard practices and recommended practices for Members to follow. | 1.1 GOS input provided to ICG-WIGOS TT-WMD 1.2 Review and provide feedback on the Core Metadata list developed by TT-WMD, prepare populated examples (e.g. for surface station, radar, etc.) 1.3 Seek feedback on 1.2 from the technical experts across all areas of OPAG IOS. 2.1 drawing on input from the technical experts across all areas of OPAG IOS, present proposals or options to TT-WMD for approaches for gathering, storing and exchanging WIGOS metadata, focusing on the GOS component. 2.2 suggest options for standard and recommended practices, and for specific arrangements for (meta)data entry to the WIR. 2.3 Consider options for a staged approach for the submission and making available of metadata. | 1.1 Jun 2013 1.2 Nov 2013 1.3 Sep 2014 2.1 Jun 2015 2.2 Nov 2015 2.3 Mar 2016 | Monnik Members of SG-WMD | TT-WMD | DONE DONE 80% 30% 30% 0% | With a view to inclusion in the 2016 version of the Manual on WIGOS |

- Activities

  - Some specific activities of note are:

- Following the chair of SG-RM's presentation to ET-SBO regarding the imperative to prepare new RM for the manual on the WIGOS, SG-MD chair was invited to a special meeting of ET-SBO, 24-28 November 2014, which had as its focus preparation of RM for AWS, Weather Watch Radars and Wind Profiling Radars. Included in the material were explicit references to recording, storing and international distribution of observations metadata. This paves the way for more explicit treatment of MD in WIGOS networks.

- Ongoing collaboration between SG-MD and TT-WMD has been greatly facilitated by having the same person as Chair/Co-chair of the two groups. This will continue to be beneficial as the WIGOS Metadata Standard (WMDS) is implemented through the OSCAR Surface;

- The SG-MD should also note that the most recent version of the WIGOS Metadata Standard was approved by Cg-XVII. This follows extensive consultation by TT-WMD via SG-MD and many other TCs to develop an inclusive standard. This is available online at:

https://drive.google.com/file/d/0B8DhC1GSWSmxb25zTzJpUFNzcjA/view

- SG-MD was represented at a video-conference between OSCAR, WIGOS Metadata and the Inter-Programme Expert Team on Metadata and Data Representation (IPET-MDRD) held over 19-20 Aug 2014. This was an exploratory meeting for MDRD members to understand the scope of WIGOS Metadata with a view to the eventual formal coding of a IT standard.

- This was followed up by a meeting of IPET-MDRD held in Melbourne, 22-25 June 2015 were SG-MD Chair was invited. The purpose of this meeting was to begin developing a generic data model for the WMDS, which is the first step before designing an application schema;

- With the release of the OSCAR/Surface for beta-testing, members of SG-MD were encouraged to access the database and add/edit metadata for a range of station types. Feedback from these tests have been provided to the OSCAR/Surface team. OSCAR/Surface is available from the following link:

http://oscar.wmo.int/surface

- Future Work

  - Further progress can be achieved at this meeting on deliverables 2.1, 2.2 and 2.3.

  - It is proposed that SG-MD give priority to:

- Familiarisation with the current version of the WDMS with a view to further development of example metadata lists for a range of GOS stations.

- Continue with the review of OSCAR/Surface keeping in mind the desire to develop training materials;

- Review references to draft regulatory material concerning metadata.

____________________________________________