|  |  |
| --- | --- |
| **WORLD METEOROLOGICAL ORGANIZATION****COMMISSION FOR BASIC SYSTEMS****THE INTER-PROGRAMME EXPERT TEAM ON WIGOS FRAMEWORK IMPLEMENTATION (IPET-WIFI)****SUB-GROUP ON REGULATORY MATERIAL*****(First Session)*** Geneva, Switzerland, 14 to 15 April 2016 | CBS/IPET-WIFI/SG-RM-Doc. 3(2) \_\_\_\_\_\_\_\_\_ITEM: 3Original: ENGLISH ONLY |

**Work Plan for IPET-WIFI SG-RM for the period 2015-2016**

*(Submitted by the Secretariat)*

|  |
| --- |
| **SUMMARY AND PURPOSE OF DOCUMENT**The document sets out the Work Plan for IPET-WIFI SG\_RM for the 2015-2016 period leading up to CBS-16 in November 2016. |

**ACTION PROPOSED**

 The Meeting is invited to review and revise the Work Plan in the light of recent progress against tasks.

\_\_\_\_\_\_\_\_\_\_\_\_

**Work Plan for IPET-WIFI SG-RM for the period 2015-2016**

*(Updated 11 February 2015)*

| **No.** | **Task** | **Deliverable/Activity** | **Due** | **Responsible** | **Impacted ETs** | **Status** | **Comment** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| *1.* | Contribute to the development and maintenance of WIGOS regulatory material, both GOS-related material and provisions common to all component systems. | 1) input to TT-WRM, to assist and review the inclusion of material from GOS Manual and TRs into the WIGOS Manual and TRs (particularly for sections 2, 3 and 7)2) proposals for updated or new regulatory material to the TRs, WIGOS Manual and/or GOS Manual (as appropriate)3.1) clear plans (with TT-WRM) for the transition and eventual phasing out of the GOS Manual3.2) lay foundation for completion of transition, after CBS-XVI (2016), from GOS Manual to WIGOS Manual4) Collaboration with TT-WRM on development of the WIGOS Guide | 1) Oct 20132) 2016 (for next edition of WIGOS Manual), & ongoing.3.1) Jun 20153.2) 20164) 2016 | **Stringer**SG-RM Members | TT-WRMICT-IOS | 100%20%40%25%15% | Interactions and feedback provided for TT-WRM on first drafts. Further input possible on next drafts.Some WIGOS and GOS updates obtained from across CBS. Need further work on GOS Manual.Done some planning, more needed on timeline for GOS Manual.Coordination established, initial changes drafted. Need more work on GOS Manual through a few stages.Initial concepts only.CBS-16 Nov 2016 |