| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMME AREA GROUP ON INTEGRATED OBSERVING SYSTEMS INTER PROGRAMME EXPERT TEAM ON WIGOS FRAMEWORK IMPLEMENTATION Second Session GENEVA, SWITZERLAND, 17-21 MARCH 2014 |  | CBS/OPAG-IOS/IPET-WIFI-2/Doc. 5.3 (04.03.2014) _______ ITEM: 5.3 Original: ENGLISH |
| --- | --- | --- |

UPDATE ON PROGRESS AGAINST ASSIGNED TASKS AND FUTURE CONSIDERATIONS FOR qUALITY MANAGEMENT

(Submitted by Kevin Schrab, SG-QM Chair)

Summary and purpose of document This document is to update IPET-WIFI on progress against assigned tasks and future considerations for Sub-Group on Quality Management (SG-QM).

Action proposed

The session is invited to discuss Sub-Group on Quality Management (SG-QM) tasks and plans for the future.

____________

UPDATE ON PROGRESS AGAINST ASSIGNED TASKS AND FUTURE CONSIDERATIONS FOR qUALITY MANAGEMENT

1.	Introduction

The Sub-Group on Quality Management (SG-QM) established its Terms of Reference at IPET-WIFI-1 in June 2013:

- Review current QM practices used within the GOS

- Review material from the WMO Quality Management Framework

- Coordinate with ICG-WIGOS TT WQM the content of a WIGOS-QMS Implementation Plan

- Compile GOS-related QM practices, including a proposal for a Fault Management System, to be included in the WIGOS Regulatory Material

- Submit contributions to the IPET-WIFI for coordination

It was also noted that active collaboration with other OPAG-IOS ETs and Rapporteurs.  And also that representation in the work of those TCs not directly represented on IPET-WIFI will be via ICG-WIGOS TT-WQM.

2.	Progress

Listed below is the progress to date on the SG-QM tasks in the Work Plan for IPET-WIFI for the period 2013-2016.  These are the deliverables/activities for Task 5 (provide advice to ICG-WIGOS via CBS on GOS Quality Management practices and procedures.

- Request TCs to nominate QM focal points for WIGOS sub-systems (action to Secretariat, due Aug 2013).  Unclear whether this action is complete.

- Review the status of WMO and Regional quality monitoring systems with a view to identifying areas for improvement and efficiency:

  - Review existing regulatory material related to QM for GOS sub-systems.

    - Due – Oct 2013.

    - Status – Ongoing.

  - Prepare recommendations on new or improved QM procedures in relation to GOS sub-systems.

    - Due – Jun 2014.

    - Status – Pending.

  - Review the outcomes of the ECMWF Workshop on NWP data monitoring requirements.

    - Due – Jul 2013.

    - Status – Complete; no resulting actions.

  - Assist in the process of integrating the procedures into the Manual or Guide on WIGOS.

    - Due – Jun 2014.

    - Status – Pending.

- Develop and document the concept of extending the Global Quality Monitoring System to a “Fault Management System”.

    - Due – Aug 2014.

    - Status – Pending.

- Contribute to the drafting work of TT-WRM in collaboration with SG-RM and provide GOS-related feedback through SG-RM on TT-WRM documentation.

    - Due – Oct 2013.

    - Status – Complete; SG-QM provided review and comment on WIGOS Manual Section 2.6 (Quality Management) to TT-WRM meeting held in Nov 2013.

3.	Issues

- It is unclear whether Technical Commissions have been asked to nominate QM focal points for WIGOS sub-systems.  These focal points could assist the SG-QM in its tasks.

- SG-QM chair has not had any interaction with ICG-WIGOS TT-WRM.  As noted in the Terms of Reference, SG-QM would be linked with TT-WRM.

- The ICG-WIGOS Task Team on Quality Management (TT-QM) is to provide direction on quality management, which SG-QM would act upon.  The TT-QM has not yet met, so no guidance has yet been provided.

4.	Recommendations

- Secretariat to confirm whether TCs have nominated focal points for WIGOS sub-systems.

- Include SG-QM chair (or other SG-QM member) in TT-WRM group (email distribution list, telecons, meetings, etc).

- Invite SG-QM chair to attend first TT-QM meeting to be held 23-24 April 2014.

5.	Proposed Future Work

SG-QM has been asked to be included in two on-going reviews.

- Request for review of WIGOS Technical Regulations Drafts.  The SG-QM has been asked to focus their review on the aspects pertaining to quality management in the draft Manual on WIGOS and the draft addition to Part I of the WMO Technical Regulations for WIGOS.  Comments are due to Dean Lockett by 26 March 2014.  This relates to deliverable/activity 3b of Task 5.

- The Expert Team on Surface Based Observations (ET-SBO) has been asked to review the WIGOS Observations Quality Improvement System – Draft Proposal.  There are linkages to the SG-QM tasks in the IPET-WIFI Work Plan.  It is proposed that the SG-QM be the lead WMO body in this activity.  The proposal suggests a virtual CBS team of 2 members of SG-QM and 2 members of ET-SBO be formed.  Input is needed for ICT-IOS-8 meeting to be held 7-10 April 2014.  This relates to deliverable/activity 5 of Task 5.

Other proposed work includes:

- Review existing regulatory materials related to QM for GOS sub-systems and prepare recommendations on new or improved QM procedures.  This is deliverable/activity 2a and 2b of Task 5.  Assign each SG-QM member to review and provide feedback to SG-QM chair.  Discuss if June 2014 due date is appropriate.

- Begin work on deliverable/activity 4 of task 5.  Current due date is August 2014.  Ask for SG-QM team member volunteer(s) to provide first draft.

6. 	Work Plan Update

Work plan will be reviewed and updates related to progress, issues, recommendations, and proposed future work to be made.