|  |  |  |
| --- | --- | --- |
| WORLD METEOROLOGICAL ORGANIZATION\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_COMMISSION FOR BASIC SYSTEMSOPEN PROGRAMMME AREA GROUP ONINTEGRATED OBSERVING SYSTEMSSecond *Ad hoc* IPET-OSDE workshop on Observing System Network DesignGENEVA, SWITZERLAND, 2-4 fEBRUARY 2015 |  | CBS/OPAG-IOS/OSDW2 / Doc. 8(13.01.2015)\_\_\_\_\_\_\_ITEM: 8Original: ENGLISH |

**Current roadmap for developing OSND principles and guidance**

*(Submitted by* *the Secretariat)*

|  |
| --- |
| **SUMMARY AND PURPOSE OF DOCUMENT**The document provides for the Current roadmap for developing OSND principles and guidance. |

**ACTION PROPOSED**

 The Meeting is invited to note the information contained in this document when considering its recommendations.

\_\_\_\_\_\_\_\_\_\_\_\_

**Appendix:** **A**. Proposed roadmap for developing OSND principles and associated guidance material

**Appendix A**

**Proposed Roadmap for the development of**

**OSND principles and associated guidance material**

*(version 3 April 2014, updated 17 December 2014 with current status)*

|  |  |  |  |
| --- | --- | --- | --- |
| ***Time*** | ***Milestone*** | ***Tasks*** | ***Status*** |
| Nov. 2013 | OSDW1TT-WRM | Produce input to OSND principlesProvide input on OSND principles and guidance to WIGOS RM | Done |
| Dec. |  | Draft OSND principles (J. Eyre) | Done |
| Jan. 2014 |  | Review by OSDW1 participantsNew draft of OSND principles produced based on feedback (J. Eyre by 27 Jan.) | Done |
| Feb. | ICG-WIGOS | Review draft OSND principlesPropose framework into which OSND principles & guidance will fit | Done |
| Mar/Apr. | IPET-OSDE-1 | Review and revise OSND principlesDraft plan for preparing OSND guidance, and tasks for Team members for drafting materials | Done |
| 4 Apr. | TT-WRM | OSND principles submitted to the TT-WRM, and the WRM review process through Technical Commissions, and WMO Executive Bodies | Done |
| Apr. | ICT-IOS-8 | Notes the OSND principlesReview/revise and approve plan for preparing OSND guidance | Done |
| May |  | IPET-OSDE members to review draft OSND guidance and provide feedback to the Chair | Done |
| Jun. | EC |  |  |
| Jul. |  |  |  |
| Aug. |  |  |  |
| Sep. | CBS Ext. (2014) | Consideration by CBS of (i) the OSND principles (to be noted by CBS), and (ii) the roadmap for producing the OSND guidance, as part of WIGOS materials for approval | Done |
| Oct. |  |  |  |
| Nov. |  | Review of Cg-17 WIGOS RM by Members | Underway |
| Dec. |  | Review of Cg-17 WIGOS RM by Members | Underway |
| Jan. 2015 |  | Review of Cg-17 WIGOS RM by Members | Underway |
| Feb. | OSDW2ICG-WIGOS-4 | OSDW2 to review/update OSND guidanceDraft OSND guidance reviewed by ICG-WIGOSNew experts invited to address all AAs |  |
| Mar. |  |  |  |
| Apr. |  |  |  |
| May. | Cg-17 | Approve WIGOS Regulatory Material |  |
| Jun. |  |  |  |
| Jul. |  |  |  |
| Aug. |  |  |  |
| Sep. |  |  |  |
| Oct. |  |  |  |
| Nov. | ET-SBO |  |  |
| Dec. |  |  |  |
| Jan. 2016 | IPET-OSDE-2 (TBD)ICG-WIGOS-5 | Draft version of OSND guidance reviewed by IPET-OSDE (slow track)Draft version of OSND guidance available and reviewed by ICG-WIGOSDraft OSND guidance submitted to EC (fast-track)  |  |
| Feb. |  |  |  |
| Mar. |  |  |  |
| Apr. |  |  |  |
| May | ICT-IOS-9 | Final draft version of OSND guidance available (slow track) |  |
| Jun | EC | OSND guidance approved by EC (fast track) |  |
| Jul. |  |  |  |
| Aug. |  |  |  |
| Sep. |  |  |  |
| Oct. | CBS | OSND Principles and Guidance endorsed by CBS (slow track)  |  |
| Nov. |  |  |  |
| Dec. |  |  |  |
| Jan. 2017 |  | Draft OSND guidance submitted to EC (slow-track) |  |
| Feb. |  |  |  |
| Mar. |  |  |  |
| Apr. |  |  |  |
| May | EC | OSND Guidance approved by EC (slow track) |  |

\_\_\_\_\_\_\_\_\_\_