| WORLD METEOROLOGICAL ORGANIZATION ____________________ COMMISSION FOR BASIC SYSTEMS OPEN PROGRAMMME AREA GROUP ON Information Systems and Services Preparatory workshop for an International Forum of Users of Satellite Data Telecommunication Systems Toulouse, France, 23-24 April 2012 |  | CBS/OPAG-ISS/SATCOM1/Doc. 6.4 (29.02.2012) _______ ITEM: 6.4 Original: ENGLISH |
| --- | --- | --- |

Workplan

(Submitted by  WMO Secretariat)

SUMMARY AND PURPOSE OF DOCUMENT The twelfth session of the CBS Management Group (CBS-MG-XII) reviewed and endorsed the proposed workplan leading in principle to the formal adoption of the Forum in 2013 (Appendix A). An updated workplan is proposed (Appendix B) that the workshop is invited to review and approve.

ACTION PROPOSED

The Meeting is invited to review and update the draft workplan, and adjust it as needed for formal adoption of the Forum by the Executive Bodies of the co-sponsor Organizations.

____________

Appendix: 	A.	CBS workplan leading to the formal establishment of the Forum

B	Draft updated workplan leading to the formal establishment of the Forum

Appendix A

Proposed workplan leading to the establishment of the forum

| Step | Action | Date/Deadline | By |
| --- | --- | --- | --- |
| 1 | Approach Co-sponsors in the view to agree on the draft Terms of Reference for the forum; and plan/organize an ad hoc workshop for the establishment of the informal forum. | Aug.-Dec. 2011 | IOC, WMO Secretariats |
| 2 | Approach operators of satellite data telecommunication systems and platform transmitter terminal, identify contact points, and discuss/negotiate the level of their contributions/participation | Aug.-Dec. 2011 | Secretariats |
| 3 | Approach users of satellite data telecommunication, inform them about the forum, and seek their participation in the forum and the ad hoc workshop | July-Dec. 2011 | Secretariats1 |
| 4 | Setup an organizing committee of the ad hoc workshop with Terms of Reference | Jan. 2012 | Secretariats1 |
| 5 | Negotiate with potential hosts, and propose a venue for the ad hoc workshop | Mar. 2012 | Organizing Committee |
| 6 | Propose agenda and documentation plan for the ad hoc workshop | Apr. 2012 | Organizing Committee |
| 7 | Inform the joint WMO-IOC Technical Commission for Oceanography and Marine Meteorology (JCOMM) about developments regarding the forum, and seek further guidance | May 2012 | Secretariats of WMO and IOC |
| 8 | Issue invitation letters for the ad hoc workshop | June 2012 | Secretariats1 |
| 9 | Coordinate documentation plan with contributors | June-Sep. 2012 | Secretariats1 |
| 10 | Inform the WMO Commission for Basic Systems (CBS) about developments regarding the forum, and seek further guidance | Sep./Oct. 2012 | WMO Secretariat |
| 11 | ad hoc workshop tasked to: Propose operating principles, including Terms of Reference of the forum’s Executive Committee Adjust draft Terms of Reference, Elect an interim Executive Committee, Review current satellite data telecommunication issues, Identify areas where progress/proposals can be made Refine the workplan for formal adoption of the forum by the Executive Bodies of the co-sponsor Organizations | Nov. 2012 | Organizing Committee and the Secretariats1 |
| 12 | Terms of Reference of the forum submitted to the parent Organizations Executive Bodies for approval and formal establishment of the forum | 2013 | Executive Bodies of WMO,IOC,FAO |
| 13 | Plan for the first meeting of the forum | 2013/2014 | Interim Executive Committee, and the Secretariats1 |
| 14 | First official meeting of the forum | 2014 | Interim Executive Committee, and the Secretariats1 |

_______________

Appendix B

Draft updated workplan leading to the formal establishment of the Forum

| Step | Action | Date / Deadline | By |
| --- | --- | --- | --- |
| 1 | Approach Co-sponsors in the view to agree on the draft Terms of Reference for the forum; and plan/organize an preparatory workshop for the establishment of the informal forum. | Aug. 2011-Jan. 2012 | IOC, WMO Secretariats |
| 2 | Approach operators of satellite data telecommunication systems and platform transmitter terminal, identify contact points, and discuss/negotiate the level of their contributions/participation | Jan - May. 2012 | Secretariats |
| 3 | Approach users of satellite data telecommunication, inform them about the forum, and seek their participation in the forum and the ad hoc workshop | July-Dec. 2011 | Secretariats1 |
| 4 | Setup an organizing committee of the ad hoc workshop with Terms of Reference and membership (see draft below) | Apr. 2012 | Preparatory workshop |
| 5 | Negotiate with potential hosts, and propose a venue for the ad hoc workshop | Mar. – Sep. 2012 | Organizing Committee |
| 6 | Inform the joint WMO-IOC Technical Commission for Oceanography and Marine Meteorology (JCOMM) about developments regarding the forum, and seek further guidance | May 2012 | Secretariats of WMO and IOC |
| 7 | Issue invitation letters for the ad hoc workshop | June 2012 | Secretariats1 |
| 8 | Inform the WMO Commission for Basic Systems (CBS) Implementation Coordination Team on Integrated Observing Systems (ICT IOS) about developments regarding the forum, and seek further guidance | June 2012 | Secretariats1 |
| 9 | Inform the Implementation Coordination Team on Information Systems and Services (ICT-ISS) about developments regarding the forum, and seek further guidance | June 2012 | Secretariats1 |
| 10 | Coordinate documentation plan with contributors | June-Sep. 2012 | Secretariats1 |
| 11 | Inform the CBS about developments regarding the forum, and seek further guidance | Sep./Oct. 2012 | WMO Secretariat |
| 12 | Propose agenda and documentation plan for the ad hoc workshop | Sep. 2012 | Organizing Committee |
| 13 | Issue invitation letters for the ad hoc workshop |  | Secretariats1 |
| 14 | See documents from contributors to the documentation plan | Sep. – Dec. 2012 | Secretariats1 |
| 15 | ad hoc workshop tasked to: Review current satellite data telecommunication issues, Identify areas where progress/proposals can be made Review and adjust as needed the draft Terms of Reference of the Forum, Review the proposed operating principles of the Forum, including Terms of Reference of the forum’s Executive Committee Elect an interim Executive Committee, Refine the workplan for formal adoption of the forum by the Executive Bodies of the co-sponsor Organizations | Feb. 2013 | Organizing Committee and the Secretariats1 |
| 16 | Terms of Reference of the forum submitted to the parent Organizations Executive Bodies for approval and formal establishment of the forum | 2013 | Executive Bodies of WMO,IOC,FAO |
| 17 | Plan for the first meeting of the forum | 2014 | Interim Executive Committee, and the Secretariats1 |
| 18 | First official meeting of the forum | 2014/2015 | Interim Executive Committee, and the Secretariats1 |

Organizing Committee for the ad hoc workshop (2013)

1) Terms of Reference:

The Organizing Committee for the ad hoc workshop shall:

- Negotiate with potential hosts, and propose a venue for the ad hoc workshop

- Investigate establishment of a trust fund, seek potential contributors, and propose initial budget for supporting the Forum’s activities

- Propose agenda and documentation plan for the ad hoc workshop

- Organize the session of the ad hoc workshop

2) Membership:

The membership of the ad hoc workshop Organizing committee includes [to be completed by the workshop]:

- Chair

- Member 1

- Member 2

- Member 3

- Representative of the CGMS Secretariat

- Representatives of the Secretariats of the co-sponsoring Organizations

_______________

# Footnotes

: Secretariats of WMO, IOC, FAO

: Secretariats of WMO, IOC, FAO