| WORLD METEOROLOGICAL ORGANIZATION __________________ WMO INTEGRATED GLOBAL OBSERVING SYSTEMS (WIGOS) PILOT PROJECT FOR AMDAR, Fifth Session & AMDAR Panel Management Group Meeting DE BILT, THE NETHERLANDS, 28 FEBRUARY – 4 MARCH 2011 |  | WIGOS-PP-5-AMDAR-MG/Doc.2.6 (22.II.2011) ______ ITEM: 2.5 & 2.6 ORIGINAL: ENGLISH |
| --- | --- | --- |

Required updates to the AMDAR Reference Manual (WMO-No. 958)

and

Framework for Generic Software Specification for AMDAR

(Submitted by the Chairman of the AMDAR Panel)

Summary and Purpose of Document This document provides an overview of the discussions concerning the required updates to the AMDAR Reference Manual (WMO NO. 958) and a framework for a generic software specification for AMDAR

## ACTION PROPOSED

The AMDAR Panel Management Group is invited to:

- note the information; and

- discuss and make recommendations for next steps to be taken.

Annexes:

- Implementation Plan for the WIGOS Pilot Project for AMDAR

  - PP AMDAR Progress Report 2011-01

  - PP AMDAR Evaluation 2011-01

___________________

1.	As part of the Implementation Plan for the WIGOS Pilot Project for AMDAR, the Update of the AMDAR Reference manual (WMO NO. 958) and the Development of the Framework for Generic Software Specification for AMDAR belong to the specified Action Items and Related Sub-Tasks (Annex 1).

2.	These two Sub-Tasks are considered as “long-term” action items because of their structural nature and the dependency of the completion of the (4) “short-term” action items in the Implementation Plan.

3.	The long-term action items are relatively large and therefore time consuming items, for which the assistance of a contractor may be helpful. An estimated budget for external support to the two action items is reflected in the AMDAR Panel Action Items (see Document 3.2).

4.	A reflection of the discussions related to these two items can be found below:

  - “It is anticipated that the deliverables of the above-mentioned (short-term) sub-projects will eventually result in the substantial update of relevant parts of both technical and scientific components of the AMDAR Reference Manual and in proposal for updates to the CIMO Guide.  The aim of the sub-project No. 5, “Update of the AMDAR Reference Manual (WMO-No.958)” is to update the AMDAR Reference Manual.” (WIGOS-PP-AMDAR-1 (2008), Final Report, Executive Summary)

  - “It was noted that in order for several of the new parameters added to the new standardized AMDAR BUFR Template would require an update to the ARINC620 Specification before the full benefit of the new AMDAR BUFR Template could be felt. It was also noted that the AMDAR Technical Coordinator would seek additional information from the IPET-DRC on the use of the 0 07 007 Height parameter.” (3.5.5 under Status of the WIGOS Pilot Project for AMDAR, Final Report ET-AIR-1/AMDAR Panel-12)

  - “In consideration of the requirements to fulfill the functions and responsibilities of the AMDAR Panel until its next meeting, the work programme will place additional emphasis on updating the existing AMDAR documentation to better reflect the rapidly developing and expanding AMDAR observing system, including:

- AMDAR Reference Manual;

- ARINC 620 Software specifications; and

- Guidelines for the establishment of AMDAR national/regional programme

(4.2.3 under Future AMDAR panel and ET-AIR Work Programme, Final Report ET-AIR-1/AMDAR Panel-12)

4.4  	“Given the advances of AMDAR, updates to several documents are required 	including a set of additional flyers designed to educate NMHS and regional aviation 	communities on the benefits resulting from AMDAR participation, the AMDAR 	Reference Manual, and a new ARINC 620 Specification. Following the DLK 	Standards Committee Meeting in Montreal, Canada, July 2010, involving the E-	AMDAR Technical Coordinator, Stewart Taylor, and SO/AIR, Michael Berechree, 	WMO hosted a short meeting to begin the process of redefining/updating the 	ARINC620 Standard, taking into account the new requirements of the new AMDAR 	BUFT Template and In-Service Aircraft for a Global Observing System (IAGOS). A 	draft version of the new ARINC620 Standard will be submitted to the AMDAR Panel 	Science and Technical Sub-Group and IAGOS review and comment before the final 	version is submitted to the ARINC Standards Committee. It is still expected that this 	development will take 2 years before a new version of the ARINC Standard is 	finalized by the ARINC Standards Committee. ( SEE Doc. 2.1(1)

(3.2.2, bullet 3, ET-AIR-1 and AMDAR panel-12/Doc. 3.1(1))

5.	The current status of the AMDAR PP action items are reflected in the reports submitted to the Fourth Session of the EC-WG/WIGOS-WIS (10-11 February 2011) and presented in Annex 2 (PP AMDAR Progress Report 2011-01 and PP AMDAR Evaluation 2011-01).

# Implementation Plan for the WIGOS Pilot Project for AMDAR

# Background

Assisted by the WMO fifteenth Congress (Cg-XV), the high-level WIGOS / WIS goal is to establish a comprehensive, coordinated, and sustainable system of observing systems with assured access to data and products from the component observing systems by interoperability arrangements. WIGOS is the system of observing systems and the WMO Information System (WIS) provides the access through interoperability arrangements. The WIGOS / WIS will address all WMO Programme requirements through its Rolling Review of Requirements (RRR) to ensure availability of required information, meet data quality standards, and facilitate access to real-time data as well as to archived information.

This Project will focus on the practices impacting AMDAR data collection, processing, archiving and dissemination.  The standard practices used in observing the atmosphere need to be well documented to ensure sufficient detail accompany the observations so that users can interpret measurements correctly. In addition new methods and procedures will be required in preparation for the deployment of new operational instruments, such WVSSII water vapour sensor.

The Ad-Hoc Steering Group Meeting on the WIGOS Pilot Project for AMDAR held its first session at the WMO Headquarters in Geneva, Switzerland, from 2 to 3 July 2008.  The Ad-Hoc Steering Group reviewed the guidance and outcomes of the first session of Executive Council Working Group on the WMO Integrated Global Observing Systems (WIGOS) and the WMO Information System (WIS), which was held in Geneva, Switzerland, from 4 to 7 December 2007.

The Implementation Plan for the WIGOS Pilot Project for AMDAR has six deliverables:

- Development of a standardised BUFR Template for AMDAR;

- Application of WMO Metadata relevant to AMDAR;

- Development of a standardised Quality Management Framework for AMDAR data;

- Validation and preparation for intercomparison of available Water Vapour sensor performance;

- Update of the AMDAR Reference Manual WMO-No.958; and

- Development of the framework for generic software specification for AMDAR.

OVERALL BUDGET AND CONTRIBUTIONS BY EACH PROJECT PARTNER (CHF)

The estimated costs for the implementation and coordination of the WIGOS Pilot Project for AMDAR were first developed by the Ad-Hoc Steering Group Meeting on the WIGOS Pilot Project for AMDAR and can be found in the final report of that meeting. It should be noted that the actual cost of implementation will be borne by the stakeholders in the project.

| Partners / Participants: | AMDAR Panel E-AMDAR and USA AMDAR Programmes WMO Technical Commissions |
| --- | --- |
| Project Cost: | Estimated costs for meetings, consultants and publication CHF 125K |
| Funding Source(s): | This project will make optimum use of the expertise available from the AMDAR Panel and its WIGOS partners. Financial support shall be required through the WMO AMDAR Panel Trust Fund and WIGOS-WIS Trust Fund. |
| Project Timescale: | Will all be done in parallel and foreseen to be completed by December 2011 |
| Deliverables: | (1) Agreed BUFR Template for AMDAR; (2) Published best metadata practice for AMDAR; (3) Published best practice for Quality Management procedures for AMDAR; (4) Published results from the validation of the available Water Vapour sensors; (5) Updated AMDAR Reference Manual WMO-No. 958; and (6) Agreed framework for generic software specification for AMDAR. Note: In case of lack of resources provided towards the WIGOS-PP-AMDAR, Deliverables will be prioritized accordingly. |
| Project Summary: | With the completion of the project aims, AMDAR will be better integrated into WIGOS by adhering to WMO standards for instrumentation, data exchange and for end products. |

WIGOS PILOT PROJECT CONCEPT OF OPERATIONS

This Pilot Project is the contribution of AMDAR to the WIGOS / WIS developments of WMO. The WIGOS has developed a Concept of Operations (CONOPS) document that provides the umbrella principles and objectives of WIGOS / WIS.

CONOPS recognizes the need for a comprehensive, coordinated and sustainable global observing system. The WIGOS is a comprehensive, coordinated and sustainable system of observing systems based on all WMO Programmes’ observational requirements. It ensures availability of required data and information and facilitates access through the WMO Information System (WIS) according to identified temporal, geographical and organizational requirements, including those for real-time, near-real time and delayed-modes to all required information and in doing so it respects data sharing policies. Additionally, it helps ensure high data quality standards and benefits from archival and technological innovations.

WIGOS development and implementation proceeds in parallel with the planning and implementation of the WMO Information System. The combination of both efforts allows for an integrated WMO end-to-end system of systems designed to improve Member’s capability to effectively provide a wide range of services and to better serve research programme requirements.

The WIGOS integration objective will be accomplished at three levels:

- Standardization of instruments and methods of observation;

- WIS information infrastructure;

- End-product quality assurance.

SECOND SESSION WIGOS PILOT PROJECT FOR AMDAR

The second session for the WMO Integrated Observing System (WIGOS) Pilot Project for AMDAR was held at KNMI Headquarters in De Bilt, The Netherlands from 10-12 February 2009.

For WIGOS Pilot Project for AMDAR objective 1, Development of a BUFR Template for AMDAR, the meeting agreed on the format of a new Standardized BUFR Template for AMDAR, 3 11 010 version 2. It also agreed on the inclusion of a number of new elements, including a new AMDAR quality element. It was agreed that the newly proposed Standardized BUFR Template for AMDAR would be provided to the AMDAR Community and major NWP Centres for review and comment. Following the review and comments of the AMDAR Community and NWP Centres the final version, version 3 of the Standardized AMDAR BUFR Template was made available to the Inter-Programme Expert Team on Data Representation and Codes (IPET-DRC) for approval.   IPET-DRC-1 (15-18 September 2009) discussed this template, in particular the representation of quality information, and finally approved 3 11 010 version 4 and the new descriptors, provided that the proposed usage of an additional descriptor is found feasible to the AMDAR users. Next step after the approval from IPET-DRC the new Standardized BUFR Template for AMDAR is being validated using independent processing centres. The validation procedure being completed, the template would then be again submitted to IPET-DRC. Following the approval of the chairperson of the IPET-DRC, chairperson of the OPAG-ISS and the president of the CBS, the Template will be declared preoperational (this is expected to be accomplished by April 2011).

The meeting also discussed the WIGOS Pilot Project for AMDAR objective 3, the development of standardized procedure for Quality Management of AMDAR data. It noted that with the ever increasing amount of AMDAR data on the GTS there is now a real need to improve the overall quality of AMDAR data disseminated on the GTS. In order to achieve this, a better coordinated response to quality control of AMDAR data is required. The meeting agreed that a set of minimum standards, including evaluation criteria and procedures, for AMDAR data monitoring need to be developed. The meeting agreed that it would evaluate the current criteria and procedures used by all national and regional AMDAR programmes and would develop a set of minimum quality standards for AMDAR data.

THIRD SESSION WIGOS PILOT PROJECT FOR AMDAR

The third session for the WMO Integrated Observing System (WIGOS) Pilot Project for AMDAR was held at KNMI Headquarters in De Bilt, The Netherlands from 1-2 July 2009.

This meeting worked on the initial classification of components of metadata associated with AMDAR.  In particular, it endeavoured to identify metadata needed for describing data and products, metadata needed for usage of data and metadata needed for the operation of the AMDAR observing system. The classification will initially focus on one fleet within the E-AMDAR Programme to gauge the level of support from that airline before embarking on all operational airlines in the E-AMDAR Programme and finally all operational AMDAR Programmes.

NEXT STEPS

A next meeting of experts will be held 28 February 4 March 2011 at KNMI Headquarters in De Bilt. At that meeting the status of the deliverables will be reviewed and final proposals will be made and decisions will be taken in order to complete the short term project aims.

ACTION ITEMS AND RELATED SUB-TASKS OF THE WIGOS PILOT PROJECT FOR AMDAR

|  | Objective | Responsibility | Action | Status | Due Date |
| --- | --- | --- | --- | --- | --- |
| 1. | Development of a BUFR Template for AMDAR | (E-AMDAR and USA AMDAR Programme representatives) in collaboration with the ET-DR&C Validation Centres (to be nominated) | 1. Investigate the various versions of BUFR templates for AMDAR and their elements currently in use by national and regional AMDAR Programs. Provide specification to ET DR&C; 2. Develop a standardised BUFR Template for AMDAR that includes all the new extensions supporting parameters for AMDAR; 3. Validation of the AMDAR BUFR Template; and 4. Approval of the AMDAR BUFR Template. | 1st meeting BUFR Template for AMDAR has been held. Components of a proposed new Standardized BUFR Template for AMDAR, 3 11 010 version 2 has been approved by the AMDAR community. AMDAR Panel Chairman to forward the new Standardized BUFR Template for AMDAR to the next meeting of ET-DR&C | 1 & 2. Q3 2008 3. Q1 2009 4. Q2 2011 |
| 2. | Application of WMO Metadata relevant to AMDAR | (Chairman of the AMDAR Panel) Contractor TBD under the guidance of the AMDAR Panel Chairperson, ad-hoc support from WIS Project Office, IPET-MI | 1. Classify components of metadata associated with AMDAR. In particular, identify metadata needed for describing data and products, metadata needed for usage of data and metadata needed for the operation of the AMDAR observing system; 2. Identify metadata for quality control and administration. Also identify relevant policies for the sharing and usage of the metadata, data and products; 3. Describe the metadata utilising WMO profile of ISO 19115 to ensure appropriate compatibility with WIS and WIGOS; and 4. Create examples and best practice guides for inclusion in the AMDAR Reference Manual and relevant CIMO documents. | 1st meeting on Metadata relevant to AMDAR has been held. Classification of components of metadata associated with AMDAR for one airline in the E-AMDAR Programme completed. | 1. & 2. Q3 2009 3. Q2 2011 4. Q4 2011 |
| 3. | Development standardised procedure for Quality Management of AMDAR data | (E-AMDAR Programme Quality Monitoring Centre) in coordination with the AMDAR Technical and Science Sub Group, other AMDAR Data Monitoring Centres | 1. Examine the requirements for Quality Monitoring and Quality Assurance of AMDAR Data; 2. Develop a Quality Framework and procedure in support of high quality AMDAR Data to users; and 3. Identify potential AMDAR archive centres (DCPCs for WIS). | Evaluation of the current criteria and procedures used by all national and regional AMDAR programmes and would develop a set of minimum quality standards for AMDAR data. | 1. Q12009 2. Q1 2011 3. Q4 2011 |
| 4. | Validation and preparation for intercomparison of available Water Vapour sensor performance | USA AMDAR Programme Representative E-AMDAR Programme in coordination with CIMO ET-UASI | 1. Perform calibration and flight test and report; and, 2. Organize preparatory meeting to define the rules and procedures for the intercomparison of AMDAR and other upper-air data. 3. Take part in the WMO Radiosonde Intercomparison, China, 2010 | The current version of WVSSIIv3 water vapour sensor is still undergoing laboratory testing in the USA and Germany. Initial contact has been made with the CIMO President to formulate a plan for an intercomparison. Organize preparatory meeting to define the rules and procedures for the intercomparison of AMDAR and other upper-air data. (Pending on results of testing in the USA and Germany) | 1. Q2 2009 2. Q3 2009 3. Q2 2010 |
| 5. | Update of the AMDAR Reference Manual, WMO-No.958 | (Chairman of the AMDAR Panel) Contractor TBD under the guidance of the AMDAR Technical and Science Sub Group, CIMO Rapporteur. | 1. Review those sections of the AMDAR Reference Manual as identified (ensure the full suite of water vapour sensors and their measurements are included, turbulence and icing and future requirements for AMDAR; 2. Update to both technical and scientific components of the AMDAR Reference Manual and propose changes to the CIMO Guide; and 3. Incorporate input from other sub projects. 4. Draft new version of AMDAR Reference Manual | Pending | 1. Q4 2008 2 & 3. Q3 2009 4. Q4 2011 |
| 6. | Development of the framework for generic software specification for AMDAR | (Chairman of the AMDAR Panel) Contractor TBD under the supervision of E-AMDAR Representative in coordination with AMDAR Panel Technical and Science Sub-Group, Aviation Industry Groups. | 1. Review all versions of current software specifications currently in use by operational AMDAR Programs; and 2. Provide framework for the development of the generic software solution for AMDAR. | Pending | 1. Q1 2009 2. Q4 2011 |

PP AMDAR Progress Report 2011-01

| 1. Introduction | This Project is focused on: Developing the practices impacting AMDAR data collection, processing, archiving and dissemination. The practices used by AMDAR in observing the atmosphere need to be well documented to ensure sufficient detail accompany the observations so that users can properly interpret measurements. Develop new methods and procedures in preparation for the deployment of new operational instruments, such WVSSII water vapour sensor. |
| --- | --- |
| 2. Implementation Progress | IPET-DRC approved the new Standardized BUFR Template for AMDAR. Validation of the AMDAR BUFR Template 3 11 010 version 4 in progress. A set of minimum standards, including evaluation criteria and procedures, for AMDAR data monitoring need to be developed. A number of operational AMDAR Programmes have provided their current criteria and procedures used for quality monitoring of AMDAR data. These criteria and procedures will be evaluated in order to develop a minimum set of general standards that any operational AMDAR Programme can implement. The 3rd WIGOS PP for AMDAR meeting, using WMO profile of ISO 19115 to ensure appropriate compatibility with WIS and WIGOS, developed metadata that would cover both the aircraft and airport. The meeting also agreed that this particular objective would be tested on a single airline in the E-AMDAR Programme before finally being distributed to other operational AMDAR Programmes. The AMDAR Panel has also had initial discussions with the WMO Secretariat and the CIMO President regarding Object 4, Validation and Preparation for Intercomparison of Available Water Vapour Sensor Performance. It was agreed that before a preparatory meeting between the AMDAR Panel and CIMO takes place to define the rules and procedures for the Intercomparison of AMDAR and other upper-air data, the WVSS-II water vapour sensor would have to complete USA and European trials and to answer pre-defined quality requirements. It is expected that these field trials are due to conclude in the 1st half of 2011. |
| 3. Implementation Constrains | Level of available resources, both experienced personnel and financial, to implement all activities and objectives under the WIGOS PP for AMDAR are insufficient to implement all objectives in time. |
| 4. Action Plan | Each WIGOS PP for AMDAR meeting covered a number of objectives to maximize the available resources. Objectives where given an order of priority as well as classifying all the objectives as short or long term. |
| 5. Lessons Learned | The AMDAR community is lacking sufficient resources (e.g. experienced personnel and time) that could actively contribute to complete all the objectives of the Pilot Project within the original deadline. The level of funds available has reduced the support to the Pilot Project such that only personnel from the E-AMDAR or the USA AMDAR Programmes have been included in the Pilot Project, where participation from other regions would have provided wider acceptance of the concept and given the Pilot Project a more global perspective. Support to the Pilot Project from the NMHSs is suffering from a low priority; most members have very active AMDAR Programme(s) and therefore members find it difficult to secure the appropriate amount of time to work on the Pilot Project objectives. Due to required upgrades to the water vapour sensing system, the availability of a reliable aircraft based water vapour sensor has been delayed, causing the need for additional development, certification and (expensive) laboratory testing and flight trials (scheduled first half 2011). |
| 6. Challenges | Managing the resources to effectively cover all short and long term objectives for the WIGOS PP for AMDAR. |
| 7. Implementation Priorities for the next period | The Main priorities are: Completion of the validation of the IPET-DRC approved Standardised BUFR Template for AMDAR (3 11 010 version 4); Further development of AMDAR requirements for the application of WMO Metadata relevant to AMDAR (Expert Meeting, 28 February-4 March 2011); Further development of a standardised Quality Management Framework for AMDAR data (Expert Meeting, 28 February-4 March 2011) ; and Organize meeting between the AMDAR partners and CIMO for the Validation and preparation for intercomparison of available Water Vapour sensor performance. |
| 8. Resources Status | This project will make optimum use of the expertise available from the AMDAR Panel and its WIGOS partners. Financial support was requested to support WIGOS PP AMDAR activities from the WMO AMDAR Panel Trust Fund and WIGOS-WIS Trust Fund. |
| 9. Project Focal Point | Contact Person: Frank Grooters Position: AMDAR Panel Chairman Organization: KNMI Phone: +31 30 2206691 E-mail: frank.grooters@knmi.nl |
| 10. Place and Date | De Bilt, 6 February 2011 |

PP AMDAR Evaluation 2011-01

- Aims

This WIGOS Pilot Project for AMDAR focuses on developing the practices that are currently impacting AMDAR data collection, processing, archiving and dissemination.  The practices used by AMDAR in observing the atmosphere need to be well documented to ensure sufficient detail accompany the observations so that users can properly interpret measurements. It will develop new standards and procedures in preparation for the deployment of new operational instruments, such WVSSII water vapour sensor.

- Key deliverables and expected benefits

- Development of a standardised BUFR Template for AMDAR;

- Implementation of the application of WMO Metadata relevant to AMDAR;

- Development of a standardised Quality Management Framework for AMDAR data;

- Validation and preparation for inter-comparison of available Water Vapour sensor performance.

- Update the AMDAR Reference Manual WMO-No.958; and

- Develop the framework for generic software specification for AMDAR.

The impacts on existing AMDAR Programs following the WIGOS PP for AMDAR will greatly assist the operations of AMDAR Programs, with improved practices impacting AMDAR data collection, processing, archiving and dissemination of AMDAR data. In particular the use of a single standardized AMDAR BUFR Template, standardized procedure for Quality Management of AMDAR data and the application of WMO Metadata will greatly assist all operational and proposed AMDAR Programs.

- Implementation constrains; problems encountered

The AMDAR Pilot Project has gained so far the following experience and lessons learned:

- The AMDAR community is lacking sufficient experienced personnel that could actively contribute to all the objectives of the Pilot Project.

- The level of funds available has reduced the support to the Pilot Project such that only experts from the E-AMDAR and the USA AMDAR Programmes have been included in the Pilot Project, where participation from other regions would have provided wider acceptance of the concept and given the Pilot Project a more global perspective.

- Support to the Pilot Project from the NMHSs is suffering from a low priority; most members have very active AMDAR Programme(s) and therefore members find it difficult to secure the appropriate amount time to work on the Pilot Project objectives (work done so far has been in parallel to other AMDAR-related meetings).

- Due to required upgrades to the water vapour, the availability of a reliable aircraft based water vapour sensor was delayed. In the USA the installation of 50+ of the latest version WVSS-II is ongoing. In Europe this sensor is still under test in 3 Lufthansa A319 aircraft. The upgrading was causing the need for additional development, certification and (expensive) laboratory testing and flight trials.

- Pending issues

There are a number aspects to this project that require further attention, however due to work load of key personnel involved from the E-AMDAR and USA AMDAR Programmes, funding limitations and clashes with other WMO Meeting/workshops it has been difficult to schedule additional time when all experts are available at the same time to discuss the project. As such several key objectives require more lead time for to be regarded as complete.

- Partners involved (internal/external)

Without the close the cooperation of the E-AMDAR and USA AMDAR Programs it would be difficult to further progress the WIGOS Pilot Project AMDAR.

- Management and governance aspects (changes of organizational structure, etc.)

The first step in addressing the governance of the WMO AMDAR Panel was the successful transfer of the AMDAR Technical Coordinator’s responsibility into WMO and the WMO Secretariat structural and organization change that included the creation of a new Aircraft Observation Unit (AIR) within the Observing and Information Systems Department (OBS) and its Observing Systems Division (OSD). The AMDAR Technical Coordinator is the Secretariat lead for the Aircraft Observation Unit, with the responsibility for aircraft observations.  The second step that addressed the governance was a recommendation of the CBS Implementation-Coordination Team (ICT-IOS-5), Geneva, 15-18 September 2008 to CBS-XIV (March 2009) to establish a CBS Expert Team on Aircraft Observations (ET-AIR), with oversight of the WIGOS PP for AMDAR. The new ET on Aircraft Observations now has the oversight of the AMDAR PP for AMDAR.

Following the CIMO_XV (Helsinki, Finland, 2-8 September 2010) a number of ET-AIR and AMDAR Panel experts were nominated and finally accepted into the working structure of CIMO, including the Theme Leader on Aircraft Measurements. This role will have the responsibility to:

- Provide technical review of approved aircraft based humidity capabilities.

- Liaise closely with Expert Team on Instrument Intercomparisons for testing and validation of the AMDAR system and aircraft based humidity sensor.

- Provide input to future updates to the CIMO guide relevant to aircraft based observations, including identification of standards for inclusion in the CIMO Guide.

- Work closely with Expert Team on Standardization for the development and provision of specifications and standards for aircraft based observation systems in order to meet user requirements.

- Communicate to the Commission the latest development in AMDAR and other aircraft based observational platforms.

- Capacity building and Outreach requirements

Capacity and out reach was not addressed in the WIGOS PP for AMDAR. This PP focused on improving the practices impacting on AMDAR data collection, processing, archiving and dissemination.

However, at the Joint meeting of ET-AIR and the AMDAR Panel (5-7 October 2010) outreach was included as an important subject in the Terms of Reference for the AMDAR Panel Training Sub-Group (TrSG).

- Benefits achieved

The benefit of the WIGOS PP for AMDAR would be improved practices impacting AMDAR data collection, processing, archiving and dissemination allow better integration of AMDAR into WIGOS.

- Lessons learned and experiences gained

See point 3.

- Legacy of the Project

The legacy of the WIGOS PP for AMDAR will allow better integration of AMDAR into WIGOS.

- Resources used

Since the beginning of the WIGOS PP for AMDAR the staff resources used to date have included the time and effort of personnel from: WMO (SO/AIR, C/OSD), AMDAR Panel Chairman, E-AMDAR and USA AMDAR Programme staff.

WIGOS Planning Office Funds used: CHF 16,500

- Planned Project completion date

There are a number of short term and long term objectives under the WIGOS PP for AMDAR. The completion of the major objectives, both short and long term, will depend on appropriate resources.  The original planned completion date for the WIGOS PP for AMDAR was the 4th quarter 2010, but is due to the reasons described above, delayed until (at least) the 4th quarter of 2011.

- Project Focal Point

Contact person: 	Frank Grooters

Position: 		AMDAR Panel Chairman

Organization:		KNMI

Phone:			+31 30 2206691

Fax:			+31 30 2211195

Email:			frank.grooters@knmi.nl

- Place and Date

De Bilt, The Netherlands, 7 February 2011