| World Meteorological Organization |  | ICG-WIGOS-4/Doc.4.1 |
| --- | --- | --- |
| INTER-COMMISSION COORDINATION GROUP ON WIGOS (ICG-WIGOS-4) |  | Submitted by: | Secretariat |
|  |  | Date: | 9.I.2015 |
| FOURTH SESSION GENEVA, SWITZERLAND 17-20 February 2015 |  | Original Language: | English |
|  |  | Agenda Item: | 4 |

Status of the Key Activity Areas Implementation

(Submitted by the Secretariat)

Summary and purpose of document This document provides information on the status of the Key Activity Areas Implementation.

Action proposed

The ICG-WIGOS will be informed on progress toward implementing the WIGOS Framework, according to the WIGOS framework Implementation Plan (WIP), v.3.0 approved by EC-66.

____________

References:

      - Executive Council - Sixty-sixth session (2014) (WMO-No. 1136) (Annex to paragraph 4.4.6 of the general summary, p. 176)

Status of the Key Activity Areas Implementation

Table 2: WIGOS Implementation Activities, extracted from WIP, v.3.0 (approved by EC-66)

Activities in bold are considered the most critical for WIGOS to be implemented by XII. 2015.

Depending on the implementation scale, planned activities are specified as follows: G = Global activity, R = Regional activity and N = National activity.

Key to activity numbers: a.b.c, where a is number of respective sub-section of section 2, b is for a global (1), regional (2) or national (3) activity, and c is a sequential number to distinguish activities from one another. RQ: Required Resources. RB = Regular Budget.

(Evaluation of Progress: Completed; On-Track; Attention needed; Overdue indicated in the column for “Target Date for Completion”)

| No. | Activity | Deliverables | Target Date for Completion | Responsibility | Estimated Costs (2012-2015) K CHF | Progress (%) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Potential Risks |
|  |  |  |  |  | RQ | RB | Shortfall | Dependencies |
| 1. Management of WIGOS Implementation |
| 1.1.1 G | 1) Develop/Revise/Update WMO Regulatory Material to include WIGOS Regulations 2) Develop WIGOS Guide 3) Develop WIGOS Functional Architecture (FA) | 1) Updated WMO Technical Regulations (WMO-No. 49) and the new WIGOS Manual for Cg-17 approval (90 %) 2) Plan for WIGOS Guide(10 %) 3) WIGOS FA (50 %) | 1) Cg-17 2) 2015 3) 2016 | ICG-WIGOS | 400 |  |  | High 3.1.1; 4.1.1 5.1.1, 5.1.2 6.1.1; 7.1.1 8.1.1 |
| 1.1.2 G | Incorporate technical aspects of WIGOS implementation and continuing evolution into existing/new TCs and RAs working structures and procedures | 1) RA &TC working structure adjusted to address WIGOS activities (100 %) 2) Cross body coordination mechanisms in place (100 %) | 1) 2014 2) 2014 | 1) RAs; TCs 2) ICG-WIGOS | 0 |  |  | Low |
| 1.1.3 G | Provide annual reports and recommendations to EC and Cg on progress in WIGOS implementation | Annual reports to EC, Cg on WIGOS implementation status (100 %) | EC-65 EC-66 Cg-17 | ICG-WIGOS | 0 |  |  | Low |
| 1.2.1R | Develop Regional WIGOS Implementation Plans (R-WIPs) | R-WIPs developed (100 %) | 2015 | RAs | 100 |  |  | Low |
| 1.3.1 N | Develop National WIGOS Implementation Plans (N-WIPs) | 1. Guidance for N-WIPs developed (10 %) 2. N-WIPs developed (10 %) | 1. 2015 2. 2019 | Members | 100 |  |  | Medium |
| 2. Collaboration with the WMO co-sponsored observing systems and international partner organizations and programmes |
| 2.1.1 G | Develop guidance, mechanisms and procedures for engagement, coordination and collaboration with partner organizations (to be used on all, global, regional and national levels) | 1) Strategy for working with Partners is published & available on the Portal (0 %) 2) MOU or relevant form of collaboration agreement concluded with interested Partners (0 %) | 1) 2015 2) 2015 | ICG-WIGOS Partners | 0 |  |  | Med 7.1.1 |
| 2.1.2 G | Develop Collaboration framework for the Architecture for Climate Monitoring from Space (ACMS) (Note: for the development of ACMS itself, see new 3.1.2) | 1) ACMS strategy approved by Partners (100 %) 2) Collaboration framework for 3.1.2 developed (80 %) 3) ACMS governance scheme approved by Partners (100 %) | 1) 2013 2) 2014 3) 2015 | CGMS, CEOS SAT, CBS | 35 |  |  | Medium |
| 2.2.1 R | Examine and recommend areas where closer regional cooperation and coordination would be beneficial | Recommendations to be included in regional WIPs (100 %) | 2015 | RAs | 0 |  |  | Low |
| 2.3.1 N | Establish closer collaboration at the national level, NMHS with other government agencies, and with potential external data providers | 1) Guidance for establishing national collaboration frameworks; (10 %) 2) National collaboration frameworks commenced (10-20 %) | 1) 2015 2) 2015 | ICG-WIGOS, Members, RAs | 0 |  |  | Medium |
| 3. Design, planning and optimized evolution of WIGOS and its regional, sub-regional and national component observing systems |
| 3.1.1 G | Complete RRR practices, procedures, responsibilities and mechanisms for all systems and agreed application areas | 1) RRR included in the WIGOS regulatory material; consistency achieved with other WMO regulatory material; (100 %) 2) Appropriate bodies have RRR responsibilities identified in their ToRs (80 %) | 1) 2014 2) 2015 | CBS other TCs | 50 |  |  | High 3.1.3 3.2.1, 3.2.2 3.3.1, 3.3.2 7.1.1 |
| 3.1.2 G | Develop the Architecture for Climate Monitoring from Space (ACMS) focusing on GFCS four priorities | 1) ACMS logical model (80 %) 2) ACMS physical planning (10 %) 3) ACMS implementation status (0 %) | 1) 2013 2) 2014 3) 2015 | CGMS, CEOS, CBS, SAT | 50 |  |  | High 2.1.2 |
| 3.1.3 G | Using the RRR process & capitalizing on relevant experience of Members, develop guidance regarding observing network design principles | Guidance document on network design provided to Members (50 %) | 2015 | IPET-OSDE, ICG-WIGOS, TCs | 50 |  |  | Low 3.1.1 3.2.1, 3.2.2 3.3.1, 3.3.2 7.1.1 |
| 3.1.4 G | To develop a concept of Regional Basic Observing Network (RBON) to be applied by RAs | Description of RBON concept applied by Regions (50 %) | 2015 onwards | ICG-WIGOS, RAs | 0 |  |  | Low 1.1.1 |
| 3.2.1 R | Evolve and implement observing systems in the Region following the technical guidance of the technical commissions as represented in the EGOS-IP and other observing system implementation plans | 1) Report back to IPET-OSDE on the actions detailed in the EGOS-IP (100 %) 2) EGOS-IP initiated within the Region (20 %) | 1) 2014 2) 2015 | RAs | 80 |  |  | High 3.1.1, 3.1.3 3.2.2 3.3.1, 3.3.2 7.1.1 |
| 3.2.2 R | Update the global RRR database to take into account regional user requirements | Refined RRR database (OSCAR) (0 %) | 2015 | RAs; IPET-OSDE | 0 |  |  | High |
| 3.2.3 R | Migrate from the existing RBSN/RBCN into an integrated RBON | RBONs adopted by RAs (0 %) | 2015 onwards | RAs, Members | 0 |  |  | Low 1.1.1 3.1.4 |
| 3.3.1 N | Contribute to the collective regional effort to evolve and implement observing systems following the EGOS-IP and other observing system implementation plans | 1) Report back to IPET-OSDE on the actions detailed in the EGOS-IP (100 %) 2) EGOS-IP initiated at a National level (0 %) | 1) 2014 2) 2015 | Members | 0 |  |  | High 3.1.1, 3.1.3 3.2.1, 3.2.2 3.3.2 7.1.1 |
| 3.3.2 N | Define sub-Regional user requirements for observations | Plan for Updated RRR database (OSCAR) (0 %) | 2015 | Members | 15 |  |  | High |
| 4. Observing System Operation and Maintenance |
| 4.1.1 G | Develop guidance, mechanisms and procedures for improved integration of observational data and products | 1) Guidance included in the plan for the WIGOS Guide (0 %) 2) Work is underway for some specific product integration activities (0 %) | 1) 2015 2) From 2015 | ICG-WIGOS | 0 |  |  | High 1.1.1; 3.1.1; 4.1.2; 6.1.1; 8.1.1 |
| 4.1.2 G | Develop guidance for the process of sharing, between component observing systems, operational experiences, sharing of expertise and a guidance for resourcing joint activities | Guidance included in the plan for the WIGOS Guide (10 %) | 2015 | ICG-WIGOS | 90 |  |  | Medium 4.1.1 |
| 5. Quality Management (QM) |
| 5.1.1 G | Develop WIGOS Quality Management guidance, mechanism, practices and procedures | 1) Initial WIGOS QM to be incorporated into WIGOS Regulatory material (100 %) 2) Appropriate bodies have responsibilities identified in their ToRs (90 %) | 1) 2015 2) 2015 | ICG-WIGOS Relevant TCs | 280 |  |  | High (Resources) 5.1.2 8.1.1 |
| 5.1.2 G | Examination of current quality management practices and procedures being used by WMO observing programmes | Report on QM practices and procedures used with identification of areas for improvement (25 %) | 2014 | ICG-WIGOS | 200 |  |  | High (Resources) 5.1.1 |
| 6. Standardization and Interoperability |
| 6.1.1 G | 1) Develop guidance for WIGOS standards 2) Document the implemented standard and recommended practices and procedures on instruments, methods of observation, data products, etc. | 1) Guidance to WIGOS standardization developed (5 %) 2) Implemented standard and recommended practices and procedures are documented and available at the Portal as appropriate (0 %) 3) Newly developed standard and recommended practices documented in the WIGOS regulatory material (5 %) | 1) 2015 2) From 2015 3) From 2015 | Relevant TCs TT-WRM WIGOS PO | 100 |  |  | Low 1.1.1; 7.1.1; 7.1.3; 8.1.1; |
| 7. The WIGOS Information Resource (WIR) |
| 7.1.1 G | Design and develop the WIGOS Information Resource (WIR) | 1) Technical Specification (100 %) 2) Decision made on developments of WIGOS Information Resource (internal vs. call for tender) (100 %) 3) Operational Acceptance (0 %) | 1) 2014 2) 2014 3) 2015 | Secretariat in cooperation with Members | 330 & HR:2Y |  |  | High 3.1.1, 3.1.3 3.2.1, 3.2.2 3.3.1, 3.3.2 |
| 7.1.2 G | Investigate the need for a database describing the Global Observational Products (Satellite Data, Weather Radar) | Documented requirements for the database (100 %) | 2013 | SAT, CBS | 0 |  |  | Low |
| 7.1.3 G | Survey WMO Members on what they could offer to support development and operations of WIGOS Information Resource | Published survey results and resulting decisions (15 %) | 2013 | WIGOS-PO | 50 |  |  | Low 7.1.1 |
| 7.3.1N | Provide information required by WIR | Required information available in WIR and maintained (0 %) | From 2015 | Members | 0 |  |  | Medium 7.1.1 7.1.3 |
| 8. Data discovery and Availability (of Data and Metadata) |
| 8.1.1 G | Develop WIGOS metadata standards, practices and procedures | 1) WIGOS Metadata standards, practices and procedures approved and incorporated in WIGOS regulatory material (90 %) 2) Initial access to WIGOS Metadata provided through the WIR (20 %) 3) Practices and procedures established in WIGOS Manual (90 %) 4) Mechanism for maintenance of MD standards established (90 %) | 1) 2015 2) 2014 3) 2015 4) 2015 | TCs ICG-WIGOS | 100 |  |  | High 7.1.1 5.1.1 |
| 8.1.2 G | To develop a mechanism to assist Members in implementing and exploiting WIGOS metadata standards, practices and procedures | 1) Mechanism developed (0 %) | 2014 (to be postponed to 2015) | ICG-WIGOS | 0 |  |  | Low 4.1.1, 8.1.1 10.1.1 |
| 9. Capacity development |
| 9.1.1 G | Develop a WIGOS Capacity Development (WCD) strategy including education and training | 1) WCD Strategy developed & available on the WIR (50 %) 2) WCD activities underway (50 %) | 1) 2013 2) 2015 | ICG-WIGOS ETR, RAs | 0 |  |  | Medium 1.1.1, 1.2.1 2.3.1,3.1.3, 3.2.1, 4.1.1, 4.1.2, 5.1.1; 6.1.1, 7.1.1; 8.1.1, 9.1.3, 9.3.1, 9.3.2 |
| 9.1.2 G | Assistance provided to Members regarding WIGOS implementation | Assistance provided to Members for the development of N-WIPs (20 %) | 2015 | WIGOS PO WMO Members | 200 |  |  | Medium 3.1.1; 4.1.1 5.1.1, 5.1.2 6.1.1; 7.1.1 8.1.1 |
| 9.1.3 G | Develop WIGOS related guidelines and training materials and other relevant documentation | Training materials and guidelines developed (0 %) | 2015 | WIGOS PO TCs | 100 |  |  | Medium 1.1.1; 7.1.1; 7.1.3; 6.1.1; 8.1.1; |
| 9.3.1 N | Mobilize resources for WIGOS implementation | More resources made available to NMHSs for WIGOS implementation (5 %) | 2015 | WMO Members with assistance from the WMO Secretariat | 0 |  |  | Medium |
| 9.3.2 N | Assist Members in using WIR Tools for the design and management of national WIGOS networks | Initial steps taken to improve design on national networks (0 %) | 2015 | WMO Members | 120 |  |  | Medium 7.1.1 |
| 9.3.3 N | Assist Members in implementing WIGOS metadata | Tools available to assist Members in providing the WIGOS metadata (0 %) | 2014 | WMO Secretariat Members | 250 |  |  | Medium 8.1.1 |
| 10. Communications and outreach |
| 10.1.1 G | Develop an effective WIGOS communications and outreach strategy | WIGOS Communications and Outreach Strategy developed (100 %) | 2013 | ICG-WIGOS | 0 |  |  | Low |
| 10.1.2 G | Develop communications and outreach materials (see Annex I for suggestions) | Communications and outreach materials available on the WIGOS Portal (75 %) | 2015 | WIGOS-PO | 125 |  |  | Low 7.1.1 |

________

# Footnotes

WIGOS Guide be delivered by Cg-18

High-level coordination, and engagement from all WMO Programmes and expertise available

Postponed after Cg-XVII (specifically in the less-least developed countries) (ICG-WIGOS-2)

Congress emphasized that strong support and close collaboration among Members were needed to advance scientific knowledge and technical infrastructure to meet the WIGOS requirements. Within the Regions, it would be desirable to strengthen cooperation and partnership through Region-wide organizations or subregional groupings overseeing the WIGOS observing components. It specifically refers to enhanced cooperation among meteorological, hydrological and marine/oceanographic institutions/services where they are separated at the national level.

High-level coordination; contributions from all WIGOS component observing systems & expertise available

HR: Human resources in number of years