| World Meteorological Organization |  | ICG-WIGOS-4/Doc.4.2 |
| --- | --- | --- |
| INTER-COMMISSION COORDINATION GROUP ON WIGOS (ICG-WIGOS-4) |  | Submitted by: | Secretariat |
|  |  | Date: | 9.I.2015 |
| FOURTH SESSION GENEVA, SWITZERLAND 17-20 February 2015 |  | Original Language: | English |
|  |  | Agenda Item: | 4 |

Status of the ACTION PLAN OF ICG-WIGOS AND TASK TEAMS

(Submitted by the Secretariat)

Summary and purpose of document This document provides information on the status of the Action Plan of ICG-WIGOS and Task Teams.

Action proposed

The ICG-WIGOS will be informed about the status of the Action Plan of ICG-WIGOS and Task Teams.

____________

References:

ICG-WIGOS-3, Final report

Appendix III

FUTURE WORK PROGRAMME AND ACTION PLAN OF ICG-WIGOS AND TASK TEAMS

| No () | Action/Activity | Deadline | Responsible | Status (by 09/01/2015) | WIGOS PO lead |
| --- | --- | --- | --- | --- | --- |
| 1 (4.1.3) | Review the drafts (WMO Technical Regulations, Vol. I, Part I and the Manual on WIGOS), and provide the feedback | 17/03/14 | ICG-WIGOS | Completed | IZ |
| 2 (4.1.3) | Check with DPMU feasibility and deadline for submission of the documents (listed under No.1) for translation; (also in connection with RA-III-16 and CBS-Ext.(2014) sessions) | 31/03/14 | WIGOS-PO | Completed | IZ |
| 3 (4.1.3) | Organize an ad-hoc workshop/meeting on Sections 4 urgently to ensure an expert review, buy-in from space agencies, and a refined draft Sections 4 | 31/03/14 | WIGOS-PO | Done in a different way (Draft Sec.4 refined by OBS staff) | LPR |
| 4 (4.1.3) | Nominate a satellite expert as a member of TT-WRM for the work in the future | 30/06/14 | WIGOS-PO | Not completed | LPR |
| 5 (4.1.5) | Consider appropriate provision(s) for the contribution of non-NMHS observations within the WIGOS relevant Technical Regulations | 31/03/14 | TT-WRM | Completed | IZ |
| 6 (4.1.6) | Ensure availability of the Drafts WMO Technical Regulations (WMO-No. 49), Volume I, PART I – WIGOS, and Manual on WIGOS for CBS-Ext.(2014) | 31/08/14 | WIGOS-PO | Completed | IZ |
| 7 (4.2.7) | Consider the additional element(s) in the next version of the draft standard, if needed, and complete WMD metadata profile as appropriate | 31/03/14 | TT-WMD | Completed | LFN |
| 8 (4.2.7) | Update the draft standard accordingly and submit the revised document to ICG-WIGOS by end of March 2014 ready for formal review by Presidents of TCs in association with the rest of the WIGOS technical regulations by the end of June 2014 | 31/03/14 | TT-WMD | Completed | LFN |
| 9 (4.2.7) | Reflect the following ways of reporting in the drafts Vol. I, Part I, and the Manual on WIGOS: (a) Mandatory elements shall be reported; (b) Conditional elements shall be reported if the condition comes true; (c) Optional elements should be reported, as they add valuable metadata information supporting adequate use of observations. | 31/03/14 | TT-WRM | Completed | IZ |
| 10 (4.2.7) | Nominate a number of individuals representing various application areas (to generate profiles and report back to TT-WMD for consolidation) | 30/06/14 | Chair, ICG-WIGOS supported by WIGOS-PO | Not completed | LFN |
| 11 (4.2.8) | Review the draft specification of the WIGOS Core Metadata standard, in association with the rest of the WIGOS technical regulations | 30/06/14 | P-TCs; EC-PORS; GCOS; WMO Space Programme | Completed | IZ |
| 12 (4.2.8) | Ensure involvement of the WMO Space Programme and EC-PORS in the review and further development of the draft specification of the WIGOS Core Metadata Standard. | 15/07/14 | WIGOS-PO | Not completed | LPR |
| 13 (4.2.9) | Organize TT-WMD-2 | 30/05/14 | WIGOS-PO | Completed | LFN |
| 14 (4.2.10) | Initiate the steps to formalize the current semantic standard needs, i.e. the decisions on fixed vocabularies (e.g., variable names, Station IDs) in support of interoperability: (a) who will drive the process of establishing governance; (b) who will take responsibility for hosting and maintaining such vocabularies? | 30/06/14 | WIGOS-PO | On track | LPR |
| 15 (4.2.14) | Develop the draft document on WIGOS Station Identifiers addressing the relevant technical issues accordingly for its submission to Cg-17 | 28/02/15 | Vice-President, CBS | On track | LPR |
| 16 (4.3.4) | Identify a member of TT-WQM with satellite expertise | 31/03/14 | WIGOS-PO | Not completed | LPR |
| 17 (4.3.4) | Organize TT-WQM-1 | 30/04/14 | WIGOS-PO | Completed | LPR |
| 18 (4.3.4) | Organize the Workshop on Quality Management with the following aim: (a) Review Regulatory Material on Quality Management; (b) Review of the observational data quality monitoring practices for the WIGOS component observing systems | 31/12/14 | WIGOS-PO | Partially Completed | LPR |
| 19 (5.1.3) | Provide the examples on how to complete the national checklist | 14/03/14 | Australia, Switzerland | Completed with a considerable delay due to overload of DPMU | IZ |
| 20 (5.1.3) | Provide the complete checklist (with the examples listed in Action No. 19) to the presidents of RAs for its distribution to all Permanent Representatives in the respective Regional Association with the request to: (1) nominate a National WIGOS Focal Point of their Country, and (2) provide their feedback on the Self-assessment Checklist, preferably by March 2015 (the completed checklist should be provided to both, the president of RA and the WIGOS Project Office) | 30/04/14 | WIGOS-PO | Progressing (with a considerable delay as a consequence of the Action No. 19) | IZ |
| 21 (5.1.4) | Report to ICG-WIGOS on a renegotiation process of the GCOS MoU with other sponsors when the process is finished | In due course | A. Simmons | Open | LPR |
| 22 (5.1.6) | Invite an AfriGEOSS representative to the remaining sub-regional WIGOS workshops | 31/03/14 | WIGOS-PO | Completed | LPR |
| 23 (5.1.6) | Provide input to the Post-2015 GEO Work Plan prior to next GEO Plenary in Gabon | 30/09/14 | Chair, ICG-WIGOS | Completed | LPR |
| 24 (5.1.8) | Incorporate the Observing System Network Design (OSND) Principles developed under the auspices of IPET-OSDE into the Manual on WIGOS and the Guide to WIGOS. | In due course | TT-WRM | Completed (Manual) | IZ |
| 25 (5.1.11) | Clarify which metadata shall be included in the OSCAR, and which shall be mandatory | 31/12/14 | TT-WMD | Completed | LFN |
| 26 (5.1.12) | Present the vision for the fully developed WIR at ICG-WIGOS-4 | ICG-WIGOS-4 | WIGOS-PO | On track | TP |
| 27 (5.1.13) | Draft one or more specific and concrete CD projects (dedicated specifically to RA I in the first instance) to undertake WIGOS implementation in a practical/tangible way | 31/07/14 | WIGOS-PO | On Track | LPR |
| 28 (5.1.14) | Use EC-66, and specifically RA III (jointly with CBS-Ext.) and RA I sessions should be used as much as possible for Communications and Outreach | In due course | WIGOS-PO | On Track | LPR |
| 29 (5.1.16) | Develop a concept paper of WIGOS Conferences presented at EC-66 | 31/05/14 | WIGOS-PO | Completed | LPR |
| 30 (5.1.17) | Distribute a circular letter of SG to PRs on progress achieved in WIGOS implementation | 31/05/14 | WIGOS-PO | Not completed | LPR |
| 31 (6.2.3) | Consider funding of ICA | 30/06/14 | WIGOS-PO | Completed | LPR |
| 32 (6.2.6) | Coordinate within CIMO the development of a brief information document to be used for communications with PRs on the Minamata Convention on Mercury (UNEO) and impacts on NMHS | CIMO-16 | President, CIMO | Completed | IZ |
| 33 (6.5.7) | Organize a dedicated WIGOS Workshop on GAW requirements for space-based observations | 31/12/14 | WIGOS-PO | Completed | LPR |
| 34 (6.6.3) | Develop a WMO position paper on WMO Data Management with a new vision and paradigm | 31/12/14 | President, CCl | Unknown | LPR |
| 35 (6.6.3) | Consider the potential for incorporating DM within the remit of WIS | CBS-Ext. | Vice-President, CBS | Unknown | LPR |
| 36 (6.6.3) | Develop DM guidance for Members with a focus on DM principles | 31/12/14 | President, CBS | Unknown | LPR |
| 37 (7.1.2) | Organize the sub-regional WIGOS/WIS workshop in the Central and East Africa, respectively | 30/06/14 | WIGOS-PO | Completed | LPR |
| 38 (7.1.4) | Incorporate R-WIP-I into AMCOMET Strategy and Implementation Plan | In due course | RA-I/TT-WIGOS WIGOS-PO | On Track | LPR |
| 39 (7.1.5) | Organize a WIGOS side event at RA-I-16 | RA-I-16 | RA-I/TT-WIGOS WIGOS-PO | On Track | LPR |
| 40 (7.1.6) | Organize a Side event on WIGOS for PRs of RA I at EC-66 | EC-66 | WIGOS-PO | Completed | LPR |
| 41 (7.3.5) | Organize a joint TECO-RECO in conjunction with CBS-Ext. and RA-III-16 sessions |  | D/DRA, D/OBS | Completed | LPR |
| 42 (7.3.6) | Organize a regular session of the RA III Working Group on Infrastructure and Technology Development (WG-ITD) | 31/05/14 | D/OBS, D/DRA | Completed | LPR |
| 43 (7.3.6) | Organize a WIGOS workshop in conjunction with the meeting WG-ITD mentioned above | 31/05/14 | D/OBS, D/DRA | Completed | LPR |
| 44 (7.4.4) | Inform OPAG-IOS and IPET-OSDE about a concern that no requirements for lightning detection are captured in the WIGOS databases | 30/04/14 | WIGOS-PO | Completed | LPR |
| 45 (7.5.5) | Consider how RECO, RA-V-16 can be used for WIGOS communications and outreach | 31/03/14 | D/OBS, D/DRA | Completed | LPR |
| 46 (7.6.2) | Develop an appropriate mechanism for how to bring TCs and RA working bodies together; | 31/12/14 | D/OBS and D/DRA | Completed | IZ |
| 47 (7.6.3) | Make available the presentations on the successes of national implementation in Region VI presented at RA-VI-16 on the WIGOS web page as a part of the Communications and Outreach effort | 31/03/14 | WIGOS-PO | Completed | IZ |
| 48 (8.2) | Request CBS to lead a development of a “Vision for the WIGOS in 2040” with the final target for approval by Cg-XVIII | CBS-Ext. | Chair, ICG-WIGOS | Completed | LPR |
| 49 (8.4) | Ensure the specified documentation for ICG-WIGOS-4 | 15/01/15 | WIGOS-PO, ICG-WIGOS | On track | IZ |
| 50 (10.1.1) | Develop a paper on generic DM aspects for this purpose (see also Actions 34 and 35) | CBS-Ext. | CBS and CCl representatives | Not completed | LPR |
| 51 (10.2.1) | Present experiences of JCOMM-OBS with non-NMHS data, as well as examples of NMHS that have successfully integrated third-party data in their operations | ICG-WIGOS-4 | JCOMM-OBS, ICG-WIGOS, WIGOS-PO | On track | LPR |
| 52 (10.3.1) | Further consideration collaboration of WMO with EUMETNET how it could be used and expanded for the other RAs | ICG-WIGOS-4 | WIGOS-PO | On Track | LPR |

________

# Footnotes

With the reference to the paragraph of the General Summary

Status column entries will be one of the following descriptors: Completed; On-Track; Overdue