| World Meteorological Organization |  | ICG-WIGOS-4/Doc.7.1(2) |
| --- | --- | --- |
| INTER-COMMISSION COORDINATION GROUP ON WIGOS (ICG-WIGOS-4) |  | Submitted by: | OPAG IOS Chair, J. Dibbern |
|  |  | Date: | 6.II.2015 |
| FOURTH SESSION GENEVA, SWITZERLAND 17-20 February 2015 |  | Original Language: | English |
|  |  | Agenda Item: | 7.1 |

# RESPONSES OF WMO TECHNICAL COMMISIONS TO WIGOS IMPLEMENTATION

(Submitted by the OPAG IOS Chair, Jochen Dibbern (Germany))

Summary and purpose of document This document provides information on the OPAG IOS efforts and recommendations regarding the development of Observing Network Design (OND) high-level guidance.

Action proposed

The Meeting is invited to note the information contained in this document when considering its recommendations.

References:

Final report, OSDW2 workshop, Geneva, 2-4 February 2015

Appendices

A	OSDW2 Recommendations to ICG-WIGOS-4

B	Proposed workplan and updated roadmap for the development of OSND guidance

____________

Discussion

  - The second ad hoc Workshop on Observing System Design, OSDW2, of the Commission for Basic Systems (CBS) Open Programme Area Group (OPAG) on Integrated Observing Systems (OPAG-IOS) Inter-Programme Expert Team on the Observing System Design and Evolution (IPET-OSDE) was held at the WMO Headquarters in Geneva, Switzerland from 2 to 4 February 2015 and was chaired by the Chair of the IPET-OSDE, Dr John Eyre (United Kingdom).

  - The workshop’s goal was to respond to the WIGOS Implementation Key Activity Area No. 3 (KAA#3) on design, planning and optimized evolution of WIGOS and its regional, sub-regional and national component observing systems. It particularly followed up from the first workshop and follow-up activities by the IPET-OSDE, which had proposed Observing System Network Design (OSND) principles to be included in the Manual on WIGOS (reviewed by Technical Commissions, endorsed by CBS Ext.(2014); afterwards submitted to Members for their review, and submitted for approval to Cg-17).

  - According to the CBS Ext.(2014) guidance and input from the participants and other groups (e.g. GRUAN WG, GAW, GCW), the workshop further developed draft high-level OSND guidance materials, based on the OSND principles. Such guidance material is provided in annexes of the report of OSDW2, and it will be used during follow-up activities by OSDW2 participants to prepare the draft high-level guidance on Observing Network Design eventually to be proposed for inclusion in the future Guide to WIGOS. It is planned to distribute the draft guidance more widely to other contributors for their review and comments with the goal of submitting draft guidance to the fifth Session of the Inter-Commission Coordination Group on the WMO Integrated Global Observing System (ICG-WIGOS) for its consideration.

  - The workshop agreed on a revised workplan and roadmap for the further development of guidance for OSND (Appendix B). The roadmap provides details on the role of this workshop’s participants and other stakeholders in this regard.

  - The Fourth session of the ICG-WIGOS, Geneva, 17-20 February 2015 is invited to review the progress and recommendations of the workshop (Appendix A) and to provide further advice to the IPET-OSDE.

  - The second session of the IPET-OSDE (tentatively scheduled in Geneva in April 2016) will review and, if necessary, revise the draft OSND guidance and roadmap.

______________

APPENDIX A

RECOMMENDATIONS TO ICG-WIGOS-4 FROM THE SECOND AD HOC WORKSHOP ON OBSERVING SYSTEM NETWORK DESIGN

(Geneva, Switzerland, 2-4 February 2015)

1.	Issues for the ICG-WIGOS to consider:

- Taking into account the OND guidance development workplan, ICG-WIGOS will be invited to seek comments from their TC and RA members on the draft OND guidance materials, when they are available in late 2015; and

- ICG-WIGOS is requested to advise on the role of IPET-OSDE, OPAG IOS and CBS with regard to the development of OND guidance materials, approval mechanisms, and to comment on the proposed workplan.

2.	Items extracted from the draft OSND guidance materials, which imply additional activities of WMO (not targeted to Members but to WMO bodies), and which the ICG-WIGOS is invited to consider:

- Develop and maintain regional (for Regional Associations, and climate regions) observational user requirements in OSCAR;

- Develop mechanisms for sharing best practice and lessons learnt on observing network design;

- Develop tools to aid design of cost-effective observing systems, including assessment of actual or anticipated impact of observations. These are needed for each Application Area;

- Develop observing network performance targets, and indicators;

- Develop guidance on the transition of existing (legacy) systems to meet WIGOS requirements and standards. e.g. CIMO could be invited to make some recommendation(s);

- Develop guidance on how to interpret UR information in OSCAR for the purpose of Network Design; and

- Develop guidance on how to design observing systems using the most appropriate technology or combination of technologies.

______________

APPENDIX B

PROPOSED WORKPLAN AND UPDATED ROADMAP FOR THE DEVELOPMENT OF OSND GUIDANCE

WORKPLAN AND UPDATED ROADMAP FOR THE DEVELOPMENT OF OSND GUIDANCE

(Version 4 February 2015 as proposed by OSDW2 workshop, with updated status)

| Time | Milestone (event) | By whom | Tasks | Status |
| --- | --- | --- | --- | --- |
| Nov. 2013 | OSDW1 TT-WRM |  | Produce input to OSND principles Provide input on OSND principles and guidance to WIGOS RM | Done |
| Dec. |  | J. Eyre | Draft OSND principles | Done |
| Jan. 2014 |  | OSDW1 participants & J. Eyre | Review by OSDW1 participants New draft of OSND principles produced based on feedback (J. Eyre by 27 Jan.) | Done |
| Feb. | ICG-WIGOS |  | Review draft OSND principles Propose framework into which OSND principles & guidance will fit | Done |
| Mar/Apr. | IPET-OSDE-1 |  | Review and revise OSND principles Draft plan for preparing OSND guidance, and tasks for Team members for drafting materials | Done |
| 4 Apr. | TT-WRM |  | OSND principles submitted to the TT-WRM, and the WRM review process through Technical Commissions, and WMO Executive Bodies | Done |
| Apr. | ICT-IOS-8 |  | Notes the OSND principles Review/revise and approve plan for preparing OSND guidance | Done |
| May |  | IPET-OSDE members | IPET-OSDE members to review draft OSND guidance and provide feedback to the Chair | Done |
| Jun. | EC-66 |  |  |  |
| Jul. |  |  |  |  |
| Aug. |  |  |  |  |
| Sep. | CBS Ext. (2014) |  | Consideration by CBS of (i) the OSND principles (to be noted by CBS), and (ii) the roadmap for producing the OSND guidance, as part of WIGOS materials for approval | Done |
| Oct. |  |  |  |  |
| Nov. |  | Members | Review of Cg-17 WIGOS RM by Members | Done |
| Dec. |  | Members | Review of Cg-17 WIGOS RM by Members | Done |
| Jan. 2015 |  | Members | Review of Cg-17 WIGOS RM by Members | Done |
| Feb. | OSDW2 ICG-WIGOS-4 |  | OSDW2 to review/update OSND guidance Draft OSND guidance reviewed by ICG-WIGOS |  |
| Mid Feb. |  | OSDW2 participants | Review of the OSDW2 final report |  |
| End. Feb. |  | Secretariat | Final report of OSDW2 published |  |
| End Mar. |  | J. Eyre | Compile draft OND guidance on the basis of OSDW2 materials |  |
| Apr. |  |  |  |  |
| May. | Cg-17 |  | Approve WIGOS Regulatory Material, including OND principles |  |
| End. May |  | OSDW2 participants | Review draft OND guidance and send back comments to J. Eyre |  |
| End Jun. |  | J. Eyre | Update OND guidance on the basis of comments from OSWD2 participants |  |
| Early Jul. |  | Secretariat | Send the draft OND guidance to IPET-OSDE members, other OPAG IOS ET Chairs, GCOS, OSDW1 & OSDW2 participants, and past contributors from GRUAN WG, GCW, GAW, requesting review by end of Sept. |  |
| Aug. |  |  |  |  |
| Sep. |  | Secretariat | Comments received |  |
| Mid. Oct. |  | J. Eyre | J. Eyre to compile next version of OND guidance on the basis of received comments |  |
| End Oct. |  | WIGOS PO | Send draft OND Guidance to ICG-WIGOS members for their review Deadline : end of Dec. 2015 |  |
| Nov. | ET-SBO |  |  |  |
| Dec. |  |  |  |  |
| Jan. 2016 |  | J. Eyre | To compile draft OND guidance on the basis of ICG-WIGOS comments, for review by IPET-OSDE-2 |  |
| Feb. | ICG-WIGOS-5 |  | Draft version of OSND guidance available and reviewed by ICG-WIGOS Draft OSND guidance (possibly to be refined by IPET-OSDE2 & ICT-IOS9 if requested by ICG-WIGOS) submitted to EC (fast-track) |  |
| Mar. |  |  |  |  |
| Apr. | IPET-OSDE-2 |  | Draft version of OSND guidance reviewed by IPET-OSDE if necessary |  |
| May | ICT-IOS-9 |  | Draft version of OSND guidance (possible revision) submitted to EC (fast track) Final draft version of OSND guidance available (slow track) |  |
| Jun | EC-68 |  | OSND guidance approved by EC (fast track) |  |
| Jul. |  |  |  |  |
| Aug. |  |  |  |  |
| Sep. | CBS-16 |  | OSND Principles and Guidance endorsed by CBS (slow track) |  |
| Oct. |  |  |  |  |
| Nov. |  |  |  |  |
| Dec. |  |  |  |  |
| Jan. 2017 |  |  | Draft OSND guidance submitted to EC (slow-track) |  |
| Feb. |  |  |  |  |
| Mar. |  |  |  |  |
| Apr. |  |  |  |  |
| May | EC-69 |  | OSND Guidance approved by EC (slow track) |  |

______________