| World Meteorological Organization |  | ICG-WIGOS-5/Doc.4.3.2 |
| --- | --- | --- |
| INTER-COMMISSION COORDINATION GROUP ON WIGOS (ICG-WIGOS-5) |  | Submitted by: | Secretariat |
|  |  | Date: | 18.I.2016 |
| FIFTH SESSION GENEVA, SWITZERLAND 25-28 January 2016 |  | Original Language: | English |
|  |  | Agenda Item: | 4.3 |

# 4.	PROGRESS TOWARDS IMPLEMENTATION OF WIGOS

# 4.3.2	REVIEW OF OUTCOMES FROM the 4th session of the task team on wigos metadata (tt-wmd-4)

(Submitted by the Secretariat)

Summary and purpose of document This document provides information on outcomes from the 4th Session of the Task Team on WIGOS Metadata (TT-WMD-4)

Action proposed

The session will be informed on the outcomes from the 4th Session of the Task Team on WIGOS Metadata (TT-WMD-4) to be taken into account when considering the relevant Agenda Item.

References:

Draft Final Report from the 4th Session of the Task Team on WIGOS Metadata (TT-WMD-4), Alanya, Turkey, 20-23 October 2015

____________

4.3.2.	REVIEW OF OUTCOMES FROM the 4TH SESSION OF the TASK TEAM ON WIGOS METADATA (TT-WMD-4)

I. Background

      - The fourth session of the Inter-Commission Coordination Group on WIGOS (ICG-WIGOS) Task Team on WIGOS Metadata (TT-WMD-4) was held at Alanya, Turkey, at the kind invitation of the Government of Turkey, from 20 to 23 October 2015.

      - The session was co-Chaired by Mr J. Klausen (Switzerland) and Mr K. Monnik (Australia), co-Chairs TT-WMD.

      - The session reviewed and took into account for the discussions, the relevant resolutions of the 17th World Meteorological Congress (Cg-17) and of the 67th WMO Executive Council (EC-67), as well as the conclusions and recommendations from various groups and task teams working on matters related with observations metadata.

II. Outcomes

      - The session reviewed the latest version of the OSCAR/Surface (the OSCAR database component concerning metadata for surface-based observations) and the need to reflect the recent changes of the OSCAR structure into the WIGOS Metadata Standard (WMDS). In particular, several code tables of the WMDS were reviewed and/or completed based on the current code tables of OSCAR/Surface.

      - The session also reviewed the draft version of the logical data model, of OSCAR/Surface, for the exchange of metadata, and made proposals for its improvement and update, towards a more complete and functional model, including the facility of machine-to-machine procedures for the automatic insert and transfer of metadata.

      - From the discussions on the governance of the WMDS, it was proposed to use the Commission for Basic Systems (CBS) “simple/fast track” procedure, for the approval of new or revised code tables in 2016. Recent follow-up discussions within the Secretariat have led to the suggestion that the draft tables be used in "pre-operational mode". This means that the draft tables are considered to be “good enough” for practical purposes, and flags that they can be used while the formal approval process proceeds at its own pace. The impact of not having formal approval is small, since any changes made during the approval process will be likely to be limited to adjustments of the wording of definitions or to addition of new entries rather than a renaming the code list identifiers (that are stored in the database). It is proposed to go through the next WIS approval “fast track” starting in June 2016, following which the code lists can be finalized.

      - The session agreed on a plan for the development of guidance material to assist Members in the application of the WMDS, including guidance on the use of the web interface of OSCAR/Surface as well as for the use of machine-to-machine interfaces to ingest and retrieve their metadata. The structure of the chapter in the Guide to WIGOS related with WIGOS Metadata, was agreed to include three sections: an introduction with the identification of roles in managing WIGOS metadata and the description of responsibilities, as well as their relation to OSCAR; the second and third sections will be dedicated to the creation and to the using of WIGOS metadata, respectively. The contents of the guide are planned to be developed by TT-WMD by June 2016.

      - Finally, taking into account the conclusions and the tasks that need to be completed before the entry into force (July 2016) of the WIGOS Regulatory Material approved by Cg-17, the session agreed on the updates to the work plan (see Appendix) including developing the guidance material and the competencies for the use of WMDS by WMO Members.

      - The “Draft Final Report from the 4th Session of the Task Team on WIGOS Metadata (TT-WMD-4), Alanya, Turkey, 20-23 October 2015” contains detailed descriptions of the proposed improvements to the logical data model and to the code tables, as well as to the approach for developing the guidance material.

________

Appendix

TT-WMD ACTION PLAN FOR THE PERIOD XI.2012 TO VI.2016

| Version | Date | Comments |
| --- | --- | --- |
| 1 | 23/11/2012 | Action plan developed at TT-WMD-01 |
| 2 | 15/3/2013 | TT-WMD-1 |
| 2a | 31/01/2014 | Intermediate update for ICG-WIGOS |
| 3 | 15/05/2014 | TT-WMD-2 |
| 4 | 04/12/2014 | TT-WMD-3 |
| 5 | 23/10/2015 | TT-WMD-4 |

| No. | Task | Deliverable/Activity | Deadline (if not stated end of month) | Responsible | Status* | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Produce proposed definition of contents of WIGOS metadata | Initial version of WIGOS metadata | 15 March 2013 | Howe | Complete 15/3/2013 | TT-WMD-1 achieved this |
| 1 | Define Initial Observation Types to be described | All WIGOS observational data types have been listed (the purpose of the list is to design a robust model for observation metadata, so although it may not be possible to include every observation type, those in the list should ensure that the range of requirements for metadata is covered), and each assigned to a relevant TC for specification of metadata requirements (TT-WMD) | May 2013 | Klausen | Task completed with sufficient coverage in the presentations for TT-WMD-1 15/3/2013 | Adequate information was provided through the presentations for the meeting. No direct further list required; review of metadata will identify further issues. |
| 2 | Define essential requirements of application areas beyond the Standard | TCs review the needs of application programmes against the specification of metadata, and propose additional elements that they consider essential for that application area. In doing this, TCs may recommend modifications to the metadata. | November 2013 | TT member for Commissions CAgM, EC-PORS contacts needed | Completed |  |
| 3 | Define essential metadata for observing systems beyond the Standard | TCs review the needs of observing programmes against the specification of Standard, and propose additional elements that they consider essential for that observing programme. In doing this, TCs may recommend modifications to the Standard. | November 2013 | TT member for Commissions CAgM, EC-PORS contacts needed | Completed |  |
| 4 | Confirm Metadata Elements | WIGOS Metadata reviewed following feedback from Commissions and first formal definition agreed. Mandatory, Conditional and Optional elements defined. | March 2014 (EC deadline for documents) | TT-WMD by correspondence | Completed | Completed with editorial changes needed |
| 5 | Formal definition of Metadata | Define, using a standard methodology, the detailed specification of WIGOS metadata, in a form that allows extension to other elements (eg using UML). Precursor to item 5 of WIP 8.1.1 (that may result in item 5 being redefined). | End of March 2016 (for submission to TCs) | Ad hoc group involvıng IPET-MDRD, TT-WMD and ET-CDMS | In progress | A joint Task team under IPET-MDRD, ıs making progress |
| 6 | Recommend to ICG-WIGOS on how they should go about deciding on approaches for gathering, storing and exchanging WIGOS metadata | Within the principle that all data must be provided along with the relevant metadata, identify how WIGOS metadata may be gathered, stored and exchanged. (Precursor for item 5 in the WIP 8.1.1 work plan that may define that item) | March 2014 (EC document deadline) | TT-WMD in consultation with IPET-WIFI/SG-OD |  | OSCAR is part of the solution for gathering, storing and exchanging MD. TT-WMD-4 has provided definitions and roles regarding MD management |
| 7 | Decide on subsets of summary metadata and how they will be presented as catalogues | Identify a subset of the metadata that has to be recorded in globally available catalogues to meet requirements for an overview of the observations available through WIGOS and for exchanging critical metadata that changes infrequently. (Precursor to item 5 in the WIP 8.1.1 work plan that may define that item 5). This may include a complete station list similar to Volume A. | November 2014 | Representative of each Commission In liaison with IPET-WIFI subgroup on WIGOS Information Resource | Completed | Completed after identification of the phases approach. |
| 8 | Monitor progress of plan | Quarterly teleconferencing meetings. | 1st Week March, May, September, December | Co-Chairs |  |  |
| 9 | Create contents of code tables | Defined contents of code tables, classifications that are needed to operate the standard | Dec 2015 | TT-WMD members to take responsibility for individual tables Co-Chairs to allocate responsibilities | 90% completed | (1-01 and 2-02 by all TC representatıves, 5-02 by Ercan Büyükbas). A governance process has been proposed |
| 10 | Development of guidance material, with examples, to assist Members with the practical implementation of the Standard | Document with proposed guidance material | June 2016 | TT-WMD | In progress | TT-WMD in alignment with OSCAR development |
| 11 | Define the requirements and configuration of metadata exchange | Document requirements for operational MD use cases of metadata exchange | September 2016 | TT-WMD and IPET-MDRD |  | Relates to task 5, 6 and 10 and partly started by the OSCAR project team |
| 12 | Develop competencies | Identify competencies required for those responsible for providing WIGOS metadata | May 2016 | TT-WMD |  | TT-WMD-4: To be completed via webex |
| 13 | Complete the final draft of the WMDS | Draft version 0.2 to be submitted to ICG-WIGOS-4 | January 2015 | TT-WMD and Secretariat | Completed |  |

* STATUS column entries will be one of the following descriptors, as determined by the Chair TT-WMD based on consultation with the responsible party (in each case, elaborative comments can be added after the standard descriptor or in the "Comment" column):

| On-Track | Under-Stress | Overdue |
| --- | --- | --- |