## Slide 1: Regional WIGOS Implementation Plan (R-WIP-I)
I.Zahumensky

## Slide 2: XVI-RA-I (3-9 February 2015)
Resolution 8 (RA I-16) – WMO Integrated Global Observing System Implementation Plan for Regional Association I (Africa);
R-WIP-I should be:
  supported by all the Members of the Region,
  guided, supervised, monitored and updated by the Management Group of RA I, with periodic reports from appropriate subsidiary bodies in charge of WIGOS

## Slide 3: XVI-RA-I (3-9 February 2015)
R-WIP-I should be further revised to accommodate new projects when submitted by Members,
President was authorized to approve any necessary revision of R-WIP-I during the intersessional period in consultation with the Management Group
RA-I/TT-WIGOS re-established.

## Slide 4: RA I WIGOS Governance and Working Structure

## Slide 5
To oversee, guide and coordinate WIGOS
To facilitate and support the operation of WIGOS
To plan, implement and evolve WIGOS component systems
To ensure supply of and access to WIGOS observations
Management of WIGOS Implementation / operation
Collaboration with co-sponsors and partners
Communications and outreach
Quality Management
Standardization, interoperability & compatibility
Operational Information Resource
Capacity Development
Design, planning and optimised evolution
Data discovery, delivery & archival
Observing system operation & maintenance
WIGOS Framework: Key activity areas
Notes: 5

## Slide 6: Plan for WIGOS Pre-operational Phase (PWPP)
Five priority areas:
  National WIGOS implementation
  WIGOS Regulatory and Guidance Material
  WIGOS Information Resource
  WIGOS Data Quality Monitoring System
  Regional WIGOS Centres

## Slide 7: Steps
Taking unto account:
  Decisions by Cg-17
  Progress achieved so far
  Better understanding of WIGOS, lessons learned, experiences
  Priorities for the RA I
  Resources available

## Slide 8: Table 2 WIGOS Implementation Activities
No. | Activity | Deliverables | Timeline | Responsibility | Estimated Costs (2012-2015) K CHF |  |  | Potential Risks
 |  |  |  |  | Total | ARB | Shortfall | 
1. Management of WIGOS Implementation in RA I |  |  |  |  |  | 
1.1 R SR N | Establish the Regional WIGOS Governance structure, including sub-regional responsible economic bodies (SADC, IGAD, ECOWAS, CEMAC/ECCAS, UMA etc.), and technical groups (ACMAD, ASECNA, ICPAC, AGRHYMET, etc.) for each subregion | RA I WIGOS Governance structure, incl. WGs established with TOR (see ANNEX 1, Figure 1) | 2012 | RA I MG, Sub-regional WIGOS Working Body; Governance |  | Low

## Slide 9: Steps
To check Table 2 line-by-line:
  Deliverable desirable to be achieved
  Activities needed to achieve it
  Realistic Deadline / Timeline
  Responsibility
  Realistic estimation of resources needed
  Potential risks to deal with

## Slide 10: Steps
To check Table 2 line-by-line:
  Deliverable desirable to be achieved
  Activities needed to achieve it
  Realistic Deadline / Timeline
  Responsibility
  Realistic estimation of resources needed
  Potential risks to deal with

## Slide 11: Steps
To consider potential Pilot Projects on:
OSCAR implementation
Data Quality Monitoring
Incident Management
Establishment of RWC
Helping the LDCs of RAI

## Slide 12: Thank you for your attention
www.wmo.int/wigos