| World Meteorological Organization |  | ICG-WIGOS/TT-WMD-2/Doc.2 |
| --- | --- | --- |
| INTER-COMMISSION COORDINATION GROUP ON WIGOS Task Team on WIGOS Meta Data (TT-WMD) |  | Submitted by: | Brian Howe |
|  |  | Date: | 07.V.2014 |
| SECOND SESSION GENEVA, SWITZERLAND 12 – 15 May 2014 |  | Original Language: | English |
|  |  | Agenda Item: | 2 |

CHAIR’S REPORT

(Submitted by B. Howe, Chair, TT-WMD)

Summary and purpose of document This document provides a brief report of the Chair, TT-WMD, on its activities since TT-WMD-1 (March 2013) and establishes objectives for TT-WMD-2.

ACTION PROPOSED The session is invited to take note of the Chair of the Task Team

____________

REPORT OF THE CHAIR, TT-WMD

Summary of activities of TT-WMD since TT-WMD-1 (March 2013)

- The TT-WMD has met through the use of monthly or bi-monthly WebEx meetings (fifteen meetings) to continue progress on development of the Core Metadata Standard. The ambition of TT-WMD in developing the standard has been to define the elements needed to make adequate use of observations with climatological applications in mind. Profiling of the standard (i.e., selection of elements needed for particular applications such as NWP, aeronautics, warnings) has not so far been the mandate of TT-WMD.

- The Core Metadata Standard has been circulated (limited) within various communities or Commissions with which members of the TT have relationships.  The feedback was considered and common themes emerging from the responses have led to the creation of enhanced details providing explanations of key points as well as the addition of specific examples.  Validation by these individuals is underway but much more feedback is expected, which will necessitate continued dedicated efforts by TT-WMD members, but also guidance by ICG-WIGOS on the direction of further work.

- TT-WMD has realized each TC’s language surrounding metadata can be divergent, which has created challenges to utilize language which will provide a common understanding, rather than lead to confusion.

- In terms of the proposed metadata elements, the Core Metadata Standard is nearly complete, but more work is needed in explaining the concepts. TT-WMD anticipates the final Draft to be ready for November 2014.

- Without engagement of all TC’s (EC_PORS, Satellite, CAgM) sufficiently broad support of the standard is difficult.

Objectives of TT-WMD-2

1. Update the existing workplan to reflect present status or pressures on deliverables (Appendix 1).

2. Address comments received:

a) Review input/comments received to date that have not yet been addressed and update the Standard accordingly.  These include CIMO (Forgan, Wier, Howe), Klausen (MeteoSwiss),  CHy (Uli Looser).

b) Consider information brought to TT-WMD’s attention by invited guests at TT-WMD-2.

c) Have comments been received from other Commissions?

3. Develop “Short” list of Mandatory elements for inclusion in the WIGOS Technical Manual (May 15th).

## Appendix 1

## TT-WMD Work Plan

TT-WMD ACTION PLAN FOR THE PERIOD XI.2012 TO VI.2015

| Version | Date | Comments |
| --- | --- | --- |
| 1 | 23/11/2012 | Action plan developed at TT-WMD-01 |
| 2 | 15/3/2013 | TT-WMD-01 |
| X | 31/01/2014 |  |

| No. | Task | Deliverable/Activity | Deadline (if not stated end of month) | Responsible | Status* | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Produce proposed definition of contents of WIGOS Core metadata | Initial version of WIGOS Core metadata | 15 March 2013 | Howe | Complete 15/3/2013 | TT-WMD-1 achieved this |
| 1 | Define Initial Observation Types to be described | All WIGOS observational data types have been listed (the purpose of the list is to design a robust model for observation metadata, so although it may not be possible to include every observation type, those in the list should ensure that the range of requirements for metadata is covered), and each assigned to a relevant TC for specification of metadata requirements (TT-WMD) | May 2013 | Klausen | Task completed with sufficient coverage in the presentations for TT-WMD-1 15/3/2013 | Adequate information was provided through the presentations for the meeting. No direct further list required; review of Core metadata will identify further issues. |
| 2 | Define essential requirements of application areas beyond the Core | TCs review the needs of application programmes against the specification of Core metadata, and propose additional elements that they consider essential for that application area. In doing this, TCs may recommend modifications to the Core metadata. | November 2013 | TT member for Commissions CAgM, EC-PORS contacts needed |  | Informal review by experts by various TC’s has been completed. |
| 3 | Define essential metadata for observing systems beyond the Core | TCs review the needs of observing programmes against the specification of Core, and propose additional elements that they consider essential for that observing programme. In doing this, TCs may recommend modifications to the Core. | November 2013 | TT member for Commissions CAgM, EC-PORS contacts needed |  | Informal review by experts by various TC’s has been completed. |
| 4 | Confirm Core Metadata Elements | Core WIGOS Metadata reviewed following feedback from Commissions and first formal definition agreed. Mandatory, Conditional and Optional elements defined. | March 2014 (EC deadline for documents) | TT-WMD by correspondence |  | Delayed to November 2014 |
| 5 | Formal definition of Core Metadata | Define, using a standard methodology, the detailed specification of WIGOS Core metadata, in a form that allows extension to other elements (eg using UML). Precursor to item 5 of WIP 8.1.1 (that may result in item 5 being redefined). | Sep 2014 (needs feedback from EC before completion) | Secretariat liaise with IPET-MDRD |  | Delayed to November 2014 |
| 6 | Recommend to ICG-WIGOS on how they should go about deciding on approaches for gathering, storing and exchanging WIGOS metadata | Within the principle that all data must be provided along with the relevant metadata, identify how WIGOS metadata may be gathered, stored and exchanged. (Precursor for item 5 in the WIP 8.1.1 work plan that may define that item)a catalogue to allow , in a form that allows extension to othe | March 2014 (EC document deadline) | ICG-WIGOS or TT-WMD? |  | This should be led by another group other than TT-WMD. |
| 7 | Decide on subsets of summary metadata and how they will be presented as catalogues | Identify a subset of the Core metadata that has to be recorded in globally available catalogues to meet requirements for an overview of the observations available through WIGOS and for exchanging critical metadata that changes infrequently. (Precursor to item 5 in the WIP 8.1.1 work plan that may define that item 5). This may include a complete station list similar to Volume A. | November 2014 | Representative of each Commission In liaison with IPET-WIFI subgroup on WIGOS Information Resource |  | This should be led by another group other than TT-WMD. |
| 8 | Monitor progress of plan | Quarterly teleconferencing meetings. | 1st Week May 2013 September, December, March | Chair |  | Now monthly or bi-monthly |
| 9 | Create contents of code tables etc | Defined contents of code tables, classifications etc that are needed to operate the Core standard | Dec 2014, but can begin during first half of 2013 | TT-WMD members to take responsibility for individual tables Chair to allocate responsibilities |  | Well underway, included within the Standard. |

* STATUS column entries will be one of the following descriptors, as determined by the Chair TT-WMD based on consultation with the responsible party (in each case, elaborative comments can be added after the standard descriptor or in the "Comment" column):

| On-Track | Under-Stress | Overdue |
| --- | --- | --- |

## ______