| World Meteorological Organization |  | EC-WG/WIGOS-WIS-3/Doc. 12 |  |
| --- | --- | --- | --- |
| EXECUTIVE COUNCIL WORKING GROUP ON THE WMO INTEGRATED GLOBAL OBSERVING SYSTEM (WIGOS) AND THE WMO INFORMATION SYSTEM (WIS) THIRD SESSION |  | Submitted by: | The WMO Secretariat |
|  |  | Date: | 16.III.2010 |
| Geneva, Switzerland, 24–26 March 2010 |  | Original Language: | English |
|  |  | Agenda Item: | 12 |

FUTURE WORK PROGRAMME AND ACTION PLAN OF EC-WG/WIGOS-WIS

## SUMMARY

## ADDITIONAL FINANCIAL IMPLICATION: None # ISSUES TO BE DISCUSSED: This document contains the draft Future Work Programme and Action Plan of EC-WG/WIGOS-WIS. DECISIONS/ACTIONS REQUIRED: The session is invited to review and approve the major tasks for steering and monitoring the WIGOS and WIS activities until its next session in 2011. REFERENCES: CONTENT OF DOCUMENT: Appendix for inclusion in the Final Report: Draft text for inclusion in the general summary of the report of the EC WG on WIGOS-WIS-3 Appendix for Information: –

DRAFT TEXT FOR INCLUSION IN THE

GENERAL SUMMARY OF THE EC-WG ON WIGOS-WIS-3

12.	FUTURE WORK PROGRAMME AND ACTION PLAN OF EC-WG/WIGOS-WIS

(Agenda item 12)

  - Based on the results of discussion, EC WG agreed on the major tasks for its Work programme and Action Plan for steering and monitoring the WIGOS and WIS activities until the next session in 2011 before Cg-XVI. Planned actions relate to the overall implementation of the WIGOS Development and Implementation Plan, Demonstration and Pilot Projects, Concept of Operations, and WIGOS Development and Implementation Strategy. The WIGOS Planning Office and WIS Project Office will regularly monitor the progress achieved and inform chairs of EC WG, SG-WIGOS and ICG-WIS respectively to take actions as appropriate. The approved WIGOS Implementation Activities are presented in the Table below.

Table:

Work Programme and Action Plan of EC WG; WIGOS and WIS Implementation Activities

(April 2010 – March 2011)

| No | TOR area/Activities | Responsibility | Target | Comments |
| --- | --- | --- | --- | --- |
| 1 | Guidance on the development and implementation of WIGOS | Chair, EC-WG |  |  |
| 1.1 | Complete CONOPS | Chair, SG-WIGOS | II. 2011 |  |
| 1.2 | Complete WDIS | Chair, EC-WG | II. 2011 |  |
| 1.3 | Develop the draft WIGOS Implementation Plan (WIP) | CBS President | II. 2011 |  |
| 2 | Coordination of WIGOS and WIS | CBS President |  |  |
| 2.1 | Linking of WIGOS and WIS requirements | Chair, EC-WG Chair, ICG-WIS | - | Coordinated through WIGOS PO and WIS PO |
| 2.2 | Coordinate involvement of RA /TC in WIGOS-WIS activities | WIGOS PO WIS PO | - |  |
| 2.2 | Organize a workshop on the use of DCPC | WIS PO |  | Depends on the WP development |
| 3 | Monitoring of development and implementation of WIGOS and implementation of WIS, incl. projects | Chair, EC-WG |  |  |
| 3.1 | Monitor WIGOS implementation | WIGOS PO | - |  |
| 3.2 | Monitor WIS implementation | WIS PO | - |  |
| 3.2 | Evaluate WPs | WIGOS PO | II. 2011 |  |
| 3.3 | Formulate recommendations based on lessons learned | EC-WG | II. 2011 |  |
| 4. | Report to Cg-XVI | Chair, EC-WG WIGOS PO |  |  |
| 4.1 | Prepare the report on Integration | WIGOS PO | II. 2011 |  |
| 4.2 | Prepare the WIGOS-related document for Cg-XVI | WIGOS PO | II. 2011 |  |
| 4.3 | Prepare the WIS-related document for Cg-XVI | WIS PO | II. 2011 |  |

Notes:

- EC-WG: EC WG on WIGOS and WIS

- ICG-WIS: Inter-Commission Coordination Group on WIS

- SG-WIGOS: Subgroup on WIGOS

- WIGOS PO: WIGOS Planning Office

- WIS PO: WIS Project Office

- WPs: WIGOS-WIS Projects

____________