WORLD METEOROLOGICAL ORGANIZATION

WMO INTEGRATED GLOBAL OBSERVING SYSTEM (WIGOS)

DEVELOPMENT AND IMPLEMENTATION STRATEGY

(WDIS)

Version 0.4

(CBS-CIMO/WIGOS-CM, 22-23 March 2010)

DOCUMENT VERSION CONTROL

| Version | Author(s) | Date | Description |
| --- | --- | --- | --- |
| 0.1 | WIGOS-PO | Feb 2010 | Reviewed by senior OBS staff |
| 0.2 | WIGOS-PO | Feb 2010 | Reviewed and approved by D/WIGOS (D/OBS) |
| 0.3 | WIGOS-PO | March 2010 | Feedback from CBS, GCOS, senior consultants |
| 0.4 | CBS/CIMO | March 2010 | Feedback from CBS-CIMO/WIGOS-CM |
| 0.5 | EC-WG/WIGOS-WIS | March 2010 | Feedback from EC-WG/WIGOS-WIS-3 |

CONTENTS

EXECUTIVE SUMMARY	4

1	INTRODUCTION	5

2	BACKGROUND	5

2.1	WMO Strategic Planning	5

2.2	WIGOS Initiative	6

2.3	Vision	6

2.4	Requirements and Objectives	7

2.5	Scope	7

2.6	Phases	7

3	WIGOS IMPLEMENTATION COMPONENTS	8

3.1	Integrated Governance and Data Policy	8

3.2	Data Delivery and Information Services through WIS	10

3.3	Quality Management and Standardization	10

3.4	Planning, Optimizing and Monitoring of Observing Systems	11

3.5	Capacity Building	11

3.6	Communications and Outreach	11

4 	WIGOS Implementation Management	12

4.1	Implementation Environment	12

4.2	Risk Assessment	12

4.3	Deliverables and Milestones	13

4.4	Project Monitoring and Review	13

4.5	Roles and Responsibilities	13

4.6	Resources	15

5	BENEFITS	15

Annex		17

List of Acronyms	19

# EXECUTIVE SUMMARY

The WMO Strategic Planning process, approved by the Fifteenth World Meteorological Congress (Geneva, May 2007) guides the Organization in delivering its contributions to desired societal outcomes.  The WMO Integrated Global Observing System (WIGOS) and the WMO Information System (WIS) are strategic initiatives of WMO, was and were included in a set of eight high-level Expected Results (ERs), in particular “Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable surface-based and space-based systems for weather, climate and hydrological observations, as well as related environmental observations, based on world standards set by WMO and partner organizations”. The success of WIGOS and WIS will have a major impact on all WMO Strategic Trusts.

Based on the WMO strategic planning principles, the WIGOS Development and Implementation Strategy (WDIS) was developed in accordance with a decision of the WMO Executive Council in 2009 (EC-LXI). This decision underscored the importance of WIGOS to WMO Members as a framework for integrating WMO observing systems and for strengthening linkages with co-sponsored observing systems.

The objective of this strategy is to describe the steps that WMO, in collaboration with partner organizations, would follow to improve governance, management, and integration of WMO observing systems, and as appropriate co-sponsored systems, so as to ensure a coordinated, comprehensive, and sustainable system that meets the requirements of WMO Members and partner organizations.  The Implementation Phase (2012-2015), described in this report, builds on lessons learned from the Test of Concept Phase (2007-2011) and lays the groundwork for the Operational Phase (from 2016 onward). As with WIS, the establishment of a WIGOS project office is essential to support the implementation phase.

In implementing WIGOS, it is imperative that the current management, governance and support activities be reviewed and aligned with WMO strategic planning and results-based management. This alignment should enable collaboration and promote cooperation and coordination at the technical, operational and administrative levels.

Achieving the benefits of WIGOS will require commitment from WMO Members, constituent bodies and from partner organizations who have agreed to participate in WIGOS. Progress in WIGOS implementation will be directly related to the level of available resources. To move forward, essential support to the Secretariat during the next financial period is required for the implementation phase. If the requested resources are not made available WIGOS implementation will be put at substantial risk.

Given the significance of active cooperation and enhanced coordination among the technical commissions, regional associations and WMO partners, appropriate steps will need to be taken to ensure that the integration process is incorporated in the work programmes and implementation plans of these entities. Both, regional associations and technical commissions will play a fundamental role in this process.

An integrated global observing system, supported by an integrated information system is essential to realizing the socio-economic benefits to be derived from a wide range of products and services concerning weather, climate, water and related disasters. WIGOS  will be is an essential component of WMO’s results-based management and will be key to the development and implementation of the Global Framework for Climate Services (GFCS). Through WIGOS and WIS, WMO will make a fundamental contribution to the success of the Global Earth Observation System of Systems (GEOSS).

- INTRODUCTION

The success of the past

For over 60 years WMO, through its Members, have advanced the observing and monitoring of weather, climate, water and the environment. This has led to a better understanding of the Earth’s environmental system, and resulted in the delivery of improved and expanded services such as weather, hydrological and air-quality forecasts, climate outlooks and predictions which have resulted in improved decision making. These services now expand across timescales from severe weather warnings via weekly forecasts to seasonal and decadal climate prediction with broad applications across social and economic sectors worldwide.

WMO has built alliances with partners that address the observational and monitoring needs associated with intersecting domains, particularly in respect of the climate system.

The challenge for the future

WMO Members need more extensive and advanced observations and information to improve both service quality and service delivery. An increasingly sophisticated user community is demanding that information reflects not only the complexity of the Earth’s environment, but it be delivered in such a way that can influence decision making at multiple scales.

The challenge today is to achieve such ambitious results in a cost-effective manner. WIGOS is a key strategy to optimize the efficiency and effectiveness of WMO services, leveraging the long-standing collaborative culture of WMO as well as new technologies and building on the investment by WMO and partner organisations in co-sponsored observing systems.

To meet this challenge, WMO Members must continue their legacy of integrated global weather observations and information and extend this legacy to climate observations and information. In doing so, observations and information from other domains, other observing systems, and other partners will be essential. Partnership agreements, governance structures, and interoperability arrangements among all of the above will present their own challenges.  WIGOS and WIS must take full advantage of advances in observation and telecommunication technologies and in existing governance structures in order to increase science-based understanding of the Earth and its environment.  The end result will be better prediction and services that provide the required information for the public and for policy and decision makers to ensure that national and international investments are being leveraged to the greatest extent possible.

- BACKGROUND

## 2.1	WMO Strategic Planning

The WMO Strategic Plan recognizes that understanding the state of the environment is essential, and it depends upon the collection and open sharing of information, often using rapid and highly reliable methods.

The implementation of WIGOS will be an essential component of WMO’s results-based management to address identified global societal needs. These needs consist of: (1) Improved protection of life and property, (2) Poverty alleviation, sustained livelihoods and economic growth and (3) Sustainable use of natural resources and improved environmental quality. WIGOS will contribute to all WMO Expected Results of the 2012-2015 Strategic Plan and is fundamental to the Strategic Thrust I "Improving Service Quality and Service Delivery".

In particular, WIGOS will deliver Expected Result 4, “Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable surface-based and space-based systems for weather, climate and hydrological observations, as well as related environmental observations, based on world standards set by WMO and partner organizations”. The success of WIGOS will have a major impact on all WMO Strategic Thrusts areas.

## 2.2	WIGOS Initiative

The concept of WIGOS, as adopted by the Fifteenth World Meteorological Congress (Resolution 30, Cg-XV, 2007), originated from the widespread recognition that establishment of a coordinated approach to the management of diverse WMO observing systems would result in substantial benefits and efficiencies for Members and stakeholders.

Cg-XV requested that the development of WIGOS proceed concurrently with the planning and implementation of the WMO Information System (WIS). The combination of both efforts would allow for an integrated WMO end-to-end system designed to improve Members’ capability to effectively provide a wide range of high quality services and to better respond to all WMO Programmes requirements.

As noted by Cg-XV, WIGOS, as it evolves, will impact the structure and function of WMO, including the WMO Programme structure, roles and responsibilities, terms of reference and working arrangements of technical commissions, the WMO Technical Regulations, and the WMO Secretariat.

In 2009, the Executive Council (EC-LXI) noted the value of including all observing systems important to the National Meteorological and Hydrological Services (NMHSs) in a single organizational framework. It underscored the need for a comprehensive, costed development and implementation strategy to address the technical and coordination challenges. This Strategy would include the designation of roles and responsibilities of WMO entities and partner organizations and the requirements for capacity building so that all WMO Members and partner organizations can benefit from WIGOS. The Strategy would also provide guidance to ensure enhanced coordination in four key areas: within WMO, with partners, with users and with the science and technology communities.

In response to Congress and the Executive Council, the WMO Technical Commissions, Regional Associations and Secretariat during the period 2007-2011 explored the concept of WIGOS through a series of Pilot Projects (by the technical commissions and, in some cases, in collaboration with partner organizations) and Demonstration Projects (by Members and the regional associations). This document builds on the lessons learned in the Test of Concept phase.

Based on the Test of Concept phase of WIGOS, the basic characteristics of WIGOS are specified in the WIGOS Concept of Operations (CONOPS) document, which describes user needs for, and expectations from, the proposed system and how the system should operate to fulfil those needs. This document provides a logical transition of WIGOS from initial to full operational capabilities, recognizing that CONOPS will continue to be refined and will remain a basic reference document to this Strategy.

## 2.3	Vision

The WIGOS Vision calls for an integrated, coordinated and comprehensive observing system to satisfy, in a cost-effective and sustained manner, the evolving observing requirements of WMO Members in delivering their weather, climate, water and related environmental services. WIGOS will enhance the coordination of the WMO observing systems with those of partner organizations for the benefit of society.

WIGOS will be a  framework enabling the integration and optimized evolution of WMO observing systems, and WMO’s contribution to co-sponsored systems. Together WIGOS and WIS, this will allow continuous and reliable access to an expanded set of environmental data and products associated metadata, resulting in increased knowledge and enhanced services across all WMO activities.

## 2.4	Requirements and Objectives

To enable improved service delivery, there is a need to improve the existing observing capability, make it more cost-effective and sustain its operation. To ensure a coordinated, comprehensive, and sustainable system that meets the requirements of WMO and partners, improved governance, management, and integration of observing systems is needed.

Integration must be pursued to ensure interoperability and facilitate optimization across constituent systems. WIGOS will also enable resources to be used more effectively to overcome existing deficiencies and gaps in the constituent observing systems.

WIGOS is expected to provide timely, quality assured, controlled and documented long-term observations. Implementing Quality Management procedures is required to enable better utilization of existing and emerging observational capabilities.

In meeting the evolving user requirements, WIGOS:

- Will better enable NMHSs to meet expanding national mandates of achieving higher national visibility with other environment related agencies.  In doing so, WMO Members will be able to better respond to natural hazards, improve weather, water, climate and related environmental monitoring, and adapt to climate change and human-induced environmental impacts;

- Through WIGOS and WIS, WMO will make a fundamental contribution to the future GFCS;

- Will provide a basis for sound decision making and enhance delivery of benefits to society.

An integrated global observing system, supported by an interoperable information system, will be a key contribution in realizing the socio-economic benefits to be derived from a wide range of products and services concerning weather, climate, water and related environment.

## 2.5	Scope

In meeting its objectives, WIGOS will not only serve WMO Members and partners but will also make a major and unique contribution to United Nations agencies that are focused on environmental stewardship, and along with WIS, will be a core contribution of WMO to GEOSS.

To achieve the objectives, which were demonstrated in the Test of Concept phase, the scope of WIGOS will encompass the following:

- Requirements: Provide a mechanism to meet new observational requirements of WMO Members and WMO partner organizations building on the existing Rolling Review of Requirements (RRR) process;

- Integration: Build upon and add value to the existing WMO observing components of GOS, GAW, and WHYCOS with emphasis on integration of surface- and space-based observations;

- Standardization: Enhance observational data quality and homogeneity by introducing improved data quality and data management standards to better satisfy user requirements;

- Access:  Improve access to, and utilization of, observations and products from WMO observing systems as well as those of co-sponsored systems.

- Coordination: Foster research and development activities and coherent planning for future observing systems and network optimization by working with all WMO Programmes and partner organizations.

## 2.6	Phases

The Test of Concept phase (2007 - 2011)

The development of WIGOS and its coordination with the development and implementation of WIS has been overseen by the Executive Council Working Group on WIGOS and WIS (EC-WG/WIGOS-WIS) established by EC (Resolution 3, EC-LIX, 2007). The EC-WG/WIGOS-WIS established a Sub-group on WIGOS (SG-WIGOS) to manage technical integration activities, the development and implementation of the WIGOS concept, and to provide recommendations to EC-WG/WIGOS-WIS. The Secretariat has provided support to EC-WG/WIGOS-WIS and SG-WIGOS.

In accordance with the recommendation of Cg-XV, development and implementation of the WIGOS concept proceeded in the phases defined by the annual sessions of the Executive Council. The WIGOS Test of Concept Development and Implementation Plan (WDIP) with the Strategic Roadmap was developed by EC-WG/WIGOS-WIS, taking into account the WIS Project and Implementation Plan, and updated annually.

The seven Pilot Projects, initiated by the technical commissions, addressed major issues of the integration process, including testing the WIGOS concept and identifying problem areas. Lessons learned emphasized the role and contributions to be made by the technical commissions and relevant partners in the integration process.

In accordance with recommendations by EC-LX, several Demonstration Projects were initiated by WMO Members. At least one ‘test-bed’ Demonstration Project was carried out within each regional association. Feedback and lessons learned from Demonstration Projects facilitated the understanding of expectations on WIGOS at national and regional levels, including importance of capacity-building activities.

The status of implementation of WIGOS Pilot and Demonstration Projects is posted on the WIGOS Web page at http://www.wmo.int/pages/prog/www/wigos/index_en.html as a communications and outreach activity.

WIGOS Implementation phase (2012 - 2015)

The Implementation phase, to be undertaken between 2012 and 2015, will focus on developing and implementing a framework for improved governance, management, integration and optimization of the multiple observing systems coordinated by WMO and its partner organizations.

WIGOS Operational phase (2016 onward)

Once this framework is established, WIGOS will enter its Operational phase. During this phase, WIGOS constituent observing systems and networks will continue to evolve to improve service delivery and support decision making in response to the evolving needs of users and technological opportunities. Although this phase is not limited in time, it is anticipated to include an initial period of rapid enhancement of observing capabilities between 2016 and 2019 in order to meet the highest priority needs.

- WIGOS IMPLEMENTATION COMPONENTS

In light of the cross cutting nature of WIGOS and its impact on organisational process and structure identified by Cg-XV, the success of WIGOS must not be detrimental to the ongoing maintenance and operational effectiveness of existing observing systems and governance. In order to manage these risks (See section 4.2), the key implementation components for this Strategy must include:

- Integrated Governance and Data Policy;

- Data delivery and information services through WIS;

- Quality Management and Standardization;

- Planning, optimization and monitoring of observing systems;

- Capacity Building;

- Communications and Outreach.

A brief description of the major implementation aspects is given in the following paragraphs.

## 3.1	Integrated Governance and Data Policy

WIGOS will address high-level observing requirements by establishing an effective and sustained organizational, programmatic, governance and procedural structure. This structure will enable a common standardization approach, uniform implementation of WMO regulations, and data integration and interoperability across all WMO observing systems. It will also provide a single focus for integrated and coordinated operational management of all WMO observing systems and a mechanism for coordination with WMO co-sponsored and contributing observing systems.

Therefore, in implementing WIGOS it is imperative that the current management, governance and support activities be reviewed and aligned with WMO strategic planning and results-based management. This alignment should enable collaboration and promote cooperation and coordination at the technical, operational and administrative levels.

Central coordination through the WMO Secretariat is essential for successful WIGOS implementation. In addition, the long-term commitment and effort of WMO Members; greater international cooperation; and sustained technological, capacity building, and financial support for developing and least developed countries is important.

The development of an effective and efficient system of governance will require adequate scientific and technical advisory mechanisms to develop, monitor, and evaluate the WIGOS implementation process.  The WMO Executive Council, through its EC-WG/WIGOS-WIS, will continue to steer and monitor WIGOS activities to ensure the broadest possible collaboration and cooperation.

Given the significance of active cooperation and enhanced coordination among the technical commissions, regional associations, and WMO partners, appropriate steps will need to be taken to ensure that the integration process is incorporated in the work programmes and implementation plans of these entities. For this purpose, it is highly desirable that an Inter-Commission Coordination Group on WIGOS (ICG-WIGOS) be established. This group would replace the Subgroup on WIGOS and would be expected to:

- Coordinate, review, refine, and assess the development and implementation of WIGOS;

- Provide technical guidance and assistance for the WIGOS development, planning, and implementation activities, such as standardization and development of WIGOS databases;

- Advise regional associations on WIGOS implementation activities;

- Advise technical commissions on the standardization process and related activities;

- Coordinate cooperation at a technical level with WMO partner organizations, including UNESCO and its IOC, UNEP, FAO, and ICSU;

- Address major issues identified by EC-WG/WIGOS-WIS;

- Advise EC-WG/WIGOS-WIS on further development and implementation of WIGOS; and

- Report to EC-WG/WIGOS-WIS.

Furthermore, for WIGOS to be successful, it will be necessary to identify terms of reference for task teams at the regional and commission levels and, when appropriate, with representatives of partner organizations.  Major tasks should be assigned as follows:

- Regional task teams will need to coordinate planning and implementation of WIGOS on the regional level with WIS implementation and, eventually, with the implementation of GFCS in order to optimize regional and national observing systems;

- Inter-Commission Task Teams, which should include representatives of partner organizations, will need to address standardization, observing system interoperability, data compatibility, data management, Quality Management System (QMS) procedures, performance monitoring, WMO regulatory material issues, and proposed improvements in observing networks/systems.

Improving coordination will be an ongoing activity at policy, technical, and Secretariat levels.  This will need to be supported by a high-level reconciliation mechanism defined in the WMO-UNESCO-IOC-UNEP-FAO-ICSU Memoranda of Understanding (MOU) in order to resolve possible problems in data policy, product delivery, and other governance issues. The existing Interagency Coordination and Planning Committee for Earth Observations (ICPC) may be an appropriate model for such high-level coordination.

These interagency and inter-observing system coordination mechanisms will need to be complemented and supported through national coordination arrangements among NMHSs and their partner organisations and coordinated with similar national implementation mechanisms for GCOS, GOOS, GTOS, and GEOSS.

Data Policy

A key part of integrated governance will be to achieve consistent data policies. WIGOS will respect the data policies of partner organizations and will adhere to Resolution 40 (Cg-XII) and Resolution 25 (Cg-XIII).  It will strive to ensure that the conditions placed by the originator on the additional data and products are respected and made known to initial and subsequent recipients for the exchange of weather, climate, and water related data and products, including guidelines on relationships in commercial meteorological and hydrological activities.

Although data policies are similar across WIGOS contributing organizations, there are some differences.  Therefore it may be necessary to follow a two-fold approach, consisting of a common set of data sharing principles supplemented by specific practices for individual WIGOS partners.

## 3.2	Data Delivery and Information Services through WIS

The WIGOS pilot projects, such as the JCOMM/IODE Ocean Data Portal, have supported the effectiveness of WIS as the core interoperability layer of WIGOS. WIS allows otherwise independent observing systems to move data between them, as well as providing the standards for more effective data management. WIS also supports the collection and sharing of observations and products within WIGOS and allows new initiatives such as the enhanced climate services being developed under the framework of GFCS to benefit easily from WIGOS data and products. A detailed description of WIS is presented in the WIS Project and Implementation Plan.

As noted by EC-LXI (2009), WIGOS is crucially dependant upon effective WIS support and services and should proceed in close coordination with WIS implementation. This includes the specialized data collection means as well as the generation, collection, management and handling of related metadata that is essential to ensuring data within WIGOS meet the stringent traceability requirements of special users such as climate scientists. The metadata also play an important role in the discovery and access to observations and products. The needed metadata therefore includes both that which pertain to the observational information as well as that which describes the observational products and which is necessary to share the information.

## 3.3	Quality Management and Standardization

Quality Management

Meeting the quality requirements and expectations of users is critical to the success of WIGOS.  This will require an in-depth examination of current practices used by WMO observing programmes, specific mission-related requirements that are already in place, and available technological opportunities. It will also be important to review the quality not only of the deliverables produced by WIGOS but also of the management processes involved.

WIGOS should embrace QMF procedures to ensure that observations, records and reports on weather, water, climate and other environmental resources, operational forecasts, warnings, related information and services are of identified quality, and in compliance with relevant joint standards agreed upon with other international organizations.

This should be based on agreed-upon quality assurance and quality control standards, with the goals of developing and implementing an integrated QMS; in doing this, it will deliver reliable and timely data streams with adequate quality control and relevant metadata.

WIGOS QMF implementation strategy will specify all processes of QMS for observational networks. Attention will also be paid to the guidance on how to manage observational networks and observing subsystems to more fully meet QMF requirements.

Standardization

As specified in CONOPS, a principal requirement for integration is the standardization in three key areas: Instruments and Methods of Observation; WIS information infrastructure; Quality Management Framework.

As part of the implementation strategy, a successful WIGOS standardization process will have to adequately address the differences and inconsistencies in current technical specifications, data acquisition and management systems used by individual NMHSs and partner organizations before national and international observing systems can be regarded as truly integrated.

## 3.4	Planning, Optimizing and Monitoring of Observing Systems

Coordinated planning based on RRR process has a great potential to enhance observing system capabilities and to increase cost-effectiveness of observing efforts and investments.

This activity will be performed through the following:

- A systematic rolling review of observing requirements from each of the user communities it intends to serve, and maintain a consolidated and evolving set of requirements;

- A regular review of the observing capabilities that are actually implemented, and a continuous monitoring of their performances;

- A review of emerging capabilities and the potential of new technology to replace or complement current observing capabilities.

This process, conducted with close involvement of both the operational and research communities, should result in Statements of Guidance that can be either specific to each constituent system or commonly applicable to all.

The coordinated planning of the evolution and enhancement of observing systems in response to these Statements of Guidance must be conducted in a coordinated way across observing systems, as far as practical, through systematic exchange of information, consultation, with the aim to develop synergy. This shall be pursued when defining sensor specifications, locations and operating mode, when sharing observation infrastructure and organizing data management and distribution. The role of regional associations (RAs) and technical commissions (TCs) will be indispensable in the overall process.

## 3.5	Capacity Building

An effective capacity-building and training strategy is an essential component of the WIGOS framework.  A coordinated capacity-building effort should assist developing and least developed countries to improve and sustain their contributions to WIGOS observing systems, including access to and effective utilization of observations, data and products, and related technologies.   As a key factor in successful WIGOS implementation, capacity building activities at national and regional levels will be focused on:

- Institutional mandates and policies;

- Infrastructure establishment and/or strengthening;

- Human skills development and training;

- Technical assistance; and

- Technology transfer.

To take advantage of WIGOS benefits and to ensure that information and services are used to the maximum extent possible, transfer of technological innovations and development of decision support tools will be essential. For this purpose, specialized education and training activities should be reflected in the Regional WIGOS Implementation Plans, especially for NMHSs of Least Developed Countries (LDCs) and Small Island Developing States (SIDS).

## 3.6	Communications and Outreach

Given numerous and geographically diverse stakeholders, development and implementation of a WIGOS communications and outreach strategy will be one of the key prerequisites to the success of WIGOS.  This strategy should comprise the following core areas:

- Interaction of the WIGOS Project Office with the secretariats of the various WMO and WMO-co-sponsored observing systems and user programmes. The Office should also coordinate with related activities such as the Global Cryosphere Watch, GCOS and GEOSS including the coordinated WMO contribution to the future GFCS;

- Active involvement of regional associations and technical commissions. The WIGOS implementation strategy includes establishment of regional/inter-commission expert teams.  These teams will participate in the development and implementation of WIGOS at the regional/ technical commission levels;

- Establishment and management of a WIGOS portal. This portal will provide relevant information to stakeholders on WIGOS development, implementation, and standardization processes and on the communications and outreach strategy;

- Proactive identification of new users as WIGOS evolves.

# 4 	WIGOS Implementation Management

## 4.1	Implementation Environment

The development and testing of the WIGOS concept after Cg-XV occurred during a long and very challenging global economic recession. This situation affected many NMHSs that had already been facing reduced budgets and therefore greater pressure to reduce operational and maintenance costs. The Test of Concept phase of WIGOS has also occurred alongside a rapidly increasing interest in climate change. Moreover, climate assessments require far more vigilance in addressing the sustainability and long-term homogeneity of data being used to assess climate variability and change.

The financial crisis and competing priorities have the potential to divert funds from core observing systems at a time when they are most needed to meet society’s needs. There is also considerable competition for funds between traditional in situ and space-based observations. While advances in numerical modelling and assimilation processes clearly show the benefits of remote sensing to weather and climate models, they also highlight the important complementarity provided by in situ observations. Therefore WIGOS will have to be supported by appropriate awareness raising and outreach activities that reinforce the importance of both in situ and space-based observations and their integration. For WIGOS to succeed, the external environment as well as the risks associated with the integration of previously independent systems must be managed. In particular, there is a need for a WIGOS Project Office with sufficient staffing and funding to carry out the necessary tasks detailed in Section 3 and reflected in the deliverables in Section 4 (see Figure 1). Noting that there is already one person in the WIGOS Planning Office, it is recommended that at least two additional staff be provided.

## 4.2	Risk Assessment

An initial risk assessment identifies the implementation of WIGOS as a high risk project for the following reasons:

- Complexity of the project.  The project involves diverse stakeholders and needs a high level of cooperation among them. Implementation activities must be integrated into the strategic planning of regional associations as well as that of individual Members to ensure connectivity  and to encourage synergies between national, regional and global activities;

- Basic infrastructure.  This must be in place to allow improved data acquisition systems, data management systems, and QMS to function effectively;

- Resources.  Substantial investment of resources and expertise are needed to support WIGOS development and implementation.

Following by EC-LXII, a skeletal WIGOS Implementation Plan will be formulated utilizing the CONOPS, WDIP and WDIS. This will be submitted to Cg-XVI.   Between Cg-XVI and Cg-XVII, a complete WIGOS Implementation Plan (WIP) will be developed including a detailed risk assessment and management plan.  Risks will need to be clearly identified and managed at various points throughout the project, including the development of associated mitigation and contingency plans. The Secretariat will take a leading role in overall risk management by providing a focal point for these activities.

## 4.3	Deliverables and Milestones

Upon the approval by Congress, WIP will  address a list of tasks associated with the key deliverables and milestones. The task list should include risk management plans and time lines for each task, along with details of task leaders. Figure 1 shows the key milestones, including routine WIGOS related reports to EC and Congress, and timelines. Some tasks such as coordination with WIGOS component systems will be essential activities throughout and beyond the Implementation phase. The WIGOS project documentation will be a key deliverable early in the period, while Regulatory Documentation will be the focus in later phases. Capacity building will focus on communications and outreach at first and then move to the development of guidelines and training material later in the project. Pilot and demonstration projects will continue to be an important activity in the later implementation stages, especially to assist developing countries including LDCs and SIDS to more fully benefit from WIGOS.

Figure 1: Key Tasks, Activities and Milestones

## 4.4	Project Monitoring and Review

The EC-WG/WIGOS-WIS will remain the prime coordinating body for WIGOS. As noted in paragraph 5.1, ICG-WIGOS would ensure coordination across all technical levels.

Depending on the availability of resources, the WIGOS Project Office will provide the operational support to overall WIGOS activities. In addition to supporting the EC-WG/WIGOS-WIS and ICG-WIGOS, it will support the WIGOS coordination functions of the working bodies of RAs and TCs and other contributing programs and mechanisms. It will continuously monitor WIGOS implementation activities, coordinate follow-up actions and regularly report to all concerned.

All information related to the implementation of WIGOS will be available on the Secretariat WIGOS web page as a component of the WIGOS communications and outreach strategy.

## 4.5	Roles and Responsibilities

As requested by Cg-XV, Members, international partner organizations and related programmes have begun to collaborate actively in the development and implementation of the WIGOS initiative.  It is recognized that full implementation of WIGOS requires long-term commitments from all participants and mutual understanding by all partners to accomplish their current and planned observational activities in a coordinated manner. WIGOS implementation will require significant effort and time.

In order to move towards full WIGOS operations, the entities listed below are considered to have essential roles and should assume, along with their general terms of reference and their commitment to the implementation of WIS, the following responsibilities:

WMO Members:

- Design, develop and implement national observing systems according to the Vision for global observing systems in 2025; GAW development Strategic Plan (2008-2015); WHYCOS guidelines; GCOS, GOOS and GTOS Implementation Plans;

- Implement standards in accordance with WIGOS regulatory material;

- Participate in national, regional and international cooperation mechanisms;

- Provide adequate resources for WMO Secretariat support for WIGOS implementation, either through regular WMO budgetary process, or in kind, via secondments and/or through contributions to the Trust Fund.

Executive Council:

- Steer and monitor WIGOS development and implementation activities, and achieve the broadest possible collaboration, cooperation and coordination all of stakeholders;

- Coordinate WIGOS and WIS plans and activities;

- Provide advice, guidance and support for the implementation of WIGOS.

Regional Associations:

- Develop and coordinate Regional WIGOS Implementation Plans,

- Incorporate WIGOS in their strategic plans and work programmes;

- Identify priority areas where observational requirements can be met more effectively through integration of surface-based and space-based subsystems;

- Determine regional priorities for observing system development and provide input for regional observing system needs into the RRR Process;

- Provide advice and feedback to Members on WIGOS related activities;

- Encourage proactive involvement of Members in regional WIGOS implementation activities.

Technical Commissions:

- Develop guidance for the design and evolution of observing systems utilizing the RRR Process;

- Integrate WIGOS activities within work programme of relevant OPAGs and/or Expert Teams;

- Develop WIGOS standards in collaboration with partners including metadata standards;

- Provide technical guidance and advice to Members and Regional Associations on WIGOS;

- Review, update and harmonize WMO Regulatory Material;

- The Commission for Basic Systems (CBS) and Commission for Instruments and Methods of Observation (CIMO) to provide the technical lead for WIGOS.

WMO Secretariat:

- Ensure management of, and support to, the WIGOS implementation process;

- Establish a WIGOS Project Office;

- Integrate WIGOS activities within work programmes of relevant OPAGs and/or Expert Teams;

- Develop proposals for programmatic and governance structures in support of WIGOS taking into account WMO’s strategic directions;

- Coordinate WIGOS and WIS implementation;

- Ensure proper linkages with GFCS as it develops;

- Coordinate and collaborate with partner organizations and programmes in WIGOS activities;

- Support regional associations in developing their WIGOS implementation strategies and projects, including outreach and capacity-building activities;

- Work with Members and donors to provide adequate resources for WIGOS implementation;

Partner Organizations:

- Collaborate with WMO in establishing appropriate coordination mechanisms;

- Coordinate with WMO to create and maintain interoperability among observing systems;

- Coordinate with WMO on data policy.

## 4.6	Resources

It should be underlined that the timely completion of the WIGOS Implementation phase in the sixteenth financial period 2012-2015 critically depends on adequate resources.

The investment for fully implementing WIGOS should be a significant focus of NMHSs’ National development and implementation plans. In addition, extra resources will need to be provided through WMO Secretariat for both staff and non-staff costs for the implementation and coordination. As a result, additional budgetary resources need to be allocated to the WIGOS implementation phase.

To ensure the funding needed for WIGOS implementation, the following resources should be considered:

- Funds for national observing systems;

- WMO Regular Budget for WIGOS implementation activities;

- WIGOS Trust Funds to supplement WMO Regular Budget;

- In kind contributions;

- Staff secondments;

- Voluntary Co-operation Programme funds for WIGOS related technical cooperation and capacity-building activities.

- Regional fundraising activities to support WIGOS.

Taking into account the role, responsibilities and scope of the work required, an adequately staffed and resourced WIGOS Project Office needs to be established within the Secretariat. This will ensure a suitable project management function, improved coordination and cooperation with technical commissions, regional associations and partner organizations essential for WIGOS implementation.

In response to the request for a WIGOS comprehensive costed development and implementation strategy, the Secretariat has provided the detailed cost statement of the resources needed (see Annex, Tables 1 and 2).

- 5	BENEFITS

In order to meet the evolving needs of WMO Members, there is a well-recognized need to improve existing observing capability, make it more cost-effective, sustain its operation and enhance service delivery. Integration of respective components and systems must be pursued to ensure interoperability, and optimize constituent observing systems within a WIGOS framework. WIGOS will also enable resources to be used more efficiently and effectively to overcome existing deficiencies and gaps.

WIGOS is expected to provide timely, quality-assured, quality-controlled and well-documented long-term observations. Implementation of Quality Management procedures will be required to enable enhanced utilization of both existing and emerging observational capabilities. In meeting the evolving user requirements, WIGOS will:

- Enable the evolution and integration of WMO observing systems and enhance collaboration with its partner organizations: this will allow access to an expanded set of environmental data and products resulting in increased knowledge and enhanced services (across weather, water and climate domains) in a cost-effective manner;

- Result in enhanced observing capabilities by improving between its surface- and space-based components;

- Enable WMO Members to meet expanding national mandates which are calling for increasing coordination and integration to help them better respond to natural hazards, improve weather, water, climate and related environmental monitoring, and adapt to climate change and other human-induced environmental impacts;

- Together with WIS, enhance operational components of WMO Programmes, especially in Developing and Least Developed Countries and provide essential contributions to the observational and information elements of the future GFCS;

- Together with WIS contribute strongly to GEOSS; and lastly,

- Provide a basis for sound decision making and enhance delivery of services to society.

An integrated global observing system supported by an interoperable information system will be essential for realizing the socio-economic benefits derived from a wide range of products and services related to WMO’s core competencies of weather, water, climate and related disasters.

________________

- Annex

Table 1: WIGOS activities and funds needed for 2012-2015 (CHF)

| No | Activities 1) | Required funds |
| --- | --- | --- |
| 1 | Governance, management, programmatic activities | 500,000 |
| 2 | Coordination with WIGOS Component Systems | 100,000 |
| 3 | Development of the WIGOS Implementation Plan | 10,000 |
| 4 | Standardization process | 100,000 |
| 5 | Revision and update of WMO Regulatory Material (Manuals, Guides) | 100,000 |
| 6 | Development of WIGOS Databases |  |
|  | Operational DB | 200,000 |
|  | Standardization DB | 200,000 |
|  | User requirements and Operational Capabilities DB | 200,000 |
| 7 | Capacity Building | 200,000 |
| 8 | Communications and Outreach | 50,000 |
|  | TOTAL: | 1,660,000 |

1) Breakdown for each activity is given below:

- Resources amounting to CHF 500K  cover:  four  meetings of  the EC WG WIGOS-WIS (4x40K=160K); four meetings of the ICG-WIGOS (4x25K=100K); six regional  WIGOS implementation-coordination meetings (6x40K=240K);

- CHF 100K is allocated to convene two WIGOS coordination meetings of experts representing GOS, GAW, WHYCOS, GCOS, GOOS, GTOS (2x50K=100K);

- CHF 10K is allocated  for consultant services to assist the Secretariat in the preparation of the WIP;

- CHF 100K covers expert services to assist countries to carry out Site classification (50K) and Maintenance  classification (50K) for each WMO region;

- CHF 100K covers consultant services to develop WIGOS-related amendments to the Manual on the GOS (10K), Guide on the GOS (10K), CIMO Guide (20K), WHYCOS Guidelines (10K), Guide to Marine Meteorological services (10K), GAW Guide (10K)  and to develop WIGOS Manual (30K);

- Resources of CHF 200K for each of three WIGOS DBs cover: two expert meetings (2x25K=50K); development of the DB’ technical specifications (40K); development of software (50K); development of the Operations Manual (10K); implementation of DBs, including data transfer and input (50K);

- CHF 200K is allocated to convene one WIGOS training workshop in each WMO Region (6x30K=180K) and accomplish four expert fact-finding missions (4x5K=20K);

- CHF 50K covers the development of the WIGOS Portal (10K); representation of WIGOS PO at the regional/inter-commission expert team meetings (20K) and at the relevant coordination meetings of partner’ organizations (20K).

Table 2: WIGOS Project Office staff resources needed for a period 2012-2015

| No | Position | Activities 2)/Duties | Staff cost for 2012-2015 (CHF) |
| --- | --- | --- | --- |
| 1 | WIGOS Project Manager 3) | 1-8: To lead the WIGOS Project Office taking into consideration lessons learned from existing and future WIGOS projects. This person would also manage and review the implementation of WIGOS, undertake the necessary liaison within the Secretariat and stakeholders and to oversee all the projects within WIGOS. | 900,000 |
| 2 | WIGOS Support and Capacity building Manager | 8: To accomplish general duties, such as outreach activities and capacity building. In particular, to assist with capacity building in Member countries and to work with Education and Training (ETR) and Development Cooperation and Regional Activities (DCR) to ensure Members, especially in least developed countries, reap the full benefits of WIGOS. An important role of this position will be to maintain the project register on activities in collaboration with other observing system staffs and task leaders including those not resident in the WMO Secretariat. | 500,000 |
| 3 | WIGOS Technical Documentation Manager | 5: To review existing Technical Documentation and Regulations for observing systems in order to prepare appropriate updates as well as an initial WIGOS Manual and related guidelines, and to support the expert teams in production of other guidance material such as those needed on the preparation and maintenance of metadata. This officer will also play a key role in the review of technical regulations in coordination with WIS. | 500,000 |
|  |  | TOTAL: | 1,9 million |

2) Activities in accordance with Table 1

3) The WIGOS Project Manager post is established and financed from the WMO regular budget

- List of Acronyms

| CBS | WMO Commission for Basic systems |
| --- | --- |
| CEOS | Committee on Earth Observation Satellites |
| CONOPS | Concept of Operations |
| CIMO | Commission for Instruments and Methods of Observations |
| CSIS | Climate Services Information System |
| D/OBS | Director, Observing and Information Systems Department |
| DMS | Data/metadata management system |
| DRR | Disaster Risk Reduction |
| EC | Executive Council |
| EUCOS | EUMETNET Composite Observing System |
| EC-WG/WIGOS-WIS | Executive Council Working Group on WIGOS and WIS |
| FAO | Food and Agriculture Organization |
| GAW | Global Atmospheric Watch |
| GCOS | Global Climate Observing System |
| GEO | Group on Earth Observations |
| GEOSS | Global Earth Observation System of Systems |
| GFCS | Global Framework for Climate Services |
| GOOS | Global Ocean Observing System |
| GOS | Global Observing System |
| GTOS | Global Terrestrial Observing System |
| ICG-WIS | Inter-Commission Coordination Group on WIS |
| ICG-WIGOS | Inter-Commission Coordination Group on WIGOS |
| ICPC | Interagency Coordination and Planning Committee for Earth Observations |
| ICSU | International Council for Science |
| IOC | Intergovernmental Oceanographic Commission |
| JCOMM | WMO/IOC Joint Commission for Marine Meteorology |
| LDCs | Least Developed Countries |
| MOA | Memorandum of Agreement |
| MOU | Memorandum of Understanding |
| NMHS | National Meteorological and Hydrological Service |
| QA | Quality Assurance |
| QC | Quality Control |
| QMF | Quality Management Framework |
| QMS | Quality Management System |
| RA | Regional Association |
| RRR | Rolling Review of Requirements |
| SG-WIGOS | Sub-group on WIGOS |
| SIDS | Small Island Developing States |
| TC | Technical Commission |
| UNEP | United Nations Environment Programme |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNFCCC | United Nations Framework Convention on Climate Change |
| WDIP | WIGOS Development and Implementation Plan |
| WDIS | WIGOS Development and Implementation Strategy |
| WHYCOS | World Hydrological Cycle Observing System |
| WIGOS | WMO Integrated Global Observing System |
| WIP | WIGOS Implementation Plan |
| WIS | WMO Information System |
| WWW | World Weather Watch |

________________

In this document “partner organizations” means: Intergovernmental, non-governmental and international organizations and groupings that operate, or co-sponsor, with WMO, observing systems that contribute to WIGOS. The main partner organizations are UNESCO and its IOC, UNEP, FAO and ICSU and the main co-sponsored observing systems are GCOS, GOOS and GTOS; partner organizations also include GEO.

It is necessary to clearly distinguish between station/platform metadata (“WIGOS metadata”) and WIS metadata needed for Data Discovery, Access and Retrieval (DAR) services that WIS must provide. Both are essential to WIGOS. Both are essential to WIGOS.