Severe Weather Forecasting Demonstration Project (SWFDP)

Regional Subproject – RA I – West Africa

(SWFDP-West Africa)

Regional Subproject Implementation Plan (RSIP)

8 September 2017

SWFDP-West Africa

Regional Subproject Implementation Plan (RSIP)

8 September 2017

Table of Contents                                                                                 	        Page

1.	Introduction                                                                                    		 	  5

1.1	SWFDP Framework and its ‘cascading forecasting process’ 		 	  5

1.2	The four phases of the SWFDP						 	  6

1.3	Foundation laid for development of SWFDP for West Africa		 	  6

1.4  	Hydrometeorological hazards in West Africa                   		  	  6

2.       Framework of SWFDP – West Africa						 	  7

2.1	Key Objectives								 	  7

2.2	Participating countries / organizations	             	 			  8

2.3	Severe weather events types to be focused					  8

2.4	Target domain								 	  8

2.5	Table of Warning Hazards and Thresholds for the issuance of RSMC

Guidance									  9

2.6	Regional Subproject Management Team (RSMT)				 10

2.6.1 Role and Responsibility of RSMT       		                              	 10

2.6.2 Members of RSMT                                                                    	 	 10

2.6.3	Responsibilities of the Members of RSMT				 11

2.7	Responsibilities of Participating Centres in Subproject Implementation  		 12

2.7.1	The Global Centres							 12

2.7.2	The Regional Centres							 12

2.7.3	The NMCs/ NMHSs							 14

3.	Data, products and support  from Contributing Centres				 15

3.1	Data and Products to be issued from Global Centres				 15

3.2	Data and Products to be issued from Regional Centres				 15

3.2.1	Data, Products and Guidance from RSMC Dakar				 15

3.2.2 	Data, products and technical support from ACMAD			 16

3.2.3	Data, products and technical support from AGRHYMET Regional Centre	 16

3.2.4 	Data, products and technical support from DMN Morocco 		 16

3.2.5 	Data, products and technical support from NIMET-Nigeria		 16

3.3	Technical feasibility including status of internet at NMCs/NMHSs          		 17

3.3.1	Technical feasibility							 17

3.3.2	Status of internet infrastructure and additional requirements 		 17

4.	Public Weather Services (PWS) Component of SWFDP				 17

4.1	WMO Strategy for Service Delivery 						 17

4.1.1	Impact-Based Forecast and Warning Services				 17            4.1.2	Common Alerting Protocol (CAP)					 18 4.1.3	WMO Register of Alerting Authorities					 18 4.1.4	The WMO Alert Hub							 18 4.1.5	Television studios							 18

4.2	Implementation plan to improve warnings and forecasts services

in NMHSs									 18

5.	SWFDP Training Programme								 18

5.1	Overview									 18

5.2	Training strategy and topics							 19

6.	Evaluation of Subproject including Feedback Mechanism				 20

6.1	Overview									 20

6.2	Quarterly Progress Reports by NMHSs and feedback from users			 21

7.	Timeline of Subproject activities							 21

8.	Subproject Costs and Resources							 22

9.	Communication & publicity of the project (Stakeholder engagement)		 22

10.	Projects in synergy with SWFDP-West Africa					 23

11.	List of the Annexes									 23

12.	References										 23

ANNEX A: Availability of Minimum Required NWP Products from Global Centres		 25

ANNEX B: List of Stations for EPSgrams (ENS Meteograms) provided by Global Centres 28

ANNEX C: Data and Products to be provided by Regional Centres including RSMC Dakar 37

ANNEX D: Template of Daily Regional Guidance to be provided by RSMC Dakar		 41

ANNEX E: Template of SWFDP Quarterly Progress Report 				 43

ANNEX F: Template of Severe Weather Event Evaluation Form				 46

ANNEX G: User Assessment Questionnaire						 52

G.1: Evaluation Questionnaire for the Public					 52

G.2: Evaluation Questionnaire for Disaster Management				 53

G.3: Evaluation Questionnaire for Media					 	 54

ANNEX H: Tentative Activity Plan for SWFDP implementation in Western Africa		 55

Version History

| Version | Date | Responsible | Comments |
| --- | --- | --- | --- |
| Ver1 | 8 September 2017 | The RSIP is prepared during the Technical Planning Meeting for SWFDP Development in West Africa (Abidjan, Ivory Coast, 4-8 September 2017) | RSIP is based on the outline developed after Dakar Workshop (November 2015) |

1.	Introduction

1.1	The SWFDP and its ‘Cascading Forecasting Process’

WMO’s Severe Weather Forecasting Demonstration Project (SWFDP) aims to enable all NMHSs to issue effective severe weather warnings to disaster management and civil protection authorities in their respective countries. Using a ‘Cascading Forecasting Process’, the Project makes global-scale products available to Regional Specialized Meteorological Centres (RSMC) that integrate and synthesize them in order to provide daily guidance for NMHSs in their geographical sub-region. Thus, the NMHSs have greater capability to identify hazardous weather conditions in the short- and medium-range and issue forecasts and warnings accordingly.

The SWFDP is guided by a Steering Group of the Commission for Basic Systems (CBS). The Steering Group has developed an overall Project Plan and a ‘SWFDP Guidebook’ on planning regional subprojects. These documents are reviewed and updated by the Steering Group. All SWFDP regional subprojects are developed and planned according to the guidelines provided in the guidebook. The SWFDP Guidebook is available on WMO website at the following link:

http://www.wmo.int/pages/prog/www/swfdp/index_en.html

The first ever SWFDP regional subproject was initiated in 2006 with involvement of just five countries in southeast Africa. The success story of this subproject provided basis for expansion of SWFDP into whole Southern Africa in 2009 with involvement of sixteen countries and later into other sub-regions of the world including Eastern Africa.

A SWFDP regional subproject implies a coordinated functioning among three types of Global Data Processing and Forecasting Systems (GDPFS) centres to implement ‘Cascading Forecasting Process’.  Conceptually, it should involve one or more global centres, one regional centre and a number of NMHSs located in a sub-region or geographical area.  In practice, a subproject may involve additional regional centres, if beneficial and practical to do so.  In case more than one regional centres are involved, one of the regional centres will serve as a lead Centre for regional forecast guidance support and coordination with participating NMHSs/NMCs. The lead regional centre shall preferably be selected from within the geographical area of the  subproject. Capacity development through regular trainings forecasting and service delivery aspects is a critical component of the subproject. Forecasters need to know how to make optimal use of the various NWP products and satellite information coming from the contributing centres.

Figure 1 – The Cascading Forecasting Process of the SWFDP.

The SWFDP regional projects are developed in a phased approach, with three phases of development and demonstration including evaluation followed by a transition to sustainable operations in Phase IV as explained in next paragraph.

1.2	The Four Phases  of SWFDP

The  development and implementation of SWFDP regional subprojects including SWFDP-West Africa involves following four phases:

Phase I: Overall Project Planning

Phase II: Regional Subproject Implementation Planning and Execution

Phase III: Regional Subproject Evaluation

Phase IV: Regional Subproject Long-term Sustainability and Future Developments

More information on SWFDP including description of the four phases is available in the above referred project documents including SWFDP guidebook.

The four phases of SWFDP are somehow aligned with the general project cycle involving identification of a project; its preparation; implementation; completion and evaluation; and post-completion follow-up actions.

1.3	Foundation laid for development of SWFDP - West Africa

Noting the significant development and progress of the SWFDP, from concepts to the first SWFDP regional subproject, implemented in the south-eastern region of Africa in 2006, the fifteenth session of World Meteorological Congress (Cg-15, Geneva, 2007 decided that the project should be expanded and implemented throughout RA I (Africa) and to other WMO Regions especially involving developing countries including least developed countries (LDCs) and Small Island Developing States (SIDSs). In that regard, Cg-15 requested the CBS to consider the possibility of implementing similar projects in Africa and the South Pacific Islands. Subsequently, SWFDP in southern Africa was expanded to benefit all 16 countries in the region and a SWFDP regional subproject was also developed in Eastern Africa with involvement of 7 countries in the region.

In 2015, the Cg-17 endorsed the recommendation of Regional Association I (Africa) about expansion of the SWFDP to the rest of Africa, starting with West Africa. Therefore, in order to respond to the regional requirements, WMO Secretariat initiated planning for developing SWFDP regional subproject in West Africa. To kick start the process, a workshop on severe weather forecasting and warning services was organized in Dakar, Senegal in November 2015 to understand operational capabilities and needs of the NMHSs in Western and Central Africa countries in preparing and delivering forecasts and warnings; and to train on the use of severe weather forecasting products, and on public weather services. The Korea Meteorological Administration (KMA) provided seed funding for this initiative. The invited countries showed keen interest to get involved in the SWFDP and benefit from the project. RSMC Dakar also agreed to serve as a lead Regional Centre for SWFDP-West Africa. As follow-up of 2015 workshop, a technical planning workshop was organized in Abidjan, Ivory Coast, in September 2017 to develop an implementation plan for SWFDP-West Africa.

1.4  	Hydrometeorological hazards in West Africa

Natural disasters including hydro-meteorological events are serious handicap to the development of many African countries. Hydro-meteorological hazards are responsible for massive losses including deaths, injuries and damages to housing, infrastructure, livestock and agriculture. The severe events that impact countries in West Africa range from drought to heavy rains, storms and floods. The region is also affected by the dry convective storms that originate from the Sahara desert. As with several other regions in the world, droughts and floods are strongly linked to food and water security in West Africa. Heavy rains and associated flooding generally occur during West African monsoon in summer months. The prediction of such events poses serious challenges for the National Meteorological and Hydrological Services (NMHSs) owing to the uncertainties associated with African monsoon weather systems and large variability of annual monsoon rains in terms of its onset, uneven distribution and span. Prolong deficiency of rain, sometimes caused by late onset of African monsoon, may cause drought conditions in the region, but on the other hand heavy monsoon rainfall events can result in flash flooding which may trigger river floods affecting large areas.

Over the past decade, flooding has been increasingly frequent in the Sahel, especially during the rainy seasons of 2005, 2008, 2009, 2010. The 2010 floods left over 111,000 people homeless across Niger. Niger was already suffering acute food shortages following prolonged drought in the Sahel region. The heavy rainfall events pushed the Niger River to its highest levels in 80 years. The floods subsequently spread along the River Niger into Nigeria, Ghana, Burkina Faso, Togo and Benin over the next few months. In 2015, heavy rains caused destruction in several countries in West Africa. In June 2015, the rainfall in Accra, the largest city of Ghana caused severe flooding. The floods resulted in heavy traffic on the roads in the city and also a halt to commercial activities as market places were flooded and workers trapped. At least 25 people died from the flooding directly, while a petrol station explosion caused by the flooding also killed at least 200 more people.   Similarly, in September 2015 in Nigeria and Guinea heavy rains caused flooding and triggered landslides. As a result, 30 people died in Nigeria and 7 people lost their lives in Guinea in addition to damage to property and infrastructure. Recently, in August 2017 flooding and mudslides due to heavy rains have affected several parts of West Africa including especially Sierra Leone, Nigeria and Niger.

More recently during 2017 summer rainy season, devastating flood events have been recorded in Sierra Leone, Niger and Nigeria, causing widespread severe losses and damages including over 500 deaths in Sierra Leone and 54 in Niger, and affecting thousands of people. According to UN Office for the Coordination of Humanitarian Affairs (OCHA), around 6,000 people were affected by the mudslide and floods in Sierra Leone. In Niger, flooding has affected 194,000 people with 9,000 houses damaged, 16,000 heads of cattle and 9,800 hectares of crop lost. In Niamey, Niger’s capital city, thousands of people were forced to evacuate their homes. In Nigeria, more than 110,000 people were displaced in its central state Benue after intense rains and flooding.

It is becoming more and more evident that the frequency of extreme events is associated with global warming.  Severe weather events in West Africa especially heavy rains and flooding are mainly associated with meso-scale thunderstorms and squall lines. Forecasting such severe weather to reduce the risk of hazards is one of the challenges faced by many NMHSs.

2.        Framework of SWFDP – West Africa

2.1	Key objectives

As per ‘SWFDP Guidebook’, the scope of the SWFDP is to test the usefulness of the products currently available from NWP centres, including EPS products  to improve severe weather forecasting and delivery of warning services in WMO Members especially where the use of NWP model outputs is limited.  The SWFDP-West Africa would make use of the cascading forecasting approach to improve severe weather forecasting and to provide greater lead-time for warnings and would, at the same time, contribute to capacity development of the participating NMHSs. It would improve links with users including especially Disaster Management and Civil Protection Authorities (DMCPA) to achieve SWFDP goals and objectives as envisioned by WMO. Given the need to work with DMCPA and media organizations to improve delivery of severe weather warning services to end users, the Public Weather Services (PWS) and Disaster Risk Reduction (DRR) aspects are integrated into the SWFDP. Further, as part of WMO Strategy for Service Delivery (approved by Cg-17 , 2015), impact-based forecast and risk-based warnings will be introduced and strengthened through improved engagement of NMHSs with users as part of SWFDP implementation. Ultimately, SWFDP-West Africa is expected to provide operational support to Multi-Hazard Early Warning Systems (MHEWS) at regional and national levels as envisioned in WMO Road Map for DRR.

2.2	Participating countries / organizations

The SWFDP-West Africa will initially involve the following countries: Benin, Burkina Faso, Cabo Verde, the Gambia, Ghana, Guinea, Ivory Coast, Mali, Niger, Nigeria, Senegal, Sierra Leone, and Togo

The participating global centres include: MeteoFrance and ECMWF (and confirmation needs to be obtained for  NOAA/NCEP, UKMO, and EUMETSAT).

The RSMC Dakar will contribute to the subproject as a Lead regional centre, while ACMAD, AGRHYMET, and DMN Morocco will serve as  regional technical and training support centres.

2.3	Severe weather events types of focus

The SWFDP-West Africa will focus on the following severe weather types:

- Heavy rainfall

- Strong wind

- High sea (damaging waves)

- Maximum Temperature (Heat wave conditions)

- Minimum Temperature (Cold wave conditions)

- Sand/dust storms

- Severe thunderstorms

2.4	Target domain

The domain to be covered for monitoring, analyzing and predicting the various severe weather events is proposed to be bounded by 0°N to 35°N and 30°W to 25°E.

Figure 2: The red-coloured rectangle is the target domain for SWFDP-West Africa.

2.5	Table of Warning Hazards and Thresholds for the issuance of RSMC Guidance to NMCs/NMHSs

Note: Thresholds in individual countries may differ but the values as given in the table below are the consensus for guidance from RSMC Dakar.  NMHSs may translate information provided in the RSMC guidance into national warnings based on their national criteria as appropriate and necessary.

| HAZARD | THRESHOLD | COMMENTS |
| --- | --- | --- |
| Heavy Rain | ≥50 mm in 12 hours ≥50 mm in 24 hours ≥100 mm in 24 hours (the risk over 200mm/24h should be described in discussion part of the RSMC Guidance) | NMHSs may translate the heavy rain into potential flooding in areas likely to be affected by heavy rain depending upon the soil condition, topography and drainage systems in respective areas. |
| Strong winds | ≥40Km/h (20 knots) ≥60Km/h (30 knots) | Affecting oceanic and coastal areas especially. Gusts on land from severe convective systems may not be predictable on this time scale effectively |
| High sea (Swell) | ≥2m ≥3m | Different thresholds have different disastrous impacts on the coastal structures in the sub-region. |
| Maximum Temperature (Heat wave conditions) | ≥35°C ≥40°C ≥45°C | NMHSs may translate this information into national warning for heat wave based on their national criteria as appropriate and necessary. |
| Minimum Temperature (Cold wave conditions) | ≤12°C ≤10°C ≤8°C | NMHSs may translate this information into national warning for cold wave based on national criteria as appropriate and necessary. |
| Poor surface/horizontal visibility (mainly due to thick dust/haze) | TBD | ACMAD to conduct study in collaboration with RSMC Dakar and NMHSs on relationship of dust load data and visibility data over West Africa to develop visibility thresholds based on dust load for the issuance of guidance. Dust information/forecasts are available through WMO SDS-WAS centres e.g. RSMC Barcelona) as well as through European Union’s Copernicus programme, previously known as GMES (Global Monitoring for Environment and Security). Please see link below: https://sds-was.aemet.es/ https://dust.aemet.es/forecast https://atmosphere.copernicus.eu/ |

2.6.	Regional Subproject Management Team (RSMT)

2.6.1	Role and Responsibility of RSMT

According to the SWFDP Guidebook, a regional subproject management team (RSMT) is to be set up with the aim of preparing the implementation of SWFDP-West Africa and managing and controlling its execution. The responsibilities of the RSMT are defined as follows:

- to prepare the Regional Subproject Implementation Plan (RSIP);

- to manage and monitor the implementation of the regional subproject.;

The RSMT will consult with relevant regional/sub-regional groups and bodies such as, RAI Management Group and the WG on DRR and Service Delivery during the planning and implementation of the SWFDP-West Africa.

2.6.2	Members of RSMT

The RSMT will mainly consist of the designated representatives of participating NMHSs and contributing global and regional centres (nominated by respective PRs and/or Heads of Centres). It will composed of the following, subject to approval by the respective Permanent Representatives/Directors:

- NMHSs

  - Benin: Mr. Boris Polynice Anato

  - Burkina Faso:  Mr Guillaume Nakoulma

  - Cabo Verde:  Mrs Eufémia Brito

  - Gambie: Mr George Stafford

  - Ghana: Mr Michael Padi

  - Guinée: Mr Goikwia Koiba

  - Côte d'Ivoire: Mr Ferdinand Eklou

  - Mali: Mr Moussa Toure

  - Niger: Mr Ousman Baoua

  - Nigeria: Dr Bako Mansur Matazu

  - Senegal: Mr Mouhamoudou Moustapha Kamara

  - Sierra Leone:  Mr Sylvanus Coker

  - Togo: Dr Latifou Issaou

- Regional Centres

  - RSMC Dakar: Mr Sadibou Ba  (Chair of RSMT)

  - ACMAD: Mr Leon Razafindrakoto

  - AGRHYMET Regional Centre: M. XXX (TBD)

  - DMN Morocco: Mr Driss Khalfi

  - NIMET Nigeria: Dr Bako Mansur Matazu

- Global Centres

  - MeteoFrance: Mr Cédric Legal

  - ECMWF: Dr Anna Ghelli

  - UK Met Office:  XXX (TBD)

  - NOAA / NCEP: XXX (TBD)

  - Environment Canada: XXX (TBD)

  - EUMETSAT: XXX (TBD)

- Regional PWS Representative (from RA I)

- The contact person of SWFDP Steering Group (from RA I): Mr Sebego Ezekiel (SAWS South Africa)

- The representative of ECOWAS: Mr XXX (TBD)

The Economic Community of West African States (ECOWAS) may also be engaged in the RSMT especially considering sustainability of the subproject in Phase IV (transition to operations) which requires subproject management by a regional entity.

2.6.3	Responsibilities of the Members of RSMT

The tasks of the members of RSMT, including during the preparation phase of the SWFDP are as follows:

    - 2.6.3.1 The chairperson will be responsible for:

- drafting a detailed RSIP and sharing between participating countries;

- ensuring the collaboration with other regional projects in synergy with SWFDP

- determining the requirements for and co-ordinating training activities that support the subproject and to provide information to WMO Secretariat;

    - 2.6.3.2 The lead person for each participating NMC/NMHS will be responsible for:

- coordinating all aspects of project implementation and execution at their respective centres;

- evaluating possible data-processing developments (e.g. work required to adjust or tailor NWP products);

- arranging for forecasters in the centres to receive or have access to the agreed products;

- defining the information to be exchanged with their DMCPA and other users;

- defining the information to be transmitted to the media;

- identifying training requirements;

- preparing regular evaluation of the warnings during the demonstration phase;

- reporting on a quarterly basis on the status of the SWFDP activities and implementation including verification of forecast/ warnings in the respective centres and feedback from users .

    - 2.6.3.3 The lead person for each participating Global Centre and RSMC will be responsible for:

- coordinating all aspects of project implementation and execution at their respective centres;

- evaluating possible data-processing developments (e.g. work required to adjust or tailor NWP products);

- arranging for verification of products from his/her global centre.

    - 2.6.3.4 The regional PWS representative will be responsible to:

- promote the awareness of the SWFDP-West Africa to stakeholders (disaster management centre, agriculture and fisheries sectors, media and the public), including through existing forums and organizations;

- enable and assist staff of participating NMHSs to build effective dialogue with stakeholders for service provision;

- in liaison with stakeholders, identify improvements and changes to products for consideration of the NMHSs’ forecasting team;

- advise participating NMHSs on methods of evaluation of public forecasts and warnings and their use by stakeholders.

2.6.3.5 The contact person of the SWFDP Steering Group will be responsible for liaising with the Project Steering Group (PSG) on aspects of the regional subproject.

2.6.3.6 Each of the participating NMHSs are requested to involve their respective national  PWS focal points in the activities of SWFDP-West Africa especially related to engagement of NMHSs with users, including delivery of warning services and users feedback. Where such a national focal point has not been nominated yet, the NMHSs concerned are invited to do so and inform the Secretariat.

2.7.	Responsibilities of Participating Centres in Subproject Implementation

Specific tasks are attributed to the three types of centres participating in the ‘cascading forecasting process’ implemented through SWFDP-West Africa.

2.7.1	The Global Centres

The MeteoFrance, ECMWF (and NOAA/NCEP, Environment Canada and UKMO pending approval) will contribute to the subproject as global centres.  The responsibilities of the Global Centres are:

- to provide the other centres with medium-range NWP guidance and EPS output including probabilistic products specially adapted to the relevant severe weather events;

- to tailor products to the requirements of the Regional Centres including the provision of sub-domain and probabilistic products according to the lists given in Annex A and Annex B;

- to suggest suitable existing satellite imagery and satellite based products that are helpful in assessing the current meteorological situation, and therefore also assess the quality of global NWP/EPS products;

- to maintain a dedicated webpage to provide NWP guidance and EPS products;

- to evaluate the efficiency of products dedicated to medium-range severe weather forecasting through the feedback provided by the other centres;

- to provide technical training support including on use of new products when become available.

2.7.2	The Regional Centres

The following Regional Centres are adopted in SWFDP-West Africa: RSMC Dakar (as lead Regional Centre), ACMAD, AGRHYMET and DMN Morocco and NIMET (Nigeria). The responsibilities of each centre are described in the following paragraphs. The list of products to be made available from Regional Centres is given in Annex C.

2.7.2.1 The Regional Specialized Meteorological Centre (RSMC), Dakar

The RSMC Dakar will serve as a lead Regional Centre for SWFDP-West Africa. The responsibilities of RSMC Dakar are:

- to redirect toward the NMHSs relevant products issued from the Global Centres (if necessary);

- to provide NMHSs with its own interpretation of the medium-range guidance, including EPS products;

- to provide the NMHSs with the short-range NWP guidance (including products adapted to severe weather events), as frequently as possible;

- to indicate existing satellite/radar imagery and satellite/radar based products that could be used for nowcasting purposes;

- to issue Daily Severe Weather Forecasting Guidance products summarizing interpretation of NWP products with respect to severe weather over the responsibility area of the NMHSs;

- to provide the other centres with short-range NWP guidance and EPS output including probabilistic products specially adapted to the concerned severe weather events;

- to tailor products to the requirements of the NMCs/NMHSs including the provision of sub-domain and probabilistic products according to the lists given in Annex C;

- to evaluate its own interpretation of EPS products as well as its NWP guidance;

- to provide global centres with a feedback about the usefulness and efficiency of global products;

- to facilitate the flow of all forecasting guidance information to all participating Centres in the SWFDP through a dedicated password protected Web site and portal. Ideally this Web site would be maintained on a 24/7 basis and dedicated for the SWFDP-West Africa;

- to coordinate real-time communications among the participating centres in the region of the project (to maintain a list of contact information; e-mail , telephone, fax).

2.7.2.2 ACMAD

The ACMAD will serve as a technical and training support centre for SWFDP-West Africa.  The responsibilities of the ACMAD are:

- to help the RSMT to organize training workshops;

- to arrange regular trainings and provide infrastructures for learners;

- to provide the NMHSs with the technical support in response to their requests;

- to provide support and contribute to the SWFDP training programmes and workshops;

- To provide additional NWP products;

- To assist NMHSs/NMCs in their case studies.

2.7.2.3 AGRHYMET Regional Centre

The AGRHYMET will serve as a technical and training support centre for SWFDP-West Africa.  The responsibilities of the AGRHYMET are:

- to help the RSMT to organize training workshops;

- to arrange regular trainings and provide infrastructures for learners;

- to provide the NMHSs with the technical support in response to their requests;

- to provide support and contribute to the SWFDP training programmes and workshops;

- to provide additional products if available.

(Subject to formal agreement by AGRHYMET)

2.7.2.4 DMN Morocco

The DMN Morocco will serve as a technical and training support centre for SWFDP-West Africa.  The responsibilities of the DMN Morocco are:

- to help the RSMT to organize training workshops;

- to arrange regular trainings and provide infrastructures for learners;

- to provide the NMHSs with the technical support in response to their requests;

- to provide support and contribute to the SWFDP training programmes and workshops;

- to provide additional products if available.

(Subject to formal agreement by DMN Morocco)

2.7.2.5 NIMET Nigeria

The Nigeria Meteorological Agency (NIMET) will serve as a technical and training support centre for SWFDP-West Africa.  The responsibilities of the NIMET are:

- to help the RSMT to organize training workshops;

- to arrange regular trainings and provide infrastructures for learners;

- to provide the NMHSs with the technical support in response to their requests;

- to provide support and contribute to the SWFDP training programmes and workshops;

- to provide additional products if available.

(Subject to formal agreement by NIMET Nigeria)

2.7.3	The National Meteorological Centres (NMCs)/NMHSs

The responsibilities of the participating NMCs/NMHSs are:

- to interpret the guidance provided by the global centre and the regional centre;

- to issue special bulletins and warnings as required by the users (hydrological services, DMCPA services, media, agriculture etc.) for dissemination to the end users when severe weather is expected;

- to use available nowcasting tools (satellite imagery or satellite based products, radar products) to update warnings;

- to exchange information on warnings between participating NMHS, and between NMHSs and RSMC;

- to provide regional and global centres with a feedback on the efficiency of the global and regional products;

- to develop a communication strategy and plan with the media and end users to ensure effective response when warnings are issued;

- to establish contacts with DMCPA services and  end users prior and during severe weather events;

- to obtain feedback from media, the public and other users as appropriate after the event (opportunity of warning, usefulness of warnings, lead time, degree of impacts)

- to obtain feedback from the DMCPAs on utilization/benefits of warnings issued by NMHSs (under the SWFDP);

- to evaluate forecasts and warnings and perform verification of forecasts and warnings;

- to compile data needed to perform the evaluation of both RSMC Daily Severe Weather Forecasting Guidance relevant to the country, and actual forecast warnings issued by  NMHSs;

- to carry out case studies of severe or high impact weather events;

- to prepare and submit SWFDP progress reports on regular basis;

- to develop training to facilitate improved communication with the users;

- to develop a generic basic set of standard operational procedures (SOPs) between a NMHS and DMCPAs to ensure effective use of the SWFDP products.

3.	Data, Products and support from contributing Centres

3.1	Data and Products to be issued from Global Centres

Global NWP graphical products which can be made available by the global centres MeteoFrance, ECMWF, NOAA/NCEP, Environment Canada and UKMO should be cut and formatted to fit the project area (0°N to 35°N and 30°W to 25°E).

NWP forecasts should be updated every 12 hours, or every 6 hours if available. In addition to the daily production all the forecasts should be archived for a minimum of 7 days.

The table in Annex A gives a comprehensive list of products and indicates which centre(s) will provide them. The list in Annex B shows the selected locations where the EPSgrams/ ENS Meteograms are required from Global Centres.

Products which are not routinely transmitted through the GTS should be provided in graphical form (Web pages) via Internet for rapid display and dissemination. Provision of data in digital format may assist regional centres in producing charts of derived parameter.

The products mainly include the following:

- Deterministic NWP Fields up to 5 days

- Probabilistic Forecast Products based on EPS

- Satellite Imagery and Satellite based Products

The available satellite imagery and satellite based products that Global Centres may suggest are:

- Satellite Images of VIS, IR and WV Channels of EUMETSAT etc.……;

- Diagnostic products, e.g.

  - Imagery with Heavy Rainfall Potential Areas produced by EUMETSAT etc….;

  - RGB Composite Imagery produced by  EUMETSAT etc.;

  - Rapid Developing Thunderstorms (RDT) products

(Needs to be agreed and confirmed by NMHSs and EUMETSAT)

3.2	Data and Products to be issued from Regional Centres

3.2.1	Data, products and guidance from RSMC Dakar

The products to be provided by the Regional Centres including RSMC Dakar are listed in the Annex C. Products which are not routinely transmitted through the GTS should be provided in graphical form (Web page) via Internet for rapid display and dissemination. The products mainly include the following:

- Deterministic Regional NWP Model fields (NWP LAM) up to 2 days and waves products	from Wavewatch3

- RSMC Daily Severe Weather Forecasting Guidance

The Daily Severe Weather Forecasting Guidance product should be issued by RSMC Dakar once per day at 1000 UTC to indicate the likelihood of severe weather occurrence. It mainly consist of a short range (up to 2 days) guidance, including the risk-table, and a medium range (up to 5 days) guidance. The Guidance product should contain the following:

- Synopsis of weather (analysis and forecast);

- the interpretation of deterministic and ensemble NWP products from the Global and Regional Centres;

- severe weather predictions (risk or probability estimates).

The threshold values to be used in RSMC Daily Severe Weather Forecasting Guidance are given in the table under Paragraph 2.5 above. A template of RSMC Daily Severe Weather Forecasting Guidance product is given in Annex D.

3.2.2	Data, Products and technical support from ACMAD

ACMAD will provide NWP products from UKMO global model disseminated through EUMETCast. Maps in JPEG format could be made available on ACMAD’s intranet after a post processing of grib2 files with GrADS software.

A WRF Africa model, with 9 km horizontal resolution, is planned to be implemented in the context of the Satellite and Weather Information for Disaster Resilience in Africa (SAWIDRA) project running over Africa  and could be accessible via a link for RSMC Dakar web site. West Africa Synthetic Analysis/Forecast (WASA/F) and Intertropical Discontinuity (ITD) maps could be made available. ACMAD will provide support for technical training to be organized within the context of SWFDP for participating countries in West Africa. ACMAD will consider also the hosting of NMHS staffs for « On the Job Training » or on secondment at ACMAD for capacity building.

3.2.3	Data, Products and technical support from AGRHYMET

(input to be provided by AGRHYMET)

3.2.4 	Data, Products and technical support from DMN-Morocco

(input to be provided by DMN Morocco)

3.2.5 	Data, Products and technical support from NIMET-Nigeria

(input to be provided by NIMET-Nigeria)

3.3	Technical Feasibility including Status of Internet at NMCs/NMHSs

3.3.1	Technical feasibility

All participating NMCs/NMHSs are expected to operate 24/7 and have sufficient operational staff (forecasters and PWS staff)  to carry out activities related to SWFDP implementation e.g. verification of forecasts/warnings, feedback from users etc.

3.3.2	Status of internet infrastructure and additional requirements

All participating NMCs/NMHSs are expected to have good internet connectivity to access to NWP products and satellite information as available from global NWP centres as well as through SWFDP including through RSMC Dakar web portal. The NMCs/NMHSs having poor internet speed may require to improve their internet speed to improve access to available high value information.

4.	Public Weather Services (PWS) Component of SWFDP

4.1	WMO Strategy for Service Delivery

The service delivery component of SWFDP starts with establishing service delivery baseline and the identification of gaps against which an action plan is developed for implementation. Examples of gaps include either the lack of staff, staff lack service delivery skills or they may have the skills but not assigned clear service delivery duties. Another gap could be insufficient communication channels available to a Meteorological Service (Website, television, radio (national, community, commercial …), social media, mobile phone app), lack of skills to provide high quality products such as impact-based forecast and warning services,  seasonal outlooks as well as having not adopted the  Common Alerting Protocol (CAP) standard to code warnings. Other gaps in NMHSs include lack of sufficient skills to work effectively with the media, the Disaster Management and Civil Protection Authorities (DMCPAs) as well as skills to develop Standard Operating Procedures (SOPs) and Memorandums of Understanding (MoUs).

4.1.1	Impact-Based Forecast and Warning Services

Impact-based warnings provide information of how hazards may impact warning recipients. NMHSs issue accurate hazard warnings yet populations suffer many casualties and damage because of lack of knowledge of likely impacts of the hazard. An NMHS cannot deliver impact-based warning services on its own. Creating systems to support impact warnings is based on close coordination between NMHSs and different organizations e.g. Disaster Reduction and Civil Protection Agencies (DRCPAs), social scientists etc. The benefits of an Impact Warning Service include:

- Relays a message to enable those at risk to take appropriate actions

- Improved planning for different scenarios based on different impacts

- Contains information about the level of confidence in the forecast for better decision-making

- Provides basis for post-event analysis of multi-hazard impacts to assist in planning, response and mitigation of impacts

- A comprehensive and coordinated process to address disaster response and preparedness

- Common situational awareness

The Public Weather Services (PWS) Programme of WMO has produced the «WMO Guidelines on Multi-hazard Impact-Based Forecast and Warning Services (WMO-No 1150)». It provides a road map to assist members develop impact-based warning services and defines the necessary steps and explains likely levels of complexity. This publication was highly recommended for use by Members in the West Africa.

4.1.2	Common Alerting Protocol (CAP)

CAP is an XML-based data format for exchanging public warnings and emergencies between alerting technologies. It is an international standard format for emergency alerting designed for “all-hazards” and “all-media”, … cell phones, faxes, radio, television, digital communication networks … It enables simultaneous communication of alerts over many different alerting systems, thus increasing effectiveness while simplifying the alerting task. Cg-15 endorsed adoption of a warnings Standard such as CAP for alerting.   PWS programme will assist SWFDP-West Africa participating countries through the «CAP Jump-start» arrangement where Experts visit NMHSs and provide training and freeware.

4.1.3	WMO Register of Alerting Authorities

The WMO Register of Alerting Authorities provides emergency managers, the media, other intermediaries and the public, an authoritative register of organizations authorized to issue alerts in each country. Under SWFDP, there will be an effort to ensure that all participating countries are current on the Register.

4.1.4	The WMO Alert Hub

WMO is planning on developing an alert hub to aggregate and make available  all alerts from Members. It is planned to provide one-stop platform for alerts provided by authorized agencies/institutions. The Filtered Alert Hub which is part of the NOAA Big Data Project is considered prototype for the WMO Alert Hub. The WMO Alert Hub is expected to be an important component of the WMO Global Multi-Hazard Alert System (GMAS).  Therefore, eventually, alerts issued by participating countries will be made available on the GMAS platform.

4.1.5	Television studios

Depending on the way a meteorological service wishes to provide services, it might be desirable to have a TV studio located at the meteorological service where weather bulletins are recorded for airing through collaboration with a broadcaster station. Where such a need exists, arrangements for assistance through SWFDP may be provided subject to availability of funds.

4.2	Implementation plan to improve warnings and forecasts services in NMHSs

Each participating NMHS will be assisted to develop a plan to improve their capacity to provide weather warnings, taking into account the realities of resources available to the NMHS. As this would contribute greatly to saving of lives, it is an important expected outcome of the project.

5.	SWFDP Training Programme

5.1	Overview

Capacity development of the NMHSs of SWFDP participating countries, through specialized training programmes on NWP, EPS and satellite products and their interpretation and use in making forecasts of impending severe weather and issuance of warnings for associated hazardous hydrometeorological conditions, is one of the key elements of SWFDP development and implementation in various regions. Based on the regional and national needs, the following approach is followed for planning and designing of the SWFDP training programmes:

- SWFDP training workshops (on NWP including EPS, and Satellite information interpretation and use of products as well as on PWS including delivery of warning services, impact-based forecasts and warnings etc.)

- RSMC Training Desk (short-term deployment of forecasters/experts  from participating countries at the regional centre to familiarize themselves with the mechanism for the preparation and issuance of guidance products)

- In-country Training

Subject to availability of resources, generally the SWFDP training workshops are held on annual basis preferably and are rotated among the participating countries of a subproject so that maximum staff can be trained in each of the participating country. Such workshops are mainly conducted for operational forecasters and public weather services (PWS) staff of the NMHSs. These workshops are organized with involvement of WMO’s GDPFS and PWS programmes and through collaboration from other relevant programmes (as appropriate and necessary) such as, Tropical Cyclone Programme (TCP), Marine Meteorology and Oceanography (MMO), Hydrology and Water Resources (HWR) and Agricultural Meteorology (AgM) Programmes.

Based on regional requirements, the establishment of a training desk at RSMC can also be considered. For this purpose, a couple of forecasters from NMHSs of participating countries are invited to work with the RSMC forecasters for a week or two. The RSMC training desk can serve two objectives: firstly, to improve the skills of invited forecasters by engaging them in the process of NWP, EPS and satellite products inference and analyses to develop RSMC Daily Guidance for the NMHSs; and secondly to provide opportunity for the RSMC forecasters to gain local knowledge from the invited forecasters through discussion in order to improve RSMC Daily Guidance for the benefitting countries.

In-country training approach is mainly adopted for relatively small NMHSs especially from  Small Island Developing States (SIDSs).

NMCs/NMHSs are encouraged to have a daily video conference with RSMC especially during rainy season in order to have discussions on current weather, synoptic analyses and inference from the NWP model products and satellite information to identify areas of potential severe weather in short- and/or medium-range. Additionally, participants from SWFDP countries are also supported and sponsored for NWP and EPS products interpretation and high resolution limited-area NWP Modelling trainings offered by various global and regional NWP centres such as: ECMWF, DWD, NOAA/NCEP and WMO RTCs etc.

NMCs/NMHSs are also encouraged to explore various other options and opportunities for the training on diversified topics including through e-learning. For example, MetEd resources could be explored to satisfy some of the needs. The MetEd website is maintained by the COMET® Program, which is part of the University Corporation for Atmospheric Research's (UCAR's) Community Programs (UCP). It provides education and training resources (online only) to benefit a range of users including operational forecasters community. The various courses are self-paced and can be accessed through MetEd website (https://www.meted.ucar.edu/index.php).

5.2	Training strategy and topics

Subject to availability of resources, NMHSs/NMCs involved in SWFDP-West Africa may benefit from SWFDP training programme as mentioned in above paragraph.  A survey can also be conducted in advance of training workshops to tailor training contents and facilitate the preparation of a learning path. However, possible contents of SWFDP-West Africa training workshops may include the following:

- Interpretation and best practice use of deterministic and probabilistic NWP products in severe weather forecasting;

- Understanding and interpretation of specialized deterministic and probabilistic NWP products for forecasting severe weather associated with tropical cyclones (e.g. for Cabo Verdi);

- Use of probabilities in the preparation of weather forecasts;

- Verification of forecast and warnings;

- Interpretation of daily RSMC Forecast Guidance product produced by RSMC Dakar and of ACMAD, Agrhynmet, NIMET products ;

- Use and application of the SWFDP-West Africa website;

- Conducting a case-study;

- Guidance on preparing SWFDP progress reports including evaluation form(s); and

- Feedback mechanisms and national contingency plans;

The PWS-related topics should typically include the following:

- Issues related to delivery of services including dealing with general public and media;

- Communicating uncertainty in forecasts;

- Coordination with Disaster Management and Civil Protection Agencies (DMCPA);

- Improvements in working relationships between NMHSs and DMCPA;

- Communication and media skills;

- Implementation of Common Alerting Protocol (CAP);

- Introducing and strengthening impact-based forecast and delivery of warning services with multi-hazard early warning system approach (MHEWS) in support of WMO Strategy for Service Delivery;

- Public Education and Outreach;

- Service Evaluation.

The detailed information about training programme will be made available to NMHSs and participants ahead of the SWFDP training workshop to ensure good preparation.

6.	Evaluation of Subproject	including feedback mechanism

6.1	Overview

Every SWFDP Regional Subproject is required to be evaluated against the SWFDP goals and objectives as mentioned in ‘SWFDP Overall Project Plan’ and ‘SWFDP Guidebook’ (see Para 2.1 above). The aim of the SWFDP evaluation also include:

- to assess the performance of RSMC’s Forecast Guidance Product;

- to assess the performance of the NMC/NMHS’s forecasting and warning system;

- to inform about the efficiency of the SWFDP and the level of satisfaction of the users.

During the demonstration phase, a continuous evaluation procedure using regular progress report must be implemented to check if the ‘cascading forecasting process’ works efficiently. At the end of the demonstration phase, a final evaluation of the regional subproject needs to be carried out by the RSMT to identify gaps and areas for improvement to ensure future sustainability of the demonstrated procedures and for other similar subprojects. In this evaluation, a qualitative assessment will be made of the success of the SWFDP related to the specific benefits of the Project and in particular the measurable improvements that have been noted in the warning services that are provided to the National Disaster Management and Civil Protection Authorities (DCMPAs) and the media.

6.2	Quarterly Progress Reports by NMHSs and feedback from users

After start of demonstration phase, each participating NMC/NMHS is required to submit quarterly progress reports including case studies to WMO Secretariat to keep regularly informed the RSMT and WMO about the progress of the implementation of SWFDP-West Africa and the project evaluation against SWFDP goals and objective.

A SWFDP database has been developed using WMO’s Country Profile Database (CPDB) web portal (https://www.wmo.int/cpdb/). Each of the NMHSs involved in SWFDP shall have a specific user ID and password to have access to the SWFDP database for submission of its progress reports.  The national focal points from each NMHSs (RSMT members) shall be responsible for implementation of the tasks related to the project at national levels including submission of SWFDP quarterly progress reports. Participating NMHSs of SWFDP-West Africa shall also be facilitated to submit their quarterly progress reports on-line through SWFDP database.

A progress report should contain information about the way the SWFDP is being implemented, such as the NWP/EPS products used in preparing severe weather forecasts and warnings, severe weather events observed, number of warnings issued during the reporting period, probability of detection and false alarms, dissemination channels,  clients/users’ feedback etc. The quarterly progress reports shall be prepared according to the schedule given in Section 10. The list of key elements and information that need to be reported in progress reports is given in Annex E.

To ensure that the needed information is reliably completed it is proposed that the information for the evaluation severe weather events be collected by using an “evaluation form”. A template of evaluation form is shown in Annex F.

This evaluation form has to be completed by the NMHS when a severe weather event has been observed or when a severe weather event has been forecast. The evaluation form needs to be formatted in a convenient form (Excel file) in order to simplify the processing and archiving of the data. The products that have been used in the production of severe weather forecasts must also be archived for use in future case studies.

Templates of ‘User Assessment Questionnaire’ are also available in Annex G. The NMHSs may develop such questionnaires to obtain feedback from users including general public, disaster managers, media, etc. The feedback obtained from users should also be reported by NMHSS as part of their progress reports as mentioned above.

7.	Timeline of Subproject activities

Subject to availability of resources, the subproject will be completed during next 3-4 years. The timeline for completion of activities for 2017-2018 to enable the subproject start its demonstration phase are given below:

| When | What Task | Who RSMT Member/Centre |
| --- | --- | --- |
| 13 October 2017 | Finalize RSIP | Chair of RSMT/ WMO Secretariat |
| 31 March 2018 | Complete further development of RSMC Dakar website (subproject web portal) | RSMC Dakar |
| 31 March 2018 | Development of NWP products | Global Centres |
| Q2/Q3 2018 | SWFDP training workshop | WMO Secretariat |
| Q3 2018 | Start of Demonstration phase | All |
| Q4 2018 | Submission of first Quarterly Progress Reports | NMHS |

8.	Subproject Costs and Resources

Financial assistance from a variety of sources will be needed to complete the SWFDP regional sub-project in West Africa. In 2015, Korean Meteorological Administration (KMA) provided seed funding to kick start the development and planning process of the subproject. There is potential for additional assistance as part of ongoing projects and activities in the sub-region. The potential impact of demonstration phase project-related activities on operational staffing should be considered by all contributing and participating centres. Generally, SWFDP is supported by global NWP and satellites centres as their in-kind contributions through WMO to assist NMHSs in developing countries including LDCs and SIDS.

For the purpose of evaluating the total cost of the regional subproject, participating centres are required to estimate all additional costs associated with the SWFDP. This should include human costs (equivalent person-months) as well as expenditures of funds if any directly related to the project.

SWFDP cost is mainly related to capacity development activities for NMHSs and to support their engagement with users including general public, DMCPAS, media (through regular SWFDP training workshops which are generally held every year) and to conduct RSMT meetings in alternate years.

CBS has commended the efforts of the Secretariat in supporting the SWFDP through optimizing activities across WMO programmes and in seeking support from donors. Following the recommendations of CBS, Members are also urged to seek funds from potential development partners and other agencies who stand to benefit from the important results of the SWFDP.

A tentative work plan of activities along with estimated costs for 2017-2020 is available as Annex H.

9.	Communication & publicity of the Subproject (Stakeholder engagement)

Informing stakeholders about the SWFDP-West Africa is an important task to improve visibility of the subproject and its synergy with other relevant projects in the sub-region as well as to secure resources for its implementation and future sustainability. There should be publicity about the initiation of the subproject as well regular progress reports.

The stakeholders may include:

- NMHSs in the region, including spreading information within the NMHS;

- RA I President and Management Groups;

- Relevant RA I Working Groups;

- AMCOMET

- ECOWAS

- Niger River Commission and Niger Basin Authority

- Executive Council;

- Aid agencies and development partners; CREWS; African Development Bank World Bank;

- WMO Secretariat

Communication could be through newsletters, information pamphlets, presentations (e.g., at the TC sessions, regular session of RA I and other regional meetings)

This Regional Subproject Implementation Plan (RSIP) should be passed to stakeholders for information and feedback. Responsibility for communicating the subproject and publicity is a task for all participants, but with overall coordination by the chairperson.

10.	Projects in synergy with SWFDP-West Africa

- Strengthening national capacities for EWS Service Delivery in Burkina Faso and Niger  (CREWS funded)

- Climate Services for increased Resilience in the Sahel (USAID funded)

11.	List of Annexes

ANNEX A: Availability of Minimum Required NWP Products from Global Centres

ANNEX B: List of Stations for EPSgrams (ENS Meteograms) provided by Global Centres

ANNEX C: Data and Products to be provided by Regional Centres including RSMC Dakar

ANNEX D: Template of Daily Regional Guidance Product to be issued by RSMC Dakar

ANNEX E: Template of SWFDP Quarterly Progress Report

ANNEX F: Template of Severe Weather Event Evaluation Form

ANNEX G: User Assessment Questionnaire

G.1 Evaluation Questionnaire for the Public

G.2 Evaluation Questionnaire for Disaster Management

G.3 Evaluation Questionnaire for Media

ANNEX H: Tentative Activity Plan for SWFDP implementation in Western Africa

12.	References

- Abridged Final Report with resolutions, decisions and recommendations of the sixteenth session of CBS (Guangzhou, China, 23–29 November 2016). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2016_Guangzhou_1183/1183_en.pdf

- Final Report of the sixth meeting of CBS Steering Group of the SWFDP (Geneva, Switzerland, 14–18 March, 2016). Available at:

http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP_Final_Report_000.pdf

- Final Report of the Technical Training Workshop on Severe Weather Forecasting and Warning Services (Dakar, Senegal, 2-6 November 2015). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html

- Abridged Final Report with resolution of the sixteenth session of Regional Association I (Africa) (Praia, Cabo Verde, 3-9 February 2015). Available at: https://library.wmo.int/pmb_ged/wmo_1151_en.pdf

- Abridged Final Report with resolutions and recommendations of the Extra-ordinary session of CBS (Asunción, Paraguay, 8–12 September 2014) (CBS-Ext.(2014)). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2014_Ext14_Asuncion_1140/1140_en.pdf

- Final Report of fifth meeting (extra-ordinary) of CBS Steering Group of  the SWFDP, Geneva, Switzerland, 3–5 December, 2013). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP_Final_Report.pdf

- Abridged Final Report with resolutions and recommendations of the fifteenth session of CBS (Jakarta, Indonesia, 10-15 September, 2012). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2012_15th_Jakarta_1101/1101_en.pdf

- Final Report of the forth meeting of CBS Steering Group of the SWFDP, Geneva, Switzerland, 28February to 2 March 2012). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/documents/SG-SWFDP-4_Final_Report.pdf

- Final Report of the third meeting of CBS Steering Group of the Severe Weather Forecasting Demonstration Project (Geneva, Switzerland, 22-26 February, 2010). Available at: http://www.wmo.int/pages/prog/www/CBS-Reports/DPFS-index.html

- Abridged Final Report with resolutions and recommendations of the fourteenth session of CBS (Dubrovnik, Croatia , 25 March -2 April, 2009). Available at: http://www.wmo.int/pages/prog/www/CBS/Reports/2009_14th_Dubrovnik_1040/1040_en.pdf

- Abridged Final Report with resolutions and recommendations of the Extra-ordinary session of CBS in 2006 (Seoul, Republic of Korea,  9-16 November 2006). Available at : http://www.wmo.int/pages/prog/www/CBS/Reports/2006_Ext06_Seoul_1017/1017_en.pdf

- Abridged Final Report of the thirteenth session of CBS (St. Petersburg, 23 February - 3 March 2005). Available at http://www.wmo.int/pages/prog/www/CBS/Reports/2005_13th_StPetersburg_985/985_en.pdf

ANNEX A: Availability of Minimum Required NWP Products from Global Centres

| Deterministic Forecasts: | Availability |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 6-hourly out to 72 hours, then 12-hourly up to 144 hours | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| Parameters: wind (streamlines and speed/direction), temperature, geopotential height, humidity Levels: Surface, 925hPa, 850hPa, 700hPa, 500hPa, 300hPa, 200hPa Purpose: General forecasting parameters to gain a perspective on the overall atmosphere. For determination of frontal system and pressure maxima locations. |  | YES | YES | YES |  |
| Parameter: vorticity, divergence Level: 850hPa, 700hPa, 500hPa, 200hPa Purpose: Determination of frontal and low pressure system locations. Crucial in locating potential severe weather outbreak locations. It can be used in determination of severe weather type |  | YES | YES | YES |  |
| Parameter: vertical velocity Level: 850hPa, 700hPa, 600hPa, 500hPa Purpose: Determination of mesoscale patterns of rising and sinking air masses (convective updrafts) |  | NO | YES | NO |  |
| SST maps |  |  |  |  |  |
| Parameter: wet bulb potential temperature OR equivalent potential temperature (Theta-E) Level: Surface,, 850hPa, 700hPa Purpose: Change in air mass including frontal position diagnosis |  | NO | YES | YES (850hPa only) |  |
| Parameters: instantaneous and accumulated precipitation, minimum temperature, maximum temperature, sea level pressure, relative humidity Level: Surface Purpose: General forecasting parameters |  | YES (Total precipitation only) | YES | YES |  |
| Parameter: 1000-500hPa thickness Level: partial atmospheric column Purpose: Freezing level determination and air mass distinguishing |  | YES |  | YES |  |
| Parameter: Precipitable water Level: atmospheric column Purpose: Determination of total liquid water in the atmosphere and thus potential rainfall |  | NO | YES | NO |  |
| Parameter: Convective Available Potential Energy (CAPE) Level: Atmospheric column Purpose: Amount of energy available in the atmosphere for storm production |  | YES | YES | YES |  |
| Parameter: Lifted index, K index, total totals index, Showalter Index Level: Stability index Purpose: Pre-calculated indices to generalize severe weather potential |  | YES | YES | Yes (Lifted index only) |  |
| Parameter: Convective inhibition (CIN), convection initiation temperature (TC) Level: stability index Purpose: Strength of force preventing convective initiation. The amount of energy (frontal forcing or daytime heating) that is needed to begin convection. |  | NO | YES (CIN only) | No |  |
| SKEW-T logarithmic forecast plots for selected grid points based on NWP output (out to 144 hours, 12-hourly) *For at least 3 stations per country |  |  | YES |  |  |
| Ensemble Forecasts: | Availability |  |  |  |  |
| 12-hourly out to 144 hours | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| Probability of 6-hour accumulated precipitation exceeding 50mm and 100mm threshold value |  | NO | YES |  |  |
| Probability of 24-hour accumulated precipitation exceeding 50mm and 100mm threshold values |  | YES | YES |  |  |
| Probability of 10-meter wind speed exceeding 20kt and 30kt threshold values |  | YES | YES |  |  |
| Probability of significant wave height exceeding 2m and 3m threshold values |  | YES |  |  |  |
| Probability of mean wave period exceeding 10s and 15s threshold values |  | YES |  |  |  |
| Ensemble Prediction System meteograms for specified locations (10-day / 15-day) |  | YES | YES |  |  |
| Spaghetti diagrams for 850hPa and 500hPa geopotential height |  |  | YES |  |  |
| Thumbnails of probability of precipitation in excess of threshold of 50mm/6h at 6 hours intervals |  |  |  |  |  |
| Extreme Forecast Index and Shift of Tails, and M-Climate for TMean, Tmax, Tmin, wind gust, wind speed, total precipitation, Max significant wave height |  | YES |  |  |  |
| ENS Cumulative Distribution Functions (Forecast and M-Climate) and EFI values (for precipitation, temperature and wind gust) |  | YES |  |  |  |
| MJO Index - Extended range forecast |  |  |  |  |  |

ANNEX B: List of Stations for EPSgrams/ ENS Meteograms and NWP based upper air sounding (Skew-T) provided by Global Centres

B.1: List of Stations for EPSgrams/ ENS Meteograms

B.1.1 Benin: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65344 | Cotonou | 6.35 | 2.3833 | 6.50 |  | YES | YES | YES |  |
| 65338 | Bohicon | 7.2031 | 2.0568 | 166.12 |  | YES | YES | YES |  |
| 65335 | Save | 8.0167 | 2.4833 | 198.0 |  | YES | YES | YES |  |
| 65330 | Parakou | 9.3557 | 2.6154 | 391.96 |  | YES | YES | YES |  |
| 65319 | Natitingou | 10.317 | 1.3833 | 429.09 |  | YES | YES |  |  |
| 65306 | Kandi | 11.133 | 2.9333 | 290.3 |  | YES | YES | YES |  |
|  | Port-Novo | 6.4833 | 2.6167 | 20 |  | YES | YES |  |  |

B.1.2 Burkina Faso: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65501 | Dori | 14.03°N | 0.03°W | 276.5 |  | YES | YES | YES |  |
| 65502 | Ouahigouya | 13.57°N | 2.43°W | 335 |  | YES | YES | YES |  |
| 65503 | Ouagadougou | 12.35°N | 1.52°W | 303 |  | YES | YES | YES |  |
| 65505 | Dedougou | 12.47°N | 3.48°W | 300 |  | YES | YES | YES |  |
| 65507 | Fada n’gourma | 12.07°N | 0.35°E | 308 |  | YES | YES | YES |  |
| 65510 | Bobo Dioulasso | 11.17°N | 4.32°W | 459 |  | YES | YES | YES |  |
| 65516 | Boromo | 11.67°N | 2.93°W | 270 |  | YES | YES | YES |  |
| 65518 | Pô | 11.18°N | 1.18°W | 321.5 |  | YES | YES | YES |  |
| 65522 | Gaoua | 10.38°N | 3.18°W | 292 |  | YES | YES | YES |  |
| 65608 | Bogande | 12.97°N | 0.08°W | 294 |  | YES | YES | YES |  |
| 65500 | Markoye | 14.63 N | 0.07 W | 295 |  | YES | YES |  |  |
| 65523 | Mangodara | 9.90 N | 4.35 W | 260 |  | YES | YES | YES |  |

B.1.3 Cabo Verde: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08583 | Mindelo | 16.8336 | -25.0547 | 20 |  |  |  |  |  |
| 08589 | Praia | 14.9411 | -23.4847 | 95 |  | YES |  |  |  |
| 08594 | Sal | 16.7419 | -22.9489 | 54 |  | YES |  |  |  |
|  |  |  |  |  |  | YES |  |  |  |

B.1.4 The Gambia: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 61717 | Kaur Met. | 13.7000 | 15.3333 | 11 |  | YES | YES | YES |  |
| 61731 | Basse Met. | 13.3167 | 14.2167 | 4 |  | YES | YES | YES |  |
| 61711 | Banjul Halfdie/ Marina | 13.4500 | 16.5667 | 2 |  | YES | YES | YES |  |
| 61712 | Kerewan Met. | 13.5000 | 16.1000 | 15 |  | YES |  | YES |  |
| 61721 | Georgetown/ Janbureh Met. | 13.5333 | 14.7667 | 1 |  | YES |  | YES |  |
| 61707 | Jenoi Met. | 13.4667 | 15.5667 | 20 |  | Yes |  | YES |  |
| 61701 | Yundum Inter. Airport | 13.3500 | 16.6333 | 33 |  | YES | YES | YES |  |
| 61705 | Sibanor Met. | 13.2167 | 16.2000 | 21 |  | YES |  | YES |  |
| 61722 | Sapu Met. | 13.5500 | 14.9000 | 3 |  | YES |  |  |  |
| 61733 | Fatoto Disp. /Met. | 13.4000 | 13.8833 | 18 |  | YES | YES | YES |  |
| 61720 | Kuntaur | 13.67 | 14.88 | 7.2 |  | YES |  |  |  |

B.1.5 Ghana: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65472 | Accra | 5.60 | - 0.17 | 67.7 |  | YES | YES | YES |  |
| 65475 | Ada-Foah | 5.7777 | 0.622 | 5.2 |  | YES | YES | YES |  |
| 65450 | Abetifi | 6.6803 | -0.7472 | 594.7 |  | YES | YES | YES |  |
| 65445 | Sefwi bekwai | 6.1965 | -2.3211 | 170.8 |  | YES | YES | YES |  |
| 65442 | Kumasi | 6.716BE9 | -1.5916 | 286.3 |  | YES | YES | YES |  |
| 65432 | Wenchi | 7.75 | -2.1 | 338.9 |  | YES | YES | YES |  |
| 65420 | Yendi | 9.45 | -0.0167 | 195.2 |  | YES | YES | YES |  |
| 65418 | Tamale | 9.5539 | -0.8624 | 168.8 |  | YES | YES | YES |  |
| 65401 | Navrongo | 10.8784 | -1.0832 | 201.3 |  | YES | YES | YES |  |
| 65404 | Wa | 10.05 | -2.5 | 322.7 |  | YES | YES | YES |  |
| 65453 | Ho | 6.6 | 0.4667 | 157.6 |  | YES | YES | YES |  |
| 65437 | Kete Krachi | 7.8167 | -0.0333 | 122 |  | YES | YES | YES |  |

B.1.6 Guinea: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 61832 | Conakry | 09.34 | -13.37 | 25.79 |  | YES | YES | YES |  |
| 61818 | Kindia | 10.03 | -12. 52 | 458.13 |  | YES | YES | YES |  |
| 61809 | Labé | 11.19 | -12.18 | 1025.00 |  | YES | YES | YES |  |
| 61829 | Kankan | 10.23 | -09.18 | 376.80 |  | YES | YES | YES |  |
| 61849 | Nzérékoré | 07.45 | -08.47 | 520.00 |  | YES | YES | YES |  |
| 61816 | Boké | 10.21 | -14.19 | 61.10 |  | YES | YES | YES |  |
| 61820 | Mamou | 10.22 | -12.05 | 782.30 |  | YES | YES | YES |  |
| 61802 | Koundara | 12.34 | -13.31 | 90.00 |  | YES | YES | YES |  |
| 61833 | Faranah | 10.02 | -10.42 | 467.08 |  | YES | YES | YES |  |
| 61834 | Kissidougou | 09.11 | -10.06 | 524 .00 |  | YES | YES | YES |  |
| 61811 | Siguiri | 10.26 | -09.10 | 361.9 |  | YES | YES | YES |  |
| 61847 | Macenta | 08.32 | -09.28 | 542.8 |  | YES | YES | YES |  |

B.1.7 Ivory Coast: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65585 | Adiake | 5.30°N | 3.30°W | 33 |  | YES | YES | YES |  |
| 65545 | Bondoukou | 8.05°N | 2.78°W | 369 |  | YES | YES | YES |  |
| 65563 | Yamoussoukro | 6.90°N | 5.35°W | 196 |  | YES | YES | YES |  |
| 65594 | San Pedro | 4.75°N | 6.65°W | 30 |  | YES | YES | YES |  |
| 65548 | Man | 7.38°N | 7.52°W | 339 |  | YES | YES | YES |  |
| 65536 | Korhogo | 9.42°N | 5.62°W | 381 |  | YES | YES | YES |  |

B.1.8 Mali: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 61202 | Téssalit | 20.2000 | 0.9833 | 490 |  | YES | YES | YES |  |
| 61214 | Kidal | 18.4333 | 1.3500 | 458 |  | YES | YES | YES |  |
| 61223 | Tombouctou | 16.7167 | -3.0000 | 263 |  | YES | YES | YES |  |
| 61226 | Gao | 16.2667 | -0.0500 | 265 |  | YES | YES | YES |  |
| 61250 | Menaka | 15.8667 | 2.2167 | 278 |  | YES | YES | YES |  |
| 61257 | Kayes | 14.4333 | -11.4333 | 47 |  | YES | YES | YES |  |
| 61265 | Mopti | 14.5167 | -4.1000 | 271 |  | YES | YES | YES |  |
| 61272 | Segou | 13.4000 | -6.1500 | 288 |  | YES | YES | YES |  |
| 61291 | Bamako | 12.5333 | -7.9500 | 380 |  | YES | YES | YES |  |
| 61297 | Sikasso | 11.3167 | -5.6833 | 415 |  | YES | YES | YES |  |

B.1.9 Niger: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 61024 | Agadez Aéro | 7.9833 | 16.9667 | 501 |  | YES | YES |  |  |
| 61017 | Bilma | 12.9167 | 18.6833 | 355 |  | YES |  |  |  |
| 61075 | Birni N'Konni | 5.2833 | 13.8333 | 272 |  | YES |  |  |  |
| 61085 | Diffa | 12.7833 | 13.4167 | 303 |  | YES | YES |  |  |
| 61053 | Dosso | 3.1833 | 13.0167 | 227 |  | YES |  |  |  |
| 61099 | Gaya | 3.4500 | 11.8833 | 202 |  | YES | YES |  |  |
| 61045 | Gouré | 10.3333 | 13.9833 | 443 |  | YES |  |  |  |
|  | Magaria | 8.9333 | 12.9833 | 402 |  | YES |  |  |  |
| 61096 | Mainé Soroa | 11.9833 | 13.2333 | 338 |  | YES |  |  |  |
| 61080 | Maradi Aéro | 7.0833 | 13.4667 | 372 |  | YES | YES |  |  |
| 61049 | N'Guigmi | 13.1167 | 14.2500 | 285 |  | YES | YES |  |  |
| 61052 | Niamey Aéro | 2.1667 | 13.4833 | 223 |  | YES | YES |  |  |
| 61043 | Tahoua Aéro | 5.2500 | 14.9000 | 390 |  |  | YES |  |  |
| 61036 | Tillabéry | 1.4500 | 14.2000 | 209 |  |  |  |  |  |
| 61090 | Zinder Aéro | 8.9833 | 13.7833 | 439 |  |  | YES |  |  |

B.1.10 Nigeria: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65125 | Abuja | 9.2500 | 7.0000 | 490 |  | YES | YES |  |  |
| 65232 | Akure | 7.2833 | 5.3000 | 350 |  | YES |  |  |  |
| 65264 | Calabar | 4.9667 | 8.3500 | 61.9 |  | YES |  |  |  |
| 65257 | Enugu | 6.4667 | 7.55 | 180 |  | YES |  |  |  |
| 65046 | Kano | 12.0500 | 8.5333 | 470 |  | YES | YES |  |  |
| 65203 | Lagos Roof | 6.4500 | 3.4000 | 14 |  | YES | YES |  |  |
| 65082 | Maiduguri | 11.8500 | 13.0833 | 324 |  | YES | YES |  |  |
| 65250 | Port-Harcourt | 4.8500 | 7.0167 | 10 |  | YES |  |  |  |
| 65010 | Sokoto | 13.0167 | 5.2500 | 305 |  | YES | YES |  |  |
| 65201 | Lagos/Ikeja | 6.5833 | 3.3333 | 40 |  |  |  |  |  |
|  | Jalingo |  |  |  |  | YES |  |  |  |
| 65055 | Bauchi | 10.2833 | 9.8167 | 609 |  |  | YES |  |  |
| 65112 | Bida | 9.1 | 6.0167 | 144 |  |  | YES |  |  |
| 65015 | Gusau | 12.1667 | 6.7 | 464 |  |  | YES |  |  |
| 65019 | Kaduna | 10.6 | 7.45 | 633 |  |  | YES |  |  |
| 65028 | Katsina | 13.0167 | 7.6833 | 520 |  |  | YES |  |  |
| 65123 | Minna | 9.6167 | 6.5333 | 243 |  |  | YES |  |  |
| 65064 | Nguru | 12.8833 | 10.4667 | 343 |  |  | YES |  |  |
| 65073 | Potiskum | 11.7 | 11.0333333333 | 415 |  |  | YES |  |  |
| 65108 | Shaki | 8.6667 | 3.3833 | 456 |  |  | YES |  |  |
| 65001 | Yelwa | 10.8833 | 4.7500 | 244 |  |  | YES |  |  |
| 65030 | Zaria | 11.1000 | 7.6833 | 641 |  |  | YES |  |  |
|  | Ilorin | 8.5300 | 4.5670 | 350 |  |  | YES |  |  |

B.1.11 Senegal: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 61627 | Linguère | 15.3800 | -15.1197 | 20 |  | YES | YES | YES |  |
| 61679 | Kaolack | 14.1300 | -16.0700 | 6 |  | YES | YES | YES |  |
| 61666 | Diourbel | 14.6500 | -16.2300 | 7 |  | YES | YES | YES |  |
| 61630 | Matam | 15.6300 | -13.2500 | 15 |  | YES | YES | YES |  |
| 61612 | Podor | 16.6497 | -14.9297 | 6 |  | YES | YES | YES |  |
| 61600 | Saint Louis | 16.0500 | -16.4497 | 2 |  | YES | YES | YES |  |
| 61641 | Dakar | 14.7300 | -17.5000 | 24 |  | YES | YES | YES |  |
| 61699 | Kédougou | 12.5700 | 12.2200 | 165 |  | YES | YES | YES |  |
| 61698 | Kolda | 12.8800 | 14.9700 | 8 |  | YES | YES | YES |  |
| 61687 | Tambacounda | 13.7697 | -13.6797 | 49 |  | YES | YES | YES |  |
| 61695 | Ziguinchor | 12.5500 | -16.2697 | 16 |  | YES | YES | YES |  |
|  | Mbour | 14.4166 | -16.9667 | 10 |  | YES | YES |  |  |
|  | Thiès | 14.83 | -17.11 | 18 |  |  | YES |  |  |
|  | Bakel | 14.9 | -12.46 | 32 |  |  | YES |  |  |
|  | Fatick | 14.36 | -16.59 | 4 |  |  | YES |  |  |
|  | Louga | 15.62 | -16.22 | 45 |  |  | YES |  |  |
|  | Ranerou | 15.3 | -13.97 | 36 |  |  | YES |  |  |

B.1.12 Sierra Leone: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Freetown | 8.4900 | 13.2300 | 26 |  | YES |  |  |  |
| 61881 | Bo | 7.9500 | -11.7667 | 100 |  | YES |  |  |  |
| 61866 | Bonthe | 7.5333 | -12.5000 | 7 |  | YES |  |  |  |
| 61891 | Daru | 7.9833 | -10.8500 | 185 |  | YES |  |  |  |
| 61886 | Kabala | 9.5833 | -11.5500 | 463 |  | YES |  |  |  |
| 61856 | Lungi | 8.6167 | -13.2000 | 25 |  | YES |  |  |  |
| 61873 | Makeni | 8.5500 | -12.0500 | 93 |  | YES |  |  |  |
| 61878 | Njala | 8.1000 | -12.1000 | 54 |  | YES |  |  |  |
| 61892 | Sefadu | 8.6500 | -10.9667 | 389 |  | YES |  |  |  |
| 61877 | Yele | 8.4167 | -11.8333 | 67 |  | YES |  |  |  |

B.1.13 Togo: List of stations for EPSgrams/ ENS Meteograms

| WMO ID | Station Name | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 65376 | Atakpame | 7.58 | 1.11 | 400 |  | YES | YES | YES |  |
| 65351 | Dapaong | 10.88 | 0.25 | 230 |  | YES | YES |  |  |
| 65357 | Kara-station | 9.55 | 1.16 | 342 |  | YES | YES | YES |  |
| 65378 | Kouma-Konda | 6.95 | 0.56 | 570 |  | YES | YES | YES |  |
| 65387 | Lome-Aero | 6.16 | 1.25 | 20 |  | YES | YES | YES |  |
| 65352 | Mango | 10.36 | 0.46 | 146 |  | YES | YES | YES |  |
| 65355 | Niamtougou | 9.80 | 1.08 | 462 |  | YES | YES | YES |  |
| 65361 | Sokode | 9.00 | 1.15 | 387 |  | YES | YES | YES |  |
| 65380 | Tabligbo | 6.58 | 1.50 | 40 |  | YES | YES | YES |  |
|  | Notse | 6.57 | 1.11 | 150 |  | YES |  |  |  |
|  | Anie-Mono | 7.80 | 1.29 | 160 |  | YES |  |  |  |
|  | Sotouboua | 8.56 | 0.97 | 380 |  |  |  |  |  |
|  | Pagouda | 9.97 | 1.31 | 430 |  |  |  |  |  |
|  | Blitta | 8.20 | 0.59 | 350 |  |  |  |  |  |
|  | Kpewa-Aledjo | 6.20 | 1.51 | 729 |  |  |  |  |  |
|  | Mandouri | 10.84 | 0.81 | 140 |  |  |  |  |  |
|  | Piya Hodo | 9.66 | 1.17 | 400 |  |  |  |  |  |
|  | Kante | 9.55 | 1.03 | 280 |  |  |  |  |  |
|  | Bassar | 9.15 | 0.49 | 315 |  |  |  |  |  |
|  | Guerin Kouka | 9.41 | 0.37 | 225 |  |  |  |  |  |
|  | Badou-Tomegbe | 7.31 | 0.36 | 257 |  |  |  |  |  |
|  | Elavagnon | 7.58 | 1.14 | 175 |  |  |  |  |  |

B.2: List of Stations for NWP based upper air sounding (Skew-T) provided by Global Centres

| Country | Stations (WMO ID) | Lat. | Lon. | Alt. (m) | Meteo France | ECMWF | NOAA/ NCEP | UKMO | Env. Canada |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BENIN | Cotonou | 2.3833 | 6.35 | 6.50 |  |  | YES |  |  |
|  | Parakou | 2.6154 | 9.3557 | 391.96 |  |  | YES |  |  |
|  | Kandi | 2.9333 | 11.1333 | 290.3 |  |  | YES |  |  |
| BURKINA FASO | Ouagadougou | 12.35°N | 1.52°W | 316 |  |  | YES |  |  |
|  | Fada n’gourma | 12.07°N | 0.35°E | 308 |  |  | YES |  |  |
|  | Bobo Dioulasso | 11.17°N | 4.30°W | 460 |  |  | YES |  |  |
| CABO VERDE | Mindelo | 16.8336 | -25.0547 | 20 |  |  | YES |  |  |
|  | Praia | 14.9411 | -23.4847 | 95 |  |  | YES |  |  |
|  | Sal | 16.7419 | -22.9489 | 54 |  |  | YES |  |  |
| THE GAMBIA | Basse | 13.3167 | 14.2167 | 4 |  |  | YES |  |  |
|  | Jenoi | 13.4667 | 15.5667 | 20 |  |  | YES |  |  |
|  | Yundum | 13.3500 | 16.6333 | 33 |  |  | YES |  |  |
| GHANA | Accra | 5.60 | - 0.17 | 67.7 |  |  | YES |  |  |
|  | Kumasi | 6.7169 | -1.5916 | 286.3 |  |  | YES |  |  |
|  | Tamale | 9.5539 | -0.8624 | 168.8 |  |  | YES |  |  |
| GUINEA | Conakry | 09°34’ N | 13°37’ W | 25.79 |  |  | YES |  |  |
|  | Kankan | 10°23’ N | 09°18’ W | 376.8 |  |  | YES |  |  |
|  | Koundara | 12°34’ N | 13°31’ W | 90 |  |  | YES |  |  |
| IVORY COAST | Bondoukou | 8.05°N | 2.78°W | 369 |  |  | YES |  |  |
|  | Man | 7.38°N | 7.52°W | 339 |  |  | YES |  |  |
|  | Korhogo | 9.42°N | 5.62°W | 381 |  |  | YES |  |  |
| MALI | Gao | 16.27 | -0.05 | 230 |  |  | YES |  |  |
|  | Kayes | 14.43 | -11.43 | 47 |  |  | YES |  |  |
|  | Mopti | 14.52 | -4.1 | 271 |  |  | YES |  |  |
|  | Bamako/ Sénou | 12.53 | -7.95 | 380 |  |  | YES |  |  |
|  | Sikasso | 11.35 | -5.68 | 375 |  |  | YES |  |  |
| NIGER | Agadez Aéro | 7.98 | 16.97 | 501 |  |  | YES |  |  |
|  | Diffa | 12.78 | 13.42 | 300 |  |  | YES |  |  |
|  | Niamey Aéro | 2.17 | 13.48 | 222 |  |  | YES |  |  |
| NIGERIA | Abuja | 9.2500 | 7.0000 |  |  |  | YES |  |  |
|  | Maiduguri | 11.8500 | 13.0833 |  |  |  | YES |  |  |
|  | Port-Harcourt | 4.8500 | 7.0167 |  |  |  | YES |  |  |
|  | Lagos/Ikeja | 6.5833 | 3.3333 | 40 |  |  |  |  |  |
| SNEGAL | Dakar | 14.7300 | -17.5000 | 24 |  |  | YES |  |  |
|  | Matam | 15.6300 | -13.2500 | 15 |  |  | YES |  |  |
|  | Saint Louis | 16.0500 | -16.4497 | 2 |  |  | YES |  |  |
| SIERRA LEONE | Bo | 7.9500 | -11.7667 | 100 |  |  | YES |  |  |
|  | Kabala | 9.5833 | -11.5500 | 463 |  |  | YES |  |  |
|  | Lungi | 8.6167 | -13.2000 | 25 |  |  | YES |  |  |
| TOGO | Atakpame | 7.58 | 1.11 | 400 |  |  | YES |  |  |
|  | Lome | 6.16 | 1.25 | 20 |  |  | YES |  |  |
|  | Kara | 9.55 | 1.16 | 342 |  |  | YES |  |  |

ANNEX C: Data and Products List issued from Regional Centres

C.1: Regional Specialized Meteorological Centre (RSMC) Dakar

| Deterministic Forecasts from global models that received at RSMC Dakar (present and near future) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Availability |  |  |  |
| All product is provided every 6-hourly out to 72 hours | ECMWF | GFS (NCEP) | ARPEGE | UKMO |
| Every 6 hours and 24 hours total accumulated precipitation | X | X | X | X |
| 2 meters temperature and dewpoint temperature | X | X | X | X |
| 2 meters relative humidity or specific humidity | X | X | X | X |
| 10 meters wind (speed and direction) | X | X | X | X |
| Pressure of mean sea level | X | X | X | X |
| Parameters: wind (streamlines and speed/direction), temperature, geopotential height, humidity Levels: 1000hPa, 925hPa, 850hPa, 700hPa, 500hPa, 300hPa, 200hPa, | X | X | X | X |
| Parameter: vorticity Level: 850hPa, 700hPa, 500hPa, 200hPa | X | X | X | X |
| Parameter: divergence Level: 850hPa, 700hPa, 200hPa | X | X | X | X |
| Parameter: vertical velocity Level: 850hPa, 700hPa, 600hPa, 500hPa | X | X | X | X |
| Parameter: potential temperature and equivalent potential temperature (Theta-E) Level: 850hPa, 700hPa | X | X | X | X |
| Parameter: Lifted index, K index, total totals index, CAPE, Showalter index, CIN (Convection inhibition), TC (Convection initiation temperature) etc. Level: Stability indices | x | X | x | x |
| Parameter: 1000-500hPa thickness | x | x | x | x |

| Deterministic Forecasts from high resolution regional models at RSMC Dakar (present and near future) |  |  |
| --- | --- | --- |
| All product is provided every 6-hourly out to 72 hours | Availability |  |
| Surface parameters | WRF | Unified Model ANACIM (project in future) |
| Every 6 hours and 24 hours total accumulated precipitation | YES | x |
| 2 meters temperature and dew point temperature | YES | x |
| 2 meters Max and Min temperature | YES | x |
| 2 meters relative humidity or specific humidity | YES | x |
| 10 meters wind (speed and direction) | YES | x |
| Pressure of mean sea level | YES | x |
| UPPER AIR PARAMETERS |  |  |
| Parameters: wind (streamlines and speed/direction), temperature, geopotential height, humidity Levels: 1000hPa, 925hPa, 850hPa, 700hPa, 500hPa, 300hPa, 200hPa, 200hPa | YES | x |
| Parameter: vorticity Level: 850hPa, 700hPa, 500hPa, 200hPa | YES | x |
| Parameter: divergence Level: 850hPa, 700hPa, 200hPa | YES | x |
| Parameter: vertical velocity Level: 850hPa, 700hPa, 600hPa, 500hPa | YES | x |
| Parameter: potential temperature and equivalent potential temperature (Theta-E) Level: 850hPa, 700hPa | YES | x |
| Parameter: Lifted index, K index, total totals index, CAPE, Showalter index, CIN (Convection inhibition), TC (Convection initiation temperature) etc. Level: Stability index | YES | x |
| Parameter: 1000-500hPa thickness | YES | x |
| Wave products (from WaveWatch3 model) |  |  |
| Parameter | Availability |  |
| Significant wave height | YES |  |
| Mean direction of swell | YES |  |
| Primary and secondary swell | YES |  |
| Wave period | YES |  |
| Wind speed | YES |  |
| Wind direction | YES |  |
| Sea wind | YES |  |
| SST | NO |  |

C.2 ACMAD

| Products to be made available from ACMAD (present and near future) |  |  |
| --- | --- | --- |
| List of Products | Availability Domain: Africa |  |
|  | UKMO global 17km All product is provided every 3-hourly out to 48 hours, 6-hourly out to-72 hours and 12 hourly out to 144 hours | WRF 9km All product is provided every 3-hourly out to 48 hours, 6-hourly out to 72 (project in future) |
| Mean sea level pressure | YES | YES |
| Geopotential height at 1000, 925, 900, 850, 700, 600, 500, 400, 300, 250, 200 hPa (11 levels) | YES | YES |
| Relative humidity at 2m and 11 upper levels | YES | YES |
| Horizontal wind (barb and stream line) at 10m and 11 upper levels | YES | YES |
| 10m Gust | YES | NO |
| Upper level max wind | YES | NO |
| Vertical velocity at 11 upper levels | YES | YES |
| Air temperature at 2m and 11 upper levels | YES | YES (2m Ta) No (11 upper levels) |
| Wet bulb potential temperature at 11 upper levels | YES | NO |
| 2m dew point | YES | NO |
| Cloud cover: convective, dynamic, low, medium, high, total, 3 different layers | YES | NO |
| Precipitations: convective rain rate, dynamic rain rate, 3hr/6hr accumulative, 24hr accumulative | YES | YES |
| Outgoing long wave radiation at the top of atmosphere | YES | YES |
| Meteo-France product : Rapid Developing Thunderstorm (15mn frequency) | N/A | N/A |

C.3 AGRHYMET

| Products to be made available from AGRHYMET (present and near future) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| List of Products | Availability |  |  |  |  |

C.4 DMN Morocco

| Products to be made available from DMN Mococco (present and near future) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| List of Products | Availability |  |  |  |  |

C.5 NIMET Nigeria

| Products to be made available from NIMET Nigeria (present and near future) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| List of Products | Availability |  |  |  |  |

ANNEX D: Template of RSMC Regional Guidance product

D.1	Regional Guidance to be issued by the RSMC Dakar for the NMHSs for Short Range Severe Weather Forecasting up to 48 Hours (for Day 1 and 2)

The daily Regional Guidance product  to be issued by the RSMC Dakar for guidance of the NMHSs for Short Range Severe Weather Forecasting up to 48 Hours (for Day 1 and Day 2) comprises five parts:

- Part A: Text; depiction of the expected evolution of the weather up to 48 h and comments about the more representative short range products that are used with reference to figures included in the part B or to charts clearly identified (model, parameter, level, forecast range).

- Part B: Figures; Charts or graphics coming essentially from deterministic models (global or LAM).

- Part C: The assessment of the degree of confidence of the forecast by the forecaster.

- Part D: Two geographical maps (Day 1 and Day 2, respectively) including the boundaries of the countries with contours identifying the areas which are likely to be hit by the severe weather event.

- Part E: Two tables (for Day1 and Day 2, respectively), summarizing the risk of severe weather as assessed by the RSMC Dakar based on its degree of confidence as proposed below. In order to provide more information about the geographical location of the severe event the following convention is adopted when filling in the cells: X for the whole country, N for the northern part, S for the southern part, W for the western part and E for the eastern part. Similarly, NE for the northeastern part and SW for the southwestern part etc.

The table below is shown as an example and it has to be defined by the RSMC Dakar. The separation of the evaluation of the risk into four categories (no risk, low risk, medium risk and high risk) are also given as example.

| Country | Severe Weather type | No risk | Low risk | Medium risk | High risk |
| --- | --- | --- | --- | --- | --- |
| Benin | Heavy rain > 50mm/12h |  | X |  |  |
|  | Heavy rain > 100mm/24h |  |  |  |  |
|  | Strong Winds ≥40Km/h (20 knots) |  |  |  |  |
|  | Strong Winds ≥60Km/h (30 knots) |  |  |  |  |
| Burkina Faso | Heavy rain > 50mm/12h | NW |  |  |  |
|  | Heavy rain > 100mm/24h |  |  |  | SE |
|  | Strong Winds ≥40Km/h (20 knots) |  |  |  |  |
|  | Strong Winds ≥60Km/h (30 knots) |  | SW |  |  |
| Cabo Verdi |  |  |  |  |  |
| more country names can be added |  |  |  |  |  |

D.2	Regional Guidance to be issued by the RSMC Dakar for the NMHSs for Medium Range Severe Weather Outlook (for Days D+3, D+4 and D+5)

The daily Regional Guidance product to be issued by RSMC for guidance of the NMHSs for Medium Range Severe Weather Outlook (for Days D+3, D+4 and D+5) comprises five parts:

- Part A: Text; depiction of the expected evolution of the weather for days 3, day 4 and day 5 and comments about the more representative medium range products that are used with reference to figures included in the part B or to graphics clearly identified (EPS charts or meteograms).

- Part B: Figures; Charts or graphics coming essentially from Ensemble Prediction Systems (EPS).

- Part C: The assessment of the degree of confidence of the forecast by the forecaster.

- Part D: Three geographical maps (for Day 3, Day 4 and Day 5, respectively) including the boundaries of the countries with contours identifying the probabilities areas for the occurrence of the weather event.

- Part E: Three tables (for day 3, day 4 and day 5, respectively), summarizing the probabilities of precipitation and wind higher than a given threshold by the RSMC Dakar as proposed below. In order to provide more detailed information about the geographical location of probabilities the following convention is adopted when filling in the cells: X for the whole country, N for the northern part, S for the southern part, W for the western part and E for the eastern part. Similarly, NE for the northeastern part and SW for the southwestern part etc.

The table below is shown as an example and it has to be defined by the RSMC Dakar (number of columns, lower and upper limits of probabilities etc.)

| Country | Severe Weather type and threshold value | Low Probability | Medium Probability | High Probability |
| --- | --- | --- | --- | --- |
| Benin | Heavy rain > 50mm/12h |  |  |  |
|  | Heavy rain > 100mm/24h | X |  |  |
|  | Strong Winds ≥40Km/h (20 knots) |  |  |  |
|  | Strong Winds ≥60Km/h (30 knots) | SE |  |  |
| Burkina Faso | Heavy rain > 50mm/12h |  | NW |  |
|  | Heavy rain > 100mm/24h |  |  |  |
|  | Strong Winds ≥40Km/h (20 knots) |  |  | SW |
|  | Strong Winds ≥60Km/h (30 knots) |  |  |  |
| Cabo Verdi |  |  |  |  |
| Please add more country names |  |  |  |  |

ANNEX E: Template of SWFDP Quarterly Progress Report (SWFDP-West Africa)

Important elements & information to be reported in the Quarterly Progress Report (to be submitted on-line through SWFDP database)

- Reporting Period (Start date to end date)

- Severe events (e.g. heavy rainfall, strong winds, high waves, flooding etc.)

- Reporting period highlights (e.g. duration and amount of rainfall, impact of rainfall and/or strong wind and high waves, affected areas, damages (if any), coordination with disaster management offices etc.)

- Clients (e.g. Disaster Management Offices, media, humanitarian organizations etc. New clients can also be added)

- Client feedback (e.g. adequacy and effectiveness of the warning and how it was used etc.)

- Desired products (e.g. NMHS may propose a demand for additional product(s) from global and/or regional centres if already not available etc.)

- Forecast Period and Area (to provide information about area of responsibility of an NMHS and the period for which NMHS issues forecast etc.)

- Dissemination channels (e.g. TV, radio, mobile SMS etc. New channel can also added)

- Observing Systems (e.g. basic synoptic network, AWS network, radar and satellite information receiving stations etc.)

- Workshop (to provide title, duration and summary outcome of the training workshops arranged for the forecasters, emergency managers, media, school officials, general public etc. during the reporting period)

- Product usage (to select various products which are available from participating global and regional centres and are used in making forecasts at national level etc.)

- Local forecasting tools (to provide information about the existing forecasting tools used at the NMHS and any new forecasting tool implemented at the NMHS etc.)

- Resources (to provide information about the budget of NMHS and the number of forecasters and observers working in NMHS etc.)

- Case Studies (to provide title and description of case studies related to the severe event(s) observed during the reporting period, key findings of the study etc.)

- Related projects (to provide information about the on-going and new related projects etc.)

- PROJECT EVALUATION AGAINST SWFDP GOALS

| SWFDP GOAL | COMMENTS ON PROGRESS TOWARDS EACH GOAL | Questions to help you with an answer for each box |
| --- | --- | --- |
| To improve the ability of NMHSs to forecast severe weather events |  | How did the products on the RSMC New Delhi help you make better severe weather forecasts and warnings? |
| To improve the lead time of alerting these events |  | How much earlier do you issue severe weather forecasts & warnings now compared to before? |
| To improve the interaction of NMHSs with Disaster Management and Civil Protection authorities (DMCPAs), the media, and the public, before, during and after severe weather events |  | Comment on any interactions with your disaster agency, media agencies and the public. Please indicate if there hasn't been any interaction since the last repor,. |
| To identify gaps and areas for improvements |  | What are the weaknesses in your forecast system? |
| To improve the skill of products from Global Centres through feedback from NMHSs |  | What weaknesses have you found in the products from RSMC, New Delhi, JMA, NCEP, UKMO, ECMWFetc.? |

- EVALUATION OF PWS COMPONENT

| Users | Question | Answer | Comments |
| --- | --- | --- | --- |
| Public | Any feedback from the public? | Yes or No | If Yes, please give details. |
|  | Any public reaction when the warnings were heard or received? | Yes or No | If Yes, please give details. |
|  | Were there any difficulties in obtaining feedback? | Yes or No | If Yes, please give details. |
| Disaster Management | Any feedback from disaster management authorities about the timeliness and/or usefulness of the warnings | Yes or No | If Yes, please give details. |
|  | Were safety messages and/or call to action statements issued by the disaster management authority in agreement with your forecasts & warnings? | Yes or No | If Yes, please give details. |
| Media | Any feedback from the Media? | Yes or No | If Yes, please give details. |
|  | How did your relationship with the Media work in getting warnings delivered? | Yes or No | If Yes, please give details. |
|  | Were their difficulties in working with the Media? | Yes or No | If Yes, please give details. |

- SUMMARY (general comments, challenges, etc)

- CASE STUDY (PowerPoint presentation to include guidance products (RSMC and NWP), satellite imagery, warnings issued, impact evidence etc.)

Case studies for each severe weather event DON'T need to be completed at the same time as the rest of this report.

Comment: Case studies don't need to be long. What's important is the learning experience that you gain from actually doing the case study.

- Severe Event Evaluation 
(See attached example of Severe Weather Event Evaluation Form)

Annex F: TEMPLATE OF A SEVERE WEATHER EVENT EVALUATION FORM

Severe Weather Event Evaluation form with forecast/warnings verification

MS Excel spreadsheet template to be prepared and completed by participating NMHSs/NMCs

Note: The proposed evaluation form is given as template for consideration by NMHSs/NMCs. It should be reviewed, formatted and develop further (e.g. using MS Excel spreadsheet) to allow NMHSs/NMCs to evaluate the performance of the RFSF Severe Weather Forecasting Guidance and as well as the efficiency of the NMHS warning system.  It must be completed by a NMHS/NMC in both of the following cases:

- a severe weather event has been observed; and

- a severe weather event has been forecast.

The evaluation form should document the characteristics of the severe weather event (whether observed or forecast) and allow to evaluate the efficiency of the forecasts given by the RFSF Severe Weather Forecasting Daily Guidance as well as the performance of the warnings issued by the NMHS. Therefore it should include the three following sections.

Section A – Identification of the severe weather event:

- NMHS/NMC concerned;

- number of the event;

- type of event;

- region affected.

Section B – Information about the observed weather event:

- start and end times of the severe weather event;

- maximum observed value of the characteristic parameter;

- assessment about the efficiency of the warning given the DMCPA;

- information from the end-users (number of interventions, casualties, damages, usefulness of the warning ).

Section C – Information about the forecast and warning issued from the NMHS:

- lead-time of the warning;

	start and end time of the severe weather event according to the forecaster’s assessment;

	level of risk as indicated in the RFSF Severe Weather Forecasting Daily Guidance;

- probabilities of medium-range in the RFSF Severe Weather Forecasting Daily Guidance;

- usefulness of the various products (RFSF Guidance, various models);

- comments including information on usefulness and applicability of used tools.

How to use this evaluation form to evaluate the performance of warnings ?

The common way to evaluate the performance of a warning system is based on the  2 x 2  contingency table matrix including the number of justified warnings (“hits”) “a”, the number of missed severe events “b” and the number of false alarms “c”. The POD index (Probability of Detection) is defined as the ratio of the number of hits by the total number of severe events, i.e., a/(a+b) ; the FAR (False Alarm Ratio) is defined as the ratio of the number of false alarms by the number warnings issued, i.e., c/(a+c).The information contained in the proposed evaluation form enables to computes the performance indicators of the warning issued by the NMHS as long as the assessment of the DMCPA (in section C) is correctly taken into consideration.

A template of an evaluation form is provided in the following pages.  The evaluation form is to be filled by the NMHSs/NMCs (preferably by a forecaster or manager of the forecasting unit) participating to the SWFDP regional subproject.  This template can be modified with respect to the products selected for preparing the severe weather forecasts and warnings.

It is important that the design of the evaluation form be adapted to allow the data and information to be easily gathered and transformed into a tabular form.  Avoid unnecessary and repetitive typing, and as much as possible to encourage and allow reliable creation and maintenance of the dataset that is needed to analyze and evaluate the performance indicators.

| SEVERE WEATHER EVALUATION FORM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (Page 1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INSTRUCTIONS: | : |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. This form must be filled in whenever: |  |  |  |  | (1) Severe weather is observed (Sections A and B) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (2) A warning has been issued to DM/CPA (Sections A and C) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Email the completed document to RFSF Martinique, WMO and other agreed recipients |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To standardize please put the title “SWFDP Evaluation Form” in the title list of the email |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. IDENTIFICATION OF THE SEVERE EVENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NMHS: |  |  |  |  |  |  | Alphabetic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Region affected: |  |  |  |  |  |  | Alphabetic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Event Number: |  |  |  |  |  |  | Numeric |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of event: |  |  |  |  |  |  | Numeric |  |  |  |  |  |  |  |  | (put the right number in the cell) |  |  |  |  |  |  |  |  |  |  |
| 1: Heavy Precipitation | (indicate the most significant phenomenon, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: Strong wind | either heavy precipitation or strong wind) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Severe convection |  |  |  |  |  |  | Numeric |  |  |  |  |  |  |  |  | (put 1 if extreme phenomena are the consequence of severe convection or 0 otherwise) |  |  |  |  |  |  |  |  |  |  |
| B. SEVERE WEATHER OBSERVED (to be completed even if no severe weather has been forecast) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | JJ |  |  | MM |  |  |  |  | DD |  |  |  |  |  | HH |  |  | MM |  |  |  |  |  |
|  | Start of the event: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | at |  |  |  |  |  |  |  |  | UTC |  |  |
|  | End of the event: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | at |  |  |  |  |  |  |  |  | UTC |  |  |
| Max. observed value: |  |  |  |  |  |  | Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Numeric |  |  |  | Alphabetic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (According to the event: accumulated precipitation, gusts, other significant parameter) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Information from the end-users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| short text explaining the consequences and possibly some figures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (number of interventions, casualties, damages, usefulness of the warning ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SEVERE WEATHER EVALUATION FORM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | (Page 2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C. SEVERE WEATHER FORECAST (to be completed even if severe weather did not occur) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | JJ |  | MM |  |  |  | DD |  |  |  |  |  | HH |  |  | MM |  |  |  |  |  |
| Time of the warning | toward DMCPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | at |  |  |  |  |  |  |  | UTC |  |  |
| Start of the event; | forecaster assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | at |  |  |  |  |  |  |  | UTC |  |  |
| End of the event; | forecaster assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | at |  |  |  |  |  |  |  | UTC |  |  |
| Usefulness of the warning (feedback from the DMCPA) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| check in the chosen cell |  |  |  |  | Lack of warning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | False alarm warning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Late warning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Useful warning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Level of risk as appreciated by RSMC |  |  |  |  | (put 1 in the chosen cell) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | No |  |  |  |  |  | Low |  |  |  |  |  |  | Med. |  |  |  |  |  | High |  |  |
| Level of risk | 1 day before: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Level of risk | 2 days before: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probabilities of medium range outlooks as appreciated by RSMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probability | 3 days before: |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probability | 4 days before: |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Probability | 5 days before: |  |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mark for usefulness of products (put 1 in the chosen cell) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KEY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A = Very useful (basis of the warning) |  |  |  | RFSF Guidance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B = Useful (aided warning confidence) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C = Neutral (not useful) |  |  |  |  |  |  |  | NWP |  |  |  |  |  | EPS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D = Negative (misleading) |  |  |  | Meteo France |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X = Not used |  |  |  | NCEP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | UKMO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | ECMWF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | NWP LAM (RFSF) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comments including information on usefulness and applicability of used tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

SEVERE WEATHER EVALUATION FORM

(Page 3)

Quarterly Evaluation Table (to be fulfilled based on the Severe Weather Event Evaluation Form)

A row has to be filled in this table whenever a severe weather event is observed or a warning is issued toward DMCPA.

Annex G:  USER ASSESSMENT QUESTIONNAIRE

## G.1 Evaluation Questionnaire for the Public

Q1.	Do you get the warnings and forecasts issued by the National Meteorological Service?

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Do the warnings and forecasts arrive early enough for you to take any actions?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How Do you get the forecasts and warnings? (Can choose more than one)

| Radio | TV |  | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ |  | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Do you understand the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	Do you take any action in response to the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what did you do?

Q6.	The warning was useful to protect your (Can choose more than one)

| family | home | boat | farm | animals | other(s) |
| --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q7.	Are warnings issued by the National Meteorological Service correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q8.	Are forecasts issued by the National Meteorological Service correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Name: 	   Date:

## G.2 Evaluation Questionnaire for Disaster Management (DMCPA)

Q1.	Did you get the warnings for the severe weather events in the period…to….? (Specify)

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Did the warnings arrive early enough for you to take the necessary actions according to your specified responsibilities?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How did you get the warnings? (Can choose more than one)

| Radio | TV | Fax | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Did you understand the warnings?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	Did you take any action in response to the warnings?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what did you do?

Q6.	In your opinion were the warnings correct?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q7.	Do you have any suggestions on how to improve the warning process, including dissemination methods, format, language etc.

Name & designation: 	   Date:

## G.3 Evaluation Questionnaire for Media

Q1.	Do you get the warnings for the severe weather events and forecasts from the National Meteorological Service?

| Yes | No |
| --- | --- |
| □ | □ |

Q2.	Do the warnings and forecasts arrive early enough for you to take the necessary actions according to your specified responsibilities?

| Yes | No |
| --- | --- |
| □ | □ |

Q3.	How do you get the warnings and forecasts? (Can choose more than one)

| Radio | TV | Fax | Internet | Telephone | Local radio network | Other(s) |
| --- | --- | --- | --- | --- | --- | --- |
| □ | □ | □ | □ | □ | □ | □ |

If other(s), please specify:

Q4.	Do you understand the warnings and forecasts?

| Yes | No |
| --- | --- |
| □ | □ |

Q5.	 Are the language and format clear enough for you?

| Yes | No |
| --- | --- |
| □ | □ |

Q6.	Do you take any action in response to the warnings and forecast you receive?

| Yes | No |
| --- | --- |
| □ | □ |

If yes, what do you do?

Q7.	In your opinion are the warnings and forecasts accurate?

| Yes | No | More or less |
| --- | --- | --- |
| □ | □ | □ |

Q8.	Do you have any suggestions on how to improve the warning and forecast process, including dissemination methods, format, language etc.

Name and designation: 	   Date:

Annex H

| Activities | 17 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | Budget (in CHF) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| 1. Preparation by the Centres including NWP products and further development of project website (RSMC Dakar web portal) to start demonstration phase in Q3 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000 |
| 1. Meetings of RSMT of SWFDP- Western Africa to review the project progress and update Regional Subproject Implementation Plan (RSIP) including preparation, execution and evaluation of demonstration phase |  |  |  |  |  |  |  |  |  |  |  |  |  | 90,000 |
| 3. SWFDP Training Workshops on Severe Weather Forecasting and Delivery of Warning Services (to be held every year) |  |  |  |  |  |  |  |  |  |  |  |  |  | 240,000 |
| 4. RSMC Dakar Training Desk (for 2 forecasters/PWS staff from the NMHSs of identified countries in Western Africa and 1 expert from a regional technical support centre) (to organized every year) |  |  |  |  |  |  |  |  |  |  |  |  |  | 60,000 |
| 5. In-country visits (2-3 countries per year) to gather information on operational weather forecasting and delivery of services; and negotiations with national project leaders |  |  |  |  |  |  |  |  |  |  |  |  |  | 60,000 |
| 6. Based on mission assessment reports, develop national implementation plans (IPs) for visited countries and reach agreement with the PRs. |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000 |
| 7. Support participants from SWFDP countries at the ECMWF (UK) annual training |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000 |
| 8. Support participants from SWFDP countries to attend trainings at global centres (e.g. MeteoFrance, NOAA/NCEP, DWD etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000 |
| 9. Public weather services (PWS) activities to be implemented on the basis of national needs including to introduce and strengthen impact based forecasts and risk based warnings (e.g. NMHS engagement with users, TV weather, radio, Mobile App. Websites, implementation of Common Alerting Protocol (CAP), impact based forecasts and risk based warnings etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  | 150,000 |
| 10. Submission of progress reports by NMHSs and continuous monitoring/ tracking of the subproject (including through RSMT as mentioned above) |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| 11. Evaluation reports |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  | Sub/total (2018): 240,000 |  |  |  | Sub-total (2019): 230,000 |  |  |  | Sub-total (2020): 230,000 |  |  |  |  |
|  |  | Total for 3 years (2018-2020) |  |  |  |  |  |  |  |  |  |  |  | 700,000 |

Tentative Activity Plan for SWFDP implementation in Western Africa