# NOTES:

(1)	Aviation Codes require ICAO coordination and approval, except for AMDAR.

(2)	SAREP and RADOB require coordination by the ESCAP/WMO Typhoon Committee.

(3)	For category 5, codes need to be reviewed in order to decide whether or not they should be migrated to BUFR/CREX.

(4)	Codes in category 6 are not to be migrated.

(5)	All dates above are meant as "not later than".  However, Members and Organizations are encouraged to start experimental exchange, and, if all relevant conditions (see below) are satisfied, to start operational exchange as soon as possible.

- Start of experimental exchange means: data will be made available in BUFR (CREX) but not operationally, i.e. in addition to the current alphanumeric codes, which are still operational.

- Start of operational exchange means: data will be made available in BUFR (CREX) whereby some (but not all) Members rely on them operationally.  Still the current alphanumeric codes will be distributed (parallel distribution).

- Migration complete means: at this date the BUFR (CREX) exchange becomes the standard WMO practice. Parallel distribution of TAC and TDCF may continue and will be discontinued within a zone in accordance with step-by-step arrangements made between the NMHS concerned.

- Parallel distribution of TAC and TDCF stopped means: at this date parallel TAC and TDCF distribution is terminated. For archiving purposes and at places where BUFR (CREX) exchange still causes problems the alphanumeric codes may be used only for the exchange of data between two NMHSs.

Relevant conditions to be satisfied before experimental exchange may start:

- Corresponding BUFR/CREX-tables and templates are available;

- Training of concerned testing parties has been completed;

- Required software of testing parties (encoding, decoding, viewing) is implemented;

Relevant conditions to be satisfied before operational exchange may start:

- Corresponding BUFR/CREX-tables and templates are fully validated;

- Training of all concerned parties has been completed;

Relevant conditions to be satisfied before TAC ceasing may end:

- All required software (encoding, decoding, viewing) is operational.