| WMO Regional Association I |  |  |
| --- | --- | --- |
| First RA I WIS Implementation Plan Workshop Pretoria, 22-26 September 2014 |  | RA-I-Imp-2014/Doc 5 |
|  |  | 23 Sept 2014 |

Summary of WIS contents of RA-I WIGOS Sub-Regional Plans

| N° |  | Activité |  |  |  | Réalisations attendues |  |  |  | Délais |  |  | Responsabilité |  | Coût estimatif (2012-2015) en milliers de CHF |  |  |  | Risques possibles |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Management of WIGOS Implementation in Central Africa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N1.3 N | Mobilize needed resources to support the WIGOS and WIS implementation in the North Africa |  |  |  |  | Appropriate resources available from Secretariat, North African stakeholders and Members |  |  |  | On going |  |  | RA-I/TT-WIGOS/NA; PRs |  |  |  |  |  |  |
| N1.4 SR N | Monitor and evaluate (M&E) WIGOS and WIS Sub-Regional implementation activities |  |  |  |  | Annual M&E reports; Problems are identified and sorted out timely |  |  |  | On going |  |  | RA-I/TT-WIGOS/NA; WMO Secretariat; Regional Office |  |  |  |  |  |  |
| N1.5 N | Develop National WIGOS and WIS Implementation Plans (N-WIPs) |  |  |  |  | N-WIPs developed |  |  |  | 2014 onwards |  |  | Members |  |  |  |  |  |  |
| 2. Collaboration with the WMO co-sponsored observing systems and international partner organizations and programmes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C2.3 SRN |  |  | Establish liaison with ASECNA re its services relevant to WIGOS WIS |  |  |  | ASECNA component of WIGOS WIS sub regional implementation plan |  | 2014 |  |  |  | WMO need to meet with ASECNA in 2013 to define WIS applications and responsibilities. Sub-regional WIGOS Working Body to oversee liaison and contribution to plan |  |  |  |  |  |  |
| W2.3 SRN |  |  | Establish liaison with ASECNA re its services relevant to WIGOS WIS |  |  |  | ASECNA component of WIGOS WIS sub regional implementation plan |  | 2014 |  |  |  | WMO need to meet with ASECNA in 2013 to define WIS applications and responsibilities. Sub-regional WIGOS Working Body to oversee liaison and contribution to plan |  |  |  |  |  |  |
| 3. Design, planning and optimized evolution of WIGOS and its sub-regional and national component observing components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N3.5 SR |  |  | Review regional communications practices and procedures and update GTS and WIS topology mappings |  |  | Updated Maps for Manual on GTS Vol. II, and WIS communications map |  |  |  | 2014 onwards |  |  | WIS NFPs with Sub-regional representatives in TT-WIGOS (Secretariat database) |  |  |  |  |  |  |
| C3.6. SR |  |  | Review regional communications practices and procedures and update GTS and WIS topology mappings |  |  | Updated Maps for Manual on GTS vol II, and WIS communications map |  |  |  | 2014 onwards |  |  | WIS FPs with Sub-regional representatives in TT-WIGOS (Secretariat database) |  |  |  |  |  |  |
| W3.6. SR |  |  | Review regional communications practices and procedures and update GTS and WIS topology mappings |  |  | Updated Maps for Manual on GTS vol II, and WIS communications map |  |  |  | 2014 onwards |  |  | WIS FPs with Sub-regional representatives in TT-WIGOS (Secretariat database) |  |  |  |  |  |  |
| 4. Observing System Operation and Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Quality Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Standardization, System Interoperability and Data Compatibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N6.3 SR N |  |  | Complete migration to TDCF in the North Africa |  |  |  | Migration completed by all Members |  |  |  | 2014 |  |  | Members |  |  |  |  |  |
| E6.4 SR N |  |  | Achieve migration to TDCF in East Africa |  |  |  | Migration completed by all Members |  |  |  | 2013-2014 |  |  | Members |  |  |  |  |  |
| C6.4 SR N |  |  | Achieve migration to TDCF in the Central Africa |  |  |  | Migration completed by all Members |  |  |  | 2013-2014 |  |  | Members, ASECNA | TAC to TCDF- New equipment should be compliant |  |  |  |  |
| S6.4 SR N |  |  | Achieve migration to TDCF in the Southern Africa |  |  |  | Migration completed by all Members |  |  |  | 2013-2014 |  |  | Members |  |  |  |  |  |
| W6.4 SR N |  |  | Achieve migration to TDCF in the Western Africa |  |  |  | Migration completed by all Members |  |  |  | 2013-2014 |  |  | Members, ASECNA | TAC to TCDF- New equipment should be compliant |  |  |  |  |
| 7. The WIGOS Operational Information Resource (WIR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Data discovery, delivery and archival |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C8.1 SR N |  |  |  | Members to designate relevant contributing centres as WIS DCPCs or NCs; Ensure that Members establish WIS NCs |  |  | Each Member has at least one designated principal GISC and a backup GISC; Relevant Members designated as DCPCs; All Members’ centres compatible with WIS |  |  |  |  | 2014 - 2015 |  | Members’ WIS FP WMO Secretariat |  |  |  |  |  |
| C8.2 N |  |  |  | Members to share data and discovery metadata via WIS, including from institutions other than NMHSs |  |  | Data and discovery metadata, including from institutions other than NMHSs, shared through WIS |  |  |  |  | 2015 onwards |  | Members WIS FP; WMO Secretariat |  |  |  |  |  |
| C8.3 |  |  |  | WIS FP to ensure WIS Discovery MD is created and publish |  |  | Discovery metadata sent to principal GISC (Morocco) |  |  |  |  | 2014-2015 And on-going |  | WIS and WIGOS FPs. | WIS - New equipment should be compliant |  |  |  | WIS FP to ensure WIS Discovery MD is created and publish |
| E8.1 SR N |  |  |  | Encourage Members to be designated as WIS DCPCs or GISCs; Ensure that Members establish WIS NCs |  |  | One Member designated as GISC; Relevant Members designated as DCPCs; All Members’ NCs compatible with WIS |  |  |  |  | 2013 - 2015 |  | Members; WMO Secretariat |  |  |  |  |  |
| E8.2 N |  |  |  | Encourage Members to share data and metadata via WIS, including from institutions other than NMHSs |  |  | Data and metadata, including from institutions other than NMHSs, shared through WIS |  |  |  |  | 2015 onwards |  | Members; WMO Secretariat |  |  |  |  |  |
| N8.1 SR N |  |  |  | 1) Encourage Members to be designated as WIS DCPCs 2) Ensure that Members establish WIS NCs |  |  | 1) Relevant Centres designated as DCPCs; 2) All NCs compatible with WIS |  |  |  |  | 2015 onwards |  | RA-I/TT-WIGOS/NA; Members; WMO Secretariat |  |  |  |  |  |
| N8.2 N |  |  |  | Encourage Members to share data and metadata via WIS, including from institutions other than NMHSs |  |  | Data and metadata, including from institutions other than NMHSs, shared through WIS |  |  |  |  | 2015 onwards |  | RA-I/TT-WIGOS/NA; Members; WMO Secretariat |  |  |  |  |  |
| S8.1 SR N |  |  |  | Encourage Members to be designated as WIS DCPCs or GISCs; Ensure that Members establish WIS NCs |  |  | One Member designated as GISC; Relevant Members designated as DCPCs; All Members’ NCs compatible with WIS |  |  |  |  | 2013 - 2015 |  | Members; WMO Secretariat |  |  |  |  |  |
| S8.2 N |  |  |  | Encourage Members to share data and metadata via WIS, including from institutions other than NMHSs |  |  | Data and metadata, including from institutions other than NMHSs, shared through WIS |  |  |  |  | 2015 onwards |  | Members; WMO Secretariat |  |  |  |  |  |
| W8.1 SR N |  |  |  | Members to designate relevant contributing centres as WIS DCPCs or NCs; Ensure that Members establish WIS NCs |  |  | Each Member has at least one designated principal GISC and a backup GISC; Relevant Members designated as DCPCs; All Members’ centres compatible with WIS |  |  |  |  | 2014 - 2015 |  | Members’ WIS FP WMO Secretariat |  |  |  |  |  |
| W8.2 N |  |  |  | Members to share data and discovery metadata via WIS, including from institutions other than NMHSs |  |  | Data and discovery metadata, including from institutions other than NMHSs, shared through WIS |  |  |  |  | 2015 onwards |  | Members WIS FP; WMO Secretariat |  |  |  |  |  |
| W8.3 |  |  |  | WIS FP to ensure WIS Discovery MD is created and publish |  |  | Discovery metadata sent to principal GISC |  |  |  |  | 2014-2015 And on-going |  | WIS and WIGOS FPs. | WIS - New equipment should be compliant |  |  |  | WIS FP to ensure WIS Discovery MD is created and publish |
| 9. Renforcement des capacités |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N9.1 SR |  |  |  | Provide assistance to Members to establish/enhance institutional mandates and policies that enable effective implementation, operation and management of WIGOS observing systems and WIS by Members |  |  | Institutional mandates and policies for effective implementation, operation and management of WIGOS observing systems and WIS by Members are established/enhanced |  |  | On going |  |  |  | WMO Secretariat; RA-I/TT-WIGOS/NA; PRs |  |  |  |  |  |
| N9.2 SR |  |  |  | Provide assistance to Members to fill the existing gaps in the design, operation and maintenance of WIGOS component observing systems and WIS, including both the infrastructure and human capacities development |  |  | Assistance provided; |  |  | 2014 ongoing |  |  |  | RA-I/TT-WIGOS/NA; WIS NFP; WMO Secretariat Members, in collaboration with regional partners and TCs |  |  |  |  |  |
| N9.3 SR N |  |  |  | Provide assistance to Members to generate WIGOS and WIS metadata required for WIR |  |  | WIGOS and WIS metadata available in WIR and GISC |  |  | 2015 ongoing |  |  |  | RA-I/TT-WIGOS/NA; WIS NFP; Members; WMO Secretariat |  |  |  |  |  |
| 10. Communication and outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N10.1 SR N |  |  |  |  | Utilise the WIGOS and WIS communications and outreach material provided by WIGOS-PO to raise awareness and commitment to WIGOS and WIS in the North Africa |  |  | 1) More communications & Outreach material available and used; 2) Key stakeholders committed to WIGOS and WIS in the North Africa is raised |  | 2014 |  |  |  | RA-I/TT-WIGOS/NA; WMO Secretariat |  |  |  |  |  |
| C10.3 SR N |  |  |  |  | Communicate WIGOS and WIS benefits using all possibilities, such as brochures, COPs, AMCOMET |  |  | Workshops and side events organized at sub-regional and national levels for promoting WIGOS and WIS |  | 2013 onwards |  |  |  | Sub-regional WIGOS Working Body; Members with support of WMO Secretariat |  |  |  |  |  |
| N10.3 SR N |  |  |  |  | Communicate WIGOS and WIS benefits using all possibilities, such as brochures, COPs, AMCOMET |  |  | Workshops and side events organized at sub-regional and national levels for promoting WIGOS and WIS |  | 2014 onwards |  |  |  | Sub-regional WIGOS Working Body; Members with support of WMO Secretariat |  |  |  |  |  |
| N10.4 N |  |  |  |  | Encourage partners to communicate benefits achieved through the WIGOS and WIS implementation |  |  | Benefits communicated |  | On going |  |  |  | Members |  |  |  |  |  |
| W10.3 SR N |  |  |  |  | Communicate WIGOS and WIS benefits using all possibilities, such as brochures, COPs, AMCOMET |  |  | Workshops and side events organized at sub-regional and national levels for promoting WIGOS and WIS |  | 2013 onwards |  |  |  | Sub-regional WIGOS Working Body; Members with support of WMO Secretariat |  |  |  |  |  |
| W10.4 N |  |  |  |  | Encourage partners to communicate benefits achieved through the WIGOS/WIS implementation |  |  | Benefits provided to WIGOS-PO and WIS Branch |  | 2015 onwards |  |  |  | Members |  |  |  |  |  |

--------------------