## Sheet1
Action Number | Decision/recommendation/ action | Task Status | Beijing | Brasilia | Casablanca | Exeter | Jeddah | Melbourne | Moscow | New Delhi | Offenbach | Pretoria | Seoul | Tehran | Tokyo | Toulouse | Washington | Task Status
14/1-1 | Decision: Endorsed the core WIS competencies and the associated output documents on competencies and learning guide: [http://wis.wmo.int/file=687] [http://wis.wmo.int/file=689]. | Open | Take into account | Noted. | Noted, and will be considered for the training session planned in 2015. | Noted | Noted, considered for training, etc. | Noted | Noted | taken into account | Noted, considered for training, etc. |  | Noted |  | Noted, take into account | take into account | Noted | The WIS competencies and learning guide were approved by CBS to be considered by Cg 17 to go into the technical regulations alongside other programmes’ competencies, and into relevant WIS documents.
14/1-2 | Action: a) Encouraged all GISCs to start to utilize the competency and learning guide in their capacity development and training activities. b) All GISCs should aim at ensuring centres in their area of responsibility have staff equipped with appropriate competencies and thus maximize their ability to support and benefit from WIS | Open | 2014.8, workshop with Pakistan 2014.6, workshop with for Kazakhstan 2014.2, workshop with for Tajikistan 2013.12, workshop with for Nepal 2013.12, workshop with for Mongolia 2013.12, workshop with for Pyongyang | Small talk to Region III representatives during the RA-III meeting in Asuncion, Paraguay. | Noted and will be considered in GISC Casablanca action plan for 2015 | A workshop organized in Toulouse, June 5th-7th 2013 in cooperation with Météo-France. We have had discussions with the NCs in our area of responsibility for Metadata update. | A workshop organized in Jeddah May 19-20 2014. Some WIS specialists from area of responsibility attended the workshop.A workshop organized in Jeddah May 19-20 2014. Some WIS specialists from area of responsibility attended the workshop. | o 5/2013: WIS and TDCF workshop for RA-V countries hosted at Melbourne. This introduced WIS to RA-V representatives and demonstrated the use of GISC Melbourne WIS portal. o 11/2013-08/2014: In-country visits to 10 NC in RA-V (PNG, Solomon Islands, Samoa, Kiribati, Fiji, Vanuatu, Cook Islands, Tonga, Niue, Tuvalu) with the goal of promoting the benefits of WIS, training NC staff on the use of GISC Melbourne WIS portal and assessing NC’s requirements and capacity in using WIS for their operations | WIS and TDCF workshop organized in RF (Zheleznodorozhny) in 11/2012 for our NCs in AoR. Support through email | A workshop being planned in India. Letters to be exchanged with NC in our area of responsibility for schedule and Metadata update. | 08/2014 Workshop with CNMCA (Italy) 11/2013 Workshop with CNMCA (Italy) 08/2013 Workshop with Slovenian Environ- ment Agency 10/2012 WIS Workshop in Turkey in cooperation with TSMS 04/2012 Workshop with RHMS (Serbia) 02/2012 Workshop with DHMZ (Croatia) 12/2011 Workshop with MeteoSchweiz (Switzerland) 09/2011 WIS Jumpstart SAWS (South Africa) 10/2010 WIS workshop in Turkey in cooperation with TSMS 10/2010 Workshop with SMHI (Sweden) In addition support through email, telephone conferences, … |  | 2014.8, 10, workshop with DCPC NMSC and DCPC LC-LRFMME of KMA 2013.10, workshop with Uzbekistan to establish DCPC Tashkent |  | In this year, 04/2014 Workshop with NCHMF (Vietnam) 04/2014 Workshop with PAGASA (Philippines) 06/2014 Workshop with DMH (Myanmar) 11/2014 WIS Workshop which is in line with the WIS Competency framework is scheduled to be held in JMA (Japan) in November 18-20. In addition support through email, ... | A workshop organized in Toulouse, June 5th-7th 2013 in cooperation with UKMet. We had many exchanges with NC in our area of responsibility for Metadata update. | Early/Mid 2015 Workshop with Region-IV NCs. | This is an ongoing activity at this time
14/1-3 | Action: Jacques Anquetil to coordinate the collection of the comments from all the GISCs on the elements proposed for monitoring and to submit a report to ET-WISC by the 27 March. It requested that the secretariat facilitate provision of the report to ET-WIS. | Closed | Pilot implement of WIS monitoring planned in 2015. |  | Noted. | in progress, we are looking how to implement the GISC monitoring. Priority action for 2015. | Noted. | Done by Jacques. | In porgress | in progress, we are looking how to implement the GISC monitoring | GISC Offenbach notes that our comments were not reflected in ICT-ISS final report. |  | Noted |  | JMA comments were not reflected in ICT-TSS final report. The question is who and how to consider the TT-GISC comments. Does TT-OM update the monitoring specification? | in progress, we are looking how to implement the GISC monitoring. Priority action for 2015 | In process, investigating/evaluating several possible ways to implement monitoring for GISC Washington. | CBS reviewed the situation and tasked ICT-ISS (TT-GISC) to complete the pilot monitoring. TT-DC asked to be involved.
14/1-4 | Action: All GISCs to work with data providers to ensure they generate and publish metadata for those bulletins that they are producing and already circulating on GTS as soon as possible [see new task 14/2-01 for BUFR] | Open | In progress. | Noted. | Noted. | In progress, new metadata is being generated for NCs in our area. | GISC Jeddah becomes fully operation in October 2014. It generated MD for all bulletins of AoR, except Qatar. Qatar DCPC generate MD for Qatar bulletins. However, GISC Jeddah harvested Qatar MD successfully. | Metadata published for all bulletins produced from Australian centres. Metadata for remaining RA-V centres currently in progress | GISC Moscow have generated metadata for all Vol.C1 bulletins in its AoR in 2014 using GISC Offenbach generator. | in progress. - No action | In August 2014 GISC Offenbach generated for all bulletins without metadata for its AoR (27 countries) metadata and submitted the metadata to NCs/DCPCs for review and approval. |  | Ongoing |  | Ongoing | 4 in progress. Due for completion (June 2015) | In process. | There are a lot of records circulating on the GTS with out metadata, including new products. OpenWIS creates interim MD records so my offer a good monitoring tool to see whtn this is completed. See task 14/2-02
14/1-5 | Decision: Agreed that GISC Tokyo provide its "WIS-UNASSOCIATED" set as the authoritative source of baseline metadata and invited all GISCs to synchronize the set. | Open | Noted. | Noted. | Accepted. | Noted, to be carried out this month. |  In October 2014, GISC Jeddah took responsibility of all MD belongs to its AoR that were served by GISC Tokyo as WIMMS.  GISC Tokyo has been harvested by GISC Jeddah. | Done. Daily synchronization of WIS-UNASSOCIATED baseline metadata in place. | Noted, daily synchronization done. | Noted | Noted. |  | Noted |  | JMA has conducted a follow-up research on metadata synchronization issues discussed at TT-GISC meeting in February. Please see the attached files. There are a few GISCs that have not provided WIS-UNASSOCIATED set. | synchronisation done ( May 2014) | Noted | Going well. New GISCs coming online are liaising with Tokyo and advising other GISCs appropriately. See report from Japan at http://wis.wmo.int/doc=3335
14/1-6 | Decision: Agreed Doc 04 provides the basic structures of OAI-Sets to be provided by each GISC. | Open | Compliant | Noted. | Accepted. | Compliant but no WIS-CATALOGUE set for the moment. | Compliant | o Point 1, 2: Compliant. o Point 3: Not implemented by GISC Melbourne. o Point 4: Compliant. An internal set WIS-UNPUBLISHED is currently used for unpublished metadata within GISC Melbourne. | Compliant. Issue to resolve - no WIS-CATALOGUE | Compliant | Compliant |  | Compliant |  | GISC Tokyo: Done. Please see the attached report for other GISCs. | Compliant but no WIS-CATALOGUE for the moment | Noted | To be reviewed at next meeting, noting global set is helpful in monitoring as well as being needed for external harvesting by systems such as GEOSS. It is a candidate approach for monitoring of metadata completeness between GISCs.
14/1-7 | Action: Requested: a) all GISCs to implement the set membership in the headers of items returned in response to the GetRecord requests; and b) each GISC to make sure that all the sets include all the records, especially records that have not belonged to any operational GISC. | Open | Compliant |  | Noted. | Done: a) November 2013 b) May 2014 | Compliant | Compliant | Noted | Compliant | Compliant |  | Compliant |  | GISC Tokyo: Done. Please see the attached report for other GISCs. | done : point A November 2013; point B May 2014 | Noted, in process | Waiting on GISCs to complete installation of this feature.
14/1-8 | Decision: Agreed to minimize the synchronization failure by following two practical rules: a) avoid using identifiers with only case difference as the primary rule, b) if there is no way other than using identifiers with only case difference, delete old records explicitly (by issuing OAI deleted message), before adding new records | Open | Compliant |  | Noted. | Metadata MF compliant; Will be deployed with OpenWIS 3.13 release in December 2014. | Compliant | o a) Aim to meet compliance of this action with the next major release of GISC Portal software (scheduled: Dec 14 to Jan 15) o b) Metadata compliant. | Compliant. | Compliant | Compliant |  | Noted and will update the related S/W in 2015 |  | Ongoing. Continue the efforts to guide NC/DCPC in the AoR of Tokyo. | Metadata MF compliant; Will be deployed with OpenWis 3.13 release in December 2014 | Noted and will be deployed in subsequent system software update in first quarter of 2015. | Waiting on GISCs to complete installation of this feature.
14/1-9 | Action: Agreed: a) That all harvesters need to be able to harvest records even with default namespace declarations; b) To encourage metadata creators to avoid using default namespace declaration. | Open | Noted. a) will be ready by March 2015. b) Compliant |  | Noted. | Compliant. | Compliant | o a) Compliant in principal: default namespaces are supported but they must refer to ISO-19139 standard namespace URLs. o b) Metadata compliant. | Noted | Compliant | Compliant |  | Noted and will update the related S/W in 2015 |  | Ongoing. Continue the efforts to guide NC/DCPC in the AoR of Tokyo. | Compliant | Compliant and will be included in Regional Workshop training sessions. | Looking good, just waiting on GISCs to report on completion of this feature.
14/1-10 | Action: Urged the GISCs to fix inaccurate datestamps in OAI headers and selective harvesting arguments: “until” and “from”, by the next ET-WISC meeting [see new action item 14/2-2 Datestamp] | Open | Compliant |  | Noted. | Will be fixed with the new OpenWIS 3.13 release in December 2014. | Compliant | Aim to meet compliance of this action with the next major release of GISC Portal software (scheduled: Dec 14 to Jan 15) | In progress | Noted | Compliant |  | Ongoing |  | No action | Will be fixed with the new OpenWis 3.13 release in December 2014 | Noted and will be included in subsequent system software update in first quarter of 2015. | Waiting on GISCs to complete installation of this feature.
14/1-11 | Action: Agreed to use the ET-WISC internal forum (http://www.wmo.int/pages/prog/www/WIS/wiswiki/tiki-view_forum.php?forumId=12) to discuss issues. | Closed | Noted | Noted. | Accepted. | Noted. | Noted | Waiting for report from TT-GISC Chair. | Noted | Noted | Noted, but no discussion there |  | Noted, no one used |  | Noted. (It might be an idea to use only TT-GISC mailing list, because no one is using WIS Wiki forum and the mailing list functions as the single source of past discussions.) | the secretariat could make a presentation to the group during the next face to face meeting | Noted | Closed, people agree that TT-GISC email is easier to use. Will leave collaboration page there. (Dave - afterthought -Think about subscribing email group to notify when collaboration site is updated)
14/1-12 | Action: a) Requested ET-CTS, while investigating cloud computing solutions, to address: legal issues of countries using storage outside of nation; - political barriers to one country using a service managed by another; and data access policy. b) The chair suggested that once ET-CTS has considered this document from a CTS perspective, it is recommended that at least a couple of GISCs experiment further with this concept. | Open | Noted. volunteer to participate experiment | Noted. | No action | a) Noted. b) UK Met Office volunteers to participate in the prototype. | No Action | No action from GISC Melbourne. Waiting for report from TT-GISC Chair. | Noted | no action. | b) GISC Offenbach volunteers to participate in a prototype. Furthermore we are curious to hear about what actions happened until now regarding Peter Silva’s (Canada) suggestion to use AMQP as notification protocol. |  | Noted |  | On going | in progress | Noted and under investigation. | et-cts to action pilot, noting legal issues etc - eg it will need DCs approval to host data in cloud
14/1-13 | Recommendation: Agreed that detailed monitoring would be at the GISC level, while only the common holding needs to be monitored globally. Thus all GISCs should meet the basic requirement set by monitoring a) The number of core Cache updates in the last 24 hours and b) 24 hour input volume and c) number of items in the complete cache, plus the status of the common holding (core) component. Each GISC is encouraged to establish more detailed monitoring for its own quality assurance process. (See also action 14/1-3) | Open | volunteer to participate pilot monitoring | Noted. Working in one application. Need more information. | Noted. | Waiting on TT GISC for decision and guidance on what has to be done for pilot (November 2014). | Noted | Investigation of detailed monitoring currently underway. | Noted | shall try as per decision and guidance of TT GISC on what has to be done for pilot monitoring. | GISC Offenbach implemented a monitoring prototype and volunteers to participate a WIS monitoring prototype. |  | Practice monitoring |  | GISC Tokyo volunteers for the pilot test of WIS monitoring. | waiting on TT GISC for decision and guidance on what has to be done for pilot (November 2014) | Awaiting decision and guidance from TT GISC. | Sub Task Team established (See Action item 14/2-03)
14/1-14 | Action: Agreed to: a) the need for GISC agreement making processes necessary to manage multilateral GISC issues. b) establish a sub team to define TOR and working practices to report back to TT-GISC on recommended procedures for approving inclusion of data in GISC core cache, and similar decisions, so it can be reported to ET-WISC and ICT-ISS. | Open | No action |  | Noted. | Noted. | No action | No action from GISC Melbourne. | No action | no action. | No action |  | Noted |  | The sub team reported back to TT-GISC in June. It will be submitted to ET-WISC by TT-GISC. | No action | No action | CBS requested ICT-ISS/Secretariat to establish an Inter-commission Task Team on WIS to look at governance process for adding or removing data streams to WIS core network and approval process for use of Global Distribution (cache me) flag. CBS also noted the need to start working on the Evolution of the WIS (e-wis) which will be Part C of the WIS implementation strategy.
14/1-15 | Action: Meeting a) confirmed file format of 24h cache to be full meteorological bulletin as in report of ET-WISC meeting, 2013. b) encouraged all GISCs to use the full “Meteorological bulletin” as default representation of GTS-bulletin data instances | Open | Noted. will be ready by March 2015. | Noted. | Noted. | In stand-by mode, but we are ready to do it. | a) noted. b) compliant | No action from GISC Melbourne. | Compliant | noted | a) noted b) compliant |  | a) Noted b) Prepare in 2015 |  | GISC Tokyo: Done | in stand by, but we are ready do it | Noted | Waiting on GISCs to complete installation of this feature.
14/1-16 | Action: Establish a method by which access to a GISC cache is reviewed/audited. [State of cache is included in the monitoring pilot and process, but this is about monitoring of who can access] | Open | No action |  | Noted. | No action. | No action | No action from GISC Melbourne. | No action | no action. | No action |  | Noted |  | No action | cache control: no action MF | No action | Chair, noting state of cache is a part of monitoring, requested someone should look more closely at this item and prepare a paper for consideration of next TT-GISC meeting.
14/1-17 | Action: TT-GISC recommended: a) GISCs should agree on a single standard to facilitate user federation; b) Establish group to investigate, including establishing basic use cases c) Confirm elements needed to be shared. [ongoing from 2015] | Open | Noted | Noted | Noted. | Noted. Subscription information is backed up in vGISC context. | Noted. .. | No action from GISC Melbourne. | Noted | noted | Noted. GISC Offenbach notes the importance of independent security audit for GISCs. |  | Noted |  | No action so far. It is important to define the scope clearly, as well as to take into account differences of software implementation and data policy between GISCs. | subscription backup in vGISC context | Noted | Not due to start until into 2015.
14/1-18 | Decision: agreed a) on the proposed GISC backup procedures in Appendix D, Annex to 9.1 to this report b) not to include metadata management in GISC backup, and c) not to exchange or transfer metadata management privilege for backup purposes d) If there is a need to exchange user information, proper security measures should be taken based on the agreement on the two GISCs. | Open | Noted | Noted | Noted. | Noted. | Noted | Noted | Noted | Noted | Noted |  | Compliant |  | Noted. DWD and JMA are going to rework the document in order to resubmit it to next TT-GISC face to face meeting. | OK | Noted | ICT-ISS updated the appendix and CBS approved their text. See Report on CBS Ext 2014 for details of amendments to manual on WIS. It will be reviewed by Cg-17 then published later in 2015.
14/1-19 | Recommendation: The meeting agreed that: a) The terms for “GISC Registered User” should be included in the Manual on WIS, and that the paragraph 3.9.2 be updated to include “In addition, GISCs are encouraged to, where feasible, provide backup for registered GISC users that are not included within the mandatory backup procedures for NCs and DCPCs within the GISCs AMDCN. b) The procedure in Appendix D, Annex to 9.3 for NCs and DCPCs changing their principal GISC for inclusion in the Guide to the WIS (WMO No 1061) | Done | Noted | No action. | Noted. | No action. | Noted | Noted | Noted | no action. | Noted |  | Noted |  | No comment | No action | No action | Done. See Report on CBS Ext 2014 for details of amendments to manual on WIS. It will be reviewed by Cg-17 then published later in 2015.
14/1-20 | Recommendation: TT-GISC a) agreed that GISC working arrangements, including recommended practices from TT-GISC, should be recorded in an easily maintained Operations Guide to GISCs (possibly a wiki) b) proposed that Appendix D, Annex to 9.2 should be included in a GISC operating guide. | Open | Noted | Noted | Noted. | Noted | Noted | Noted | Noted | Noted | Noted |  | Noted |  | No comment | Action plan : define a subgroup for this action | Noted | Development of the operations guide not started. Follow up at next TT-GISC meeting as proposed by France.
14/1-21 | Recommendation: TT-GISC recommends that WMO be registered as a DCPC with a principal GISC of Toulouse. | Open | Noted | Noted | Noted. | Noted | Noted | Noted | Noted | no action. | Noted |  | Noted |  | No comment |  | Noted | WMO secretariat looking at internal processes. Need to work with Toulouse and go through certification process once ready.
14/1-22 | Action: TT-GISC: a) Agreed that there was a need for a standard format and method along the lines proposed by GISC Pretoria and described in Appendix D, Annex to 9.4. b) Requested France and Germany to explore this issue further to prepare a report to TT-GISC with an aim to including the details in the GISC Practices Guide | Open | Noted | No action. | Ok | No action. | No Action | Noted | No action | Noted | No action |  | Noted |  | No comment |  | No action | ICT-ISS agreed but requested ET-WISC to take this one step further to be and DC to DC/GISC communication.
14/2-01 | TT-GISC agreed that all GISCs should work with data providers to ensure all BUFR traffic originating from their AMDCN has appropriate Discovery Metadata. [Extension of task 14/1-04 beyond GTS traffic] | Open | [15 empty] | Open
14/2-02 | Target to get OpenWIS interim metadata records to zero [Extension of task 14/1-04] | Open
14/2-03 | TT-GISC Demonstration sub task team to develop pilot GISC monitoring and lead demonstration to Cg 17 | Open | [15 empty] | • TT-GISC 2014/2 established a sub team to develop a plan and organize WIS monitoring demonstration, according to the document provided by TT-OM, volunteers and lead for this action. o Who (sub task team) - Lead to be determined over discussion over next week - Participants: DWD, CMA, JMA, UK, BoM, INMET, TT-DC reps (Liaise with chair TT-DC) o What - DWD, BoM & INMET share work on what has been done internally on populating a dashboard, and develop a pilot demonstration - once approved by TT-GISC, other GISCs and Centres will be encouraged to join in for demonstration to Cg 17. o When - Demo to Cg 17 (May 2015) - March 2015 – test pilot of WIS Monitoring has a global view of dashboard with several giscs o Output - results of pilot to next tt-gisc (Telco or meeting) - Demonstration of monitoring dashboard to Cg 17
14/2-04 | Toulouse to provide a working paper on file format for data access by users at next TT-GISC face to face meeting (Toulouse). Note that the aim is so end users of all giscs can get the same file format delivered. | Open | [15 empty] | Toulouse proposed to define the file format for data exchange, the file shall regroup the result of a query, and the name of the file shall use the file naming convention. (See paper by Benjamin Saclier for ET-CTS) – Meeting concluded to receive a working paper at next TT-GISC face to face meeting (Toulouse). Note that the aim is so end users of all giscs can get the same file format delivered.
14/2-05 | Offenbach to work with GISC Moscow to present paper to next TT GISC meeting about their ftp server to provide their standard as a model for harmonization of ftp servers for GISC portals. | Open | [15 empty] | Toulouse proposed to define a common organisation to retrieve data on ftp server, in order to facilitate exploration for GISC users when moving from one GISC to another. Action to be from a GISC with an ftp server to provide their standard as a model for harmonization. Offenbach to work with GISC Moscow to present paper.
14/2-06 | GISCs to follow up on sending of data from AMDCN to all other operational GISCs and report on progress at next Telco | Open | [15 empty] | Resolution 13 (EC-65) requested “all operational GISCs to connect to the WIS core network and transmit information collected from their area to all other operational GISCs.” The secretariat, noting that it has seen newly operational GISCs requesting other GISCs to exchange data, would like to be informed on the progress of GISCs in making their arrangements