## Scope of Work Plan
Scope of Work Plan
Is Included | Is Not | Undecided
Amend METCE
Amend IWXM
Amend Technical Regulations
Amend Data Quality
Amend Sampling Regime
Develop WIGOS Logical Data Model for
Communications via AdHoc 1 list
Review TT-WMD, ET-CDMS, TOR to include WLDM work
Prove that WLDM is viable via Testbed and is documented in regulations for CBS approval

## Tasks
Tasks
Task | How Measured | Responsible Person | By When | Realistic?
METCE, IWXM, |  | Jeremy | Before AvXML in Sep | Y
Technical Regulations |  | Jeremy, Dom, Bruce | End Dec prepared. CBS Fast Track starts Feb
Resolve Data Quality Concerns WIGOS Logical Data Model - resolve issues | Data Model resolved | Joerg, Karl, Dom, Jeremy, Meaghan, Denis | 1st draft - End August
Sampling Regime - Resolve Data Model | Data Model resolved | Joerg, Karl, Dom, Jeremy, Meaghan | 1st draft - End August
Develop WIGOS Logical Data Model that is suitable to assess viability to support XML exchange format. Built using monthly sprints to resolve issues. | Data Model EAP project file that can be used to auto generate GML and semi-automate Regulations data | Dom, Jeremy, Karl, Joerg, Denis, Silvano, Bruce, CK, Choy | For CBS to approve in November 2016. Therefore data tech Regs available for Puplication - By June 2016
Develop First Draft |  | Dom | By end August
Develop WLDM RC |  | Dom | End January 2016
Test WLDM in a Test Bed | Feb and March | Joerg | March
Requests for Public Comment - OGC, Program focal points, WIGOS etc, Commissions | Feb and March | Bruce, Steve, Commission Reps | March
Review public comments and result of test bed, requests for change |  | Karl | 2016-04-01
Monthly Schedule teleconf |  | Bruce | 2016-06-01
Edit / Maintain WIGOS Logical Data Model as EDITOR | Data Model EAP project file that can be used to auto generate GML and semi-automate Regulations data | Dom | 2016-06-01
EA 12 purchased, installed and configured, training |  | All | ASAP
Confirm WLDM is consistent with domain requirements - based on Nov draft |  | IPET-MDRD Commission representatives | 2015-12-01
Revise Model, Technical Regulations, other Documentation |  | Dom, Jeremy, Bruce | 2016-06-01

## Communication Plan
Communication Plan
Who to Contact | What Message | When | Responsible Person
WMO Commissions
Danial Mickelsen | RADAR (Sweden) IPET-WIPI? |  | Karl
Oceans
TTavXML |  |  | Jeremy
CBS Fast track |  |  | Steve
OGC TC MeteoDWG, HDWG + mailing lists | Advertise for public comment re: Testbed of WLDM