| WORLD WEATHER WATCH COMMISSION FOR BASIC SYSTEMS |  |  |
| --- | --- | --- |
| IPET-MDRD-2-T2 Teleconference, 0700 UTC, 28 October 2015 |  | ITPET-MDRD-2-T2/Report |
|  |  | 28 October 2015 |

# Minutes of Ad Hod Task Team on WIGOS and Climate Station Metadata – Teleconference 2

# DISCLAIMER

Regulation 43

Recommendations of working groups shall have no status within the Organization until they have been approved by the responsible constituent body. In the case of joint working groups the recommendations must be concurred with by the presidents of the constituent bodies concerned before being submitted to the designated constituent body.

Regulation 44

In the case of a recommendation made by a working group between sessions of the responsible constituent body, either in a session of a working group or by correspondence, the president of the body may, as an exceptional measure, approve the recommendation on behalf of the constituent body when the matter is, in his opinion, urgent, and does not appear to imply new obligations for Members. He may then submit this recommendation for adoption by the Executive Council or to the President of the Organization for action in accordance with Regulation 9(5).

© World Meteorological Organization, 2015

The right of publication in print, electronic and any other form and in any language is reserved by WMO. Short extracts from WMO publications may be reproduced without authorization provided that the complete source is clearly indicated. Editorial correspondence and requests to publish, reproduce or translate this publication (articles) in part or in whole should be addressed to:

Chairperson, Publications Board

World Meteorological Organization (WMO)

7 bis, avenue de la Paix				Tel.: +41 (0)22 730 84 03

P.O. Box No. 2300				Fax: +41 (0)22 730 80 40

CH-1211 Geneva 2, Switzerland				E-mail: Publications@wmo.int

NOTE:

The designations employed in WMO publications and the presentation of material in this publication do not imply the expression of any opinion whatsoever on the part of the Secretariat of WMO concerning the legal status of any country, territory, city or area or of its authorities, or concerning the delimitation of its frontiers or boundaries.

Opinions expressed in WMO publications are those of the authors and do not necessarily reflect those of WMO. The mention of specific companies or products does not imply that they are endorsed or recommended by WMO in preference to others of a similar nature which are not mentioned or advertised.

This document (or report) is not an official publication of WMO and has not been subjected to its standard editorial procedures. The views expressed herein do not necessarily have the endorsement of the Organization

# Minutes OF AD HOD TASK TEAM ON WIGOS AND CLIMATE STATION METADATA – TELECONFERENCE 2

The teleconference was held at 0700 UTC on 28 October 2015. It was chaired by Mr Lowe. Mr Choy attended, and Mr Foreman was the secretary.

# 1. Progress update (including TT-WMD-4)

Sampling regime: TT-WMD-4 identified that there was a missing time description.

# 2. Work required before next release

Data quality: work is still needed to see how much of the ISO data quality standard can be reused.

EA 11 had the facilities that were required unless transformations were required. Choy recommended the corporate edition because it had features that were required.

Mr Tandy’s proposed changes to METCE had been included in the repository as a branch.

The updated work plan is in the Annex.

# 3. Next release date

Mr Lowe would include changes from the TT-WMD-4 meeting before issuing the next draft. That draft would be issued to the team for internal review by 6 November. Review comments were needed by 20 November.

A teleconference in week of 23-27 would be used to resolve any outstanding issues from the feedback. The date would be Tuesday 24th at 0700 UTC.

# 4. AOB

There was no any other business.

The meeting closed at 0734 UTC

# Action and Decision Summary

## Actions

- There were no actions identified that were not implied by the decisions.

## Decisions

D1	Mr Lowe would include changes from the TT-WMD-4 meeting before issuing the next draft. That draft would be issued to the team for internal review by 6 November. Review comments were needed by 20 November.

D2	A teleconference in week of 23-27 would be used to resolve any outstanding issues from the feedback. The date would be Tuesday 24th at 0700 UTC.

-----------

# Annex. Work plan

## Plan for preparing Data Representation for WIGOS and Station Metadata.

Updated 28 October 2015

| Id | Deliverable | Responsible | Due date | Comments |
| --- | --- | --- | --- | --- |
| P01 | Modified IWXXM and METCE, to provide facilities needed for WIGOS metadata | Tandy | Early September 2015 (before TT-AvXML) | Proposal made |
| P02 | Presentation to TT-AvXML on proposed changes to IWXXM and METCE | Tandy | TT-AvXML, September 2015 | Done |
| P03 | Technical regulation changes specified for IWXXM and METCE | Tandy, Lowe, Bannerman | February 2016 |  |
| P04 | Complete Fast Track approvals process for IWXXM and METCE | Foreman | August 2016 |  |
| P05 | Definition of data quality representation in data model (more detailed mapping required) | Klausen, Monnik, Lowe, Bannerman | August 2015 | Work in progress |
| P06 | Definition of representation of sampling regime in data model (requirements to be determined, and then model to be updated) | Klausen, Monnik, Lowe, Tandy, Flannery | August 2015 | Work in progress |
| P07 | Publish initial communications plan | Bannerman | August 2015 |  |
| P08 | All developers have access to EA12 and version control software | Lowe, Tandy, Klausen, Monnik, Stuber, Pan, Choy, Pecora | July 2015 | Most only have access to EA11. Dom considers that will be sufficient for the moment. Denis has EA11 because 12 not yet supported by MF. The team will use EA11 and upgrade if essential. |
| P09 | Team trained in use of EA 12 (or EA 11 as available) | Lowe | October 2015 | Self-training |
| P10 | Logical data model for WIGOS suitable for review as to its viability for deriving an exchange format. Zeroeth draft. | Lowe | End August 2015 | Draft issued for comment |
| P11 | Logical data model for WIGOS suitable for review as to its viability for deriving an exchange format. Zeroeth draft. | Lowe | End September 2015 | No revisions made – open questions for discussion before new design appropriate. |
| P12 | Logical data model for WIGOS suitable for review as to its viability for deriving an exchange format. First draft. | Lowe | End October 2015 | This would be ready in the first week of November to allow decisions at TT-WMD-4 to be included. |
| P13 | Logical data model for WIGOS suitable for review as to its viability for deriving an exchange format. Second draft. | Lowe | End November 2015 |  |
| P14 | Results of Logical Data Model testing in test bed provided to team for technical response. | Klausen | March 2016 |  |
| P15 | Logical data model for WIGOS suitable for review as to its viability for deriving an exchange format. Release candidate 1. | Lowe, | End January 2016 |  |
| P16 | OGC TC informed of forthcoming public review of logical data model. Other potential reviewers informed. MetOcean DWG, Hydro DWG and others as determined by team. | Bannerman | November 2015 |  |
| P17 | Confirmation by representatives from Commissions on team that the November draft of the Logical Data Model is consistent with the needs of their domain requirements | Stuber, Bannerman, Monnik, Pecora, Klausen | December 2015 |  |
| P18 | Request for public comments issued (WIS focal points, WIGOS focal points, DWGs, Commission focal points, Programme focal points). Objective to ensure that it is consistent with domain requirements | Bannerman, Foreman | End January 2016 |  |
| P19 | End of public review of Logical Data Model | Bannerman, Lowe, Tandy | End March 2016 |  |
| P20 | Review public comments, requests for change and results of testbed and recommend modifications to Logical Data Model to accommodate priority requirements. | Monnik | End April 2016 |  |
| P21 | Monthly telephone conferences | Foreman | Monthly from July 2015 to June 2016 |  |
| P22 | Logical data model documentation (EAP project) available for deriving GML schema and for semi-automatically generating Technical Regulations. Includes response to requests for change from testbed and reviews. Ready for submission to CBS-16 for their recommendation. | Lowe | End of June 2016 |  |
| P23 | Recommendation of GML and Technical Regulations by CBS-16 | Foreman | Nov 2016 |  |
| P24 | Pre-operational use based on CBS-16 approved versions | Foreman | January 2017 |  |
| P25 | Communication list for team set up (cbs-adhoc-01@wmo.int) | Foreman | 26 September 2015 | Done. Steve will tell people where it is. |
| P26 | Approval by Executive Council | Foreman | June 2016 |  |
| P27 | Operational use |  | November 2016 |  |
| P28 | Review TT-WMD Terms of Reference to make sure that they cover work to develop the data reference (so TT-WMD members can participate in the work). IPET-MDRD members already covered by IPET-MDRD ToRs, as are ET-CDMS by theirs. [WIGOS Logical Data Model – WLDM] | Monnik | July 2015 |  |
| P29 | Wiki repository for documents available | Foreman | End June 2015 |  |

## Communications Plan

| Id | Stakeholder | Objective | Responsible | Due | Comments |
| --- | --- | --- | --- | --- | --- |
| C01 | Techical Commissions | Inform about developments. Seek review comments before submission to CBS | Bannerman | Complete review March 2016 |  |
| C02 | BALTRAD (Daniel Michelson) | Build confidence that this user community will be able to use the Logical Data Model | Monnik | Complete review March 2016 |  |
| C03 | JCOMM | Build confidence that this user community will be able to use the Logical Data Model | Monnik | Complete review March 2016 |  |
| C04 | TT-AvXML | Ensure developments of the Logical Data Model are consistent with the evolution of IWXXM | Tandy | Initial September 2015 | Done |
| C05 | CBS Codes Focal Points | Prepare for consultation on the Logical Data Model so that meaningful review comments are received | Secretariat | Ongoing |  |
| C06 | OGC MetOcean DWG, HydroDWG (plus mailing lists) | Request public comment and participation in testbed | Bannerman | December 2016 |  |