| WORLD WEATHER WATCH COMMISSION FOR BASIC SYSTEMS |  |  |
| --- | --- | --- |
| WIS Training and Planning Workshop Nairobi, Kenya, 2-6 November 2015 |  | WIS-RA-1M2/Report |
|  |  | 8 December 2015 |

# Report of the WIS Training and Planning WOrkshop held in Nairobi, 2-6 NOvember 2015

# DISCLAIMER

Regulation 43

Recommendations of working groups shall have no status within the Organization until they have been approved by the responsible constituent body. In the case of joint working groups the recommendations must be concurred with by the presidents of the constituent bodies concerned before being submitted to the designated constituent body.

Regulation 44

In the case of a recommendation made by a working group between sessions of the responsible constituent body, either in a session of a working group or by correspondence, the president of the body may, as an exceptional measure, approve the recommendation on behalf of the constituent body when the matter is, in his opinion, urgent, and does not appear to imply new obligations for Members. He may then submit this recommendation for adoption by the Executive Council or to the President of the Organization for action in accordance with Regulation 9(5).

© World Meteorological Organization, 2015

The right of publication in print, electronic and any other form and in any language is reserved by WMO. Short extracts from WMO publications may be reproduced without authorization provided that the complete source is clearly indicated. Editorial correspondence and requests to publish, reproduce or translate this publication (articles) in part or in whole should be addressed to:

Chairperson, Publications Board

World Meteorological Organization (WMO)

7 bis, avenue de la Paix				Tel.: +41 (0)22 730 84 03

P.O. Box No. 2300				Fax: +41 (0)22 730 80 40

CH-1211 Geneva 2, Switzerland				E-mail: Publications@wmo.int

NOTE:

The designations employed in WMO publications and the presentation of material in this publication do not imply the expression of any opinion whatsoever on the part of the Secretariat of WMO concerning the legal status of any country, territory, city or area or of its authorities, or concerning the delimitation of its frontiers or boundaries.

Opinions expressed in WMO publications are those of the authors and do not necessarily reflect those of WMO. The mention of specific companies or products does not imply that they are endorsed or recommended by WMO in preference to others of a similar nature which are not mentioned or advertised.

This document (or report) is not an official publication of WMO and has not been subjected to its standard editorial procedures. The views expressed herein do not necessarily have the endorsement of the Organization

# REPORT OF THE WIS TRAINING AND PLANNING WORKSHOP HELD IN NAIROBI, 2-6 NOVEMBER 2015

## Workshop Contents

The meeting was opened by Mr David Mburu, on behalf of Ms Stella Aura (Deputy Director/Principal, IMTR (WMO RTC)). He welcomed participants to the Kenya Meteorological Department (KMD) and Regional Telecommunications Centre, and noted that KMD hosted the Regional Office for Africa of WMO and the offices of the IGAD Climate Prediction & Applications Centre (ICPAC).

Mr Steve Foreman, on behalf of the Secretary-General of WMO, thanked KMD for its invitation to host the workshop, and the participants for attending. He noted that the WMO Information System (WIS) was critical to operations and would underpin research and development activities. WIS expanded on the Global Telecommunications System, allowing industry standard technologies to be used, and providing access to a wider range of information. The workshop would concentrate on what participants needed to know to use the WIS, and the planning session would provide an opportunity to start planning how participants could make use of WIS in their own services.

Mr Peter Abenje (Deputy Director of KMD) on behalf of Mr James Kongoti (Permanent Representative of Kenya to WMO), also welcomed participants to KMD. He thanked Morocco and South Africa for supporting the region by providing GISCs Casablanca and Pretoria. He informed participants that RTH Nairobi was supporting centres attached to it by converting between the Traditional Alphanumeric Codes (TAC) and the Table Driven Code Forms (TDCF). KMD was using two numerical models (COSMO and WARF) to support the regional SWFDP activities in East Africa. KMD had a new database management system operational. Implementation for WIS and WIGOS was being achieved through a combined plan covering both areas, and Kenya had almost finished recording the WIGOS metadata for its observations.

Mr Edwad Muriuki (Senior Assistant Director, Education and Training, IMTR) proposed a vote of thanks.

The list of participants in the workshop is given in Annex 1, and the Agenda in Annex 2.

The training used the WIS Competences and Training and Learning Guide to guide the training activities. A key aspect of the training was practice in creating and editing WIS Discovery Metadata using the facilities of GISC Casablanca. A discussion at the start of each half-day reinforced the previous learning, and on the Wednesday, participants presented brief overviews of the topics that had been covered by the training. This prepared the participants for their role of passing on the training to their colleagues in their own services. The planning session allowed consolidation of the learning from the training.

During the planning workshop, participants reviewed the RA-I WIS Implementation Plan and updated the contents, in particular to correct the details of the international telecommunications available in their countries. They also produced draft National WIS Implementation plans that could be used as a starting point for implementation of WIS (where the country did not already have a plan). The working draft plans are in Annex 3 for use as starting points by participants when developing their national plans.

During discussion of preparation of the national plans, it was realized that Permanent Representatives, and others, might need to be persuaded of the benefits of WIS. To support this, a short session on the differences between “features” and “benefits” was held so that participants would be better placed to identify the most relevant benefits of WIS for their countries.

A WIGOS meeting for Permanent Representatives had been held in Namibia the same week as this workshop. Participants in the workshop were likely to be asked about WIS and WIGOS metadata by the Permanent Representatives when discussions were held on the WIS National Implementation Plans. To assist participants, a brief presentation on the differences between WIS and WIGOS metadata was added to the workshop.

The meeting closed at 1630 on Friday 6 November 2015.

## Lessons learned from Workshop

The following issues arose during the workshop that needed to be addressed.

### Structure and facilities of WIS

Nairobi RTH offered metadata editing facilities for the centres attached to it. Those centres had as Principal GISCs Casablanca, Exeter and Pretoria, whereas Nairobi’s Principal GISC was Offenbach. What would be the best way for the WIS catalogue to reflect the changes made by centres through Nairobi?

Many centres would need additional support before they made full use of WIS. The main source of assistance should be through the GISCs, but they would need to plan how they could provide that support and resource its delivery. The workshop recommended that the RA-I WIS Implementation Task Team should ask Members to notify their GISCs by the end of January 2016 their requests for support. This would give the GISCs an opportunity to plan their training.

Topics of particular concern were the migration to Table Driven Code Forms and creating and updating WIS metadata records. Participants asked if some on-line training materials could be produced to assist them with their planning and implementation of these.

National Implementation would require the support of the Permanent Representative. Participants suggested that one way of supporting this would be for meetings of Permanent Representatives to have a short agenda item reporting the progress on the implementation of WIS (that could be created from the reports to the RA-I WIS Implementation Team).

Metadata records created during the workshop appeared on the WIS catalogue and had to be removed by the system administrators. A method of creating and editing records during training sessions is needed to avoid training examples being visible in the WIS catalogue (and such a facility might also allow draft records to be reviewed before being published in the catalogue).

### Running of the workshop

Pre-registration and authorization of participants on the GISC would have saved a lot of time. Registering at the workshop resulted in delays in performing the exercises (especially is it took a while for everyone to connect their laptops to the network).

All participants arrived at the workshop with laptops, though some laptops lacked the performance to handle all the documents.

The new WMO laptops do not have VGA connectors, so WMO staff need to travel with mini-DVI or HMDI converters. Apple converters work from the mini-DVI port.

Response from the GISC was slow, and at times connections were timing out, even though other sites were accessible.

The Dell E7250 laptop used by WMO would not sustain a connection to the CISCO Linksys router used to provide the wifi connection (even when connected through a cable). On another mission recently, users of Dell Latitude laptops (WMO and others) were unable to sustain a wifi connection (the model of router was not known). This has a serious impact when paperless meetings are held and documents created during the meeting are shared online. As a countermeasure, where WMO staff are leading a workshop, the local organizers should be asked to provide a projection PC that could be used to run the meeting.

## Annex 1: List of participants

| Hailemariam Beyene KINFE (Invited member) Proposed by: Ethiopia | National Meteorological Agency P.O. Box 1090 ADDIS ABABA Ethiopia Email: kinfe_hm@yahoo.com |
| --- | --- |
| Peter. K. MUTAI (Invited member) Proposed by: Kenya | Kenya Meteorological Services (KMS) Dagoretti Corner Ngong Road P.O. Box 30259-00100 NAIROBI Kenya Fax: +254 20 3867955 Tel: +254 20 3867880 Mobile: +254 722 670 907 Email: pmutai@meteo.go.ke, pmutai@gmail.com |
| Samuel MWAURA KAMAU (Invited member) Proposed by: Kenya | Kenya Meteorological Service Ngong Road P.O. Box 30259 00100 NAIROBI Kenya Fax: +254 20 387 6955 Tel: +254 20 387 6957 Email: mwaura@meteo.go.ke |
| Andrew NDENGU (Invited member) Proposed by: Kenya | Kenya Meteorological Service Ngong Road P.O. Box 30259 00100 NAIROBI Kenya Fax: N/A Tel: N/A Email: andengu@yahoo.fr |
| Candasamy RAMASAWMY (Invited member) Proposed by: Mauritius | Meteorological Services St. Paul Road VACOAS Mauritius Fax: +2306861031 Tel: +2306861033 Email: rcp.ram@gmail.com |
| Mohamed EL HAITI (Invited member) Proposed by: Morocco | Direction de la Météorologie Nationale, DMN B.P. 8106 en face de la prefecture Hay Hassani CASABLANCA Morocco Fax: N/A Tel: +212 614322002 Mobile: +212 522654093 Email: mohaiti@gmail.com |
| Godfrey HABUKURI (Invited member) Proposed by: Rwanda | Ministry of Nature Protection Government Building 3 375010 YEREVAN Armenia Tel: +250 783077577 Email: g.habukuri@meteorwanda.gov.rw |
| Mohamed Hussein (Adi) MOHAMED (Invited member) Proposed by: Somalia | Department of Hydrology Ministry of Water and Energy MOGADISHU Somalia Fax: N/A Tel: +252 612 333 747 Email: engcaadil@gmail.com |
| Edward Andrew ASHIEK (Invited member) Proposed by: South Sudan | South Sudan Meteorological Department (SSMD) Juba International Airport Met Office Juba South Sudan Tel: +211956361111 Email: edwardashiek@gmail.com |
| Elsir Mohammed Ali ATIF (Invited member) Proposed by: Sudan | Sudan Meteorological Authority (SMA) P.O. Box 574 KHARTOUM Sudan Email: tifaelsir@yahoo.com |
| Emanuel Tumaini KIDEBWANA (Invited member) Proposed by: Tanzania | Tanzania Meteorological Agency Ubungo Plaza 3056 Dar es Salaam United Republic of Tanzania Fax: +255 22 246 07 35 Tel: +255 22 246 07 06 Mobile: +255 713 251911 / +255767251911 Email: emanuel.tumaini@meteo.go.tz, etumaini@hotmail.com |
| Festus Alex NYAMUJUNGA (Invited member) Proposed by: Uganda | Department of Meteorology P.O. Box 7025 KAMPALA Uganda Tel: +256 774 419950 Email: alex.festus@yahoo.com |
| Steve FOREMAN (Secretariat) Proposed by: WMO Secretariat | World Meteorological Organization 7 bis, avenue de la Paix Case postale No. 2300 CH-1211 2 GENEVA Switzerland Fax: +41 22 730 8021 Tel: +41 22 730 8171 Email: sforeman@wmo.int |
| Elijah MUKHALA (Secretariat) Proposed by: WMO Secretariat | World Meteorological Organization PO Box 1395-00606 Dagoretti Corner KENYA NAIROBI Kenya Fax: +254 20 387 7373 Tel: +254 20 387 7371 Mobile: +254 731 794 075 Email: emukhala@wmo.int |

## Annex 2: Agenda

| Time | Topic | Leader |
| --- | --- | --- |
|  | MONDAY |  |
| Monday am 30m | Opening of workshop | Led by local host |
|  | · Welcome | Host and WMO |
|  | · Working arrangements for the workshop | Host |
|  | · Objectives of the workshop | WMO |
| Monday am 1h | Overview of WIS (101-1) | WMO |
| Monday am 30m | WIS Competences (101-0) | WMO |
| Monday am 30m | Introduction to GISC Casablanca | GISC Casablanca |
| Monday am 30m | Introduction to GISC Pretoria | GISC Pretoria |
| Monday pm 10m | Summary of overview of WIS | Participant |
| Monday pm 1h | Exchanging data in WIS (101-2) | WMO / GISC |
| Monday pm 30m | Practice downloading and subscribing to information |  |
| Monday pm 1h | WIS Discovery metadata (101-6) | WMO / GISC |
| Monday pm 30m | GISC Casablanca metadata editor | GISC Casablanca |
| Monday pm 30m | GISC Pretoria metadata editor | GISC Pretoria |
|  | TUESDAY |  |
| Tuesday am 10m | Summary of exchanging data in WIS | Participant |
| Tuesday am 10m | Summary of WIS Discovery Metadata | Participant |
| Tuesday am 10m | Reminder on metadata editors | GISCs |
| Tuesday am 1h | Practice entering and editing metadata | GISCs |
| Tuesday am 1h | Managing WIS (101-3) | WMO / GISC |
| Tuesday pm 10m | Summary of Managing WIS | Participant |
| Tuesday pm 1h | Operating WIS (101-4) | WMO / GISC |
| Tuesday pm 1h | Telecomms in WIS (101-5) | WMO / GISC |
| Tuesday pm 1h | Completion of national WIS questionnaires | WMO |
| Tues pm 15m | Ranking of national WIS-related priorities | WMO |
| Tuesday pm 10m | Summary of operating WIS | Participant |
| Tuesday pm 10m | Summary of telecoms in WIS | Participant |
|  | WEDNESDAY |  |
| Wednesday am 20m | Summary of WIS training | Participants |
|  | · Exchanging data |  |
|  | · WIS Discovery Metadata |  |
|  | · Managing WIS |  |
|  | · Operating WIS |  |
|  | · Telecommunications in WIS |  |
| Wed am 1h | Tour of operational centre including WIS systems | Local organizer |
| Wed am 1h | Introduction to RA I WIS plan | Member of RA I WIS Implementation Team |
| Wed pm | National status of WIS and key challenges |  |
| 15m | Ethiopia | Participant |
| 15m | Kenya | Participant |
| 15m | Mauritius | Participant |
| 15m | Rwanda | Participant |
| 15m | Somalia | Participant |
| 15m | South Sudan | Participant |
| 15m | Sudan |  |
| 15m | Tanzania | Participant |
| 15m | Uganda | Participant |
| Weds pm 1h | Identify common themes | Member of RA I WIS Implementation Team |
| Weds pm 15m | Review of WIS competencies relevant to creating national plan and introduction to Thursday morning activities | WMO |
|  | THURSDAY |  |
| Thurs am 1h | Identify solutions to common themes in the national reports that could be re-used | Member of RA I WIS Implementation Team |
| Thurs am 90m | Prepare outline national plans | Participants |
| Thurs pm 1h | Report back on outline national plans and their needs from international plan | Participants |
| Thurs pm 2h | Prepare outline international plan | Member of RA I WIS Implementation Team |
|  | FRIDAY |  |
| Fri am 3h | Draft annex to RA I Implementation Plan for international components | Language-based teams |
| Fri pm 1h | Update outline national plans | Participants |
| Fri pm 90m | Confirm international plan and those responsible for actions | Member of RA I WIS Implementation Team |
| Fri pm 30m | Summary and close |  |

## Annex 3: Draft National action plans prepared during the meeting to Initiate Preparation  of Plans

### Ethiopia

National WIS Implementation Plan of Ethiopia

| No | Activity/Action | Time | Responsible | Budget estimation | Output | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Briefing/training of Met staffs and management on WIS and WIS plan (Share manuals, guides and other WIS related documents) | Nov 9-20,2015 | WIS-FP | - | Understanding and commitment on WIS |  |
| 2 | Establish a national WIS Implementation Task Team (N-WIS-IP-TT) | Nov 9-20, 2015 | PR | - | N-WIS-IP-TT established |  |
| 3 | Prepare detailed National WIS IP and get approved by the PR | Nov 20-Dec , 2015 | N-WIS-IP-TT+ PR |  | Agreed N-WIS-IP |  |
| 4 | Decide to join WIS as NC and identify the Principal and secondary GISC | Dec 1-15, 2015 | WIS - FP, N-WIS-IP-TT + PR | - | GISC identified and communicated to WMO and GISC |  |
| 5 | Assess and propose effective communication system between stations, the center and to Nairobi RTH including details of hardware , software, training , and associated budget estimate requirements, also TDCF conversion and data integration from stations report to a consolidated bulletins | Dec 15, 2015 to February 15 2016 | N-WIS-IP-TT | - | Defined feasible communication system | WMO, RTH Nairobi and GISC give technical support |
| 6 | Implement the proposed communication system through budgeting, procurement, installation, testing and training | Feb - Dec 2016 | N-WIS-IP-TT +PR | Un-known | Communication between GTS station-National Center and RTH is in place | Subject to financing |
| 7 | Set up a communication link to the principal GISC and create user accounts at the GISC for using the GISC systems and attain NC certification Assign FP for NC, MD and GTS | Feb – Mar, 2016 | WIS-FP and PR | - | NC-GISC linked, NC certified | Could be done using Internet |

| No | Activity/Action | Time | Responsible | Budget estimation | Output | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 8 | Create/Update the metadata using Internet link to GISC | Feb – Mar, 2016 | WIS-FP | - | Metadata updated | Obtain training from WMO |
| 9 | Train Met staff on the use of WIS system (Explore and identify WIS resources to improve our service) | Jan –Mar 2017 | N-WIS-IP-TT, WIS-FP | Un-Known | MET staff start using WIS for their service | WMO support |
| 10 | Train end-users on WIS use (Explore and identify WIS resources for potential end users service enhancement) | Jan –Mar 2017 | N-WIS-IP-TT, WIS-FP | Un-Known | End users start using WIS for their service | WMO support |
| 11 | Regularly monitor and evaluate the N-WIS-IP performance | Nov, 2015-Mar 2017 | WIS-FP, PR |  | Implementation of N-WIS-IP |  |
| 12 | Manage External Interactions - Center to Center Interaction - Users Interaction Detail how do we communicate to staff, users in the implementation plan | Always | WIS-FP + PR + NC-FP |  | WIS operations ensured | GISC support |

- List of key services to be improved using WIS

- Exploring what is available on WIS and utilize for the enhancement of its service

- 60% of Forecast and early warning use WIS product

- 70% of Aviation service use WIS products for the improvement of its service

- 90% Climate Change Study and other research will use resources under WIS

- Explore and introduce data, products and services on WIS to sector users such as agriculture, water, health, energy  and disaster prevention so that 20% of our user start using WIS by 2017

### Kenya

KENYA – NATIONAL WIS DCPC/NC IMPLEMENTATION PLAN (RA1 WIS TRAINING AND PLANNING WORKSHOP)

|  | Task | Objective | Action (Timeline) | Status | Responsible/ Coordination | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Inform WMO, in particular CBS, by letter from the PR about the wish to become a DCPC. | Apply to Register as WIS-DCPC |  | Completed | PR |  |
| 2 | Identify the Principal GISC | Comply with WIS requirements |  | Completed | PR |  |
| 3 | Nominate the WIS Centre Focal Point for the DCPC. |  |  | Completed | PR |  |
| 4 | Prepare Implementation Plan | Prepare concept note |  | Completed | PR + WIS FP |  |
| 5 | Upgrade Internet Bandwidth at RTH | Increase capacity to allow enhanced data exchange (National and Regional) and serve users more efficiently |  | Competed | WIS-FP | Upgraded internet to 12Mbps |
| 6 | Enhance National Telecommunication Network | Improve national data collection | June 2015 | Completed | PR + GTS FP +WIS FP | Established 1Mbps MPLS links to 8 stations(airports) |
| 6 | Procure HPC for NWP | Produce NWP products | December 2011 | Completed |  |  |
| 7 | Upgrade Meteorological Message Switch | Improve data collection and address TDCF migration issues | July 2015 | Completed |  |  |
| 6 | Connect to RMCDN | Improve data exchange within WIS core network | June 2016 | On going | WIS-FP | The PR has accepted in principle and formal communication to be initiated to management team of RMCDN. Procurement process will started once necessary approval and annual budget have been obtained |
| 7 | Implement WIS DCPC system | Install WIS DCPC system | December 2015 | Completed | WIS-FP | OpenWIS software and hardware have been installed |
| 8 | Integrate NWP products in WIS | Operationalize Production Centre component of WIS DCPC | December 2015 | On-going | WIS-FP |  |
| 9 | Prepare Metadata for Kenya | Comply with metadata discovery | March 2015 | Completed | WIS FP |  |
| 10 | Certification of WIS DCPC | Demonstrate compliance with WIS requirements | Jan 2016 | Principal GISC has been notified | ET-WISC+CBS | Demonstration test document has been sent to GISC |
| 11 | Training | Capacity building (Local and area of responsibility) | 2015 to 2017 | On-going | PR + WIS FP + WMO Sec | Ensure that the required competencies are available locally and within area of responsibility |
| 12 | Improve on User Interactions | Identify potential users of WIS and provide training or sensitize them on benefits of WIS | 2015 to 2017 | On-going | PR+ WIS-FP | Get more users to use WIS |
| 13 | Support Monitoring | Ensure high performance standards are maintained and make reports to principal GISC | Continuous process | Continuous process | WIS-FP |  |

### Mauritius

### Rwanda

### Somalia

Country: Somalia

| Action No | Action | Responsibility | TIME |
| --- | --- | --- | --- |
| 1. | National Decision to join WIS as NC - Brief of Met Staff and Management on WIS and WIS plan - Identification of principal GISC - Nomination of WIS focal point - Communicating to WMO about the decision - Implementation Task team | PR | January 2016 |
| 2 | Telecommunication and Networking infrastructure - Leasing Dedicated and high speed Internet capacity - Additional Communication means such as Satellite Communication if needed - Establishing connection Between central office to sub-national centres - Set up a communication link to the principal GISC and create user accounts at the GISC for using the GISC systems. - Set up a communication link to the RTH | PR+WMO PR+Task -Team | Short Time Plan January 2015 Long-Time Plan December 2016 |
| 3 | National/sub-national Services - Transmit information to national users: Interim Solution: Users Registration and Subscription of GISC - Transmit information to international users – management of data flow | PR+GISC | Interim Solution April 2016 Final Solution February 2017 |
| 6 | NC Certification - Communicate with the chosen Principal GISC for support in the process of NC certification. - support Metadata creation and update remotely by GISC - Inform WMO by letter from the PR on The decision to become an NC and the endorsement from the Principal GISC - Creation and maintenance of WIS Discovery metadata records | PR+ Task Team | May 2016 |
| 7 | Work shop and Training - TOT- Train a staff member in the WMO metadata Core Profile by sending them to training courses organized by WMO or the GISC. - Ask for on-site support/training through the WMO WIS Jumpstart Offer - Train all staff and end users in WIS System | PR+Task Team | November 2015 to November 2016 |
| 8 | Use WIS Functionality - Start using the WIS functionality for sending and receiving data with their associated metadata. - Join the user group of the GISC by attending meetings and other organized events. - Regularly monitor and evaluate the WIS performance | FP+ Task-Team | March 2016 |

### South Sudan

Directorate of Meteorology

National WIS Implementation Plan of South Sudan

Date: 05-11-2015

| S/No | Activity/Action | Time | Responsible | Budget estimation | Output | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Briefing to PR and Staffs on WIS | November 2015 | PR + WIS-FP | - | Understanding on WIS |  |
| 2 | Establish a national WIS Implementation Task Team (N-WIS-IP-TT) | November 2016 | PR | - | N-WIS-IP-TT established |  |
| 3 | Mobilize needed resources to support the WIS implementation in South Sudan (international communication) | December 2015-2016 | Sub-regional WIS Working Body Coordination Group + PR | - | Support implementation of WIS |  |
| 4 | Improved the internet connection in the SSMD | December 2015 | PR + PF |  | Better connection internet | WMO Support |
| 5 | Prepare detailed National WIS IP and get approved by the PR | January 2016 | N-WIS-IP-TT+ PR |  | Agreed N-WIS-IP |  |
| 6 | Decide to join WIS as NC and identify the Principal and secondary GISC | January 2016 | WIS - FP, N-WIS-IP-TT + PR | - | GISC identified and communicated to WMO and GISC |  |
| 7 | Training of Met staffs and management on WIS and WIS plan | February 2016 | PR +FP | - | Understanding and commitment on WIS | WMO Support |
| 8 | Assess and propose effective communication system between stations, the center and to Nairobi RTH including details of hardware , software, training , and associated budget estimate requirements, also TDCF conversion and data integration from stations report to a consolidated bulletins - List of key services to be improved using WIS - Improved forecast products and enhancing services such as warnings to (Aviation, Agriculture and Public). - Improved the climate change research studies. - Availability of data products that support others sectors specially (Agriculture, Water and Health). - Continuity improvements for observation. | March 2016 | N-WIS-IP-TT | - | Defined feasible communication system | WMO, RTH Nairobi and GISC give technical support |
| 9 | Implement the proposed communication system through budgeting, procurement, installation, testing and training | 2016 | N-WIS-IP-TT +PR | - | Communication between GTS station-National Center and RTH is in place | Subject to financing |
| 10 | Set up a communication link to the principal GISC and create user accounts at the GISC for using the GISC systems and attain NC certification | April 2016 | WIS-FP | - | NC-GISC linked, NC certified | Could be done using Internet |
| 11 | Create/Update the metadata using Internet link to GISC | May 2016 | WIS-FP | - | Metadata updated | Obtain training from WMO |
| 12 | Train Met staff on the use of WIS system | June 2016 | N-WIS-IP-TT, WIS-FP | Un-Known | MET staff start using WIS for their service | WMO support |
| 13 | Train end-users on WIS use | August 2016 | N-WIS-IP-TT, WIS-FP | Un-Known | End users start using WIS for their service | WMO support |
| 14 | Regularly monitor and evaluate the N-WIS-IP performance | January 2016- Jan 2017 | WIS-FP, PR |  | Implementation of N-WIS-IP |  |

### Sudan

Country: Sudan

| Action No | Action | Responsibility | TIME |
| --- | --- | --- | --- |
| 1. | National Decision to join WIS as NC - Brief of Met Staff and Management on WIS and WIS plan - Identification of principal GISC - Nomination of WIS focal point - Communicating to WMO about the decision | PR + FP | Completed |
| 3 | Telecommunication and Networking infrastructure - Leasing Dedicated and high speed Internet capacity - Additional Communication means such as Satellite Communication if needed - Establishing connection Between central office to sub-national centres - Set up a communication link to the principal GISC and create user accounts at the GISC for using the GISC systems. - Set up a communication link to the RTH - Reception of information from international centres (including GTS) | PR+WMO | Completed |
| 4 | National/sub-national Services - TDFC conversion and data integration from station report to a consolidated bulletins - Transmit information to national users - Transmit information to international users – management of data flow (including GTS) | NC + FC | January 2016 |
| 6 | NC Certification - Communicate with the chosen Principal GISC for support in the process of NC certification. - Decide to support Metadata creation and update locally or remotely by GISC - Inform WMO by letter from the PR on The decision to become an NC and the endorsement from the Principal GISC - Creation and maintenance of WIS Discovery metadata records | PR+FP | February 2016 |
| 7 | Work shop and Training - Train a staff member in the WMO metadata Core Profile by sending them to training courses organized by WMO or the GISC. - Train all Technical staff about WIS - Train end users in WIS System | PR+WMP | November 2015 |
| 8 | Use WIS Functionality - Start using the WIS functionality for sending and receiving data with their associated metadata. - Join the user group of the GISC by attending meetings and other organized events. - Regularly monitor and evaluate the WIS performance | FP | Jul 2016 |

### Tanzania

NC Tanzania Meteorological Agency

| Action | Resources Required | Time Frame | Action Responsible Personnel | Deliverables | Status |
| --- | --- | --- | --- | --- | --- |
| - Make (national) decision to join WIS as a NC. | Commitment |  | PR | - Supporting WMO Program - Improving Service Delivery |  |
| - Identify the Principal GISC. | Official Request |  | PR | GISC Exeter Identified | Done |
| - Nominate the WIS Focal Point for the NC. | Capable HR |  | PR | Focal Point Appointed | Done |
| - Review the status of the information technology and communication network, in particular the bandwidth to the current RTH and the bandwidth of the Internet connection. |  | December 2015 | FP and WIS ITT | Reliable internet available | Partially |
| - Review the current GTS operation in terms of data exchange and ensure that the communication network is sufficient to send and receive data in a reliable and timely fashion under WIS. If this is not the case, the improvement of the communication network would be a priority. Solutions, such as increasing the bandwidth existing network or adopting additional communication means (e.g. satellite communication etc.) need to be implemented. |  | December 2015 | FP and WIS ITT |  | On Going |
| - Communicate with the chosen Principal GISC for support in the process of NC certification. Test cases listed in Appendix IV need to be carried out in cooperation with the GISC and approved by GISC. |  | Sept 2016 | PR | WIS Implementation Through technical support and consultancy | On Going |
| - Set up a communication link to the principal GISC and create user accounts at the GISC for using the GISC systems. |  | December 2015 | FP and WIS TT | Facilitation of Flow of and Access of to GISC | On Going |
| - Decide whether the metadata generation/update should be supported locally or remotely by the GISC. In view of this decision, set up the necessary software environment: either by installing the metadata editor on a local server or by setting-up a connection to the GISC to use the metadata editing facility on GISC system |  | December 2015 | PR |  | Not Yet |
| - Inform WMO by letter from the PR on:(a) the decision to become an NC and the endorsement from the Principal GISC after the success in performing the test cases; (b) the choice of the principal GISC and the nomination of the WIS Focal point, if haven’t done so yet |  | Past | PR | Confirmation for Operations | Done |
| - Train a staff member and, if possible, a back-up in the WMO metadata Core Profile by sending them to training courses organized by WMO or the GISC. It is also possible to ask for on-site support/training through the WMO WIS Jumpstart Offer. |  | Feb 2016 | PR | Capacity development for competence | On Going |
| - Take over responsibility for the metadata records describing the data submitted by the NMHS and modify/update them, if necessary. |  | March 2016 | FP |  | Not Yet |
| - Start using the WIS functionality for sending and receiving data with their associated metadata. |  | June 2016 | FP and WIS TT |  | Not Yet |
| - Join the user group of the GISC by attending meetings and other organized events. |  | On Going | PR and FP | Learning opportunities and addressing Challenges | On Going |
| - Support the monitoring of the regional WIS operation by responding to queries and/or questionnaires from the Principal GISC, which collects information, including availability of service, network traffic status, errors and other comments etc. |  | On Going | FP | Understanding the progress | On Going |

### Uganda

DRAFT WIS ACTION IMPLEMENTATION Plan FOR UGANDA

| Action No. | Action | Responsible | Time frame |
| --- | --- | --- | --- |
| 1. | Decision to join WIS | PR |  |
|  | - Nomination Of the Focal Point - Establishment of Task force on WIS implementation - Identifying the Principal GISC |  | December 2015 |
| 2 | Procure and installation of communication infrastructure | PR |  |
|  | - Upgrade the Band width |  | April 2016 |
|  | - AMSS |  | May 2016 |
| 3 | NC certification |  |  |
|  | - Contact the chosen Principal GISC for support in the process of certification and establish a communication link to the principal GISC. - Create user accounts at the GISC for using the GISC systems. - Metadata generation/update | PR PR Task force Task force | Jun 2016 |

| Action No. | Action | Responsible | Time frame |
| --- | --- | --- | --- |
| 4 | Implementation | PR |  |
|  | - Training work plan - Train all the Staff/users. - Testing - The decision to become an NC and the endorsement from the Principal GISC after the success in performing the test cases - Start using the WIS for sending and receiving data with the associated metadata | Task force Task force PR,GISIC, Task Force PR and Principle GISC | July 2016 September 2016 October 2016 December 2016 |
| 5 | WIS Monitoring and Evaluation |  | continuous |