Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres

- Several amendments of the WIS Manual – for example

  - Metadata keyword “GlobalExchange” indicating send to and Cache in all GISCs

  - Metadata Fast Track MM22 (November 2015 edition)

  - Metadata Category Code – NoLimitation (May 2015 edition)

  - Metadata XPath and Category Keywords spaceweather, .. (May 2014)

  - Clarification in the sections 2.3 “ Procedure for designating a DCPC“and 3.5 “GISCs
responsibilities” , updated List of GISCs and DCPCs and introduce list of NC, core profile 1.3 added to Manual on WIS (2013 Update)

Operate the procedures for technical endorsement of WIS centres

- TT-CAC all GISCs are endorsed – pre-operational status: GISC Casablanca and GISC Pretoria

  - Several DCPCs not engaging in certification, TT-CAC needs will try to be more proactive – TT-CAC wants GISCs also to be more pro-active in certifying DCPCs in their AOR.

  - NC certification now in Manual, key role of Principal GISC in process. Need to report certifications to TT-CAC (and secretariat)

Propose procedures for periodic assessment of the WIS centres, especially GISCs

- Periodic GISC review: TT-CAC Meeting March 2014 – which suggest to start with Audits in 2016; until now no further actions – no updates to on test cases yet – duality of guidance.doc on the one-side the template for the test on the other side leads to hurdles in running the performance tests – TT-DC suggested review of template

Request: TT-CAC meeting in Europe to develop the GISC review cycle, clean-up guidance.doc and target duality of guidance.doc and reporting template

Oversee and perform WIS operational and monitoring activities

- WIS Monitoring: January 2014 TT-OM workshop, outcome reviewed by TT-GISC and (partially) forwarded to ICT-ISS. Demonstration at Cg XVI of WIS Common Dashboards prepared by CMA, JMA and INMET – participating GISCS: Beijing, Brasilia, Casablanca, Exeter , Melbourne, Moscow, Offenbach, Seoul, Tokyo and Toulouse. Specification: initial version were prepared by BOM and then extended by CMA, JMA and DWD

- Procedure to change Principal GISC developed and discussed at TT-GISC 2014 now in Manual

OAI Test bed

- OAI Test bed – submitted to ET-GDPP chair and ET-WISC chair 2012, since 2013 in TT-CAC Trello – no feedback from any user

Develop a WIS Curriculum and Education requirements

- WIS Curriculum: Meeting and WIS curriculum prepared 10/2013 now in Manual and Guide but not published

  - GISC training in several GISCs, but need more aimed at increasing use of WIS by NC staff. Some GISCs have not reported any training

Quick addressed during TT-CAC telco today:

- Structure (TT-CAC)

  - TT-CAC should be independent of ET-WISC reporting to ICT-ISS (Separation of powers so to speak).

  - TT-CAC struggling with member availability (one reason for increasing GISC activity is to reduce work of TT-CAC members)

  - TT-CAC need to attract people with audit and QMS experience

- Structure (TT-OM, TT-GISC, TT-DC)

  - Not really working. RTHs missing working group ET-OI

  - Solution, Roll TT-OM back into TT-DC so ET-WISC has two TTs. GISCs and DCs

  - This way TT-DC takes over roll of ET-OI in coordinating RTHs