| World Meteorological Organization | CBS-MG-16/Doc. 03 |  |
| --- | --- | --- |
| COMMISSION FOR BASIC SYSTEMS MANAGEMENT GROUP | Submitted by: | Secretary-General |
|  | Date: | ...X.2015 |
| Sixteenth Session Geneva, 15-19 February 2016 | Original Language: | English |
|  | Status: | DRAFT 1 |

## Agenda Item 2: Organization of CBS-16

## Agenda Item 2.5: Review of the Performance of the CBS

# Review of OPAG IOS Workplan 2012-2016

# SUMMARY

Brief summary of the document

This document includes details about the OPAG IOS Expert Teams, Inter Programme Expert Teams, and Steering Group on Radio-Frequency Coordination (SG-RFC) workplans for the period 2012-2016, with updated status.

### DECISIONS/ACTIONS REQUIRED:

(a)	Advise whether any of the OPAG IOS Expert Teams, Inter Programme Expert Teams, and Steering Group on Radio-Frequency Coordination (SG-RFC)  work plans should be updated;

(b)	Recommend that the activities under Item no. 5 of the IPET-WIFI work plan (i.e. provide advice to ICG-WIGOS via CBS on GOS Quality Management practices and procedures) should be transferred into the work of the ICG-WIGOS WDQMS. ….;

### CONTENT OF DOCUMENT:

The Table of Contents is available only electronically as a Document Map*.

# DRAFT TEXT FOR INCLUSION IN THE GENERAL SUMMARY

## 2.	Organization of CBS-16 (agenda item 2)

### 2.5	Review of the Performance of the CBS (agenda item 2.5)

#### 2.5.1	Review of the OPAG IOS Workplan for 2012-2016 (agenda item 2.5.1)

The Group reviewed the OPAG-IOS Expert Teams and Inter Programme Expert Teams, as well as the one of the Steering Group on Radio-Frequency Coordination (SG-RFC). Key points for decision by the CBS-16 are addressed under agenda item 4.1.

IPET-WIFI

The Group reviewed the work plan of the Inter-Programme Expert Team on WIGOS Framework Implementation Matters (IPET-WIFI) for the period 2012 to 2016. The work plan with updated status as of 15 January 2016 is provided in Annex IV.

The Group noted that discussions regarding the possible transfer of activities from IPET-WIFI to ICG-WIGOS will take place under item 4.1 (OPAG-IOS).

The Group recalled the responsibility of the various Teams under OPAG-IOS with regard to OSCAR.

| CBS Team | Role | Reporting to |
| --- | --- | --- |
| ICT-IOS | Lead | ICG-WIGOS |
| IPET-WIFI | 1) Overall coordination and leadership at the technical level 2) Regulatory Materials and metadata required in liaison with ICG-WIGOS and its dedicated Task Teams | ICT-IOS |
| IPET-OSDE | 1) Functional requirements with regard to the tools required for the RRR process 2) Review content required for the RRR process including the observational requirements from application areas | IPET-WIFI |
| ET-SAT | Space-based observing systems capabilities (programmatic and technical updates) | IPET-WIFI |
| IPET-SUP | Space-based observing systems capabilities (user assessments) | IPET-WIFI |
| ET-ABO | Aircraft-based observing systems capabilities | IPET-WIFI |
| ET-SBO | Surface-based observing systems capabilities | IPET-WIFI |

Table 1

IPET-OSDE

The Group reviewed the work plan of the Inter-Programme Expert Team on Observing System Design and Evolution (IPET-OSDE) for the period 2012 to 2016 as decided by IPET-OSDE-1 (April 2014). The work plan with updated status as of January 2016 is provided in Annex I.

IPET-SUP

The Group reviewed the work plan of the former Expert Team on Satellite Utilization and Products (ET-SUP) for the period 2012 to 2014. Key results are provided for reference in Annex V. Recognizing the need to strengthen connections of the Team with applications-oriented Programmes and Technical Commissions, CBS-Ext. (2014) approved the Terms of Reference of the Inter-Programme Expert Team on Satellite Utilization and Products (IPET-SUP).

IPET-SUP proposes a new work plan covering the period 2015-2019, for consideration by ICT-IOS and adoption by CBS in 2016. The Group concurred with the new workplan provided in Annex VI.

ET-SAT

The Group recalled that CBS-Ext. (2014) adopted new Terms of Reference of the Expert Team on Satellite Systems (ET-SAT).  At its 10th session in November 2015, ET-SAT agreed to defer the review of the ET-SAT future work plan to a virtual meeting in spring 2016. It was highlighted however that the following three tasks are central to the work of ET-SAT in 2016:

- finalizing a draft Vision of the WIGOS space-based component in 2040

- in accordance with the Terms of Reference and the decision from CBS, to oversee the development of OSCAR/Space version 2 and to keep under review the description of space–based capabilities in OSCAR (programmatic and technical update),

- to conduct a gap analyses using the updated OSCAR/Space

The assigned responsibilities of ET-SAT and IPET-SUP for maintaining OSCAR/Space are provided in Table 1 for reference (CBS-Ext. (2014)).

ET-ABO

The Group reviewed the work plan of the Expert Team on Aircraft-Based Observing Systems (ET-ABO) for the period 2012 to 2017 as reviewed by the ET-ABO at its December 2015 meeting. The Group noted that there will probably have to be a further iteration before it is approved together with the budget for 2016-2017. The work plan with updated status as of December 2015 is provided in Annex II. Further information on work plans and budget for the Aircraft-Based Observations Programme (ABOP) is also available on the WMO website.

ET-SBO

The Group reviewed the work plan of the Expert Team on Surface-Based Observing Systems (ET-SBO) which status was updated based on the outcomes of ET-SBO-2 in October 2015. The work plan with updated status as of October 2015 is provided in Annex III.

SG-RFC

The Group reviewed the work plan of the Steering Group on Radio-Frequency Coordination (SG-RFC) noting its seven main elements. As indicated by Res 29 (Cg-17), the World Radiocommunication Conference (WRC) cycle continues to be a priority with the next WRC being in 2019 (WRC-19). In parallel and complementary to the WRC activity is the need to continue to monitor and address spectrum issues related to meteorological and earth exploration systems and communication systems associated with WMO activities. A key item will be the determining of Space Wx present and future radio frequency needs. As noted in the Strategic Plan for radio frequency coordination, a critical activity is the collaboration with ITU’s working groups and regional elements as well as with other specialist bodies such as the Space Frequency Coordination Group (SFCG), CGMS and GEO. Key tactical activities will be the review of the joint WMO/ITU Handbook “Use of radio spectrum for meteorology: weather, water and climate monitoring and prediction” and the conducting of a joint WMO/ITU workshop. Both these were last addressed in 2008 and 2009.

The work plan is provided in Annex VII.

______________

Annex I

Inter Programme Expert Team on Observing System Design and Evolution (IPET-OSDE) workplan 2012-2016

with status of tasks

(Workplan as decided by IPET-OSDE-1, April 2014; status of tasks as of 19 January 2016)

| Id | Priority | Objective | Outcome | Deliverable | Activity | Leader | Due | OtherETs | Effort | StatusReport |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | To contribute to the implementation of WIGOS, including WIGOS Manual, and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by Congress XVI, and then ICG-WIGOS | Relevant WIP activities addressed | Meeting | Chair IPET-OSDE | Ongoing | ICG-WIGOS, IPET-WIFI |  | OND Principles included in WIGOS Manual OND Guidance addressing the principles under development Vision 2040 & updated Vision 2025 to be discussed at IPET-OSDE-2 |
| 2 | 1 | Survey and collate user requirements for observations for WMO and WMO-sponsored programmes | Review and update WMO database of observational user requirements, through Points of Contact for application areas. | OSCAR/Requirements up to date | Review by FPs | Chair IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; PoCs regularly contacted for updates |
| 3 | 1 | Survey and collate observing systems capabilities for surface-based and space-based systems that are components or candidate components of WIGOS | Review and update WMO database of observing system capabilities, in collaboration with other OPAG IOS ETs and other Technical Commissions as appropriate. | OSCAR/Space & OSCAR/Surface up to date | Review by Members (coordination via NFPs) | Chair IPET-OSDE | Ongoing / Annual review | ICT-IOS, ET-ABO, ET-SBO, ICG-WIGOS/TT-WMD |  | Ongoing for space-based, and recorded in OSCAR/Space. Ongoing for surface-based through feedback from the NFPs. OSCAR to be used when operational in April 2016 |
| 4 | 1 | Maintain Rolling Review of Requirements (RRR) for observations in several application areas, using subject area experts, including appropriate liaison with Technical Commissions and programmes and co-sponsored programmes (e.g. CAS, JCOMM, CAeM, CAgM, CHy, CCl, GCOS, GFCS, and GCW) | Continue RRR process for the listed application areas and expand to new areas as required: review and update as necessary Statements of Guidance on the extent to which present/ planned observing system capabilities meet user requirements, through Points of Contact on application areas. | Statements of Guidance for all Application Areas | Application Area Contact Points; Meeting | Chair IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; some SoG reviewed. Overall review done by IPET-OSDE1. Some updates to user requirements and SoGs made after IPET-OSDE1 |
| 5 | 1 | Prepare and maintain reviews of observation impact studies undertaken by NWP centres and provide information for consideration by IPET-OSDE and OPAG-IOS | Rapporteurs on Impact Studies and NWP experts, review results of impact studies relevant to the evolution of observing systems. Organize and hold next NWP Impact Studies Workshop in 2016. | Findings of impact studies | Impact studies | Rapporteurs on Scientific Evaluation of Impact Studies undertaken by NWP Centres | 2016: workshop |  |  | Report of the 5th NWP “Impact” workshop (Sedona, 2012) Published. Ongoing; recent findings, and proposals for new impact studies discussed at IPET-OSDE1 and approved by CBS Ext.(2014) |
| 6 | 1 | Promote CBS activities in support of GCOS goals | Review the implications of the progress on the GCOS Implementation Plan for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCOS | Meeting | Rapporteur on GCOS matters | 2013 2016 |  |  | Ongoing interactions between IPET-OSDE Chair and GCOS. |
| 7 | 1 | Promote CBS activities in support of GFCS goals | Review the implications of the GFCS IP for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GFCS | Meeting | Chair IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE1. GCOS/GFCS interaction encouraged. |
| 8 | 1 | Promote CBS activities in support of GCW goals | Review the implications for the activities of CBS of the GCW developments, including the GCW Implementation Strategy, and the Cryosphere theme report for the IGOS partnership. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCW | Meeting | Chair IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE1. CBS CWP submitted to the AOS1. |
| 9 | 1 | Monitor progress and actions by Members and partner Organizations per the approved Implementation Plan for the Evolution of the global observing systems (EGOS-IP), fully responding to the “Vision for the GOS in 2025”,and promote activities in support of progress | Seek feedback from National Focal Points, Expert Teams, relevant Technical Commissions, and other groups on the implementation of EGOS-IP, and keep the EGOS-IP progress report up to date. Initiate and monitor activities which promote progress. | EGOS-IP progress report | Survey with FPs, TCs; meeting | Chair IPET-OSDE | Ongoing / Annual review |  |  | Ongoing. Feedback against the new EGOS-IP requested to the NFPs for 2013. Reviewed at IPET-OSDE1. New feedback by action “owners” and NFPs for 2014 and 2015 to be reviewed by IPET-OSDE-2 |
| 10 | 1 | Propose guidance regarding observing system network design principles | Draft guidance document on network design (to be further discussed at IPET-OSDE-1 in 2014) | Guidance document on network design | Meeting | Chair IPET-OSDE | End 2013 2014 |  |  | 2 workshop organized in Nov. 2013 and Feb. 2015. OND Principles approved with WIGOS Manual. Draft OND guidance initiated, as well as roadmap. |

___________

Annex II

EXPERT TEAM ON AIRCRAFT-BASED OBSERVING SYSTEMS (ET-ABO) WORK PLAN, 2016-2017

(2016.1D3, Draft, December 2015)

| No. | ToR | Task | Sub-tasks | Description | Responsible | Commence | Complete | Status | Deliverables/ Activities | Progress | 2015 Budget Expend | 2016 Budget Estimate | 2017 Budget Estimate |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | (a) | Compile ET-ABO work plan and budget. | - 2016 WP & Budget - 2017 WP & Budget |  | Ch/ET-ABO | Q4 2013 | Ongoing | 2 | Work Plan, Ann. Budget 2016,2017 | - Plan & Budget 2015 approved. |  |  |  |
| 2 | (a) | Meetings of ET-ABO |  | Hold a meeting, 2nd half of 2015. Requirements: - Agenda (Ch-ET-ABO); - Meeting Form (SO/ARO) - Meeting Q4 2017 | Ch/ET-ABO | Q1 2015 | Ongoing | 1 | Agenda, Meeting Form, Meeting | - ET-ABO-1 held in Sep 2013 - ET-ABO-2 in progress, Dec 2015 |  |  |  |
| 3 | (b) | Establishment of ABO Metadata (national, international) | Finalise Imp. Plan |  | S.Taylor, SO/ARO | Q3 2013 | Q4 2013 | 2 | AMDAR Metadata IP | This task is now incorporated in OSCAR development |  |  |  |
|  |  |  | Incorporate metadata specification into draft Reg. Material |  | S.Taylor, SO/ARO | Q2 2013 | Q4 2015 | 1 | Metadata definition incorporated into WIGOS Reg. Mat. | This task will be incorporated into Task 28. |  |  |  |
|  |  |  | Establish Metadata Pilot Project | Pilot project to test the exchange of metadata. Will need a recipient data centre (e.g. CMC or the AO Data Centre?) Funding possibly required for software development | S.Taylor, SO/ARO | Q4 2013 | Q1 2014 | 0 | Pilot project in place. | This task has been overtaken by activities related to OSCAR OSC development. Expect ABO metadata will be incorporated within OSCAR. |  |  |  |
|  |  |  | ABO metadata management in OSCAR | - Assist in and contribute to the establishment of a system for ABO metadata management in OSCAR. - Contribute to documentation/guidance of OSCAR | S.Taylor, SO/ARO | Q2 2014 | Q4 2016 | 1 | ABO global metadata management system in OSCAR | - Requirements for ABO metadata management and capabilities have been provided. | 0 (30) | 57 |  |
| 4 | (b) | Establish AO Data Centre | - Write to pros. Centres; - Define requirements of AO DC - Finalise agreement with NOAA/MADIS - Submit proposal to ICT-IOS, CBS | Prospective centres: - NCEP - CMC - NOAA NCDC - EUMETNET - Panasonic Aviation May require both establishment and ongoing funding support. | Ch/ET-ABO, SO/ARO | Q1 2013 | Q4 2016 | 2 | AO Data Centre | - Initial approaches made to prospective centers (Q3 2013) - Set of requirements finalized - Discussions & meetings with NOAA re MADIS over 2015. | 0 (25) |  |  |
| 5 | (b) | Document ABO QMS |  | Include: - Recomm. from Workshop on DM | J.v.d.Meulen, ET-ABO | 2012 | Q4 2014 | 1 | ABO QM Documented in WMO Reg. Mat. | This task will be incorporated into Task 28. |  |  |  |
| 6 | (b) | Revise and update AOP Data QC and QM procedures |  | Include: - Relevant recomm. From Workshop on DM - Use of flags - Policy on ICAO data QM - Spec. of QC by DPCs/NMSHSs - Reqs for NWP - Radiosonde comparison | J.v.d.Meulen, D.Body | Q4 2013 | Q4 2014 | 0 | QC Procedures updated in WIGOS Reg. Mat. | This task will be incorporated into Task 28. |  |  |  |
|  |  | Improve QC and management of ADS Data | - Provide requirements to ICAO - Liaise with WAFC toward solution to ADS-C QC establishment. - Meet with ICAO and WAFC reps in 2015 to finalise arrangements - Meet with ICAO and WAFC reps in March 2016 - Develop plan for ADS-C migration to BUFR - Develop plan for ADS-C data processing by WAFC center delegates - Develop guidance on QC |  | - SO/ARO - SO/ARO - SO/ARO - SO/ARO - JvdM - C Tyson, M Strahan - S. Taylor; C Tyson | Q4 2013 | Q4 2016 | 1 | - Requirements developed & provided to ICAO - ADS-C Implemented. | - WAFC representatives to ET-ABO identified, added as assoc. members. - Workshop held with representatives of ICAO and WAFCs in October 2015 |  |  |  |
| 7 | (c) | Coordinate with CIMO ET-AO on Scientific & Technical Matters | - Coord. Finalization of 2016-17 WP. |  | Ch-ET-ABO, SO/ARO | 2012 | Ongoing | 2 | Harmonised Work Plan & Budget for the ABO Program. | - Ch-ET-AO attended ET-ABO-1 - Vc-ET-ABO attended ET-AO-1 as member - Joint meeting of ET-ABO/ET-AO Dec 2015 |  |  |  |
| 8 | (c) | B777 Software Dev. | - Finalise negotiations with AFR and KLM in consult. with E-AMDAR & Meteo-France. - Finalise agreement with stakeholders on final costs. - Finalise implentation and software roll out. | - Combined action with ET-AO | Ch/ET-ABO, SO/ARO, Ch-ET-AO, S.Stringer (E-AMDAR PM) | 2012 | Q2 20165 | 2 | B777 AMDAR Software application | - Activity delayed in 2013 due to neg. with AFR and KLM. - Agreement signed with AFR for S/W development Dec 2014 - S/W developed by Air France Q3 2015. - QC of operational data by E-AMDAR ongoing |  | In ET-AO Budget |  |
| 9 | (d) | Study on Data Coverage and Airline Capabilities | Complete study & publish |  | SO/ARO | Q1 2012 | Q1 2013 | 4 | Published study | Study completed and published. COMPLETED |  |  |  |
| 10 | (d) | Mexico Prog Implement. | - Finalise ARINC Contract - Monitor contract & data - Seek extension of contract for 2017-18 funded by SMN Mexico |  | SO/ARO | 2012 | Q4 2016 | 2 | Contract | - Contract with ARINC delayed - WMO approval for contract provided in Nov 2013 - Program operational in Oct 2014 - SMN to pay 1st year of data costs – WMO to pay 2nd year. - ARINC Contract est. July 2014 - Est. contract paid Jan 2015 - Monthly billing comm. from Jan 2015. | *19 (24) | 24 (SMN Mexico via Trust) | 24 (SMN Mexico via Trust) |
| 11 | (d) | Employ AMDAR Dev. Officer (ADO) | - Negotiate with EUMETNET for 0.5 persons working with E-AMDAR for WMO ABO. |  | SO/ARO, Ch/ET-ABO, GF | Q1 2013 | Q4 2016 | 2 | Job Description, ADO employed. | - Mr Stig Carlberg was employed as ADO over period July 2013 through January 2015. - Mr Carlberg completed contract in Jan 2015. - Expectation is that a continuing arrangement will be made with a technical consultant to provide technical support for international AMDAR development. | 0(30) | 40 | 60 |
| 12 | (d) | Develop Global & Regional ABOP Imp. Plans | ABOP Strategy & Implementation Plan (A-SIP) | This may incorporate the following: - WVSS Implementation - Letter to airlines based on consideration of Data Coverage & Airline Targeting study; - Letter to PRs of relevant countries based on consideration of Data Coverage & Airline Targeting study; - Letter to RAs. - Update A-SIP to version 2016. | SO/ARO, Ch/ET-ABO, Vc/ET-ABO | Q1 2013 | Q4 2016 | 4 | - A-SIP Completed and published; - Draft A-RIP Template completed. - A-SIP ver. 2016 | Ver. 2015.1 COMPLETED |  |  |  |
|  |  |  | Development of Region I ABOP Regional Implementation Plan | - Possible that these plans can be developed in coordination with RA sessions. - Attend RA I session in Feb 2015 and present A-RIP - Work with RA I on: 1) A-RIP in WIGOS-IP, 2) Form RA I work group. - Meet with AMCOMET Project Officer - Quarterly meetings of Region I work group. - Participate in Int. Aviation Conf. April 2016. - Maintain A-RIP | SO/ARO, G.Ilboudo, F.Mosetlho | Q2 2013 | Q4 2016 | 2 | - Region I A-RIP - Participation at RA I session in Feb 2015 | - Mature draft A-RIP has been produced. - Item on RA I RECO on AMDAR has was presented by SO/ARO (Feb 2015). - AMDAR adopted as AMCOMET Project. | 0 |  |  |
|  |  |  | RA I AMDAR Workshops | - Schedule first in 1st half of 2015, likely to be held in Kenya in April. - Possible 2nd workshop to be held in Morocco in 2nd half of 2015 possibly in conjunction with joint meeting of ETs. | ET-ABO, SO/ARO, J.Ngamini, RA I FPs | Q2 2013 | Q4 2015 |  | - AMDAR Workshop held in Kenya - AMDAR Workshop held in Morocco | - Requests to host workshops have been received from KMS and Morocco MS. - Negotiations with KMS have commenced to hold workshop in April 2015. - Workshop held in June 2015 - Workshop held in Morocco, Dec 2015 | 22 (Ken.) *16 (Mor.) |  |  |
|  |  |  | AFIRS Trial in RA I | Investigate and, if feasible, implement a trial of AFIRS data provision within RA I. | G Ilboudo, ET-ABO, SO/ARO | Q1 2014 | Q4 2016 | 1 | - Data from trial obtained and analysed. - Report to ET-ABO and CBS. | - Consulted with FlyHt and obtained quotation – expect to go ahead in 2015. - Activity included in draft A-RIP. | 0 (17) | ? | ? |
|  |  |  | E-AMDAR Data Provision Trial Region I | - Investigate and if feasible request E-AMDAR to provide all possible AMDAR data over Region I for a one year period. - Ensure all Region I Members are aware of the trial. - Ensure an impact assessment is undertaken - Seek collaboration with Region I Members for continuation of data provision beyond the trial. - Extend scope to include data from B777s. | ET-ABO, SO/ARO | Q4 2014 | Q4 2016 | 1 | - E-AMDAR AMDAR data made available for one year. - Region I Members reports on impact of data. - (NWP) Impact assessment on supplementary data. | - Costing has been provided by E-AMDAR (4K per annum) - Activity has been included in the draft A-RIP - E-AMDAR have provided est. costs for existing fleets exc. B777s | 0(2) | ? | ? |
|  |  |  | Development of Region II ABOP Regional Implementation Plan |  | ADO, SO/ARO, ? | Q2 2013 | Q4 2016 | 2 | Region II A-RIP | - No significant progress |  |  |  |
|  |  |  | Development of Region III ABOP Regional Implementation Plan |  | ADO, SO/ARO, J.Horler | Q2 2013 | Q4 2016 | 2 | Region III A-RIP | - No significant progress on A-RIP - AMDAR was presented at RA III session in Sep 2014 – rapporteur on AMDAR was appointed. |  |  |  |
|  |  |  | Development of Region IV ABOP Regional Implementation Plan |  | ADO, SO/ARO, G.Fournier | Q2 2013 | Q4 2016 | 2 | Region IV A-RIP | - Draft A-RIP has been developed. - RA has been contacted and request for review of A-RIP made. |  |  |  |
|  |  |  | Development of Region V ABOP Regional Implementation Plan |  | ADO, SO/ARO, D. Body | Q2 2013 | Q4 2016 | 2 | Region V A-RIP | - Draft A-RIP has been developed. - R. Stringer (Lead WG on Infrastructure) presented ET-ABO coordination plans to the RA Session in May 2014 – A WG on AMDAR would be established if enough Members nominated experts. |  |  |  |
|  |  |  | Development of Region VI ABOP Regional Implementation Plan |  | ADO, SO/ARO, S.Stringer | Q2 2013 | Q4 2016 | 2 | Region VI A-RIP | - Draft A-RIP has been developed. - RA has been contacted and request for review of A-RIP made. - WMO and EUMETNET have agreed on collaboration on AMDAR international regional development under their MoU. |  |  |  |
|  |  |  | Request collaboration with RAs | Collaborate with RAs towards adoption of A-RIPs. | ET-ABO Region Leads, SO/ARO | Q4 2013 | Q4 2016 | 2 | - Correspondence to Pres. RAs compiled and sent. | - ET-ABO Regional Leads have corresponded with relevant working group leaders and other members of RAs. |  |  |  |
|  |  |  | Request collaboration with NMHSs | - List of target NMHSs (based on target airlines) to be compiled; - Ch-ET-ABO to write to PRs of NMHS to request collaboration on programme development - Letter to 10 target NMHS in 2016 | Ch-ET-ABO, SO/ARO | Q4 2013 | Q1 2014 | 4 | Letters to target NMHSs compiled and sent. | - Letter was sent to all PRs in Q1 2014 - CBS approved RA collaborative process (ext-2014) |  |  |  |
|  |  |  | RA V Air Niuguini FlyHt/AFIRS Project | Objective is to implement (3) Air Niugini aircraft and fund data for 1 year and ensuring future continutation. - Investigate options for equipping Air Niugine aircraft for reporting. - Determine requirements and means for data processing for GTS trans. - Implement project. - Investigate options for future funding. | D.Body | Q1 2015 | Q4 2016 | 1 | ABO Data for SW Pacific | - Initial investigations have been made. - Offer provided by FlyHt - Proposal has been prepared by ADO. - Initiative has been delayed until 2016 due to excessive cost of software. | 0(17) | 15 | 5 |
|  |  |  | Consultancy for AMDAR expansion & enhancement project | Project initiated during 2014 in consultation with WMODevelopment and Regional Activities to formulate business case materials and comms strategy for AMDAR program development. - Develop statement of work. - Undertake tendering process in WMO Sec. 3. Contract consultant and provide subject matter expertise. | SO/ARO, ET-ABO | Q2 2014 | Q1 2015 | 4 | - Roadmap and Funding proposal. - Business cases. - Communications Strategy | - Sub-tasks 1 and 2 completed. - Consultancy firm Dalberg has been contracted. - Roadmap and Funding proposal has been delivered. - Draft Comms strategy and business cases have been delivered. COMPLETED | 50 (49) |  |  |
| 13 | (d) | Polar ABO | Report on the availability of observations over polar regions |  | Ch-ET-ABO | Q3 2013 | Q4 2013 | 4 | Ch-ET-ABO to report to EC-PORS (24-28 Feb. 2014) | COMPLETED |  |  |  |
|  |  |  | Investigate and report on possible airlines/aircraft to enhance polar ABO coverage | 1. G.Fournier to follow up with Panasonic re Arctic coverage. | ET-ABO, N.Jacobs | Q3 2013 | Q4 2013 | 4 | Provide input to Ch-ET-ABO for report to EC-PORS | COMPLETED |  |  |  |
|  |  |  | Seek proposal from PAC for sat comm. ABO data provision for 1 year | G. Fournier |  |  |  |  |  |  |  | ? | ? |
| 14 | (d) | Establish ASECNA requirements for Supplementary AMDAR Data |  |  | SO/ARO, J.Ngamini | Q2 2013 | Q2 2014 | 4 | Data Agreement with EUMETNET/E-AMDAR | - ASECNA approached and declined. - This activity is now being taken up under the Region I A-RIP. COMPLETED |  |  |  |
| 15 | (d) | Optimise Existing Program Coverage | - Determine existing potential coverage, capacity to provide the additional potential data & cost of doing so. | AMDAR Program Managers to provide potential vertical profile coverage. SO/ARO to make request. | ET-ABO, Operational Program FPs | Q1 2013 | Q2 2015 | 2 | Report to ET-ABO | - E-AMDAR have identified potential to provide supplementary data. This will be incorporated in Region I A-RIP under task 12 |  |  |  |
|  |  |  | - Investigate WMO ability to admin. MoUs between NMHSs - WMO Sec. to establish MoU system and Trust budget line for sup. Data provision |  | SO/ARO | Q2 2013 | Q4 2016 | 2 | Report to ET-ABO |  |  |  |  |
|  |  |  | - Fund supplemenary agreed data provision activities | Region I, B777, PAC |  |  |  |  |  |  |  | 50 | 50 |
| 16 | (d) | Develop guidelines for AMDAR Program Dev. | - provide revised draft to ET-ABO - Guidelines to be published in Man. or Guide on WIGOS | Publish in relevant guide. | - Ch-ET-ABO, S.Taylor - Review group, Task 28 | Q3 2013 | Q1 2014 | 4 | Guidelines for AMDAR Prog. Dev. Published in Reg. Material. | - Guidance published as WIGOS TR 2014-2 COMPLETED. |  |  |  |
| 17 | (d) | Attend meetings of relevance to global AMDAR dev. | - Establish collaboration with ICAO Met Panel, IATA FOSTF, AMS | This may include: - 2 E-AMDAR TAG meetings per annum; - Participation in ICAO/ASECNA meeting RA I (Aug 2014) - Others. | SO/ARO, ET/ABO | Q2 2013 | Q4 2016 | 2 | Meetings attended. Reports produced for ET-ABO and Secretariat | - Ch-ET-ABO attended IPET-OSDE, Feb 2014 (1.9K) - Ch-ET-ABO attended ICT-IOS-8, Mar 2014 (2.2K) - ET-ABO Chair attended meetings 23, 24 (2014) (3.3K) - D.Lockett attended NOAA Workshop on ABO, April 2014 (5.7K) - G.Fournier participated in the ICAO/ASECNA meeting in Aug. 2014 (1.9K) - S.Carlberg attended ET-ABO/SG-RM Meeting (2.1K) - S.Pritchett attended DLUF Feb. 2015 - S.Taylor attended AEEC GA, Apr. 2015 - D.Lockett attended E-AMDAR ET, Nov 2015 | 4 (15) | 15 | 15 |
| 18 | (e) | Papers on Impact of AMDAR Data | - Publish 2 papers on AMDAR data impact - Prepare and present paper at ATRS Conf, Bordeaux, July 2014 (SSA ext.) | - Draft papers received - Papers reviewed - Papers published | SO/ARO, ET-ABO Review Team | 2012 | Q4 2014 | 4 | Published papers | - Drafts received and reviewed Q3 2014 - Final versions of submitted papers received. - R.Petersen attended ATRS meeting, Bordeaux, June 2014 (6K) - Papers will be published in BAMS in Q1 2015. - Papers merged and published as WIGOS TR (July 2015) COMPLETED |  |  |  |
| 19 | (e) | AMDAR Impacts and Benefits Documentation | Benefits for Aviation Document | - Revise & Finalise Statement of Work - Seek EoIs from consultants and commence and complete SSA - Publish report as WIGOS TR | Ch/ET-ABO, SO/ARO | Q1 2013 | Q1 2016 | 2 | - SoW - SSA with selected Consultant and delivery of benefits document | - Kick-off meeting held 9 December 2013 - 1s draft has been provided and reviewed - SSA Appointed Feb 2014 completion has been delayed due to complexity - SSA Extended to include provision of modeling study on fuel burn. - SSA completed (Sep 2015). | 34(24) |  |  |
|  |  |  | ABO Benefits to Meteorology & Aviation Document | Work collaboratively with ABO Focal Points to compile a general ABO benefits document. | Ch/ET-ABO, SO/ARO, FPs Op. Programmes | Q3 2013 | Q1 2014 | 4 | ABO Benefits Document completed & published online. | - Document published as WIGOS Tech. Report 2014-1 COMPLETED |  |  |  |
|  |  |  | Publish Flyers on AMDAR Program Benefits | Develop 3 new short flyers on AMDAR benefits to/from: - Aviation - Meteorology - Water vapour measurement | ET-ABO, ADO, SO/ARO | Q1 2014 | Q4 2016 | 1 | Flyers published | - Flyer on AMDAR benefits to aviation has been completed and published - Drafts of flyers 2 and 3 have been completed by ADO. - Flyer 1 pub. Aug 2014. |  |  |  |
| 20 | (e) | AMDAR Training Module | Develop SoW for Training Module | - Present SoW to ET/ABO for assessment; - As per AMDAR-15, funding to be sought as ring-fenced item in TF. | Lead AMDAR Training & Outreach (C.Weiss) | Q3 2013 | Q4 2013 | 4 | SoW | COMPLETED |  |  |  |
|  |  |  | Investigate possible joint NOAA/WMO project to fund COMET to develop module. | - C.Weiss to investigate possibility within NOAA - SO/ARO to investigate possibility within WMO - If all ok, proceed to having funding approved - Develop project in collaboration between NOAA, ET-ABO & COMET | C.Weiss, SO/ARO, Ch-ET-ABO, Vc-ET-ABO, Ch-ET-AO | Q1 2014 | Q3 2014 | 4 | Contract secured with COMET. | - Kick-off meeting held 29 November 2013 - Module has been completed and will be released in Q1 2015. (+30K from NOAA) COMPLETED |  |  |  |
| 21 | (e) | Attend Relevant Aviation Meetings | Attend AEEC Data Link Users Forum, 2012-2016 | - S.Prtichett to represent ET-ABO at AEEC DLUF meeting in Panama, Feb 2015 | ET-ABORep, SO/ARO, Ch-ET-ABO. | Q4 2013 | Q4 2016 | 2 | Attend meetings; report to ET-ABO; | - C.Weiss, S.Taylor attended USA, Europe meeting in 2013; Reports produced. - S. Taylor attended DLUF meeting in Brussels, Sep 2014; Report produced. | 2 (2) |  |  |
|  |  |  | Promote AMDAR & ABO at WMO/ICAO Joint Meeting, July 2014, Montreal | This may also potentially be used as the venue to launch a WMO/ICAO joint project on ABO development. | SO/ARO, Ch-ET-ABO | Q4 2013 | Q3 2014 | 4 | Report to ET-ABO on promotion activities. | - Submitted discussion paper to joint meeting. Funding from Item 17 COMPLETED |  |  |  |
| 22 | (e) | WMO AMDAR Newsletter | Produce Newsletter Vol 5 |  | ET-ABO, AMDAR FPs, SO/ARO | Q2 2013 | Q2 2013 | 4 | Newsletter Vol 5 | COMPLETED |  |  |  |
|  |  |  | Produce Newsletter Vol 6 |  | ET-ABO, AMDAR FPs, SO/ARO | Q4 2013 | Q4 2013 | 4 | Newsletter Vol 6 | COMPLETED |  |  |  |
|  |  |  | - Produce NewslettersVols 9 &10 (2015) - Produce NewslettersVols11 &12 (2016) |  | ET-ABO, AMDAR FPs, SO/ARO | Q1 2014 | Ongoing | 2 | - Newsletter Vol 7 & Vol 8; - Newsletter Vol 9 & Vol10 - Newsletter Vol 11 & Vol12 | - Vol 7 and Vol 8 published (2014). |  |  |  |
| 23 | (e) | Global AMDAR Program Development Workshops and Seminars | - Workshop in Region II, Mid-east. - Workshop in ? |  | ET-ABO | Q2 2013 | Q4 2016 | 2 | - Region II Workshop | - Workshop postponed until 2015 - Middle-East Workshop postponed until 2016 | 0 (20) | 40 | 40 |
| 24 | (e) | Maintain & Develop WMO ABO and AMDAR Websites | Operational programmes to produce a technical description of their programmes for the website | - SO/ARO to develop a template - Operational programme managers to provide the input. | SO/ARO, Op. Programme Managers | Q4 2013 | Q4 2016 | 2 | AMDAR Programme Technical Descriptions published online. | - Template developed. - E-AMDAR implemented new template (December 2014). |  |  |  |
|  |  |  | Investigate Cross-promotion from Av. Org. Websites | - SO/ARO to contact N.Halsey to investigate possibilities for ICAO website X-promotion; - SO/ARO to contact H-R Sonnabend to investigate possibilities for IATA website X-promotion | SO/ARO | Q4 2013 | Q4 2016 | 1 | X-promotion on ICAO and IATA websites | - No progress due to other priorities |  |  |  |
| 25 | (f) | Provide input to ICG-WIGOS/TT-WMD | Attend TT-WMD Meetings |  | S.Taylor, SO/ARO | Q1 2013 | Ongoing | 2 | Determine req. for input to TT-WMD | - Commenced - S.Taylor attended TT-WMD meeting, December 2014 - S.Taylor attended TT-WMD-4, Oct 2015 |  |  |  |
| 26 | (f) | Provide input to ICG-WIGOS/TT-WRM | Attend TT-WRM Meetings |  | J.v.d.Meulen | Q1 2012 | Ongoing | 2 | Determine req. for input to TT-WRM | - J.v.d. Meulen attended TT-WRM meetings, June and November 2013. |  |  |  |
| 27 | (f) | Contribute to the WMO/CBS RRR Process | - WAFCs to review AeM SoG. | Continuous process | SO/ARO, ET-ABO | 2012 | Ongoing | 2 | Input in RRR Database SoR Document/ input in RRR OSC Database | - SO/ARO and S.Taylor provided requirement specification for determination of aircraft systems capabilities. |  |  |  |
| 28 | (f) | Revision of AMDAR Regulatory Material in WIGOS context | - Revise current status. - Develop plan for update process. - Meeting of SG-RM (Dec 2014) - Consolidation of draft material for ET-ABO-2 | - Develop new ABO input to the Manual on the GOS and Guide to the GOS - Finalise input through the CBS process. | ADO; J.v.d.Meulen, Ch-ET-ABO, A.Hoff, D.Body SO/ARO to form review team on Reg. Mat. | Q3 2013 | Q4 2016 | 2 | - Plan for integration of AMDAR RM into WIGOS RM. - Commence and complete update of Reg. Mat. in Man. on WIGOS and Man. on GOS | - Review team met as Sub-Group on Regulatory Material in December 2014 – produced initial draft of ABO content for Manual on GOS and Guide to GOS. |  |  |  |

Notes

- Status

- Idea

- Initiated/Commenced

- Ongoing

- Review Deliverable

- Deliverable accepted/Activity Completed

- ET-ABO ToR: http://www.wmo.int/pages/prog/www/CBS/Lists_WorkGroups/CBS/opag%20ios/et-abo/tors

- For context and long-term plans, see: http://www.wmo.int/pages/prog/www/GOS/ABO/ABO_Work_Program.html

Annex III

EXPERT TEAM ON SURFACE-BASED OBSERVING SYSTEMS (ET-SBO) WORK PLAN for the period 2013 – 2016

Version 1.5

Includes updates from review during ET-SBO-2 in Tokyo Japan October 2015.

Additional information added to plan to improve clarity

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Helping WIGOS Succeed Original Text: Contribute to the implementation of WIGOS by undertaking those tasks assigned to it by the OPAG IOS Chair from the WIGOS Framework Implementation Plan [ToR a] Informally, as discussed at ET-SBO-1 and ET-SBO-2, this ToR has become: “Contribute to the implementation of WIGOS by undertaking those tasks assigned to it by the CBS/IOS IPET WIFI Chair and other relevant groups” In 2015/6 the focus will be on developing the Quality Management and Incident Management Function as discussed at the December 2014 QM Workshop. The proposal will be presented to CBS in 2016 for approval. This task includes work taken from work plan item 6 to simplify the reporting of tasks. | Address relevant items of WIGOS Implementation Activities assigned to ET-SBO, details to be forthcoming during work plan period, see individual task sheets for more detail. | Ongoing | Co-ordination Lead: Chair ET-SBO for overall delivery with lead and contributors for each task identified | On track | 100 days provisionally assigned to this work plan item. SJG 21/10/15: At ET-sBO-2 it was highlighted that other tasks would come to ET-SBO for review from WIGOS Task Teams. However they would not all be explicitly included in the work plan. |
| 1.1 |  | Regulatory Material Review the following sections of the Manual on the GOS: Part III (surface-based sub-system) except 2.5 and 2.7. See Annex III Breakout Group 1 information for more detail. | October 2013 | Task Lead and Contributors: See the detailed attachment on pages 3 to 5 of Annex III. | Complete | Significant task requiring ~20 days of effort in total. SJG 19/12: Report submitted to TT-WRM before November meeting, suggest task complete. |
| 1.2 |  | Metadata Use several specific surface-based observing systems to road-test the draft WIGOS metadata core profile. After road tests review the lessons learnt | November 2013 | Task Lead and Contributors: See the details in the report of Break out group 1 on page 2 for details. | Complete | Significant task requiring ~20 days of effort in total. SJG 19/12: Review of Profile complete and top level feedback given to TT-WMD, suggest task complete. |
| 1.3 |  | Quality Management Improve quality monitoring of WMO / CBS / GOS surface-based observations exchanged globally by: Review the operation of the current centres; Develop the proposed role and terms of reference of a global ‘WMO Lead Centre for Quality Monitoring of Land Surface Observations’; Develop an Incident Monitoring framework for land Surface Observations; Undertake pilot projects to demonstrate the value of the quality monitoring and fault monitoring system. See December 2014 Workshop report for action details. | Complete by Q1 2016 Done at December Workshop Q3 2015 Q2 2015 Q3 & Q4 2015 | Task Lead: Stuart Goldstraw Contributors: Henry Karanja and others yet to be identified. Joint with IPET-WIFI SG-QM Support TT-WQM Stuart & Henry jointly | Good Progress, workshop held Dec 2014 Some progress by Dean Lockett. Stefan developing Specs Not yet started | Significant task requiring ~20 days of effort in total. SJG21/10/15: Dean Lockett has invested considerable effort in developing the concept of the WMO Lead Centre for QM of land surface obs. Hentry Karanja has suggested a list of countries that could be included in the East African Pilot Project.Next Webex to be held on 27th October to discuss next steps. Stefan Klink is developing the functional and technical specifications for the Incident Monitoring System. |
| 2. | Improving Technical Documents Develop and update relevant elements of the Manual and the Guide on the GOS in the context of WIGOS, with initial priority on weather radar and AWSs [ToR b] In 2015 the focus will be to finish the draft material prepared in the November 2015 Sub Group meeting and hold a mini Sub Group meeting to draft revised material for the Radiosonde component in the Manual of the GOS. | Review and update the technical content on Weather Radars, AWS and other high priority systems in SBOs area of responsibility currently held in Manual and Guide for the GOS, noting a new technical document structure may be implemented during the period. | March 2014 & March 2016 | Co-ordination Lead: Islam Ameen | On Track | 60 days provisionally allocated, 110 days recorded below. SJG 21/10/15; Excellent progress made by SG teams on AWS, RWP & WxR. Actions for Chair to review material and propose, where possible, unified wording for consideration by IPET-WIFI in January 2015. |
| 2.1 |  | Weather Radar Review Update WMO No.544 to reflect the importance of Weather Radar operations in WIGOS. Details in break out group 4 report. | November 2014 plus additional work thereafter | Task Lead: Daniel Michelson Task Contributors: Al Wissman, Aki Umehara & Tom Kane (Nov workshop) | On Track | 50 days of effort from ET members but others will be engaged SJG 21/10: Unified task comments from SJG by mid November is the next step before wider circulation. |
| 2.2 |  | Wind Profiler Review Update WMO No.544 to reflect the importance of Wind Profiler operations in WIGOS. Details in break out group 4 report. | November 2014 plus additional work thereafter | Task Lead: Dominique Ruffieux Task Contributors:Al Wissman, Volker Lehman, Aki Umehara & Tom Kane | On Track | Effort required to be assessed after Wind Profiler Survey comment. # SJG 21/10: Unified task comments from SJG by mid November is the next step before wider circulation. |
| 2.3 |  | Upper air synoptic stations Update WMO No.544 to reflect the current status of operational radiosonde synoptic reporting operations in WIGOS. Reference to the need for operational data from GRUAN also needs to be considered. | 2015, as a follow on to success of SG meeting in November 2014. | Task Lead: Tim OakleyTask Contributors: Rongkang Yany | Not yet started | 30 days of effort from ET members but others will be engaged. SJG 21/10; Tim Oakley has agreed to review some text. An informal meeting will be arranged in Geneva when Tim and SJG are next in WMO headquarters to agree next steps. New ET member Rongkang Yang from CMA has agreed to join this mini team. |
| 2.4 |  | Surface synoptic stations Update WMO No.544 to reflect the current status of surface land reporting operations in WIGOS. Details in break out group 4 report. | November 2014 plus additional work thereafter | Task Lead: Karl Monnik Task Contributors: Henry Karanja, Islam Ameen & Charles Paterson. | On Track | 30 days of effort from ET members SJG 21/10: Unified task comments from SJG by mid November is the next step before wider circulation. |
| 2.5 |  | AWS Technical Manual Create an AWS technical manual from all material generated by ET-AWS over the past 7 meetings and publish as a technical document under new WIGOS banner. (Suggest task is superseded by WIGOS initiative) | November 2014 plus additional work thereafter? | Task Lead: Karl Monnik Task Contributors: Henry Karanja, Islam Ameen & Charles Paterson. | Replaced by WIGOS led task | Details of resources required to be confirmed by Karl. SJG 26/02/15: Karl is happy that material can be turned into WIGOS technical reports, following review, which will meet this action. Next steps to finalise draft and send to ET-SBO as a whole for feedback. SJG 21/10: This task has now been superseded by the work to generate a WIGOS led AWS Manual. Close working relationship between ET-SBO & WIGOS is expected. |
| 3. | Status of Implementation Monitor and assess the status of planned and operational surface-based observing systems and ensure this is adequately described in Volume A and metadata database(s) of Members’ observing system capabilities [ToR c] The focus in 2015 will be to continue the evolution of the WMO Radar Metadata Database, hosted by TMS, and to identify where Wind Profiling Radar metadata should be held in the future. | Complete the outstanding actions associated with the Wind Profiler Questionnaire including results analysis. Review content of WMO No.9 Vol A including R/S catalogue and ensure it is fit for purpose and up to date, noting any future plans for changes in light of WIGOS and in particular the WIGOS Information Resource | Ongoing / Annual review | Co-ordination Lead To be confirmed | On track | 60 days provisionally allocated. SJG 26/02/2015: Excellent progress being made. Task 3.4 deleted as very similar to task 5.1 |
| 3.1 |  | WMO Radar Metadata Database Maintenance and improvement of the WMO Radar Database, specifically the improved functionality identified at the WMO WxR Data Exchange Workshop, under recommendation 11. | Ongoing + annual report | Task Lead: Oguzhan Sireci Task Contributors: To be identified | On track | SJG 26/02/2015: Excellent progress being made by Oguzhan and TMS with historical metadata function and planned stations function being added to WMO RMD. Next steps to add the radar exchange tracking function. |
| 3.2 |  | Wind Profiling Radar Survey Complete the outstanding actions associated with the Wind Profiler Questionnaire including results analysis. See Breakout report for details but main focus is the metadata hosting question. | April 2014 | Task Lead: Dominique Ruffieux Task Contributors: Dean Lockett, OSCAR working group | On track | SJG 26/02/15: Excellent progress with take with only the outstanding issue of metadata collection and storage remaining. Plans for this need to be considered in 2015. Current discussion to harmonize the questionnaire to be OSCAR compatible. |
| 3.3 |  | Validation of ‘Vol A’ metadata Details of task to become clear once proposals for migration of Vol A to new framework completed. | 2015? | Task Lead and Contributor: N/A | Superseded by IPET_WIFI led task. | Needs close liaison with IPET-OSDE and IPET WiFI needed. SJG 26/02/12015: Careful consideration of this task and its link to other groups included OSCAR oversight team potentially undertaking the same task needed. SJG 21/10: IPET-WIFI SG-OD now leading on Vol A issues and so this task is no longer needed, although support from ET-SBO may be required? |
| 4. | Meeting User Requirements In collaboration with IPET-OSDE, assess the contribution of current and planned SBO systems to meeting user requirements for all Application Areas [ToR d] The main focus of this work plan item is to provide Expert Team input to IPET-OSDE led meetings, workshops and other initiatives. | Provide reports to IPET-OSDE on the suitability of each observing system in meeting each Application areas requirement | Ongoing | Co-ordination Lead still to be to be identified currently being undertaken by Stuart & Dean | Responding to requests as raised. | SJG 26/02/2015: Good progress with IPET-OSDE engagement as part of Observing System Design Workshops. An outstanding task is the review of the status of the EGOS-IP actions. SJG 21/10: EGOS-IP review triggered at ET-SBO-2, feedback expected over next few weeks. Many team members have contributed to other task, such as the development of OSND Principles. |
| 5. | Delivering the EGOS-IP Facilitate the delivery of those EGOS-IP actions identified as priorities for OPAG-IOS [ToR E] The main focus here is for ET-SBO to have suitable oversight and monitoring of progress with EGOS-IP actions assigned to it for review and to undertake the specific tasks associated with G48. | Undertake Radar Data Exchange Workshop and ensure follow up actions triggered. Review EGOS-IP and proposed priority actions for consideration to ICT-IOS. Undertake agreed follow up actions |  | Co-ordination Lead: TBD | Some progress being made | SJG 26/02/2015: Need to identify a co-ordination lead. Good progress being made with Wx Radar exchange tasks. Next steps to review EGOS-IP to identify actions ET-SBO can really assist with. Task 5.3 removed until task 5.2 is completed. |
| 5.1 |  | Next steps with Weather Radar Data Exchange Action G48 WxR Data Exchange Task Team – details of ToR and work plan for TT to be found in final report in annex III pages 6 to 12. | March 2016 & beyond. | Task Lead: Daniel Michelson Task Contributors: See TT membership | On track | SJG 23/07/14: TT formed and work plan made available by Chair. SJG 21/11: Daniel and team hoping to have first TT meeting in Q1 2016. |
| 5.2 |  | Identify EGOS-IP Actions for ET-SBO Analyze existing EGOS-IP actions using methodology defined by ET-SBO-1 Breakout Group 6 and recommend actions to be supported by ET-SBO to ET Members. Task replaced with task identified by ICT-IOS – develop options for implementing G10 Optimising R/S programmes to take account of the complementary nature of AMDAR | November 2013 | Task Lead: TBD Task Contributors: Jean-Luc Cheze & Tom Szynborski Task Lead: Tim Oakley Task Contributors: RongKang Yang | Superceded On Track | Approximately 10 days in total should be assigned to this task. SJG 21/10: Tim and Yang sent outline ideas on how to develop the proposal following ET-SBO-2. An informal meeting will be set up in Geneva to progress this work in Q4 2015 and Q1 2016. |
| 6. | Promoting Best Practice Monitor the status of operational networks of SBO systems, promote best practice among WMO Members and provide advice on operational matters [ToR F] The focus here is to develop a web page within the WIR that contains useful technical documents that ET-SBO members believe would be useful for WMO operational observing managers to have access to. A WebEx will be arranged with Henry and others to agree how to proceed with this work plan item. | Establish an improved source for technical advice documents “SBO Portal” as part of the WIGOS Information Resource. Populate Portal with national best practice documents. Respond to requests for advice from members | 2014 for Portal then ongoing for other actions | Co-ordination lead: Henry Karanja as Vice Chair SBO All members will support this activity. | Progress Delayed | SJG 23/07/14: Some progress has been made with this task but predominantly by Dean Lockett. SJG 26/02/2015: A task specific WebEx is required to kick start this task. SJG 21/10: Lots of discussion at Et-SBO-2 on this matter but actions from meeting report will provde clear guidance as to next steps. It is not clear how much work will be undertaken by ET-SBO in next 6 months. |
| 6.2 |  | Best Practice Portal Create an observing networks operations best practice portal, described and linked from the WIGOS Information Resource (WIR) under Operations & Maintenance topic. | November 2014 | Task Lead: Edmundo Lucas | Progress Delayed | Suggested 10 days are associated with this task. SJG 23/07/14: Requires a review of the plan SJG 26/02/2015: A task specific WebEx is required to kick start this task. SJG 21/10: lots of encouragement from Chair to keep this task simple. Actions from ET-sBO-2 will identify next steps. |
| 6.3 |  | Quality Monitoring Portal Specify structure, review current best practice and implement a QM portal within the WIR | November 2014 | Task Lead: Tim Oakley? | Limited Progress | Suggested 10 days are associated with this task. SJG 23/07/14: Requires a review of the plan SJG 26/02/2015: A task specific WebEx is required to kick start this task. SJG 21/10: Tim Oakley provided links to a number f monitoring sites. This will provide the starting point for developing this portal of useful links. |
| 7. | Purposeful Horizon Scanning Assess the potential contribution of new and emerging SBO technologies in meeting the Vision for the GOS in 2025, in collaboration with CIMO [ToR G] The focus here is to co-ordinate the efforts of ET-SBO members in the gathering of intelligence about the evolving state of observing system technology and the likelihood of it being suitable for operational implementation at some point in the future. A WebEx will be arranged with Richard and others to discuss how to best progress this item. | Report on the suitability of new and emerging technologies for operational network implementation. Propose updates to the Vision for the GOS. Ensure close collaboration with relevant CIMO ETs & other working groups. | 20014 2015, 2016 | Co-ordination Lead: Richard Ice with all members of ET acting as contributors. | Limited Progress | SJG 26/02/15: A specific WebEx is required to discuss how best to progress this task. SJG 21/10: Richard Ice has retired and a lead for this task has not been forthcoming. Co-ordinating this task in the context of all the work being undertaken by CIMO is key.A new task may trigger an improved activity within ET-SBO. |
| 7.1 |  | CIMO Teams identified where close co-ordination and review of their meeting reports is required: CIMO OPAG-S&I ET-A2 New In-situ Technologies; CIMO OPAG-RSNT ET-B1 Operational Remote Sensing; CIMO OPAG-RSNT ET-B2 New Technology and Test Beds; Note CIMO ET team names changed since CIMO Commission session. It is assumed the work of all CIMO ETs is relevant and so outcomes of all meetings need to be reviewed. |  | Task leads: to be identified. | Task delayed | Report from each meeting is ~2 days of effort SJG 26/02/2015: It is proposed to hold a joint session with ET-ORS in October 2015. SJG 21/10: Little progress with this item. |
| 7.2 |  | In addition a review of papers submitted to major scientific and technical conferences, such as: AMS2014, EMS, ERAD, ISTP, others to be added. | Dates tbc | Task leads: to be identified. | Limited Progress | Report from each meeting is ~2 days of effort. SJG 19/12: Daniels’s report provides good style to follow. SJG 23/07/14: No additional visit reports produced. SJG 21/10: no additional visit reports |
| 7.3 |  | Produce Annual Report for ET-SBO members. Annual report is a synthesis of likely future operational observing systems and their potential in meeting stated requirements. | March 2014, March 2015,/ March 2016 | Task Lead: Richard Ice | Not undertaken | Annual report is ~2 days of effort per year. SJG 23/07/14: No annual report mechanism put in place to date but Richard is developing a report on emerging remote sensing technology. A follow up WebEx to support Richard is required. |
| 7.4 |  | Provide input to the new Vision for the GOS in 2040, considering the current and likely evolution of R&D observing capabilities | March 2016 | Task Lead: TBD | On track | SJG 21/10: This was triggered by an action from ET-SBO-2 and will be the de-facto outcome of the tasks originally considered important in 7.1 to 7.3 above. |
| 8. | Reporting Progress to ICT-IOS Provide advice and support to the Chairperson of OPAG-IOS on the implementation of the WIGOS framework and its operational aspects [ToR H] | Deliver progress reports and recommendations for changes to operating practices, technical documents and guidance to ICT-IOS during inter-sessional period. | 2014 and 2016 | Task Lead: Chair ET-SBO | On track | SJG 26/02/15: Reporting on track. Resource commitments the major issue. |
| 8.1 |  | Generate report of work for ICT-IOS-8. Requires input from all ET Members. | April 2014 (tbc) | Chair ET-SBO with review of report by all members. | Complete |  |
| 8.2 |  | Attend ICT-IOS-8, report progress with work plan activities and provide feedback to ET Members | April 2014 | Chair ET-SBO | Complete | Chair 5 days |
| 8.3 |  | Generate report of work for ICT-IOS-9. Requires input from all ET Members. | April 2016 (tbc) | Chair ET-SBO with review of report by all members. | On track |  |
| 8.4 |  | Attend ICT-IOS-8, report progress with work plan activities and provide feedback to ET Members | May 2016 (tbc) | Chair ET-SBO | On track |  |

Annex IV

INTER-PROGRAMME EXPERT TEAM ON WIGOS FRAMEWORK IMPLEMENTATION MATTERS (IPET-WIFI) WORK PLAN

for the period 2012-2016 with updated status

Updated on 15 January 2016

| No. | Task | Deliverable/Activity | Due | Responsible | Impacted ETs | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Contribute to the development and maintenance of WIGOS regulatory material, both GOS-related material and provisions common to all component systems. | 1) Input to TT-WRM, to assist and review the inclusion of material from GOS Manual and TRs into the WIGOS Manual and TRs (particularly for sections 2, 3 and 7) 2) Gather and review proposals for updated or new regulatory material to the TRs, WIGOS Manual and/or GOS Manual (as appropriate) 3.1) Clear plans (with TT-WRM) for the transition and eventual phasing out of the GOS Manual 3.2) Lay foundation , by undertaking some of the drafting steps, for completion of transition, after CBS-XVI (2016), from GOS Manual to WIGOS Manual 4) Collaboration with TT-WRM and WIGOS P.O. on development of the WIGOS Guide 5) Develop a proposal, with TT-WRM, for a mechanism for ongoing review and update of regulatory material, for example a WIGOS editorial board | 1) Oct 2013 2) Apr 2016 (for next edition of WIGOS Manual), & ongoing. 3.1) Nov 2015 3.2) 2016 4) May 2016 (for the initial Guide) 5) 2016 | Stringer SG-RM Members | TT-WRM ICT-IOS all teams and rapporteurs | 1) 100 % 2) 40 % and ongoing 3.1) 60 % 3.2) 50 % 4) 30 % 5) 30 % | 1) Interactions and feedback provided for TT-WRM on first drafts, and further revisions up to endorsement by CBS and approval by Cg. 2) Some WIGOS and GOS updates obtained from across CBS. Need further work on Manual on GOS. 3) Cg & CBS noted synchronized changes leading to phasing out, but more timeline planning needed Cg has approved the first synchronized Manuals on GOS and WIGOS. More steps are needed on GOS Manual changes. 4) Requested initial edition by July 2016. Some work underway. 5) Important to have all TC / programme collaborators participating |
| 2. | Contribute to the development of guidance, mechanisms and procedures for engagement, coordination and collaboration with partner organizations. | Report on lessons learned from RA III Project on collaboration between meteorological and hydrological communities | Apr 2016 | Arimatea | ICT-IOS | 50 % |  |
| 3. | Network Planning / RRR | Close cooperation between IPET-WIFI and IPET-OSDE, feedback to IPET-OSDE as required. | Ongoing | Dibbern Stringer | IPET-OSDE | 80 % | Stringer and Dibbern are both contributing to IPET-OSDE activities. |
| 4. | Develop guidance on: 1) mechanisms and procedures for improved integration of GOS observational data and products, 2) Process of sharing, between GOS and other component observing systems, operational experiences, sharing of expertise and guidance for resourcing joint activities | 1) Contribution to guidance documentation on best practice for integration, quality control and maintenance of GOS observational data and products in RA I 2.1) Identification and documentation of issues that need to be addressed by regional cooperation, 2.2) Proposals for joint resources activities at the sub regional level. | 1) Mar 2016 2.1) Mar 2016 2.2) Mar 2016 | Merrouchi Mosetlho | ICT-IOS ET-WISC-OM ICT-IOS | 1) 0 % 2.1) 0 % 2.2) 0% | 1) Proposed Method: Arrange for a session on this topic to be conducted as part of a WIGOS RA I workshop that is planned under ICG-WIGOS. 2) Procurement, instrument maintenance, spectrum management, etc. |
| 5.* | Provide advice to ICG-WIGOS via CBS on GOS Quality Management practices and procedures: 1) Finalise SG-QM Work Plan 2) Establish a group of GOS observing sub-system focal points that can provide expertise and knowledge on QMon practices and regulations to SG-QM. 3) Review the status of WMO and Regional quality monitoring systems with a view to identifying areas for improvement and efficiency 4) For the land surface-based observing system, develop and document the concept of extending global quality monitoring to include a “Global Fault Management System”: 5) In consultation and collaboration with TT-WQM, develop and revise QM and QMon regulatory material and guidelines for inclusion in WIGOS and GOS regulatory materials. 6) Contribute to the drafting work of TT-WRM in collaboration with SG-RM and provide GOS-related feedback through SG-RM on TT-WRM documentation. | [Work Plan] 2a) Finalise list of sub-systems to be reviewed by SG-QM; 2b) Finalise list of GOS OS-S focal points. 2c) Create a FP email list for collaboration. [Group of OS-S FPs established.] 3a) In consultation with TT-WQM determine the scope and requirements for the review to be undertaken by OS-S FPs. 3b) Review existing regulatory material related to QMon for GOS sub-systems. 3c) Review existing regional QMOn systems and their procedure in place, for example ECMWF, EUCOS, etc. 3d) Prepare recommendations on new or improved QMon procedures in relation to GOS sub-systems. [Document that can be used as input to the deliverable of TT-WQM] 4a) Review the outcomes of the ECMWF Workshops on NWP data monitoring requirements 4b) Revise, update and finalise the draft proposal developed by ET-SBO to define the scope and deliverable of this activity. 4c) Liaise with ET-SBO and ICT-GDPF regarding revision of the Manual on the GDPFS re requirements for monitoring of the GOS by NWP. 4d) Develop an updated plan and procedures for quality and quantity monitoring of land, surface-based observing systems of the GOS. 4e) Update appropriate manuals and guides based on the outcomes of this activity. 4f) Assist IPET-WIFI in reporting to CBS [1. Revised international structure and framework for international observations monitoring 2. Updated regulatory material on Qmon of land surface-based system of the GOS] 5a) Liaise with ET-SBO and ICT-GDPF re appropriate location for regulatory material relating to monitoring of the GOS by NWP. 6a) Provide feedback to TT-WRM on current draft version of the Manual on WIGOS with respect to quality monitoring aspects. 6b) Do it again for next version | Mar 2014 Aug 2014 2016 (CBS) 2016 (CBS) a) Aug 2014 b) Aug 2014 c) Feb 2015 d) Dec 2015 e) Feb 2015 f) Jun 2016 2016 (CBS) Mar 2014 | Secretariat Schrab Secretariat Schrab Schrab SG-QM Schrab SG-QM ET-SBO SG-QM SG-QM | TT-WQM ET-ABO ET-SBO TT-WQM ET-SBO ICT-GDPF ICT-ISS ET-SBO ET-ABO IPET-GDPF TT-WRM | 100% 100% a) 100% b) 20% c) 0% 0% 100% ??50% 50% 0% 0% 0% 5% 100% | SG-QM to review and reach agreement on work plan. Ch-TT-WQM to review and agree on work plan. Summarised plan to be updated in IPET-WIFI work plan (Final Report IPET-WIFI-2) Participation of Chair SG-QM required in WIGOS Quality Workshop (Apr 2014) Likely list of 6 GOS OSS for review of QM: (a) Surface synoptic stations (Land and Sea stations); (b) Upper-air synoptic stations (Land and Sea stations); (c) Aircraft meteorological stations; (d) Aeronautical meteorological stations; (l) Weather radar stations; and (n) Wind profiler stations. Can the scope for this task be expanded to quality management rather than just QMon? This task is a contribution to a parent task of TT-WQM and related to Activity 5.1.2 of the WIP. Include consideration of the possibility of combining the roles of global quality and quantity monitoring. To improve the feedback mechanisms and process so as to better ensure the identification and rectification of missing data, station outages and specific quality issues. Include consideration of the possibility of combining the roles of global quality and quantity monitoring. 2nd workshop to be held in 3rd quarter 2014 – Ch-ET-SBO will attend. Take the lead in drafting QM material on GOS for Tech Regs (incl Common Elements of Surface.Based Obs Systems) and WIGOS Manual. Task leader will participate in TT-WRM teleconferences. This task is a contribution to WIP Activity 5.1.1 |
| 6. | 1) Describe the standard practices and recommended practices for collecting observations, applicable to instruments and methods of observation with a focus on the GOS 2) Provide guidance to Members on how to implement those standard and recommended practices | 1.1) Existing standard practices and recommended practices, described in a manner suitable for inclusion in WIGOS regulatory material (TRs or Manual on WIGOS) 1.2) Proposed new standard practices and recommended practices, described in a manner suitable for inclusion in WIGOS regulatory material (TRs or Manual on WIGOS) 2.1) Identify and if necessary further develop guidance on how to implement those existing standard and recommended practices, described in a manner suitable for inclusion in a relevant Guide (WIGOS, GOS, CIMO or other guidance material). 2.2) Guidance on how to implement the proposed new standard and recommended practices, described in a manner suitable for inclusion in a relevant Guide (WIGOS, GOS, CIMO or other guidance material). 2.3) Maintain a watching brief on existing guidance material with a view to identifying candidates which have become ready to be elevated to the WIGOS regulatory material as observing systems mature. | Nov 2013 Dec 2016 Nov 2013 Dec 2016 Dec 2016 | Kurz IPET-WIFI Members | CIMO ETs (CIMO Ed Board, Standardization) TT-WRM SG-RM | 1.1) 100% 1.2) ongoing 2.1) 100 % Ongoing Ongoing | An annual activity An annual activity An annual activity |
| 7 | 1) Lead and coordinate the drafting of updated OSCAR Update/Maintenance Procedures 2) Oversee development and provide feedback on an OSCAR “User Guide” 3) Lead and coordinate development of a mechanism for the provision of OSCAR User Support with primary focus on Content (Timo advised on 20/11 that the necessary documentation was not yet ready for review.) 4) Review the plan prepared by the WIGOS PO for transition from the use of Volume A to OSCAR. 5) Provide advice as required to the OSCAR Project Team on requisite design features to facilitate the use of OSCAR for RRR gap analysis. 6) OSCAR/Surface content quality management 7) Liaise with the OSCAR Project Team to keep abreast of the latest developments. 8) Provide advice to the OSCAR Project team on specific topics of concern. Update 10/12/15 - No requirements so far. 9) Report to IPET WIFI periodically on progress made by the Sub Group Update 10/12/15 - ongoing. | 1.1) Request relevant ETs to review and update OSCAR/Space and OSCAR/Requirements Update/Maintenance doc. 1.2) Add OSCAR/Surface procedures including the Quality Management of data that has been identified as questionable. 1.3) Submit to IPET-WIFI for review and approval by Chair OPAG-IOS. 2.1) Beta test OSCAR 2.2) Assist OSCAR Project Team to develop User Guide. (incl. FAQs) 2.3) Oversee review of Guide 3.1) Draft high level doc describing overall process for OSCAR user support 3.2) Assist in the implementation of a second line response mechanism to deal with content enquiries. 3.3) Participate in provision of support to users, redirecting enquiries to Subject Matter Experts if required 3.4) Provide feedback (via Uli) for User Guide input. 4.1) Review 1 page simple summary document outlining the plan. 4.2) Review and provide a recommendation to IPET-WIFI on the draft plan for transition from Vol A to OSCAR. 4.3) Report back to OSCAR Project Team on IPET-WIFI endorsement. Provide coordinated responses on request to issues raised by OSCAR Project Team in regard to RRR gap analysis: - Initial input - Ongoing Propose a mechanism for checking and correction (through interaction with data owners) of ‘bad data’ in OSCAR/Surface 7.1) Sec to provide Committee Meeting documents to chair as soon as available. 7.2) Sec to provide feedback on Project Team meetings asap after meetings Provide SG-OD advice on each issue to WMO Project Team. Semi-annual SG-OD reports to IPET Chair | 1.1) 10/15 1.2) 02/16 1.3) 03/16 2.1) 08/15 2.2) 3/16 2.3) 05/16 3.1) 02/16 3.2) 06/16 3.3) Ongoing 3.4) Ongoing 4.1) 09/15 4.2) 09/15 4.3) 10/15 5. a) 03/16 5. b) Ongoing 7.1) Ongoing 7.2) Ongoing Ongoing 6 monthly | Rainer Rabia Uli All Simon All Rabia All Simon Timo, Rainer Simon, Timo Simon | ET-SAT IPET-SUP, IPET-OSDE, ET-ABO, ET-SBO IPET-OSDE, Other ETs, SMEs as required. All CBS ETs | 1.1) 100 % 1.2) 20 % 1.3) 0 % 2.1) 100 % 2.2) 0 % 2.3) 0 % 3.1) 0 % 3.2) 0 % 3.3) 0 % 3.4) 0 % 4.1) 100 % 4.2) 100 % 4.3) 0 % 5.a) 20 % 0 % | Onus to be on WMO Members for maintenance of content of OSCAR/Surface Chair OPAG-IOS to submit the doc to ICG-WIGOS Project Team to be kept in the loop Straw man done. Feedback from beta testers to be incorporated. SMEs to provide content as required WIGOS PO will set up google forum. OSCAR Project Team to implement Forum plus email group. MeteoSwiss to provide first line support (IT). Close monitoring of resources required. NWH response to user queries within agreed time 4.1) Document circulated and approved by IPET WIFI – 3. 4.2) As above Pending on above decision Update 10/12/15 - No further activity on this, Gap Analysis element was agreed to be developed after the initial OSCAR/Surface implementation. Update 10/12/15 - More regular liaison with project team following on from project meetings would be appreciated. Minutes etc. Chair/Sec to represent the SG at Project meetings Chair to assign specific questions to specific team members. Ad hoc as Specified from time to time by Project Team |
| 8. | 1) Compile and provide input to the development of WIGOS (interpretation) metadata, focusing on the GOS component. 2) Compile and provide input to the development of approaches for gathering, storing and exchanging WIGOS metadata, focusing on the GOS component. This should lead to a number of standard practices and recommended practices for Members to follow. | 1.1) GOS input provided to ICG-WIGOS TT-WMD 1.2) Review and provide feedback on the Core Metadata list developed by TT-WMD, prepare populated examples (e.g. for surface station, radar, etc.) 1.3) Seek feedback on 1.2 from the technical experts across all areas of OPAG IOS. 2.1) Drawing on OPAG IOS expertise, review and complete outstanding WMDS code tables for consideration by TT-WMD, with priority given to Phase 1 fields. 2.2) Develop guidance material suitable for the WIGOS Guide concerning WMDS elements. 2.3) In cooperation with SG-OD contribute to the preparation of training materials for WIGOS metadata collection, storage and sharing of WMDS elements. | 1.1) Jun 2013 1.2) Nov 2013 1.3) Sep 2014 2.1) Phase 1 – June 2016, Phase 2 – Jun 2017, Phase 3 – June 2018 2.2) Phase 1 – Mar 2016, Phase 2 – Mar 2017, Phase 3 – Mar 2018 2.3) Jun 2016 | Monnik Members of SG-WMD | TT-WMD | 1.1) 100 % 1.2) 100 % 1.3) 100 % 2.1) 30 % . | With a view to inclusion in the 2016 version of the Manual on WIGOS |
| 9. | 1) Contribute to the development of a WIGOS capacity development strategy. 2) Contribute to WIGOS capacity development, as required. | 1) Review and provide feedback to ICG-WIGOS on draft WIGOS Capacity Development Strategy. 2) Assist in the organization and conduct of WMO seminars/workshops on the benefits of regional cooperation (such as for design, implementation and management of observing systems). | 1) Oct 2013 2) 2014-2015 | Pei IPET-WIFI Members | ICT-IOS | 1) 100 % 2) 0 % |  |
| 10 | 1) Contribute to the development of a WIGOS Communications and Outreach Strategy (WCOS) and plan 2) Contribute to WIGOS communication and outreach activities | 1. Provide feedback to ICT-IOS on the WIGOS Communications and Outreach Strategy (WCOS) and plan 2.1) Enhance understanding of WIGOS and its benefits at appropriate WMO meetings. 2.2) Contribute to WIGOS quarterly newsletter 2.3) Draft WIGOS article for Meteoworld in cooperation with WIGOS PO | 1) Jun 2013 2.1) Ongoing 2.2) Recurring 2.3) Oct 2015 | Pei All IPET-WIFI Members All Dibbern |  | 1) 100 % 2.1) Ongoing 2.2) Ongoing 2.3) 0 % |  |
| 11 | Improve future cooperation between IPET-WIFI and ICG-WIGOS | Propose to ICG-WIGOS that IPET-WIFI activities will be integrated into ICG-WIGOS TTs after CBS 16, if conditions permit | Nov 2016 | Dibbern |  | 0 % |  |

*NOTE on Item No. 5: In September 2015 the chair of the SG-QM resigned and it was proposed by IPET-WIFI-3 and confirmed by ICG-WIGOS-4 that activities of the SG-QM will be transferred into the work of the ICG-WIGOS WDQMS.

ANNEX V

Expert Team on Satellite Utilization and Products (ET-SUP)

RESULTS OF Work Plan for the period 2012-2014

(FINAL UPDATE: 20 JAN 2016)

(a proposal for the 2015-2019 work plan of IPET-SUP will be presented to ICT-IOS-9 in April 2016)

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Monitor the progress of satellite data availability and use by WMO Members, related issues and expectations, with the aim to publish findings and recommendations in a WMO document | Biennial survey Analysis of responses Findings and recommendations Advice to Regional Associations on follow-up actions WMO document for publication Next survey | 2012/2 2012/4 2012/4 2012/4 2013/1 2015 | WMO SP Secretariat and ET-SUP | 2012 Survey completed; Results guided WMO action in key areas (data access, product development, training) |  |
| 2 | Provide advice and support to the development and implementation of WIGOS, from a satellite user's perspective and coordinate with ET-SAT and ET-EGOS on the evolution of the space-based component of Global Observing Systems; | Contribute to the evolving EGOS IP, the Manual on the GOS, the Vision for the GOS 2025, and the WIGOS IP Support WMO Programmes (both operational and research) in their satellite data and product-related needs | 2012/2 and as required Continuous | ET - SUP and WMO SP Secretariat | Revision to EGOS-IP approved at ET-EGOS in May 2012; interaction with ET-SAT on key topics such as data policy, private satellite operators, Vision WIGOS Space 2040 |  |
| 3 | Initiate and promote activities to improve the availability of operational and R&D satellite data according to user needs, monitor these activities in close coordination with the relevant CGMS working group(s) and with WIS activities; | Promote the development and maintenance of Regional Satellite Data Requirements in all Regions, as appropriate Provide feedback on the progress of IGDDS and RARS Guide and assist new Regional Satellite Requirements Coordination Groups | 2013 onwards | ET - SUP and WMO SP Secretariat, with assistance from Int'l WGs IGDDS and RARS implementation groups | Interaction with ITWG, IWWG, IPWG, IROWG, ICWG Nowcasting and other expert groups strengthened Partnership with SWFDP reinforced Satellite Data Dissemination Strategy established, with 10 key targets, in support of IGDDS and including RARS/ DBNet Regional requirements newly established in RA III/IV |  |
| 4 | Review present and future R&D satellite data and products including their availability and potential applications, and provide advice with a view of increased utilization by WMO Members; | Review of relevance and availability of R&D satellite data, based on global/regional requirements; Strengthen interaction with R&D agencies in the area of altimetry, soil moisture, precipitation, and climate Make recommendations for improved availability, information and training, especially for developing countries | Ongoing | ET - SUP and WMO SP Secretariat | Participation in relevant fora (CHy, Altimetry Symposium); International Soil Moisture Workshop Jul 2013, ESA Living Planet Symposium 2013) Involvement of R&D agencies in WMO efforts to facilitate data access (e.g., Product Access Guide) |  |
| 5 | Review and assist in addressing the needs of WMO Members for information regarding access to and utilization of satellite data and products; | Maintain a list of satellite data access points, processing and analysis software tools on WMO webpage Include updated list of VLab-relevant tools | 2012/3 (continued yearly) | ET - SUP and WMO SP Secretariat | Relevant resources established on WMO website (Product Access Guide, Data Access, Tools) |  |
| 6 | Promote development and harmonization of satellite data and products responding to WMO Members’ needs | Continue to provide guidance to phase 2 of Sustained Co-ordinated Processing of Environmental Satellite Data (SCOPE) for Climate Monitoring as a key contribution to the architecture for climate monitoring from space. Assess and further the concept of SCOPE for Nowcasting, through pilot projects Develop Product Access Guide, in coordination with satellite operators | 2013/1 (call for proposals) 2013 (prototype developed) 2013 (updated version published) | ET - SUP and WMO SP Secretariat and responsible for the SCOPE-NWC projects | SCOPE-CM now involves 9 projects that are successfully increasing the maturity of multi-agency climate data records Pilots Projects defined; first results achieved; updated work plan under development Established on WMO SP website |  |
| 7 | Keep under review the needs of WMO Members for training in satellite meteorology and related fields, and engage with the Management Group of the Virtual Laboratory for Education and Training in Satellite Meteorology (VLab) to address these needs, towards full utilization of satellite data from operational and R&D satellites, in accordance with the 2009-2013 Virtual Laboratory Training Strategy; | Regular reviews of the VLab status, activities and plans (training resources, courses, meetings, newsletters); Support existing VLab CoEs and the establishment of new ones; Provide guidance to meet users' needs, especially from less developed Members and for the next generation of satellites; Explore training partnerships Contribution to training resource development | 2012/3 (continued yearly) 2013/1 2013/1 and continuing 2013-2014 Continuous activity | VLMG, WMO SP Office and ET-SUP | VLMG meetings held in 2012 and 2014; virtual meetings every 3 months; new 5-year VLab strategy approved Candidature of CoE Morocco agreed; launch event Focus on user preparation to new-gen satellites through training and side events, SATURN online portal, new VL CBS Guidance developed; WMO-COSPAR MoU signed in 2013 and extended in 2015; several joint capacity building activities |  |

_________________

ANNEX VI

Inter Programme Expert Team on Satellite Utilization and Products (IPET-SUP)

PROposed Work PROGRAMME for the period 2015-2019

(LAST UPDATE: 20 JAN 2016)

(this work plan is to be presented to the OPAG-IOS Chair, then updated by the Team to assign responsibilities, deadlines, and indicate status)

| No. | Task (ToR) | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Monitor the progress of satellite data availability and use by WMO Members, related issues and expectations, with the aim to publish findings and recommendations in a WMO document | Quadrennial survey Analysis of responses Findings and recommendations Advice to Regional Associations on follow-up actions WMO document for publication Next survey | Feb 2016 Apr 2016 Apr 2016 Sep 2016 Jan 2017 2020 | WMO SP Secretariat and IPET-SUP | Planning for 2016 Survey commenced |  |
| 2 | Provide advice and support to the development and implementation of WIGOS, from a satellite user's perspective and coordinate with ET-SAT and IPET-OSDE on the evolution of the space-based component of Global Observing Systems; | Contribute to the evolving EGOS IP, the Manual on the GOS, WIGOS Regulatory Material, the Vision for the WIGOS component systems 2040, and the WIGOS IP Support WMO Programmes (both operational and research) in their satellite data and product-related needs | As required Continuous | IPET - SUP and WMO SP Secretariat | IPET-SUP provided input to the initial Vision for the WIGOS space-based components in 2040 |  |
| 3 | Initiate and promote activities to improve the availability of operational and R&D satellite data according to user needs, monitor these activities in close coordination with the relevant working groups, regional associations and with WIS activities | Promote the development and maintenance of Regional Satellite Data Requirements Groups and satellite data requirements in all Regions, as appropriate Provide feedback on the progress of the Satellite Data Dissemination Strategy and DBNet (RARS) Encourage and assist Regional Satellite Data Requirements Coordination Groups in carrying out Region-based user surveys | 2015 onwards | IPET - SUP and WMO SP Secretariat, with assistance from Int'l WGs IGDDS and RARS implementation groups | Regional Groups active in RA I, II, III/IV Development of progress indicators ongoing, including for DBNet Ongoing |  |
| 4 | Review present and future R&D satellite data and products including their availability and potential applications, and provide advice with a view of increased utilization by WMO Members; | Review of relevance and availability of R&D satellite data, based on global/regional requirements; Strengthen interaction with R&D agencies in the area of altimetry, soil moisture, precipitation, and climate Make recommendations for improved availability, information and training, especially for developing countries | Ongoing | IPET - SUP and WMO SP Secretariat | Participation in relevant fora, focus WMO survey on these topics and interaction with CEOS as appropriate |  |
| 5 | Review, and assist in addressing, the needs of WMO Members and regional associations for information regarding satellite capabilities and in particular access to and utilization of satellite data and products; | Maintain OSCAR/Space and a list of satellite data access points, processing and analysis software tools on WMO webpage Support activities to achieve user readiness for the new generation of meteorological satellites, including the development of guidelines for users and satellite operators | 2015/3 (continued yearly) | IPET - SUP and WMO SP Secretariat | Next-generation of OSCAR/Space, Product Access Guide and SATURN |  |
| 6 | Promote development and harmonization of satellite data and products responding to WMO Members’ needs | Provide guidance to Sustained Co-ordinated Processing of Environmental Satellite Data (SCOPE) for Climate Monitoring as a key contribution to the architecture for climate monitoring from space. Continue to develop and promote the SCOPE-Nowcasting, initiative and support the work of the coordinating group. Collaborate with WIGOS, WIS and CGMS on developing data format and metadata standards Exploit commonalities of instruments on the new meteorological satellites in generation of product and training material | 2015-2018 | IPET - SUP and WMO SP Secretariat, SCOPE-CM Executive Panel, and SCOPE-Nowcasting Coordination Group | SCOPE-CM IP under review Four Pilot Projects in progress |  |
| 7 | Keep under review the needs of WMO Members for training in satellite meteorology and related fields, and engage with the Management Group of the Virtual Laboratory for Education and Training in Satellite Meteorology (VLab) to address these needs, towards full utilization of satellite data from operational and R&D satellites, in accordance with the 2015–2019 Virtual Laboratory Training Strategy; | Regular reviews of the VLab status, activities and plans (training resources, courses, meetings, newsletters); Support existing VLab CoEs and the establishment of new ones; Provide guidance to meet users' needs, especially from less developed Members and for the next generation of satellites; Explore training partnerships Contribution to training resource development | Continuous activity | VLMG, WMO SP Office and IPET-SUP | VLab 2015-2019 strategy updated Events on user preparedness planned |  |
| 8 | Holding joint and/or overlapping meetings with ET-SAT as appropriate, to facilitate interaction between users and providers of satellite systems, data and products | Plan for joint session of ET-SAT and IPET-SUP in 2016 | 2016/3 | WMO SP Office |  |  |
| 9 | Coordinate with ET-SAT with a view to making recommendations and receiving input on matters, such as the exchange, management, and archiving of satellite data and products, radio frequency utilization, as well as education and training and other appropriate capacity-building measures related to the use of satellite data in all WMO Programmes; | As above Exchange meeting reports Engage with ET-SAT on specific issues as required, such as developing the Vision for WIGOS space-based component systems in 2040 | Ongoing | WMO SP Office, IPET-SUP Chair |  |  |
| 10 | Coordinate with WMO Technical Commissions and Programmes, including co-sponsored Programmes, activities related to satellite utilization and products, through ex-officio membership on the Team | Increase engagement with WMO Technical Commissions Develop and implement communications strategy | Ongoing 2015/4 | IPET-SUP Chair and WMO SP Office IPET-SUP Chair |  |  |

________________

ANNEX VII

STEERING GROUP ON RADIO-FREQUENCY COORDINATION (SG-RFC) WORK PLAN for the period 2016-2019

| Id | Priority | Objective | Outcome | Deliverable(s) | Activity | Leader | Due | OtherETs | Effort |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | WRC-19 | Radio Regulations ensure WMO observing and communications systems have uninterrupted access to necessary frequencies | - WMO Position Paper on WRC-19 Agenda. - Studies and inputs relating to future WRC items, including Space Wx. | - Representation at Conference Preparations meetings for WRC-19 - Preparation of a preliminary position paper on WRC-19 agenda, maintain and update for final submission to WRC-19. - Organization of studies and submission of contributions supporting the WMO position at ITU-R Working Parties involved) - Participation in ITU-R study groups - Representation of WMO at ITU-R Regional Organizations meetings. | Chair | Various times throughout the period. WRC-19 scheduled for Nov 2019 |  |  |
| 2 | 1 | Monitor and address Spectrum issues related to meteorological and Earth exploration applications/systems | Present and future meteorological and related needs for spectrum are met |  | - Participation in ITU-R study groups and working parties. - Participate in national activities in support of ITU-R processes. | - Chair - Focal points (See Attachment 1) | On-going | - ICT-IOS, - ET-WISC, - ET-CTS - CIMO |  |
| 3 | 2 | Monitor ITU-R regional organization activities and represent WMO issues where possible | Regional organizations decisions take into account WMO’s needs | Regional organization representation for WMO | - Bring to the attention of SG-RFC any regional issues affecting WMO and vice versa | - Focal points, (see attachment 3) | On going |  |  |
| 4 | 2 | Cooperation with other organizational entities such as GEO, SFCG, CGMS | WMO needs are taken into consideration of other environmental related activities | Participation and representation of WMO | - Bring to the attention of SG-RFC any issues from other earth observations related organizations affecting WMO and vice versa | - Focal points, (see attachment 2) | On going |  |  |
| 5 | 2 | Update the joint WMO/ITU Handbook “Use of radio spectrum for meteorology: weather, water and climate monitoring and prediction” | Members have current information on the applications and needs of radio spectrum | Revised joint handbook on spectrum usage … | - Coordinate the review of chapters with relevant experts. - Collaborate with ITU-R SG07 to ensure joint ownership of handbook - Review by CBS XIV - Review by EC-69 | - Gilles Fournier | CBS-14 |  |  |
| 6 | 2 | Conduct joint workshop of ITU regulators and NMHS frequency experts | New regulators and NMHS frequency experts are familiar with meteorological and frequency management | Joint Workshop | - Utilise WMO/ITU handbook on spectrum use in meteorology … and new Guide to Participation in RFC (WMO No | - E.Allaix, V. Nozrin, D.Thomas | June 2017 |  |  |
| 7 | 1 | Identify WMO Space Wx frequency requirements and ensure present and future needs are addressed in relevant Radio Regulations | Space Wx frequency requirements are address in Radio Regulations | Studies, questionnaires, information needed for WRC-23 cycle on space wx. | - Work with space wx experts to identify frequency usage, present and future - Work in ITU processes on the question of space wx - Prepare input for WRC-23 on space wx | - Dave Franc | On going | WMO Space Programme & Aviation programme Joint AEM/CBS TT on space wx. |  |

Attachment 1 – Focal points on SG-RFC specific activities

- Meteorological-satellite service (MetSat): Markus DREIS, David FRANC

- Earth exploration-satellite service (EESS) (passive): Thomas Von DEAK, David FRANC, Markus DREIS

- EESS (active): Bryan HUNEYCUTT,

- Radars (weather radars and wind profilers): Eric ALLAIX, Neil BEWLEY

- Meteorological aids service (MetAids) - Radiosondes: David FRANC, Paul HETTRICK, Neil BEWLEY,

- Lightning detection: Neil BEWLEY, Paul HETTRICK

- Space Weather: David FRANC, Neil BEWLEY, Bryan HODGE

- Handbook “Use of radio spectrum for meteorology: weather, water and climate monitoring and prediction”– Gilles FOURNIER, Eric ALLAIX

Attachment 2 – SG-RFC Focal Points for cooperation with other organizations

- Commission for Instruments and Methods for Observations (CIMO)

  - Mr Oguzhan Sireci (Turkey TSMS) and Mr David Franc are CIMO’s Theme Leaders on radio-frequency matters.

- Group on Earth Observations (GEO)

  - Mr Jose Arimatea de Sousa Brito.

- Coordination Group of Meteorological Satellites (CGMS)

  - Mr Markus DREIS

- Inter-commission Coordination Team on Space Weather (ICTSW)

  - Mr Dave FRANC, Mr Neil BEWLEY, Mr Bryan HODGE

- Space Frequency Coordination Group (SFCG)

  - Secretariat (Mr David THOMAS)

Attachment 3 – WMO focal points in WRC regional preparation meetings:

- CITEL: Jose Arimatea DE SOUSA BRITO, Dave FRANC and Carmelo RIVERA

- APT:  	 Paul HETTRICK, Bryan HODGE

- CEPT: 	 Markus DREIS and Philippe TRISTANT

- African group (including SADC): Henry KARANJA

- RCC: 	Alexandre AZAROV

- ASMG: None (to be defined)

__________________

* 	In MS Word 2007 or 2003, go to “View” > “Document Map”.  In MS Word 2010, go to “View” > “Navigation Pane”.  
In MS Word on a Mac, go to “View” > “Navigation Pane”, select “Document Map” in the drop-down list on the left.

http://www.wmo.int/pages/prog/www/GOS/ABO/ABO_Work_Program.html