| World Meteorological Organization | CBS-MG-16/Doc. 06 |  |
| --- | --- | --- |
| COMMISSION FOR BASIC SYSTEMS MANAGEMENT GROUP | Submitted by: | Secretary-General |
|  | Date: | 3.II.2016 |
| Sixteenth Session Geneva, 15-19 February 2016 | Original Language: | English |
|  | Status: | DRAFT 1 |

## Agenda Item 2.4: review of the performance of cbs

# REVIEW OF OPAG PWS WORKPLAN 2012-2016

# SUMMARY

This document highlights the current status of the OPAG/PWS workplan as of December 2015.

WORKPLAN ON OPAG/PWS

ICT/PWS

(as of December 2015)

| Action(s): | Status 2016: |
| --- | --- |
| Deliverable 1: Noting the publication of the “WMO Strategy for Service Delivery and its Implementation Plan”, ensure that actions relevant to PWS are carried out |  |
| Initiating the discussion on the re-alignment of the OPAG with the elements of Service Delivery | This has been superceded by the new proposed structure of OPAG/PWS resulting from the ICT Meeting in December 2015 |
| Deliverable 2: Establish contact with relevant people in the other CBS OPAGs, Commissions, etc., as required |  |
| Contact Chairpersons of OPACE III/IV to explore possible collaboration | Closed |
| Contact representatives of CHy to explore possible collaboration | Closed |
| Deliverable 3: Facilitate the development of one or a number of “one-stop-shops” for the provision of advice and assistance to the Humanitarian Response Community |  |
| Prepare an inventory of data and products that are currently available and can be used by Humanitarian Response agencies | Completed |
| Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | Completed |
| Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of National PWS Focal Points as a resource in the context of national operations of Humanitarian Response agencies | Ongoing |
| Deliverable 4: Promote the concept of NMHS as the Single Official Voice at times of severe/high-impact weather |  |
| Make use of the new “WMO Register of Alerting Authorities” to promote and embed the SOV concept | Ongoing |
| Designate an Expert Advisor to assist with the implementation of CAP at NMHSs and to promote registration of Members in the “WMO Register of Alerting Authorities” | Completed |
| Ensure inclusion of this principle in all relevant PWS documents | Ongoing |
| Deliverable 5: Detailed feedback from recipients of targetted PWS activities, such as SWFDP, Learning-Through-Doing (LTD) Projects, training, etc. |  |
| Organize the collection and analysis of feedback from training participants and PRs | Ongoing |
| Collate information flowing back from the feedback mechanisms built into the SWFDP and publish on the PWS Website | Ongoing |
| Organize the reception of bi-annual reports from Members participating in LTD Projects (through Focal Points where possible) and publish on the PWS Website | Completed |
| Deliverable 6: Develop a Competency Framework for PWS Forecasting and Activities |  |
| Draft a Competency Framework relevant to PWS Forecasters and circulate to all ICT Members, ETR Representatives, etc. | Completed |
| Review draft and provide feedback to WMO Secretariat/ Chairperson | Completed |
| Finalize PWS Competency Framework for CBS-Ext.(2014) | Completed |
| Deliverable 7: Develop materials on the Social and Economic Benefits of NMHSs as decided by the RA VI (Europe) Task Team and the World Bank Project |  |
| Compile and carry out comparative analysis of the impact of the services provided by NMHSs through socio-economic benefits studies | Completed |
| Improve methodologies in SEB studies through concurrent field testing and training as part of specific demonstration/pilot projects as well as on-going NMHSs’ investment programmes | Completed |
| Disseminate an authoritative joint WMO-World Bank guidance document | Completed |
| Deliverable 8: Future activities as a follow-up to WENS |  |
| Finalize “Concept Note” developed in Shanghai in November 2011 regarding the follow-up activities to WENS | Completed |
| Implement follow-up activities as defined in the “Concept Note” | Closed |
| Prepare publications, etc., as outlined in Section 12 of the WENS Final Report | Closed |
| Deliverable 9: Guidelines for Meteorological Support to Olympic Games |  |
| Review current draft and bring it up-to-date, include the Beijing and Vancouver Games, then provide to IOC and other sporting organizations as appropriate, and publish on PWS Webpage | Onoing |
| Deliverable 10: Strengthen the involvement of the NMHSs’ Focal Points with the work of the OPAG and of the PWS Programe |  |
| Update the list of National PWS Focal Points periodically | Ongoing |
| Request PRs to appoint National PWS Focal Points in Member countries where none are, as yet, identified | Ongoing |
| Carry out a regular survey of the work of the National PWS Focal Points in relation to PWS functions and publish the results | Ongoing |
| Keep National PWS Focal Points fully involved and informed in the activities of the PWS Programme and of the OPAG | Ongoing |
| Deliverable 11: Market and promote the availability and use of PWS material among the NMHS/PWS community |  |
| Periodically review statistics on the hits and usage of PWS pages on the WMO Website | Ongoing |
| Continue to implement strategies for increasing the ease of access to PWS pages through Google and other search engines | Ongoing |

ET/DPM

(as of 26 March 2015)

| Action(s): | Status 2016: |
| --- | --- |
| Deliverable 1: Finalize document entitled “WMO Guide for National Meteorological and Hydrometeorological Services (NMHSs) on the Provision of Impact-Based Products and Services |  |
| Review outline developed at meeting and identify gaps within existing document entitled “WMO Guide for National Meteorological and Hydrometeorological Services (NMHSs) on the Provision of Impact-Based Products and Services” . Provide assessment to the Chair. | Done |
| Based on the Assessment, request team members to write specific sections as needed. This should include devopment of Glossary. Agreement reached on assignments. | Done |
| Team members complete writing assignments and sent to Chair. | Done |
| Chair completes amalgamation of submitted sections into complete draft document and sends to team for final review and comments. | Done |
| Team members submit final comments; Chair integrates into final document and submits to Secretariat | Done |
| Secretariat submits draft document to CBS | Guidelines published in 2015 |
| Delivrable 2: Training requirements document for early warning systems and impact-based forecasting |  |
| Based on final document, develop training requirements document to address needs associated with early warning systems and impact-based forecasting. |  |
| Circulate competency document to all team members for information. | Done Competency framework approved by Cg-17 |

ET/COPE

(as of 20 January 2015)

| Action(s): | Status: |
| --- | --- |
| Deliverable 1: Develop NMHS survey on the usage of different media for PWS delivery |  |
| Prepare draft of survey | Done |
| Review draft survey | Done |
| Publish survey and send to NMHSs for completion | Done |
| Analyse results of survey and prepare report | Done |
| Publish the results of the survey | Done |
| Deliverable 2: Develop guidance material for senior NMHS managers on working with senior Government decision-makers, with a focus on communicating the socio-economic benefits of NMHSs |  |
| Request Regional Associations, with the assistance of the Secretariat, to issue guidance material to Members | Closed |
| Deliverable 3: Develop online eLearning training modules for NMHS staff, including senior managers, on priority areas of PWS communication, including on working with the media, handling difficult interviews and communicating forecast uncertainity |  |
| Develop online eLearning module on media training and handling difficult interviews | Done |
| Develop online eLearning module on communicating forecast uncertainty | Done |
| Deliverable 4: Develop Summary Guide for NMHSs on the use |  |
| Draft Summary Guide | Done |
| Publish Summary Guide, circulate to WMO Members and publish on WMO PWSP Website | Done |

ET/SPII

(As of 21 October 2014)

| Action(s): | Status: |
| --- | --- |
| Deliverable 1: Publish guidance on the adoption of a service-driven approach to development of Nowcast Systems |  |
| Gather data/information on nowcast systems representing various levels of technological development and in varying climate regimes: - Develop questionaire on Nowcasting systems for members; - Check on any existing questionaire related to Nowcasting; - Distribute questionaire to team members for final review; - Distribute to all countries; - Collect and send all input to Lead. | Done |
| Analyze and summarize questionaire responses. | Done |
| Develop guidance for members at different levels of capability to assist in applying a service driven approach to the development of nowcast systems. Include steps for identifying user requirements, current capabilities, gaps and the process to improve services to meet user needs. | To be done |
| Engage with members who offer to share knowledge as appropriate (eg. to assist in reviewing draft guidance, to participate in any workshops or training activities that may follow). | To be done |
| Produce a report including the current status of members nowcasting capability from analysed survey and guidance on recommended processes to improve nowcast services based on user requirements and available resources. | To be done |
| Circulate final report to Commission on Instruments and Methods of Observations, Commission on Atmospheric Sciences, and OPAG on DPFS for information and guidance via OPAG PWS Chair. | To be done |
| Circulate final report to all WMO Members. | To be done |
| Deliverable 2. Provide comments/input on Impact-Based Forecasting document developed by ET/DPM |  |
| Team members review and provide comments. | Done |
| Finalize review document. | Done |
| Send comments to ET/DPM. | Done |
| Deliverable 3: Coordinate with WMO ETR to develop training material on forecast uncertainity for use by NMHSs and WMO training activities |  |
| Identify and review resources/training materials, including EPS application-focused training, for inclusion in inventory. | On-going |
| Summarize and review training inventory developed by ET (Edwin Lai) (resource web page). | To be done |
| Collect examples from NMHSs on how they interact with users to define/ incorporate uncertainty in PWS products and services. | To be done |
| Deliverable 4: Assess the needs and interest in verification of WWS max/min temperature forecasts from participating NMHSs and assess uptake and usability by those participating NMHSs |  |
| Contact WWIS focals points to identify interest in project. | Done |
| Depending on response, establish pilot project. | Done |
| If a pilot project is established, share results with Team at next meeting for evaluation/further action. | Done. |
| Deliverable 5: Enhancement of WWIS and SWIC Websites |  |
| Increasing of the MyWorldWeather language verisons. | Done |
| Launch of Android version of MyWorldWeather. | Done |
| Revamp of WWIS Website. | Done. WWIS V2 to launch in June 2014 |
| Revision of SWIC Website and add social media component. | SWIC has been enhanced and TC positions were updated as soon as possible |
| To investigate the feasibility of including warnings for the WWIS: - Identify those WWIS members who provide warning data as a public online data service in structured format such as CAP, XML, etc. and ask them whether warnings are applicable to the cities on the WWIS; - Study the format of warning data; - Conduct feasibility study to incorporate the warning data into WWIS unified database; - Design the layout for WWIS/MyWorldWeather for incorporation of the warnings; - Prepare reports and findings. | To be done |
| To add current weather information to the WWIS to enrich the content of the website: - Coordinate with WWIS members to find out (i) whether to put current weather for their cities on WWIS; (ii) the most suitable SYNOP, AWS stations, weather photo for representing the current weather for a city; - Develop data acquisition module for ingesting the current weather data into the WWIS unified database in a real time manner; - Modify WWIS/MyWorldWeather for incorporation of the current weather. | To be done |
| Team continue to keep abreast of the performance and enhancement of the WWIS and SWIC. | To be done |
| Deliverable 6: Assist in the adoption of the Service Delivery Approach to delivering Forecast and Warning Services |  |
| To develop a fact sheet as guidance to members on deciding on the way forward for providing weather information on mobile platform for their users and to the Secretariat on how to advise members and respond to their requests in this regard. | Done |
| Deliverable 7: Explore the issue of increasing amounts of data in the forecast process – Confronting the “Big Data” issue |  |
| Contact DPFS OPAG Chair to discuss how to jointly address the issue of managing the increasing amount of data available to forecasters. | Done |
| Establish a joint view of the requirements of the forecasting community from the research community in order to provide the best forecasts and warnings for end users. | To be done |
| Armed with this information, engage with WMO Research Programmes to share and discuss these requirements, with specific attention to the WWRP High Impact Weather Project. | To be done |
| If required based on the outcomes from the above, conduct follow up activities such as a workshop, involving selected participants from the research and operational communities to test the findings of the above, with a view to devising a future strategy on this issue. | To be done |
| Deliverable 8: Investigate NMHS application of Geo-Spatial Data (GIS) |  |
| Team members undertake to ask one or two other Members about their status in applying GIS: (a) Send sample questions to ET members; (b) ET Members follow up with responses. | To be done |
| Assess the need for guidance from WMO | To be done |
| Develop fact sheet/discussion paper. | To be done |