Annex I

Table 1: Requests by Cg-17

Legend:

Yellow - CBS takes a lead role

light blue - CBS is a co-leader or leads certain activities.

light brown - CBS contributes to activities

| Para | Request / decision (addressee in bold) | Approach to address the request | Timeframe | Status | CBS role (lead, leader, Contributing) Items left blank are not linked to CBS) |
| --- | --- | --- | --- | --- | --- |
| Governance (Strategic Priorities, WMO DRR Roadmap, Coordination with RAs, TCs, and TPs, EC WG on DRR, etc.) |  |  |  |  |  |
| 3.2.1 | Recalled its decision to establish the cross-cutting DRR Programme through Resolution 29 (Cg-XIV). | - Further development of the WMO DRR Roadmap - Development of a WMO DRR Work Plan for 2016-2017 |  | - ongoing |  |
| 3.2.32 | Noted Resolution 8 (EC-66) requesting the Secretary-General to “urgently develop a WMO DRR Roadmap of prioritized and realistically achievable activities and deliverables, that are consistent with the WMO Strategic and Operating Plans, as well as the work plans for relevant WMO Programmes and projects” | - Continue updating the draft DRR Roadmap based on consultations with DRR FP RA-TC-TP, UI-EAGs, PTC/PRA, Members, EC WG on DRR |  | - ongoing | Contributing |
| 3.2.33 | The WMO DRR Programme should, in close collaboration with relevant technical programmes, and in particular the PWSP and HWRP, facilitate efforts that promote delivery of authoritative forecast and warning information to decision-making authorities at local, national, regional, and global levels as well as provide relevant hazard and risk analysis and assessment to assist DRM. |  |  |  | Lead |
| 3.2.34 | Requested the Secretary-General to leverage existing guideline documents already created by expert teams within the TCs, gather lessons learned from NMHSs and disaster management partners, and identify existing gaps within the DRR Roadmap outline, which need to be filled. | - Collect, review and synthesize existing guidelines, lessons learnt, gaps, etc. |  | - ongoing | Contributing |
| 3.2.35 | Emphasized that all DRR work should proceed in consideration of all relevant guidelines and documents created by the expert teams within TCs, as well as input provided from NMHSs’ own DRR roadmaps, frameworks, and best practices. | - Collect, review and synthesize existing guidelines, lessons learnt, gaps, etc. |  | - ongoing | Contributing |
| 3.2.37 | Noted that specific thematic areas to be addressed by the Roadmap should be closely interlinked with the priorities for action of the Sendai Framework for DRR 2015-2030, including the emphasis on a people-centred, multi-hazard approach to DRR underpinned by science and technology. | - Align the DRR Roadmap with the Sendai Framework priorities and components as well as its targets and indicators |  | - ongoing | Lead for CBS (PWS) |
| 3.2.39 | Noted the enormous significance of the Sendai Framework for DRR 2015-2030 to the DRR priority of WMO and the need for assisting WMO Members in the effective implementation of this Framework through: - Developing DRR knowledge products - Assisting with the coordinated national /regional DRR capacity development activities - Promoting, engaging in, and facilitating multi-stakeholder partnerships on different levels. | - Develop the DRR Roadmap and its Work Plan 2016-2017 |  | - ongoing | Contributing |
| 3.2.40 | Requested the Secretary-General, in consultation with Members and collaboration with TCs and RAs, to develop a final draft of the WMO DRR Roadmap for consideration and approval by EC-68 in line with the Sendai Framework and other relevant international development frameworks (e.g. on sustainable development, climate change, humanitarian assistance, and urban issues). | - Continue updating the draft DRR Roadmap based on consultations with DRR FP RA-TC-TP, UI-EAGs, PTC/PRA, Members, EC WG on DRR | - PTC/PRA Meeting on 20-21 Jan 2016 - 1st Meeting of the EC WG on DRR planned for 5-7 April 2016 (tentative) - EC-68 on 15-24 June 2016 | - ongoing |  |
| 3.2.41 | Requested EC to establish an appropriate governance mechanism to guide the implementation of the WMO DRR priorities through the DRR Programme with the aim to strengthen the capacities of Members, especially of their NMHSs, and the role of the WMO operational and research networks and designated entities assisting and cooperating with WMO, to deliver high-quality services for DRR towards building resilience at all levels. | - EC-67 created the EC WG on DRR | - 1st Meeting of the EC WG on DRR planned for 5-7 April 2016 (tentative) | - Teleconference of the co-chairs of the EC WG on DRR and of the DRR RA-TC-TP scheduled - Teleconference of EC WG on DRR members planned |  |
| 3.2.20 | Requested the DRR FP TC-TP to include DRR focal points of the regional associations. | - Ask PRA to nominate DRR Focal Points | - Teleconference of the DRR FP RA-TC-TP planned in the week 11-15 Jan 2016, then every quarter - Meeting of the DRR FP RA-TC-TP in Q4 2016 | - RA DRR Focal Points nominated and included in the DRR FP RA-TC-TP - Meeting of the DRR FP RA-TC-TP held on 3-5 Nov 2015 |  |
| Service delivery & stakeholder engagement (Support to Humanitarian Agencies, Response to major disasters, User-Interface Expert Advisory Groups (UI-EAGs), etc.) |  |  |  |  |  |
| 3.2.7 | Recalled Resolution 8 (EC-64) “Enhanced Capabilities of Members to Reduce Risks and Potential Impacts of Hazards Caused by Weather, Climate, Water and Related Environmental Elements” and its Annex “DRR Programme Work Plan”, including the adoption of an user-driven approach and the endorsement of UI-EAGs. | - Development of a WMO DRR Work Plan for 2016-2017 |  | - ongoing | Contributing |
| 3.2.8 | Encouraged continuation with UI-EAGs and requested to develop a set of clear deliverables to allow progress to be tracked. | - Formalize memberships and TOR - Organize their meetings - Identify deliverables | - UI-EAG HRA Meeting on 13-15 Dec 2015 - UI EAG MHEWS Meeting on 9-11 Feb 2016 (tentative) | - Status document prepared for DRR FP RA-TC-TP - Invitations for nominations for the UI-EAG HRA sent |  |
| 3.2.19 | Agreed that the UI-EAGs can contribute to the Global Framework for Climate Services (GFCS) User Interface Platform (UIP) and that the deliverables of the WMO DRR Roadmap are relevant to strengthening of the UIP. | - Coordinate with GFCS (Office), Task Team on the GFCS 2015-2018 Operational and Resource Plan (TT-ORP), Task Team on Monitoring and Evaluation (TT-M&E) - Identify deliverables | - Partners Advisory Committee (PAC) Q1 & Q4 2016 (?) - IBCS Management Committee Q4 2016 (?) - IBCS-3 in 2018 |  |  |
| 3.2.25 | Requested the Secretary-General, in coordination with the TCs, RAs, RSMCs, and other operational centres to analyse the issue [response to major disasters] and develop a draft working arrangement that elaborates the roles and responsibilities for the coordination of WMO’s response to Members' requests for assistance, noting that operational responsibility lies with the Members, and to report to EC for consideration. | - Development of internal guidelines / SOPs?`/ “Helpdesk”? |  |  | Contributing |
| Knowledge products (Guidelines, training material, identifiers for cataloguing extreme weather and climate events) |  |  |  |  |  |
| 3.2.15 | Urged the RAs, with support from the Secretariat, to document lessons learnt from the approach of the DRR Programme and the engagement of the RAs in the implementation of the DRR capacity development projects and to submit recommendations to EC on how the RAs can be effectively engaged in promoting this approach in other WMO Regions. | - Incorporation in guidelines and training modules - Publications (books, fact sheets, flyers, posters, website, etc.) | - To be distributed at major events (e.g. COP21 30 Nov – 11 Dec 2’015, World Humanitarian Summit 23-24 May 2016, IDRC 28-31 Aug 2016, Habitat III 17-20 Oct 2016, COP22 7-18 Nov 2016, etc.) | - Chapters for a book on disaster risk financing (status 2011?) available |  |
| 3.2.16 | Requested the Secretary-General to provide further guidance to Members in this area [guidelines, standards, assessment reports, and training modules in the main areas of work of the DRR Programme that are consistent with Quality Management System (QMS) principles and that are to be demonstrated and further developed in the afore-mentioned capacity development projects]. |  |  | - Draft guidelines for MHEWS available |  |
| 3.2.18 | Requested the Secretary-General to arrange for a review, regular update and access to DRR training material as a contribution to WMO’s Capacity Development Strategy and as part of the WMO DRR Roadmap implementation. | - Develop training modules - Review and update these - Make them accessible (coordinate with ETR, CADRI, UNISDR, etc.) |  | - Engaged in CADRI and with UNISDR Centre in Korea | Contributing |
| Resolution 9 (Cg-17) | Identifiers for cataloguing extreme weather, water and climate events. Decided to standardize weather, water, climate, space weather and other related environmental hazard and risk information and develop identifiers for cataloguing weather, water and climate extreme events. Requests EC to provide oversight on the standardization of hazard information for loss and damage assessment; Requests the CBS to develop, in collaboration with all TCs and RAs, a proposal on standardized identifiers for cataloguing hazardous events for consideration by EC; Requests the Secretary-General to take the necessary actions, within the available budgetary resources, to facilitate the work on this important issue. | - Employ consultant - Coordinate with CLW and OBS as well as CCl, CHy, JCOMM, etc. - Conduct UI-EAG HRA meeting - Engage in relevant international processes (IRDR, INFORM, UNECE Task Force on Measuring Extreme Events and Disasters, CRED, etc.) | - UI-EAG HRA Meeting on 13-15 Dec 2015 - 1st Meeting of the EC WG on DRR planned for 5-7 April 2016 (tentative) - EC-68 on 15-24 June 2016 | - ongoing | Leader |
| National DRR capacity development projects with regional cooperation frameworks |  |  |  |  |  |
| 3.2.9 | Stressed the need to build on the lessons learnt from this Project [Costa Rica Early Warning Systems for Hydrometeorological Hazards Project, completed in 2013] and encouraged further expansion of such national DRR capacity development projects with regional cooperation frameworks. |  |  |  |  |
| 3.2.12 | Supported the multi-national approach taken in this Project [South-east European Project Building Resilience to Disasters in the Western Balkans and Turkey], including the project recommendations which include further actions in building a multi-hazard early warning platform which will contribute to better collaboration and harmonization of warnings and advisories in the region. | - Project proposal for a “South East European Multi-hazard Early Warning Platform” - Coordinate with DRA (ROE) |  | - Draft proposal available |  |
| 3.2.13 | Highlighted that these activities [assessment of the institutional and technical capacities and needs of the Caribbean region to support MHEWS and risk assessment during 2010-2011] provide the foundation for future capacity development projects in the region. |  |  |  | Contributing |
| 3.2.14 | Requested the Secretary-General to continue to support the Haiti NMHS. | - Coordinate with DRA |  |  | Leader |
| 3.2.21 | Requested the Secretary-General, together with the PTC and with support from the DRR FP TC-TP, RA II, Members and partners, to facilitate the scoping of the proposal [DRR demonstration project in South-East Asia that focuses on capacity development for risk analysis and MHEWS] to complement existing relevant projects and activities in order to avoid duplication … and to provide relevant information including the scoping of the proposal for consideration by EC. | - Project proposal “Strengthening Regional Cooperation for Development and Sustainability of Meteorological, Hydrological and Climate Services to support DRR and Adaptation in Southeast Asia” - Coordinate with DRA, CLW, OBS, RES |  | - Draft proposal available | Contributing |
| 3.2.21 | Requested CBS, in collaboration with CCl and CHy, and in coordination with UNOCHA, to continue to work on the revision, with appropriate testing, of the Arrangements for the Provision of Meteorological Assistance to UN Humanitarian Missions, which are described in the Manual on the GDPFS (WMO No. 485, Vol. I, Appendix 1-5). | - Coordination (e.g. through MoU) with UNOCHA, UNITAR, and JRC (GDCACS) |  | - MoU with UNITAR signed - Draft MoU with UNOCHA available | Leader |
| Partnerships (Sendai Framework for DRR 2015-2030, follow-up actions to WCDRR, engagement in national, regional and global Platforms for DRR and forums, etc.) |  |  |  |  |  |
| 3.2.62 | Encouraged all Members to adopt a shared approach with relevant agencies and organizations at the national level to promote implementation of the Sendai Framework; emphasized the need for a set of core commitments and actions to address the issue of resilience. |  |  |  | Contributing |
| 3.2.64 | Urged Members to proactively engage in their national DRM and take on a leading role in relevant areas such as early warning and/or multi-hazard early warning systems to assist the development of DRR SOPs for appropriate response to these warnings. | - Support Members to develop SOPs for their MHEWS |  | - Support provided to Tanzania and Mauritius (upon their request) | Contributing |
| 3.2.65 | Encouraged WMO Members and the Secretariat to engage in relevant partnerships for effective implementation of the Sendai Framework, and in particular to take on a leading role in the fields of MHEWS and in identifying / cataloguing extreme weather and its impacts, water and climate events in cooperation with all activities of the GFCS. | - Identify relevant networks and partnerships (MHEWS, Earth observations for DRM, reducing landslide disaster risk, water resources management, coherence with climate change adaptation initiatives, international partnership of science and technology for DRR, etc.) | - UNISDR Science & Technology Conference 27-29 Jan 2016 - Etc. | - WMO on the Organizing Committee for the UNISDR Science & Technology Conference 27-29 Jan 2016 |  |
| Resolution 10 (Cg-17) | Sendai Framework for Disaster Risk Reduction 2015-2030 and WMO participation in the International Network for MHEWS (IN-MHEWS) Requests EC, working with RAs and relevant TCs, to guide the WMO contribution to the development of the hydrometeorological elements of IN-MHEWS, including possible governance mechanisms, operating modalities and appropriate monitoring and evaluation procedures; Requests the Secretary-General: - To proactively and continuously assist Members in their efforts to implement the Sendai Framework; - To ensure relevant stakeholders in hydrometeorological aspects are actively engaged in the planning meetings of IN-MHEWS in 2015 to develop its collaborative arrangements and integrated plan of action; - To keep Members informed about the progress in the establishment of IN-MHEWS and its activities; Requests the RAs to assist with the development of IN-MHEWS and to cooperate with the regional organizations and regional bodies to strengthen partnerships and support WMO Regional Centres to promote the implementation of the Sendai Framework, in particular MHEWS; Requests the TCs: - To assist with the development of IN-MHEWS, in particular the development of science-based methodologies and tools to support MHEWS; - To develop appropriate training modules to enhance the capacity of NMHSs in implementing the Sendai Framework, in particular MHEWS, and climatological aspects of extreme weather impacts for planning and prevention; Requests Members to adopt a shared approach with relevant agencies and organizations at the national level to promote implementation of the Sendai Framework. | - Take on a proactive role in establishing and maintaining the IN-MHEWS - Coordinate with CREWS - Organize an International Conference on MHEWS (IC-MHEWS), drawing from the IN-MHEWS, to help facilitate wider implementation and awareness of MHEWS among Members | - Teleconference of core partners planned for 3 or 4 Dec 2015 - UNISDR Science & Technology Conference 27-29 Jan 2016 - IC-MHEWS 5-9 Dec 2016 (tentative) | - Representatives from a number of UN and other agencies and Members supported the IN-MHEWS - Concept notes for IN-MHEWS and IC-MHEWS available - German National Platform for DRR contacted to sound out support and potential funding from the German Government - Coordination meetings with UNISDR held | Contributing |
| 3.2.23 | Urged the participation of NMHSs and RAs in the national, regional, and global DRR platforms as this will lead to strengthened partnerships and cooperation for the identification and implementation of DRR capacity development projects. Cooperation with civil protection and planning agencies in national and regional Platforms for DRR and forums are particularly important as long and short-term decisions are taken on that level. Congress stressed the importance of engaging the RAs, through their various DRR task teams or working groups, in DRR capacity development projects to provide advice and expertise on implementation, review, and evaluation of the outcomes, and recommendations for improvements, sustainability, and scaling up of the projects. | - Encourage NMHSs to participate in the national, regional, and global DRR platforms (e.g. through (semi-)circular letters) - Coordinate with RA/TC TTs, WGs etc. on DRR-related topics | - Regional Platforms on DRR in 2016 - Global Platform on DRR in 2017 | - C/DRR participated in Pacific DRR forum - C/DRR participated in the Africa WG on DRR Meeting in Youndé | Contributing |
| 3.2.29 | Noted that relations and partnerships with disaster risk management authorities, other national bodies and regional and global stakeholders [mentioned: UNISDR, IFRC, UNESCAP, development banks and World Bank in particular] should be improved for the efficient management of all disasters, including the reduction of risks and the prevention of creating new risks. | - Develop actions pertaining to existing MOUs | - 32th IFRC Conference 8-10 Dec 2015 |  |  |
| 3.2.30 | Requested the Secretary-General to engage in a comprehensive dialogue with GDACS and other third-party service providers to facilitate improved cooperation and coordination of activities, while stressing the need to emphasize the mandated role of the NMHSs. | - Coordination (e.g. through MoU) with UNOCHA, UNITAR, and JRC (GDCACS) |  | - MoU with UNITAR signed - Draft MoU with UNOCHA available | Leader |
| 3.2.31 | Requested the Secretary-General to further strengthen WMO partnerships with UNISDR and other relevant partners for the implementation of national and regional DRR projects in line with the Sendai Framework for DRR 2015–2030, including the partnerships of RAs, bodies such as the regional typhoon / hurricane committees which in many cases have existing DRR working structures, and WMO Regional Offices with regional bodies of international organizations and other partners. | - Engage in the Words into Action guides - Coordinate with regional typhoon / hurricane committees |  | - Interest and WMO focal points for the Words into Action guides conveyed to UNISDR |  |
| Requests by Cg-17 related to DRR within other Programme documents (non-exhaustive list) |  |  |  |  |  |
| Resolution 4 (Cg-17) PWS | REPORT OF THE EXTRAORDINARY SESSION (2014) OF THE COMMISSION FOR BASIC SYSTEMS RELEVANT TO TECHNICAL REGULATIONS CONCERNING PUBLIC WEATHER SERVICES COMPETENCIES Recommendation 1 (CBS-Ext.(2014)) – Competency Framework for Public Weather Services Forecasters and Advisers (a) Approves the Public Weather Services (PWS) forecasters and advisers top-level competency requirements to take effect from 1 December 2017, as follows: Competency requirements for a disaster prevention and mitigation weather adviser - Communicate warnings and associated information, including uncertainties and confidence levels, to users; - Develop products, procedures and services to meet user needs; - Develop and manage disaster prevention and mitigation stakeholder relationships; - Promote and implement impact assessments and community outreach; - Ensure the quality of information, services and procedures; |  |  |  | Leader |
| 3.1.64 TCP | Stressed that such [nationally and regionally coordinated early warning mechanisms under the TCP and increased accuracy of TC forecasting and preparedness] early warning mechanisms should be further strengthened and improved by making use of all available modern technologies and advances in sciences which can contribute to improved DRR services |  |  |  | Leader |
| 3.1.92 TCP | Urged Members and encouraged the Secretary-General to promote the involvement of hydrologists and DRR experts in the activities of regional TC bodies, in particular their annual and biennial sessions, to maximize the synergies between the three areas and thus fully meet the varied regional requirements. |  |  |  |  |
| 3.1.94 TCP | Emphasized the cross-cutting nature of the activities of the TCP in addressing this priority area of the Sendai Framework and it reaffirmed that the TCP should continue to place emphasis on the people-centred early warning systems of tropical cyclones and further strengthen the global mechanisms to reduce the disaster risk associated with the tropical cyclones. |  |  |  |  |
| 3.1.96 TCP | Requested the Secretary-General to enhance the contribution of the TCP to DRR services delivery through the implementation of impact-based monitoring, forecasting and risk-based warnings as well as through enhanced coordination of the TCP with other technical programmes. |  |  |  | Leader |
| 3.1.107 MMO | Encouraged the TCs to undertake collaborative and joint activities and projects for accelerated implementation of these and other activities [Guide to Storm Surge Forecasting, the Storm Surge Watch Scheme (SSWS), etc.] for risk reduction in coastal areas. |  |  |  | Contributing |
| 3.1.109 MMO | Requested JCOMM and CHy, with support from the Secretary-General, to ensure continuing and close coordination on CIFDP, and advise on possible ways to take maximum benefit from these projects for the Members of the Regions who have similar issues of coastal inundation and requirements for integrated multi-hazard forecasting for coastal zones. |  |  |  | Contributing |
| 3.1.111 MMO | Encouraged JCOMM to develop a strong collaboration between the CIFDP, the WMO SWFDP and the TCP. |  |  |  | Contributing |
| Resolution 13 (Cg-17) DPFS | REPORT OF THE EXTRAORDINARY SESSION (2014) OF THE COMMISSION FOR BASIC SYSTEMS CONCERNING THE GLOBAL DATA-PROCESSING AND FORECASTING SYSTEM AND EMERGENCY RESPONSE ACTIVITIES Requests the Executive Council to guide the cross-programmatic integration in SWFDP and the mechanism [GDPFS/ERA] to strengthen operational centres. |  |  |  | Lead |
| 4.1.55 | Congress urged early finalization of this important work [CCl work on definitions of extreme weather and climate events] with recommendations on and formulation of agreed definitions and tools for appropriate consideration to be included or referenced in the WMO Technical Regulations. |  |  |  | Contributing |
| 4.1.90 AgMP | Congress noted that there is currently no global, authoritative, and consistent information on drought that is easily accessible to all users, including real-time assessments of ongoing drought and information on the understanding of the physical mechanisms and predictability of drought. With this in mind, Congress supported of the efforts of the WMO Secretariat, the TSU of the IDMP, the World Climate Research Programme, GEO, and the US NOAA to further develop the Global Drought Information System (GDIS). |  |  |  | Contributing through the DRR FP RA-TC-TP (see 4.1.92 below) |
| 4.1.92 AgMP | Congress encouraged the Secretariat to liaise and coordinate with these activities [DRR FP RA-TC-TP and implementation of the Sendai Framework] to ensure that drought issues are adequately represented. |  |  |  | Contributing |
| 4.2.4.22 WWW | Recommended that best practices be shared to ensure that key satellite data and products are available in critical situations. In this regard, Congress noted the planned WMO Joint RA II and RA V Workshop on WIGOS for DRR, to be convened in Jakarta, Indonesia, from 13–15 October 2015. |  |  |  | Lead |