| Id | Priority | Objective | Outcome | Deliverable | Activity | Leader | Due | Other ETs | Effort | Status Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | To contribute to the implementation of WIGOS, including WIGOS Manual, and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by Congress XVI, and then ICG-WIGOS | Relevant WIP activities addressed | Meeting | Chair IPET-OSDE | Ongoing | ICG-WIGOS, IPET-WIFI |  | OND Principles included in WIGOS Manual OND Guidance addressing the principles under development Vision 2040 & updated Vision 2025 to be discussed at IPET-OSDE-2 |
|  |  | Deliver authoritative forecast and warning information to decision-making authorities at local, national, regional, and global levels as well as provide relevant hazard and risk analysis and assessment to assist DRM. (Cg-17: 3.2.33) | Address WMO core mandate to assist members in protecting lives and property through the provision of accurate and timely forecast and warning information. | Authoritative forecasts and warnings |  |  | ongoing |  |  |  |
|  |  | Contribute to the development of a WMO DRR Roadmap of prioritized and realistically achievable activities and deliverables, that are consistent with the WMO Strategic and Operating Plans, as well as the work plans for relevant WMO Programmes and projects” (Cg-17 3.2.7, 3.2.37, 3.2.40) | Relevant items of Resolution 8 (EC-66) addressed. | DRR Roadmap | TBD by CBS | Contributing | Meeting of the EC WG on DRR planned for 4-7 April 2016 EC-68 on 15-24 June 2016 |  |  | Updated drafts for comment are available on the DRR Programme homepage |
|  |  | Assist members in delivering better DRR Services (Cg-17: 3.2.34-35, 3.2.18)) | Improved WMO DRR Roadmap | Better alignment of WMO guidelines and knowledge products with DRR Roadmap | Collect, review and synthesize existing guidelines, lessons learnt, training material to find gaps which need to be filled. |  |  |  |  |  |
|  |  | Assist Members in the effective implementation of the Sendai Framework Agreement (Cg-17: 3.2.39, 3.2.64, Resolution 10) | Members implementation of the Sendai Framework Agreement | Through encouragement of members to develop a shared approach and development of DRR knowledge products, Coordinated capacity development projects, engaging in multi-stakeholder partnerships | TBD by CBS |  |  |  |  |  |
|  |  | Coordination of WMO’s response to Members requests for assistance (Cg-17: 3.2.25) | More effective response to Members requests for assistance | Development of SOPs, or other guidelines, helpdesk, etc |  |  |  |  |  |  |
|  |  | Strengthen the capacities of Members, especially of their NMHSs, to deliver high-quality services for DRR towards building resilience at all levels (Cg-17: 3.2.62, 3.2.64, | Address WMO core mandate to assist members in protecting lives and property through the provision of accurate and timely forecast and warning information. | Authoritative forecasts and warnings |  |  |  |  |  |  |
|  |  | Develop Identifiers for cataloguing extreme weather, water and climate events. (Cg-17: Resolution 9) | High impact weather events are catalogued to enable linkages to be established with associated loss and damage data bases. | Cataloguing process developed for recommendation to Cg-18 | Recommend the establishment of ICT |  | Cg-18 |  |  |  |
|  |  | Contribute to WMO’s Capacity Development Strategy through integrated DRR Projects such as the EWS Costa Rica and development of holistic DRR projects in areas such as in the Caribbean, South East Asia, south East Europe. (Cg-17: 3.2.9, 3.2.12, 3.2.13, 3.2.21, 3.2.23) | Members increased DRR capacities and Improved DRR training leading to improved DRR services. | training modules | TBD CBS |  |  |  |  |  |
|  |  | Arrangement of meteorological services to humanitarian agencies (Cg-17: 3.2.21). | Improved services provided to humanitarian agencies |  | Through the DRR EAG – Hum |  |  |  |  |  |
|  |  | Help Members to engage in their national DRM and take on leading roles in relevant areas such as MHEWS and assist in development of SOPs (Cg-17: 3.2.64) | Members engaged in their national DRM activities. |  |  |  |  |  |  |  |
|  |  | Work with GDACS and other third party service providers to facilitate improved cooperation and coordination of activities. (Cg-17: 3.2.30) | Clear roles and responsibilities with GDACS and other third-party providers. Mandated role of NMHSs is retained. | Improved DRR services | Meetings, possibly in conjunction with meetings with humanitarian agencies |  |  |  |  |  |
|  |  | Nationally and regionally coordinated early warning projects under the TCP and increased accuracy of TC early warning mechanisms should be further strengthened and improved. (Cg-17: Resolution 4, 3.1.64) | Improved competency framework. | Improved DRR services | Meetings |  |  |  |  |  |
|  |  | Enhance contribution of the TCP to DRR service delivery through implementation of Impact-based monitoring, forecasting and risk based warnings. (Cg-17: 3.1.96) | Improved TCP and DRR service delivery | TBD |  |  |  |  |  |  |
|  |  | Collaborate with other TCs to improve risk reduction in coastal areas. (Cg-17: 3.1.107) | Improved costal risk reduction | Collaboration and input to activities and projects such as Storm Surge Watch Scheme (SSWS) | Coordination with JCOMM |  |  |  |  |  |