draft Work Plan for IPET-WIFI for the period 2013 – 2016 
updated 03 April 2013 by Roger Atkinson
	No.

	Task
	Deliverable/Activity
	Due
	Responsible
	Impacted ETs
	Status
	Comment

	1.
	Contribute GOS–related input for the development of WMO Regulatory Material for WIGOS:
1) WMO Technical Regulations

2) WIGOS Manual

3) WIGOS Guide
	1a) GOS-related draft text for WIGOS Section of WMO Technical Regulations.
1b) Draft amended text for WWW/GOS Section of WMO Technical Regulations

2a) Draft text on GOS component for WIGOS Manual

2b) Draft amended GOS Manual

3a) Draft text on GOS component of WIGOS Guide

3b) Draft amended Guide to GOS
	1a) Dec 2013
1b) Dec 2013

2a) Dec 2014

2b) Jun 2015

3a) Dec 2015
3b) Jun 2016
	
	ICG-WIGOS TT-WRM
	
	

	2.
	Contribute to the development of guidance, mechanisms and procedures for engagement, coordination and collaboration with partner organizations.
	Document on strategy for GOS-related engagement with partner organizations developed and provided by CBS to ICG-WIGOS. 
	Dec 2014
	
	
	
	

	4.
	Develop guidance on:

1) mechanisms and procedures for improved integration of GOS observational data and products,
2) process of sharing, between GOS and other component observing systems, operational experiences, sharing of expertise and guidance for resourcing joint activities
	1) Guidance document on data and product integration provided by CBS to ICG-WIGOS.
2) Guidance document on sharing provided by CBS to ICG-WIGOS.
	1) Jun 2015 

2) Jun 2015
	
	
	
	

	5.
	Provide advice on GOS Quality Management practices and procedures.
	Document describing quality management practices and procedures with the GOS component of WIGOS provided by CBS to ICG-WIGOS
	Dec 2014
	
	
	
	

	6.
	1) Contribute to the development of guidance for WIGOS standards 

2) Document implemented standards and recommended practices and procedures on GOS data integration and products.
	Document describing existing and recommended standards provided by CBS to ICG-WIGOS
	Dec 2014
	
	
	
	

	7.
	N/A
	
	
	
	
	
	

	8.
	1) Contribute to the development of WIGOS metadata standards, practices and procedures, focusing on GOS-related metadata.
2) Contribute GOS-related input for the development of a mechanism to assist Members in implementing and exploiting WIGOS metadata standards, practices and procedures.
	1) GOS input provided by CBS to ICG-WIGOS TT-WMD
2) Document on proposed mechanism provided by CBS to ICG-WIGOS TT-WMD
	1) Jun 2014
2) Dec 2014
	
	
	
	

	9.
	1) Contribute to the development of a WIGOS capacity development strategy.

2) Provide other CBS-related advice on WIGOS capacity development, as required.
	1) Document on suggested WIGOS capacity development strategy provided by CBS to ICG-WIGOS.
2) Other contributions towards WIGOS capacity development, provided by CBS to ICG-WIGOS.
	Dec 2013
2014-2015
	
	
	
	


� Corresponds with WIGOS Activity Area Number.





