## TaskEntry
Id | ER | OPAG | Priority | ET | Objective | Outcome | Deliverable | Activity | Leader | Due | Effort (days) | Impacted ETs | StatusReport | Updated
WISC/a/1 | 4 | ISS | 1 | ET-WISC | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Develop the technical and operational specifications for the interoperability of GISCs, including security, user management and metadata collection and distribution catalogues to support GISC operations in backup mode | None - Outcome to be discussed at ET-WISC meeting in 2013 | J. Anquetil | 2013-12-31 |  |  | Continue to develop the basic services fo GISCs to take the advantage of new infromation and communication technologies and practices.
WISC/a/2 | 4 | ISS | 1 | ET-WISC | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Review the technical and operational specifications for the components and interafces of WIS centres and criteria for interoperability, certification and quality management of WIS certres | None - Outcome to be discussed at ET-WISC meeting in 2013 | J. Anquetil | 2013-12-31 |  |  | Continue to develop the basic services fo GISCs to take the advantage of new infromation and communication technologies and practices.
WISC/b/1 | 4 | ISS | 1 | ET-WISC | Operate the procedures for technical endorsement of WIS centres | Operate the procedures for technical endorsement of WIS centres | GISCs audit | March 2013 : GISC Moscow As requested by candidate centres | B. Raoult | 2013-05-01 |  |  | (1) GISCs audit (2) DCPCs review (3) Periodic assessments of operational GISCs and DCPCs
WISC/b/2 | 4 | ISS | 1 | ET-WISC | Operate the procedures for technical endorsement of WIS centres | Operate the procedures for technical endorsement of WIS centres | DCPCs review | March 2013 : Russian DCPCs As requested by candidate centres | B. Raoult | 2013-12-31 |  |  | (1) GISCs audit (2) DCPCs review (3) Periodic assessments of operational GISCs and DCPCs
WISC/b/3 | 4 | ISS | 1 | ET-WISC | Propose procedures for periodic assessment of the WIS centres, especially GISCs | Propose procedures for periodic assessment of the WIS centres, especially GISCs | Proposed procedures for periodic assessment of the WIS centres, especially GISCs | None - Outcome to be discussed at ET-WISC meeting in 2013 | B. Raoult | 2013-12-31 |  |  | Review the operational criteria and the periodic assessments procedures for GISCs and DCPCs
WISC/c/1 | 4 | ISS | 1 | ET-WISC | Oversee and perform WIS operational and monitoring activities | Oversee and perform WIS operational and monitoring activities | Determine the monitoring requirements for the WIS and develop WIS monitoring scheme to monitor the WIS-GTS operational information flow and the conformance of WIS centres' interfaces to the agreed specifications and practices | september 2013 : first draft of the monitoring requirments for the WIS december 2013 : first draft of the monitoring scheme for the WIS | L. Bezruk | 2013-12-31 |  |  | (1) Pilot implementation of WIS monitoring in the operational WIS centres (2) Analyse the implementation status and monitoring results (3) Review the monitoring scheme
WISC/c/2 | 4 | ISS | 1 | ET-WISC | Oversee and perform WIS operational and monitoring activities | Oversee and perform WIS operational and monitoring activities | Monitor WIS daily operations assisting Centres in working within WIS standars, addressing operational issues in a timely manner to ensure WIS works effectively | Monitor WIS daily operations assisting Centres in working within WIS standars, addressing operational issues in a timely manner to ensure WIS works effectively | L. Bezruk | 2013-12-31 |  |  | Li Xiang -This task Added by Dave - Ongoing december 2013 : first draft of the monitoring scheme for the WIS
WISC/d/1 | 4 | ISS | 1 | ET-WISC | Review and develop the Manual on WIS, the Guide on WIS | Review and develop the Manual on WIS, the Guide on WIS | Develop a management procedure to deal with the future requests for possible changes of the associations between National Centres and their Principal GISCs and Associated GISCs. | Maintain the technical aspects the Manual on WIS, Manual on GTS and their Guides | X. Li | 2013-12-31 |  |  | december 2013 : first draft of the management procedure
WISC/e/1 | 4 | ISS | 1 | ET-WISC | OAI Test bed | OAI Test bed | OAI Test bed | None - Outcome to be discussed | M.Heene | 2013-12-31 |  | TT-CAC IPET-MDRD | TBD
WISC/f/1 | 4 | ISS | 1 | ET-WISC | Develop a WIS Curriculum and Education requirements | Develop a WIS Curriculum and Education requirements | Develop a WIS Curriculum and Education requirements | None - Outcome to be discussed | M.Heene | 2013-12-31 |  | TT-CAC IPET-MDRD | TBD
MDR/a/1 | 4 | ISS | 1 | IPET-MDRD | Delivery of Aviation XML standard | Delivery of Aviation XML standard | Delivery of AvXML 1.0 data exchange standard to ICAO | (dec 2012 : release candidate 1 published) march 2013 : release candidate 2 published jul 2013 : final release - including publication of necessary regulatory and supporting materials for the aviation XML standard to be implemented nov 2013 : establish framework agreement with ICAO for on-going WMO engagement in Aviation XML roll-out and adoption 2013-2016 | E. Fucile | CBS Ext(2014) |  |  | DONE (dec 2012 : release candidate 1 published) CBS-Ext(2014) - formal documentation submitted march 2013 : release candidate 2 published jul 2013 : final release - including publication of necessary regulatory and supporting materials for the aviation XML standard to be implemented nov 2013 : establish framework agreement with ICAO for on-going WMO engagement in Aviation XML roll-out and adoption 2013-2016 | 2014-08-27
MDR/a/2 | 4 | ISS | 1 | IPET-MDRD | WaterML2 standardisation | WaterML2 standardisation | Standardisation path within WMO agreed for WaterML2 standard (developed in OGC) | ??? 2013 : standardisation framework agreed with WMO, ISO/TC 211 & OGC ??? 2013 : standardisation pathway for WaterML2 agreed | TBA (candidate pending discussion: A. Woolf) | REPLACED |  | CHy (specific expert team to be identified) | REPLACED BY NEW ACTION Chy has not yet agreed Part I as a standard. Recommendation from IPET-MDRD that Part I is used as a base for all time series representations of weather, climate and water information. expect CBS-16: WaterML2 Part 1/TIMESERIESML endorsed as WMO standard (CBS, CHy) | 2014-08-27
MDR/a/3 | 4 | ISS | 1 | IPET-MDRD | Further development of WMO METCE (logical data model) | Further development of WMO METCE (logical data model) | Application schema and GML schema for ground-based climate observations published for comment (exemplar for ad-hoc observation collection requirements in WIGOS) | SEE NEW ACTION on further development of AvXML | J.Tandy | 2013-12-31 |  | IPET-DRMM WIGOS ? | SEE NEW ACTION on further development of AvXML and WIGOS metadata | 2014-08-27
MDR/a/4 | 4 | ISS | 1 | IPET-MDRD | Standard for serialisation of WMO METCE (logical data model) compliant content using Common Alerting Protocol (CAP) | Standard for serialisation of WMO METCE (logical data model) compliant content using Common Alerting Protocol (CAP) | Proposal for serialising data products conforming to WMO METCE using Common Alerting Protocol (CAP) published for comment | TBD | J.Tandy | REMOVED |  | IPET-DRMM | REMOVED - NO REQUIREMENT 'Recommendation for serialising data products conforming to WMO METCE using Common Alerting Protocol (CAP) published (CBS-2014) | 2014-08-27
MDR/a/5 | 4 | ISS | 1 | IPET-MDRD | Automated transformation of WMO METCE Application Schema to TDCF-templates | Automated transformation of WMO METCE Application Schema to TDCF-templates | Proposal for serialising data products conforming to WMO METCE Application Schema as BUFR4 / GRIB2 published for comment | ??? 2013 : Technical proposal delivered outlining mapping conceptual model elements (from WMO METCE) to BUFR4 ??? 2013 : Provision of report on implications of 'model-driven' approach to next version of BUFR ??? 2013 : Technical proposal delivered outlining mapping conceptual model elements (from WMO METCE) to GRIB2 ??? 2013 : Provision of report on implications of 'model-driven' approach to next version of GRIB | TBD | POSTPONED |  | IPET-DRMM | POSTPONED Proof-of-concept implementation demonstrating automated generation of GRIB2 and/or BUFR4 templates shared with interested Members | 2014-08-27
MDR/a/6 | 4 | ISS | 1 | IPET-MDRD | Further development of WMO METCE (logical data model) | Further development of WMO METCE (logical data model) | To be determined - pending discussion with GRUAN project team | ??? 2013 : metadata and data exchange requirements for upper-air climate observing networks agreed with GRUAN project team | J.Tandy | REPLACED |  | CCl WMO GRUAN project | REPLACED with WIGOS metadata ??? 2013 : metadata and data exchange requirements for upper-air climate observing networks agreed with GRUAN project team | 2014-08-27
MDR/a/7 | 4 | ISS | 1 | IPET-MDRD | Publication of WMO code-table resources as web-accessible registers | Publication of WMO code-table resources as web-accessible registers | Sub-set of WMO code-tables published as web-accessible resources in wmo.int domain (e.g. a registry); scope limited to support of Aviation XML (July 2013) and WIS DAR metadata | mar 2013 : beta release of web-accessible registers publically deployed in support of AviationXML release candidate 2 jul 2013 : initial operating capaility of web-accessible registers deployed in support of AviationXML ??? 2013 : additional registers deployed to support WIS DAR metadata | J.Tandy | ONGOING |  | IPET-DRMM ET-WISC | DONE: mar 2013 : beta release of web-accessible registers publically deployed in support of AviationXML release candidate 2 DONE: jul 2013 : initial operating capaility of web-accessible registers deployed in support of AviationXML ONGOING: ??? 2013 : additional registers deployed to support WIS DAR metadata ONGOING: Updates to contents of codes register | 2014-08-27
MDR/a/8 | 4 | ISS | 1 | IPET-MDRD | Use of web-accessible registers to support TDCF | Use of web-accessible registers to support TDCF | Proposal for how publication of WMO code-tables within web-accessible registers can support TDCF data exchange published for comment | TBD | J.Tandy | COMBINED |  | IPET-DRMM | ONGOING: Recommendation for how publication of WMO code-tables within web-accessible registers can support TDCF data exchange published (CBS-2014); absorb into item on codes registers | 2014-08-27
MDR/a/9 | 4 | ISS | 1 | IPET-MDRD | Recommendation of keyword thesauri for WIS DAR metadata | Recommendation of keyword thesauri for WIS DAR metadata | Recommendation outlining a set of reference keyword thesauri for use by metadata authors published | ??? 2013 : assessment of existing third party keyword thesauri completed ??? 2013 : assessment of WMO code-tables as candidate sources for keyword thesauri completed ??? 2013 : WMO code-tables recommended as keyword thesauri published as web-accessible registers (see Objective MDR/a/7) | J.Tandy | REMOVED |  | ET-WISC | CLOSED Simpler solution needed. Absorbed into action on metadata guidance. | 2014-08-27
MDR/a/10 | 4 | ISS | 1 | IPET-MDRD | Use of XLINKs within WIS DAR metadata | Use of XLINKs within WIS DAR metadata | Guidance on the use of XLINKs within WIS DAR metadata published for comment | ??? 2013 : proposal on use of XLINKs in WIS DAR metadata published for internal review ??? 2013 : validation of proposal by GISC and/or DCPC operators completed ??? 2013 : final guidance published for external review (amended in light of validation experience) | TBD (noting engagement from T. Habermann in previous session) | COMPLETE |  |  | COMPLETE Using x-links causes too many operational problems. Include in guidance the recommendation not to use them | 2014-08-27
MDR/a/11 | 4 | ISS | 1 | IPET-MDRD | WIS DAR metadata education programme | WIS DAR metadata education programme | Contributions to ET-WISC led education and curriculum activity | REMOVED: Will concentrate on improved guidance materials | E. Toyoda | REMOVED |  | ET-WISC | REMOVED: Will concentrate on improved guidance materials | 2014-08-27
MDR/a/12 | 4 | ISS | 1 | IPET-MDRD | WIS DAR metadata analysis tooling | WIS DAR metadata analysis tooling | Technical specification of WIS DAR metadata analysis tool published. Pilot implementation provided. | ??? 2013 : assess existing tooling from NGDC/NOAA for deployment at GISCs or other centres to analyse and report on metadata compliance with formal requirements and guidance ??? 2013 : metadata analysis tool technical specification published ??? 2013 : pilot implementation of metadata analysis tool completed | E. Toyoda (noting engagement from T. Habermann & John Kozimor in previous session) | MOVED |  |  | REMAINING ACTIONS recorded under new item DONE: assess existing tooling from NGDC/NOAA for deployment at GISCs or other centres to analyse and report on metadata compliance with formal requirements and guidance ONGOING : metadata analysis tool technical specification published DONE : pilot implementation of metadata analysis tool completed | 2014-08-27
MDR/a/13 | 4 | ISS | 1 | IPET-MDRD | Change / defect management tooling for WMO Core Metadata Profile | Change / defect management tooling for WMO Core Metadata Profile | Redmine change/defect tracking tool (piloted by JMA) to support management of change to WMO Core Metadata Profile actively used for capturing change requests for WMO Core Metadata Profile | ??? 2013 : implement Redmine for managing change requests to WMO Core Metadata Profile ??? 2013 : assessment of applicability to managing change requests for WMO TDCF completed | E. Toyoda | COMPETE |  |  | COMPLETE | 2014-08-27
MDR/a/14 | 4 | ISS | 1 | IPET-MDRD | Provision of WIS DAR metadata guidance & examples | Provision of WIS DAR metadata guidance & examples | Ongoing provision of additional guidance material and automated validation tests (rubric) in response to emerging inconsistencies in metadata style observed in WIS DAR metadata | ??? 2013 : exemplar WIS DAR metadata records for commonly used WMO code forms published CBS-16: Sumbit formal document on WIS Discovery Metadata guidance for both v1.3 and 2.0 ??? 2013 : guidance for specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins published ??? 2013 : guidance on the use of Digital Object Identifiers (DOI) provided | TBD | 2013-12-31 |  | ET-WISC | Available on WIS wiki : exemplar WIS DAR metadata records for commonly used WMO code forms published Partly developed on WIS wiki : guidance for specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins published No clear requirements identifier : guidance on the use of Digital Object Identifiers (DOI) provided | 2014-08-27
MDR/a/15 | 4 | ISS | 1 | IPET-MDRD | Evolution of WMO Core Metadata Profile specification | Evolution of WMO Core Metadata Profile specification | Provision of incremental amendments to WMO Core Metadata Profile specification; agreed through fast-track process. | ??? 2013 : Amendment to WMO_CategoryCode to include additional terms (e.g. 'spaceWeather') ??? 2013 : Formalise specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins ??? 2013 : Formalise use of Digital Object Identifiers (DOI) in WIS DAR records ??? 2013 : Assess implications to WMO Core Metadata Profile from ISO 19115-1:2013, ISO 19115-2:2009, ISO 19157:2013 & ISO 19115-3:2013 ??? 2013 : Agree engagement plan with GISC implementors to assess and validate proposed changes for WMO Core Metadata Profile v2 | TBD | 2015-06-01 |  | ET-WISC | Done : Amendment to WMO_CategoryCode to include additional terms (e.g. 'spaceWeather') Done : Formalise specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins No clear requirement beyond metadata fileIdentifier: Formalise use of Digital Object Identifiers (DOI) in WIS DAR records Awaits formal agreement by ISO : Assess implications to WMO Core Metadata Profile from ISO 19115-1:2013, ISO 19115-2:2009, ISO 19157:2013 & ISO 19115-3:2013 Moved to new item : Agree engagement plan with GISC implementors to assess and validate proposed changes for WMO Core Metadata Profile v2 | 2014-08-27
DRMM/a/1 | 4 | ISS | 1 | IPET-DRMM | Review and further develop the Table Driven Code Forms by defining descriptors, common sequences, data templates and the regulations supporting these, including data representation of regional practices, so they meet the requirements of all Members, WMO Programmes and other concerned international organizations, such as ICAO | Review and further develop the Table Driven Code Forms by defining descriptors, common sequences, data templates and the regulations supporting these, including data representation of regional practices, so they meet the requirements of all Members, WMO Programmes and other concerned international organizations, such as ICAO | Updates to Manual on Codes | May 2013 : update to code tables Nov. 2013 : update to code tables | TT-BUFR, TT-GRIB | 2013-11-30 |  |  | May 2013 : update to code tables Nov. 2013 : update to code tables
DRMM/a/2 | 4 | ISS | 1 | IPET-DRMM | Review and update guidance to Members and technical commissions on data representation, including national practices, and invite, coordinate and assist Members to validate modified or new data representations | Review and update guidance to Members and technical commissions on data representation, including national practices, and invite, coordinate and assist Members to validate modified or new data representations | Updated guidance material as required | - | TT-BUFR, TT-GRIB | 2013-12-31 |  |  | -
DRMM/a/3 | 4 | ISS | 1 | IPET-DRMM | Review, develop and update the Manual on Codes (WMO-No 306) and associated reference and guidance material as required, and publish these in suitable electronic formats for human and automated use | Review, develop and update the Manual on Codes (WMO-No 306) and associated reference and guidance material as required, and publish these in suitable electronic formats for human and automated use | Updates to Manual on Codes | May 2013 : update to code tables Nov. 2013 : update to code tables | TT-BUFR, TT-GRIB | 2013-11-30 |  |  | May 2013 : update to code tables Nov. 2013 : update to code tables
DRMM/a/4 | 4 | ISS | 1 | IPET-DRMM | Review and develop procedures and guidance to enable the interoperability of metadata and data between WMO standards and formats used within other communities, such as NetCDF, using the WMO Logical Data Model as a tool to achieve this | Review and develop procedures and guidance to enable the interoperability of metadata and data between WMO standards and formats used within other communities, such as NetCDF, using the WMO Logical Data Model as a tool to achieve this | TBD | - | TT-DSM | 2013-12-31 | IPET-MDRD |  | -
DRMM/a/5 | 4 | ISS | 1 | IPET-DRMM | Monitor conformance of data exchanged within the WIS and metadata records published to the WIS DAR catalogue with WMO data representation standards for utility and conformance with the guidance and WMO Core Metadata Profile, and develop action plans, including capacity building, to address issues identified by monitoring | Monitor conformance of data exchanged within the WIS and metadata records published to the WIS DAR catalogue with WMO data representation standards for utility and conformance with the guidance and WMO Core Metadata Profile, and develop action plans, including capacity building, to address issues identified by monitoring | TBD | - | TT-DSM | 2013-12-31 | IPET-MDRD |  | -
DRMM/a/6 | 4 | ISS | 1 | IPET-DRMM | Review and update the procedures used to maintain WMO data representations, taking into account opportunities presented by the WMO Logical Data Modelas a tool to achieve this | Review and update the procedures used to maintain WMO data representations, taking into account opportunities presented by the WMO Logical Data Modelas a tool to achieve this | Updated procedures for maintenance of WMO data representations | - | TT-DSM | 2013-12-31 | IPET-MDRD |  | -
DRMM/a/7 | 4 | ISS | 1 | IPET-DRMM | Monitor progress towards and coordinate actions to implement migration to Table Driven Codes Forms | Monitor progress towards and coordinate actions to implement migration to Table Driven Codes Forms | Updated status report on migration | - | TT-MTDCF | 2013-12-31 | ET-WISC |  | -
DRMM/a/8 | 4 | ISS | 1 | IPET-DRMM | Identify implementation issues requiring the urgent consideration of the OPAG on ISS | Identify implementation issues requiring the urgent consideration of the OPAG on ISS | - | - | IPET-DRMM | 2013-12-31 | Potentially any |  | -
ISS/a/1 | 4 | ISS | 1 | OPAG-ISS | xxx | xxx | xxx | xxx | xxx | 2013-12-31 |  |  | xxx
ISS/a/2 | 4 | ISS | 1 | OPAG-ISS | xxx | xxx | xxx | xxx | xxx | 2013-12-31 |  |  | xxx
| 4 | ISS | 1 | IPET-MDRD | Develop WMO Discovery Metadata Core Profile v2 | Updated WMO Core Profile compatible with ISO 19115-1, 19115-2 | New WMO Core Profile standard, guidance and supporting schemas and tools | 2015-06: WCMP2-RC1 requirements defined and first draft 2015-12: WCMP2-RC2 specification 2016-03: GISC involvement in development of drafts 2016-04: WCMP2-FD Final draft 2016-04: Guide to WCMP v1.n 2016-09: CBS-16 Approval of WCMP2-FD to go to between sessions approval 2016-12: Guide-2.1 guide for WCMP2 metadata 2016-12: Migration plan 2017-03: CBS Approval between sessions: WCMP2, Guide 2.1, Migration-WCMP2 2017-06: GISC Beta implementations 2018-01: WCMP2 allowed in GISC catalogues | tandy | CBS-16 |  | ET-WISC | NEW 2015-06: WCMP2-RC1 requirements defined and first draft 2015-12: WCMP2-RC2 specification 2016-03: GISC involvement in development of drafts 2016-04: WCMP2-FD Final draft 2016-04: Guide to WCMP v1.n 2016-09: CBS-16 Approval of WCMP2-FD to go to between sessions approval 2016-12: Guide-2.1 guide for WCMP2 metadata 2016-12: Migration plan 2017-03: CBS Approval between sessions: WCMP2, Guide 2.1, Migration-WCMP2 2017-06: GISC Beta implementations 2018-01: WCMP2 allowed in GISC catalogues | 2014-08-27
| 4 | ISS | 1 | IPET-MDRD | Provision of “metadata quality assessment techniques” in light of outcomes of WIS Monitoring workshop and provision of analysis/validation tools | Tools available for users and centres to assess (techincal) quality of WIS Discovery Metadata | Toolset for deployment by centres | CBS Ext(2018) Toolsets available for v1 and v2 | Toyoda | CBS Ext(2018) |  | ET-WISC | CBS Ext(2018) Toolsets available for v1 and v2 | 2014-08-27
| 4 | ISS | 1 | IPET-MDRD | IWXXM incremental changes to support ICAO Annex 3 Amd 77 ... period 2014-2016 | IWXXM supports ICAO changes to technical regulations | Additional data types represented in IWXXM; IWXXM adjusted to match new ICAO business rules | CBS-16: Additional elements in IWXXM presented for approval | Fucile | CBS-16 |  | ICAO | NEW CBS-16: Additional elements in IWXXM presented for approval | 2014-08-27
| 4 | ISS | 1 | IPET-MDRD | TimeSeriesML and incorporation of WaterML 2 Part 1 Timeseries in WMO Technical Regulation | Following approval by Chy, WaterlML2 Paret I/TimeseriesML recorded in WMO technical regulations | Schemas, code lists, documentation and othe tools to support WaterML2/TimeseriesML use by WMO Programmes | 1. [Sep 2014] TimeseriesML SWG Charter; for submission to OGC TC, 15-19 September 2014, Calgary CA. 2. [~Jun 2015] TimeseriesML 1.0 standard, including both Application Schema and GML encoding; for submission to OGC TC, June 2015. 3. [~Jun 2015] WaterML SWG Charter amendment; for submission to OGC TC, June 2015. 4. [~Sep 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate TimeseriesML 1.0. 5. [~Dec 2015] Revision of WaterML 2.0 Part 1 – Timeseries, refactored as a profile of TimeseriesML; for submission to OGC TC, December 2015. 6. [~Dec 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate revised WaterML 2.0 Part 1 - Timeseries. | TBD | CBS-16 |  | CHy (specific expert team to be identified) | 1. [Sep 2014] TimeseriesML SWG Charter; for submission to OGC TC, 15-19 September 2014, Calgary CA. 2. [~Jun 2015] TimeseriesML 1.0 standard, including both Application Schema and GML encoding; for submission to OGC TC, June 2015. 3. [~Jun 2015] WaterML SWG Charter amendment; for submission to OGC TC, June 2015. 4. [~Sep 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate TimeseriesML 1.0. 5. [~Dec 2015] Revision of WaterML 2.0 Part 1 – Timeseries, refactored as a profile of TimeseriesML; for submission to OGC TC, December 2015. 6. [~Dec 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate revised WaterML 2.0 Part 1 - Timeseries. | 2014-08-27
| 4 | ISS | 1 | IPET-MDRD | Represent WIGOS metadata | Model drived representations of WIGOS metadata | XML and TDCF representations of WIGOS metadata with supporting documentation and tools | Plan to be developed by a sub-team of members of IPET-MDRD and TT-WMD | Bannerman | Draft Dec 2015 |  | TT-WMD | NEW Plan to be developed by a sub-team of members of IPET-MDRD and TT-WMD | 2014-08-27
| 4 | ISS | 3 | IPET-MDRD | Registration of WMO Application Schemas with ISO/TC 211; as profiles of ISO 19156:2011 O&M | ISO list WMO representations as conformant | ISO listing of WMO representations | As standards approved, discuss with ISO how they can be recorded by ISO TC 211 | tandy | CBS-16 |  | CHy (specific expert team to be identified) | NEW As standards approved, discuss with ISO how they can be recorded by ISO TC 211 | 2014-08-27
| 4 | ISS | 1 | O{ET-MDRD | Establish mappings from WMO codes to CF-Standard names under shared governance with CF community | Able to use WMO and NetCDF datasets together | Mappings to allow different names used by WMO and NetCDF data representations to be reconciled | TBD | Tandy | CBS-16 |  |  | NEW | 2014-08-27
CTS/a/1 | 4 | ISS | 1 | ET-CTS | WMO IPv6 Initiative | Consolidate and expand the IPv6 pilot network | At the end of 2013, the 5-year project will be up to speed and the 1st results will be available (questionnaire, pilot, newsletter). An IPv6 pilot network allowing members to gain IPv6 knowledge and exchange data using IPv6 network | june 2013 : 1st result of questionnaire november 2013 : Preliminary results of the pilot network | O.Gorwits | 2016-03-01 |  |  | The 1st phase of the task is now completed. The task has been expanded with one main task and 3 subtasks that are described below. The next major update will be in 2016. | 2014-09-01
CTS/a/1.1 | 4 | ISS | 1 | ET-CTS | WMO IPv6 Initiative | Relaunch the IPv6 questionnaire | As planned, the first run of the IPv6 questionnaire was completed in H2-2013. The results are presented in ET-CTS 2014 meeting report | Q1-2015 - relaunch IPv6 questionnaire to asses the progression of IPv6 ussage and knowledge. | R.Giraud | 2015-12-31 |  |  |  | 2014-09-01
CTS/a/1.2 | 4 | ISS | 1 | ET-CTS | WMO IPv6 Initiative | IPv6 Business Case | IPv6 is not really taking off within the members as most os them are lacking a business case | Establish a draft business case on why Members should introduce IPv6 into their environment. | P.Silva | 2016-03-01 |  |  |  | 2014-09-01
CTS/a/1.3 | 4 | ISS | 1 | ET-CTS | WMO IPv6 Initiative | Reviewing the Guide to Information Technology Security (WMO doc No. 1115) | IPv6 creates new security challenges | A Draft to update WMO doc. 1115 will be prepared including IPv6 material. | I.Glaser | 2016-03-01 |  |  |  | 2014-09-01
CTS/a/2 | 4 | ISS | 1 | ET-CTS | Multicast for the GISC | Multicast for the GISC | Multicast looks potentially attractive for exchange of data between GISC. However, major technical problems are to be faced. | The Task Team will keep abreast with new development on Multicast and potential new software solutions | G.Molloy | 2016-03-01 |  |  |  | 2014-09-01
CTS/a/3 | 4 | ISS | 1 | ET-CTS | Design principles for the WIS data communication structure | Design principles for the WIS data communication structure | Pilot a "cloud" based solution for cache synchronisation and metadata exchange | To establish a pilot environment involving multiple GISC to study the attractivness of this solution | O.Gorwits | 2015-12-01 |  |  |  | 2014-09-01
CTS/a/4 | 4 | ISS | 1 | ET-CTS | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | None - Outcome to be discussed at ET-CTS meeting in 2014 | H.Ayina Akilotan (if available for the group) | 2013-12-31 |  |  | The task is likely to be abandoned. | 2014-09-01
CTS/a/5 | 4 | ISS | 1 | ET-CTS | Contribute to the development of WIS educational requirements an capacty building led by ET-WISC | Contribute to the development of WIS educational requirements an capacty building led by ET-WISC | Network and related applications component of WIS Curriculum | TBD | TBD | 2013-12-31 |  | TT-OM | Done | 2014-09-01
CTS/a/6 | 4 | ISS | 1 | ET-CTS | Contribute to the development of WIS monitoring requirements led by ET-WISC | Contribute to the development of WIS monitoring requirements led by ET-WISC | Network and related applications component of WIS monitoring requirements | TBD | TBD | 2013-12-31 |  | TT-OM | Done. A new task might be created for the particpation in the pilot phase of the monitoring activity.. | 2014-09-01
CTS/a/7 | 4 | ISS | 1 | ET-CTS | Development and mainenance of WIS Core Network | Development and mainenance of WIS Core Network | Development and mainenance of WIS Core Network | TBD | TBD | 2013-12-31 |  | RA VI RMDCN TT | Done. The RMDCN Next Generation migration is completed. Coopation between ECMWF, ET-CTS and WMO will continue to facilitate the connection of the 3 GISCs not yet connected to the RMDCN (Brazil Iran, Saudi-Arabia). | 2014-09-01
CTS/a/8 | 4 | ISS | 1 | ET-CTS | Develop a coordination mechanism for users and suppliers of satellite data collection systems (Satcom) | Develop a coordination mechanism for users and suppliers of satellite data collection systems (Satcom) | SATCOM | JCOMM/CBS leading preliminary negotiations and planning on formal development of SATCOM | TBD | 2013-12-31 |  | JCOMM | ET-CTS made a proposal to extend its ToR to cover Data Collection Systems issues. Depending on the outome of CBS -16 in Paraguay, this task will be modified accordingly. | 2014-09-01

## Summary
ER | (All)
OPAG | ISS
Count of Activity | [8 empty] | Due
ET | Priority | Objective | Outcome | Deliverable | Activity | Leader | StatusReport | Impacted ETs | 2013-05-01 | 2013-12-31 | 2013-11-30 | CBS Ext(2014) | REPLACED | REMOVED | POSTPONED | ONGOING | COMBINED | COMPLETE | MOVED | COMPETE | 2015-06-01 | CBS-16 | CBS Ext(2018) | Draft Dec 2015 | 2016-03-01 | 2015-12-31 | 2015-12-01
ET-CTS | 1 | WMO IPv6 Initiative | Consolidate and expand the IPv6 pilot network | At the end of 2013, the 5-year project will be up to speed and the 1st results will be available (questionnaire, pilot, newsletter). An IPv6 pilot network allowing members to gain IPv6 knowledge and exchange data using IPv6 network | june 2013 : 1st result of questionnaire november 2013 : Preliminary results of the pilot network | O.Gorwits | The 1st phase of the task is now completed. The task has been expanded with one main task and 3 subtasks that are described below. The next major update will be in 2016. | (blank) | [16 empty] | 1
|  |  | Relaunch the IPv6 questionnaire | As planned, the first run of the IPv6 questionnaire was completed in H2-2013. The results are presented in ET-CTS 2014 meeting report | Q1-2015 - relaunch IPv6 questionnaire to asses the progression of IPv6 ussage and knowledge. | R.Giraud | (blank) | (blank) | [17 empty] | 1
|  |  | IPv6 Business Case | IPv6 is not really taking off within the members as most os them are lacking a business case | Establish a draft business case on why Members should introduce IPv6 into their environment. | P.Silva | (blank) | (blank) | [16 empty] | 1
|  |  | Reviewing the Guide to Information Technology Security (WMO doc No. 1115) | IPv6 creates new security challenges | A Draft to update WMO doc. 1115 will be prepared including IPv6 material. | I.Glaser | (blank) | (blank) | [16 empty] | 1
|  | Multicast for the GISC | Multicast for the GISC | Multicast looks potentially attractive for exchange of data between GISC. However, major technical problems are to be faced. | The Task Team will keep abreast with new development on Multicast and potential new software solutions | G.Molloy | (blank) | (blank) | [16 empty] | 1
|  | Design principles for the WIS data communication structure | Design principles for the WIS data communication structure | Pilot a "cloud" based solution for cache synchronisation and metadata exchange | To establish a pilot environment involving multiple GISC to study the attractivness of this solution | O.Gorwits | (blank) | (blank) | [18 empty] | 1
|  | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | Pilot revision of WMO No. 386, Vol II, sections B.I-1 to B.I-15 | None - Outcome to be discussed at ET-CTS meeting in 2014 | H.Ayina Akilotan (if available for the group) | The task is likely to be abandoned. | (blank) |  | 1
|  | Contribute to the development of WIS educational requirements an capacty building led by ET-WISC | Contribute to the development of WIS educational requirements an capacty building led by ET-WISC | Network and related applications component of WIS Curriculum | TBD | TBD | Done | TT-OM |  | 1
|  | Contribute to the development of WIS monitoring requirements led by ET-WISC | Contribute to the development of WIS monitoring requirements led by ET-WISC | Network and related applications component of WIS monitoring requirements | TBD | TBD | Done. A new task might be created for the particpation in the pilot phase of the monitoring activity.. | TT-OM |  | 1
|  | Development and mainenance of WIS Core Network | Development and mainenance of WIS Core Network | Development and mainenance of WIS Core Network | TBD | TBD | Done. The RMDCN Next Generation migration is completed. Coopation between ECMWF, ET-CTS and WMO will continue to facilitate the connection of the 3 GISCs not yet connected to the RMDCN (Brazil Iran, Saudi-Arabia). | RA VI RMDCN TT |  | 1
|  | Develop a coordination mechanism for users and suppliers of satellite data collection systems (Satcom) | Develop a coordination mechanism for users and suppliers of satellite data collection systems (Satcom) | SATCOM | JCOMM/CBS leading preliminary negotiations and planning on formal development of SATCOM | TBD | ET-CTS made a proposal to extend its ToR to cover Data Collection Systems issues. Depending on the outome of CBS -16 in Paraguay, this task will be modified accordingly. | JCOMM |  | 1
ET-WISC | 1 | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Review and further develop the technical and operational specifications for the components and interfaces of WIS Centres | Develop the technical and operational specifications for the interoperability of GISCs, including security, user management and metadata collection and distribution catalogues to support GISC operations in backup mode | None - Outcome to be discussed at ET-WISC meeting in 2013 | J. Anquetil | Continue to develop the basic services fo GISCs to take the advantage of new infromation and communication technologies and practices. | (blank) |  | 1
|  |  |  | Review the technical and operational specifications for the components and interafces of WIS centres and criteria for interoperability, certification and quality management of WIS certres | None - Outcome to be discussed at ET-WISC meeting in 2013 | J. Anquetil | Continue to develop the basic services fo GISCs to take the advantage of new infromation and communication technologies and practices. | (blank) |  | 1
|  | Operate the procedures for technical endorsement of WIS centres | Operate the procedures for technical endorsement of WIS centres | GISCs audit | March 2013 : GISC Moscow As requested by candidate centres | B. Raoult | (1) GISCs audit (2) DCPCs review (3) Periodic assessments of operational GISCs and DCPCs | (blank) | 1
|  |  |  | DCPCs review | March 2013 : Russian DCPCs As requested by candidate centres | B. Raoult | (1) GISCs audit (2) DCPCs review (3) Periodic assessments of operational GISCs and DCPCs | (blank) |  | 1
|  | Propose procedures for periodic assessment of the WIS centres, especially GISCs | Propose procedures for periodic assessment of the WIS centres, especially GISCs | Proposed procedures for periodic assessment of the WIS centres, especially GISCs | None - Outcome to be discussed at ET-WISC meeting in 2013 | B. Raoult | Review the operational criteria and the periodic assessments procedures for GISCs and DCPCs | (blank) |  | 1
|  | Oversee and perform WIS operational and monitoring activities | Oversee and perform WIS operational and monitoring activities | Determine the monitoring requirements for the WIS and develop WIS monitoring scheme to monitor the WIS-GTS operational information flow and the conformance of WIS centres' interfaces to the agreed specifications and practices | september 2013 : first draft of the monitoring requirments for the WIS december 2013 : first draft of the monitoring scheme for the WIS | L. Bezruk | (1) Pilot implementation of WIS monitoring in the operational WIS centres (2) Analyse the implementation status and monitoring results (3) Review the monitoring scheme | (blank) |  | 1
|  |  |  | Monitor WIS daily operations assisting Centres in working within WIS standars, addressing operational issues in a timely manner to ensure WIS works effectively | Monitor WIS daily operations assisting Centres in working within WIS standars, addressing operational issues in a timely manner to ensure WIS works effectively | L. Bezruk | Li Xiang -This task Added by Dave - Ongoing december 2013 : first draft of the monitoring scheme for the WIS | (blank) |  | 1
|  | Review and develop the Manual on WIS, the Guide on WIS | Review and develop the Manual on WIS, the Guide on WIS | Develop a management procedure to deal with the future requests for possible changes of the associations between National Centres and their Principal GISCs and Associated GISCs. | Maintain the technical aspects the Manual on WIS, Manual on GTS and their Guides | X. Li | december 2013 : first draft of the management procedure | (blank) |  | 1
|  | OAI Test bed | OAI Test bed | OAI Test bed | None - Outcome to be discussed | M.Heene | TBD | TT-CAC IPET-MDRD |  | 1
|  | Develop a WIS Curriculum and Education requirements | Develop a WIS Curriculum and Education requirements | Develop a WIS Curriculum and Education requirements | None - Outcome to be discussed | M.Heene | TBD | TT-CAC IPET-MDRD |  | 1
IPET-DRMM | 1 | Review and update guidance to Members and technical commissions on data representation, including national practices, and invite, coordinate and assist Members to validate modified or new data representations | Review and update guidance to Members and technical commissions on data representation, including national practices, and invite, coordinate and assist Members to validate modified or new data representations | Updated guidance material as required | - | TT-BUFR, TT-GRIB | - | (blank) |  | 1
|  | Review, develop and update the Manual on Codes (WMO-No 306) and associated reference and guidance material as required, and publish these in suitable electronic formats for human and automated use | Review, develop and update the Manual on Codes (WMO-No 306) and associated reference and guidance material as required, and publish these in suitable electronic formats for human and automated use | Updates to Manual on Codes | May 2013 : update to code tables Nov. 2013 : update to code tables | TT-BUFR, TT-GRIB | May 2013 : update to code tables Nov. 2013 : update to code tables | (blank) |  |  | 1
|  | Review and develop procedures and guidance to enable the interoperability of metadata and data between WMO standards and formats used within other communities, such as NetCDF, using the WMO Logical Data Model as a tool to achieve this | Review and develop procedures and guidance to enable the interoperability of metadata and data between WMO standards and formats used within other communities, such as NetCDF, using the WMO Logical Data Model as a tool to achieve this | TBD | - | TT-DSM | - | (blank) |  | 1
|  | Review and update the procedures used to maintain WMO data representations, taking into account opportunities presented by the WMO Logical Data Modelas a tool to achieve this | Review and update the procedures used to maintain WMO data representations, taking into account opportunities presented by the WMO Logical Data Modelas a tool to achieve this | Updated procedures for maintenance of WMO data representations | - | TT-DSM | - | (blank) |  | 1
|  | Monitor progress towards and coordinate actions to implement migration to Table Driven Codes Forms | Monitor progress towards and coordinate actions to implement migration to Table Driven Codes Forms | Updated status report on migration | - | TT-MTDCF | - | (blank) |  | 1
|  | Identify implementation issues requiring the urgent consideration of the OPAG on ISS | Identify implementation issues requiring the urgent consideration of the OPAG on ISS | - | - | IPET-DRMM | - | (blank) |  | 1
|  | Review and further develop the Table Driven Code Forms by defining descriptors, common sequences, data templates and the regulations supporting these, including data representation of regional practices, so they meet the requirements of all Members, WMO Programmes and other concerned international organizations, such as ICAO | Review and further develop the Table Driven Code Forms by defining descriptors, common sequences, data templates and the regulations supporting these, including data representation of regional practices, so they meet the requirements of all Members, WMO Programmes and other concerned international organizations, such as ICAO | Updates to Manual on Codes | May 2013 : update to code tables Nov. 2013 : update to code tables | TT-BUFR, TT-GRIB | May 2013 : update to code tables Nov. 2013 : update to code tables | (blank) |  |  | 1
|  | Monitor conformance of data exchanged within the WIS and metadata records published to the WIS DAR catalogue with WMO data representation standards for utility and conformance with the guidance and WMO Core Metadata Profile, and develop action plans, including capacity building, to address issues identified by monitoring | Monitor conformance of data exchanged within the WIS and metadata records published to the WIS DAR catalogue with WMO data representation standards for utility and conformance with the guidance and WMO Core Metadata Profile, and develop action plans, including capacity building, to address issues identified by monitoring | TBD | - | TT-DSM | - | (blank) |  | 1
IPET-MDRD | 1 | Delivery of Aviation XML standard | Delivery of Aviation XML standard | Delivery of AvXML 1.0 data exchange standard to ICAO | (dec 2012 : release candidate 1 published) march 2013 : release candidate 2 published jul 2013 : final release - including publication of necessary regulatory and supporting materials for the aviation XML standard to be implemented nov 2013 : establish framework agreement with ICAO for on-going WMO engagement in Aviation XML roll-out and adoption 2013-2016 | E. Fucile | DONE (dec 2012 : release candidate 1 published) CBS-Ext(2014) - formal documentation submitted march 2013 : release candidate 2 published jul 2013 : final release - including publication of necessary regulatory and supporting materials for the aviation XML standard to be implemented nov 2013 : establish framework agreement with ICAO for on-going WMO engagement in Aviation XML roll-out and adoption 2013-2016 | (blank) |  |  |  | 1
|  | WaterML2 standardisation | WaterML2 standardisation | Standardisation path within WMO agreed for WaterML2 standard (developed in OGC) | ??? 2013 : standardisation framework agreed with WMO, ISO/TC 211 & OGC ??? 2013 : standardisation pathway for WaterML2 agreed | TBA (candidate pending discussion: A. Woolf) | REPLACED BY NEW ACTION Chy has not yet agreed Part I as a standard. Recommendation from IPET-MDRD that Part I is used as a base for all time series representations of weather, climate and water information. expect CBS-16: WaterML2 Part 1/TIMESERIESML endorsed as WMO standard (CBS, CHy) | CHy (specific expert team to be identified) |  |  |  |  | 1
|  | Further development of WMO METCE (logical data model) | Further development of WMO METCE (logical data model) | Application schema and GML schema for ground-based climate observations published for comment (exemplar for ad-hoc observation collection requirements in WIGOS) | SEE NEW ACTION on further development of AvXML | J.Tandy | SEE NEW ACTION on further development of AvXML and WIGOS metadata | IPET-DRMM WIGOS ? |  | 1
|  |  |  | To be determined - pending discussion with GRUAN project team | ??? 2013 : metadata and data exchange requirements for upper-air climate observing networks agreed with GRUAN project team | J.Tandy | REPLACED with WIGOS metadata ??? 2013 : metadata and data exchange requirements for upper-air climate observing networks agreed with GRUAN project team | CCl WMO GRUAN project |  |  |  |  | 1
|  | Standard for serialisation of WMO METCE (logical data model) compliant content using Common Alerting Protocol (CAP) | Standard for serialisation of WMO METCE (logical data model) compliant content using Common Alerting Protocol (CAP) | Proposal for serialising data products conforming to WMO METCE using Common Alerting Protocol (CAP) published for comment | TBD | J.Tandy | REMOVED - NO REQUIREMENT 'Recommendation for serialising data products conforming to WMO METCE using Common Alerting Protocol (CAP) published (CBS-2014) | IPET-DRMM | [5 empty] | 1
|  | Automated transformation of WMO METCE Application Schema to TDCF-templates | Automated transformation of WMO METCE Application Schema to TDCF-templates | Proposal for serialising data products conforming to WMO METCE Application Schema as BUFR4 / GRIB2 published for comment | ??? 2013 : Technical proposal delivered outlining mapping conceptual model elements (from WMO METCE) to BUFR4 ??? 2013 : Provision of report on implications of 'model-driven' approach to next version of BUFR ??? 2013 : Technical proposal delivered outlining mapping conceptual model elements (from WMO METCE) to GRIB2 ??? 2013 : Provision of report on implications of 'model-driven' approach to next version of GRIB | TBD | POSTPONED Proof-of-concept implementation demonstrating automated generation of GRIB2 and/or BUFR4 templates shared with interested Members | IPET-DRMM | [6 empty] | 1
|  | Publication of WMO code-table resources as web-accessible registers | Publication of WMO code-table resources as web-accessible registers | Sub-set of WMO code-tables published as web-accessible resources in wmo.int domain (e.g. a registry); scope limited to support of Aviation XML (July 2013) and WIS DAR metadata | mar 2013 : beta release of web-accessible registers publically deployed in support of AviationXML release candidate 2 jul 2013 : initial operating capaility of web-accessible registers deployed in support of AviationXML ??? 2013 : additional registers deployed to support WIS DAR metadata | J.Tandy | DONE: mar 2013 : beta release of web-accessible registers publically deployed in support of AviationXML release candidate 2 DONE: jul 2013 : initial operating capaility of web-accessible registers deployed in support of AviationXML ONGOING: ??? 2013 : additional registers deployed to support WIS DAR metadata ONGOING: Updates to contents of codes register | IPET-DRMM ET-WISC | [7 empty] | 1
|  | Use of web-accessible registers to support TDCF | Use of web-accessible registers to support TDCF | Proposal for how publication of WMO code-tables within web-accessible registers can support TDCF data exchange published for comment | TBD | J.Tandy | ONGOING: Recommendation for how publication of WMO code-tables within web-accessible registers can support TDCF data exchange published (CBS-2014); absorb into item on codes registers | IPET-DRMM | [8 empty] | 1
|  | Recommendation of keyword thesauri for WIS DAR metadata | Recommendation of keyword thesauri for WIS DAR metadata | Recommendation outlining a set of reference keyword thesauri for use by metadata authors published | ??? 2013 : assessment of existing third party keyword thesauri completed ??? 2013 : assessment of WMO code-tables as candidate sources for keyword thesauri completed ??? 2013 : WMO code-tables recommended as keyword thesauri published as web-accessible registers (see Objective MDR/a/7) | J.Tandy | CLOSED Simpler solution needed. Absorbed into action on metadata guidance. | ET-WISC | [5 empty] | 1
|  | Use of XLINKs within WIS DAR metadata | Use of XLINKs within WIS DAR metadata | Guidance on the use of XLINKs within WIS DAR metadata published for comment | ??? 2013 : proposal on use of XLINKs in WIS DAR metadata published for internal review ??? 2013 : validation of proposal by GISC and/or DCPC operators completed ??? 2013 : final guidance published for external review (amended in light of validation experience) | TBD (noting engagement from T. Habermann in previous session) | COMPLETE Using x-links causes too many operational problems. Include in guidance the recommendation not to use them | (blank) | [9 empty] | 1
|  | WIS DAR metadata education programme | WIS DAR metadata education programme | Contributions to ET-WISC led education and curriculum activity | REMOVED: Will concentrate on improved guidance materials | E. Toyoda | REMOVED: Will concentrate on improved guidance materials | ET-WISC | [5 empty] | 1
|  | WIS DAR metadata analysis tooling | WIS DAR metadata analysis tooling | Technical specification of WIS DAR metadata analysis tool published. Pilot implementation provided. | ??? 2013 : assess existing tooling from NGDC/NOAA for deployment at GISCs or other centres to analyse and report on metadata compliance with formal requirements and guidance ??? 2013 : metadata analysis tool technical specification published ??? 2013 : pilot implementation of metadata analysis tool completed | E. Toyoda (noting engagement from T. Habermann & John Kozimor in previous session) | REMAINING ACTIONS recorded under new item DONE: assess existing tooling from NGDC/NOAA for deployment at GISCs or other centres to analyse and report on metadata compliance with formal requirements and guidance ONGOING : metadata analysis tool technical specification published DONE : pilot implementation of metadata analysis tool completed | (blank) | [10 empty] | 1
|  | Change / defect management tooling for WMO Core Metadata Profile | Change / defect management tooling for WMO Core Metadata Profile | Redmine change/defect tracking tool (piloted by JMA) to support management of change to WMO Core Metadata Profile actively used for capturing change requests for WMO Core Metadata Profile | ??? 2013 : implement Redmine for managing change requests to WMO Core Metadata Profile ??? 2013 : assessment of applicability to managing change requests for WMO TDCF completed | E. Toyoda | COMPLETE | (blank) | [11 empty] | 1
|  | Provision of WIS DAR metadata guidance & examples | Provision of WIS DAR metadata guidance & examples | Ongoing provision of additional guidance material and automated validation tests (rubric) in response to emerging inconsistencies in metadata style observed in WIS DAR metadata | ??? 2013 : exemplar WIS DAR metadata records for commonly used WMO code forms published CBS-16: Sumbit formal document on WIS Discovery Metadata guidance for both v1.3 and 2.0 ??? 2013 : guidance for specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins published ??? 2013 : guidance on the use of Digital Object Identifiers (DOI) provided | TBD | Available on WIS wiki : exemplar WIS DAR metadata records for commonly used WMO code forms published Partly developed on WIS wiki : guidance for specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins published No clear requirements identifier : guidance on the use of Digital Object Identifiers (DOI) provided | ET-WISC |  | 1
|  | Evolution of WMO Core Metadata Profile specification | Evolution of WMO Core Metadata Profile specification | Provision of incremental amendments to WMO Core Metadata Profile specification; agreed through fast-track process. | ??? 2013 : Amendment to WMO_CategoryCode to include additional terms (e.g. 'spaceWeather') ??? 2013 : Formalise specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins ??? 2013 : Formalise use of Digital Object Identifiers (DOI) in WIS DAR records ??? 2013 : Assess implications to WMO Core Metadata Profile from ISO 19115-1:2013, ISO 19115-2:2009, ISO 19157:2013 & ISO 19115-3:2013 ??? 2013 : Agree engagement plan with GISC implementors to assess and validate proposed changes for WMO Core Metadata Profile v2 | TBD | Done : Amendment to WMO_CategoryCode to include additional terms (e.g. 'spaceWeather') Done : Formalise specification for metadata in WIS DAR records required to populate Vol C1 entries for GTS bulletins No clear requirement beyond metadata fileIdentifier: Formalise use of Digital Object Identifiers (DOI) in WIS DAR records Awaits formal agreement by ISO : Assess implications to WMO Core Metadata Profile from ISO 19115-1:2013, ISO 19115-2:2009, ISO 19157:2013 & ISO 19115-3:2013 Moved to new item : Agree engagement plan with GISC implementors to assess and validate proposed changes for WMO Core Metadata Profile v2 | ET-WISC | [12 empty] | 1
|  | Develop WMO Discovery Metadata Core Profile v2 | Updated WMO Core Profile compatible with ISO 19115-1, 19115-2 | New WMO Core Profile standard, guidance and supporting schemas and tools | 2015-06: WCMP2-RC1 requirements defined and first draft 2015-12: WCMP2-RC2 specification 2016-03: GISC involvement in development of drafts 2016-04: WCMP2-FD Final draft 2016-04: Guide to WCMP v1.n 2016-09: CBS-16 Approval of WCMP2-FD to go to between sessions approval 2016-12: Guide-2.1 guide for WCMP2 metadata 2016-12: Migration plan 2017-03: CBS Approval between sessions: WCMP2, Guide 2.1, Migration-WCMP2 2017-06: GISC Beta implementations 2018-01: WCMP2 allowed in GISC catalogues | tandy | NEW 2015-06: WCMP2-RC1 requirements defined and first draft 2015-12: WCMP2-RC2 specification 2016-03: GISC involvement in development of drafts 2016-04: WCMP2-FD Final draft 2016-04: Guide to WCMP v1.n 2016-09: CBS-16 Approval of WCMP2-FD to go to between sessions approval 2016-12: Guide-2.1 guide for WCMP2 metadata 2016-12: Migration plan 2017-03: CBS Approval between sessions: WCMP2, Guide 2.1, Migration-WCMP2 2017-06: GISC Beta implementations 2018-01: WCMP2 allowed in GISC catalogues | ET-WISC | [13 empty] | 1
|  | Provision of “metadata quality assessment techniques” in light of outcomes of WIS Monitoring workshop and provision of analysis/validation tools | Tools available for users and centres to assess (techincal) quality of WIS Discovery Metadata | Toolset for deployment by centres | CBS Ext(2018) Toolsets available for v1 and v2 | Toyoda | CBS Ext(2018) Toolsets available for v1 and v2 | ET-WISC | [14 empty] | 1
|  | IWXXM incremental changes to support ICAO Annex 3 Amd 77 ... period 2014-2016 | IWXXM supports ICAO changes to technical regulations | Additional data types represented in IWXXM; IWXXM adjusted to match new ICAO business rules | CBS-16: Additional elements in IWXXM presented for approval | Fucile | NEW CBS-16: Additional elements in IWXXM presented for approval | ICAO | [13 empty] | 1
|  | TimeSeriesML and incorporation of WaterML 2 Part 1 Timeseries in WMO Technical Regulation | Following approval by Chy, WaterlML2 Paret I/TimeseriesML recorded in WMO technical regulations | Schemas, code lists, documentation and othe tools to support WaterML2/TimeseriesML use by WMO Programmes | 1. [Sep 2014] TimeseriesML SWG Charter; for submission to OGC TC, 15-19 September 2014, Calgary CA. 2. [~Jun 2015] TimeseriesML 1.0 standard, including both Application Schema and GML encoding; for submission to OGC TC, June 2015. 3. [~Jun 2015] WaterML SWG Charter amendment; for submission to OGC TC, June 2015. 4. [~Sep 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate TimeseriesML 1.0. 5. [~Dec 2015] Revision of WaterML 2.0 Part 1 – Timeseries, refactored as a profile of TimeseriesML; for submission to OGC TC, December 2015. 6. [~Dec 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate revised WaterML 2.0 Part 1 - Timeseries. | TBD | 1. [Sep 2014] TimeseriesML SWG Charter; for submission to OGC TC, 15-19 September 2014, Calgary CA. 2. [~Jun 2015] TimeseriesML 1.0 standard, including both Application Schema and GML encoding; for submission to OGC TC, June 2015. 3. [~Jun 2015] WaterML SWG Charter amendment; for submission to OGC TC, June 2015. 4. [~Sep 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate TimeseriesML 1.0. 5. [~Dec 2015] Revision of WaterML 2.0 Part 1 – Timeseries, refactored as a profile of TimeseriesML; for submission to OGC TC, December 2015. 6. [~Dec 2015] Draft amendments to WMO No. 306 Vol I.3, Manual on Codes, to incorporate revised WaterML 2.0 Part 1 - Timeseries. | CHy (specific expert team to be identified) | [13 empty] | 1
|  | Represent WIGOS metadata | Model drived representations of WIGOS metadata | XML and TDCF representations of WIGOS metadata with supporting documentation and tools | Plan to be developed by a sub-team of members of IPET-MDRD and TT-WMD | Bannerman | NEW Plan to be developed by a sub-team of members of IPET-MDRD and TT-WMD | TT-WMD | [15 empty] | 1
| 3 | Registration of WMO Application Schemas with ISO/TC 211; as profiles of ISO 19156:2011 O&M | ISO list WMO representations as conformant | ISO listing of WMO representations | As standards approved, discuss with ISO how they can be recorded by ISO TC 211 | tandy | NEW As standards approved, discuss with ISO how they can be recorded by ISO TC 211 | CHy (specific expert team to be identified) | [13 empty] | 1
O{ET-MDRD | 1 | Establish mappings from WMO codes to CF-Standard names under shared governance with CF community | Able to use WMO and NetCDF datasets together | Mappings to allow different names used by WMO and NetCDF data representations to be reconciled | TBD | tandy | NEW | (blank) | [13 empty] | 1
OPAG-ISS | 1 | xxx | xxx | xxx | xxx | xxx | xxx | (blank) |  | 2