| World Meteorological Organization | Cg-17/Doc. 10.1(2) |  |
| --- | --- | --- |
| WORLD METEOROLOGICAL CONGRESS | Submitted by: | Secretary-General |
|  | Date: | 3.III.2015 |
| SEVENTEENTH SESSION Geneva, 25 May to 12 June 2015 | Original Language: | English |
|  | Status: | DRAFT 1 |

AGENDA ITEM 10: WMO STRATEGIC PLAN AND BUDGET

WMO OPERATING PLAN 2016-2019

SUMMARY

DECISIONS/ACTIONS REQUIRED:

Congress is invited to approve the attached draft text for inclusion in the general summary of Cg-17, and to note and use the draft WMO Operating Plan 2016-2019 in the discussions of the Secretary-General’s budget proposal for the seventeenth financial period.

CONTENT OF DOCUMENT:

The Table of Contents is available only electronically as a Document Map*.

APPENDIX A:  
DRAFT TEXT FOR INCLUSION IN THE GENERAL SUMMARY

10.	WMO STRATEGIC PLAN AND BUDGET (AGENDA ITEM 10)

………

WMO Operating Plan 2016-2019

10.2(2).1	Congress noted the draft WMO-wide Operating Plan (2016–2019) as a component of the WMO’s Result-based Management (RBM) framework. Congress noted that the draft WMO Operating Plan (2016–2019) provided details on expected results, key outcomes, deliverables and time-bound activities, which have been used to guide resource estimates and allocations in the Secretary-General’s budget proposal for the seventeenth financial period. Congress appreciated the contributions of the technical commissions and regional associations to the development of the WMO Operating Plan 2016–2019.

10.2(2).2	Congress requested the Secretary-General to finalize the WMO Operating Plan taking into account all the decisions of the Seventeenth Congress and to make the final version of the Plan available on-line for use by all management groups, the Executive Council and the Secretariat.

# APPENDIX B:
FOR INFORMATION -
NOT TO BE INCLUDED IN THE GENERAL SUMMARY

# DRAFT

# WMO OPERATING PLAN 2016-2019

# table of contents

EXECUTIVE SUMMARY						4

INTRODUCTION						5

PROGRAMME ACTIVITIES PLANNED AND FUNDED FOR IMPLEMENTATION
IN 2016-2019							19

TECHNICAL COMMISSIONS OPERATING PLANS			44

III.1	COMMISSION FOR INSTRUMENTS AND
METHODS OF OBSERVATION (CIMO) OPERATING PLAN 2016-2019	44

III.2	COMMISSION FOR HYDROLOGY (CHy) OPERATING PLAN 2016-2019	45

III.3	COMMISSION FOR ATMOSPHERIC SCIENCES (CAS)
OPERATING PLAN 2016-2019					51

REGIONAL ASSOCIATIONS OPERATING PLANS			53

IV.1	REGIONAL ASSOCIATION II (ASIA)				53

ANNEX: PROGRAMMATIC FOCUS TO ACHIEVE EXPECTED RESULTS		63

List of Acronyms and Abbreviations					73

EXECUTIVE SUMMARY

The WMO Operating Plan (OP) for the period 2016-2019 is developed using a results-based approach in planning programme activities and projects to achieve Expected Results in line with decisions of the Congress and Executive Council. It is based on the draft WMO Strategic Plan for the period 2016-2019 and lists time-bound programme activities and projects planned for implementation by the technical commissions (TCs), regional associations (RAs) and the Secretariat to achieve the vision and mission of the Organization. It forms the basis for the WMO budget for the seventeenth financial period, and the WMO Monitoring and Evaluation System (M&E).

The OP is organized by Expected Results and focuses on priorities defined in the draft Strategic Plan. It comprises the planned programme activities and projects to achieve Expected Results. It also presents timelines, allocated resources, Key Performance Indicators and other details on each activity.  Areas of focus in the planning of programme activities and projects are presented in the Annex.

The OP is a living document that will be updated regularly to include any adjustments as required.

## INTRODUCTION

Purpose of the WMO Operating Plan and linkage to the Strategic Plan and Results-based Budget

An operating plan represents an action stage in the strategic planning and implementation process. The WMO Operating Plan (OP) is one of the components of the WMO strategic planning process and Results-based Management Framework (RBM) (Figure 1) and guides the implementation of programme activities aimed at achieving the Expected Results (Table 1) to realize the mission of the Organization as presented in the WMO Strategic Plan (SP) for the period 2016-2019. The OP presents time-bound programme activities and projects to be implemented to achieve Expected Results and the associated Key Outcomes and deliverables. The Operating Plan provides the foundation for WMO Results-based Budget (RBB), which identifies regular resources to implement programme activities and projects in the OP, as well as voluntary resources for project initiatives that contribute to the achievement of the Expected Results.

The OP is also an essential element in the implementation of the WMO Monitoring and Evaluation (M&E) System, which is the other component of the WMO strategic planning process and RBM.

GSN

Priorities

ERn1

KOn12

KOn11

KOn13

Del

Del

Del

Act

Act

Act

Act

Budget

Budget

Budget

OP

RBB

Budget

M&E

SP

Figure 1: 	Schematic representation of WMO Strategic Planning process and Results-based Management Frameworks showing linkage in the components (SP, OP, RBB and M&E).

Table 1: Schematic representation of the structure and scope of the WMO Strategic Plan

| Global Societal Needs |  | Priorities |  |  | Expected Results |
| --- | --- | --- | --- | --- | --- |
| Improved protection of life and property |  | Disaster Risk Reduction Global Framework for Climate Services WMO Integrated Global Observing System Aviation meteorological services Polar and high mountain regions monitoring, prediction and services Capacity development WMO governance |  | 1 | Improved service quality and service delivery Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warnings and services in response to users’ needs and to enable their use in decision-making by relevant societal sectors |
|  |  |  |  | 2 | Reduced Disaster Risk Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements |
| End poverty, ensure sustainable resilient livelihoods, food security, sustainable access to water and energy, healthy lives, gender equality and economic growth, and combat climate change |  |  |  | 3 | Improved Data Processing, Modelling and Forecasting Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support, in particular, reduced disaster risk and climate impact and adaptation strategies |
|  |  |  |  | 4 | Improved Observations and Data Exchange Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO |
|  |  |  |  | 5 | Advance Targeted Research Enhanced capabilities of Members to contribute to and draw benefits from the global research capacity for weather, climate, water and the related environmental science and technology development |
| Sustainable use of natural resources and improved environmental quality |  |  |  | 6 | Strengthened Capacity Development Enhanced capabilities of Members’ NMHSs, in particular, in developing and least developed countries and Small Island Developing States, to fulfil their mandates |
|  |  |  |  | 7 | Strengthened Partnerships New and strengthened partnerships and cooperation activities to improve NMHSs’ performance in delivering services and to demonstrate the value of WMO contributions within the United Nations system, relevant regional organizations, international conventions and national strategies |
|  |  |  |  | 8 | Improved Efficiency and Effectiveness Promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources |

Specific elements of the OP are:

- Expected Results and the associated Key Outcomes and Key Performance Indicators to measure the progress in the achievement of Expected Results (Table 2); and

- The programme activities planned for implementation and the associated deliverables and costs.

The SP and OP provide the foundation for effective use of resources. These are the products of a WMO integrated planning process in which the Secretariat, working with Members, regional associations and technical commissions, identifies very specific activities and initiatives that need to be implemented to achieve Expected Results and the resources required to meet them. The end state is a four-year Results-based Budget, which is linked to the WMO Strategic Plan. The planning process ensures the linkage among the components of the strategic planning process and RBM, namely the SP, OP, RBB and M&E (Figure 1) to enable efficient and effective implementation of the Strategic Plan to achieve the ERs. The risks that may influence the achievement of ERs and actions to mitigate them are presented in Table 3.

Table 2: Expected Results, Key Outcomes and Key Performance Indicators

| Expected Result 1: (Improved service quality and service delivery) - Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warnings and services in response to users' needs, and to enable their use in decision-making by relevant societal sectors |  |  |  |
| --- | --- | --- | --- |
| KO 1.1 | Improved access to seamless weather, climate, water, and related environmental products and services (e.g. warnings, forecasts and supporting information) | KPI 1.1.1 | Number of Members demonstrating quantitative measurements of the socio-economic benefits of their products and services (too general; how we measure improvement?) |
|  |  | KPI 1.1.2 | Percentage of NMHSs with regular access to products provided by global and regional centres |
| KO 1.2 | Delivery of weather, climate, water and related environmental products and services to users' communities is improved | KPI 1.2.1 | Number of NMHSs expressing user satisfaction with the (a) availability, (b) reliability and (c) range of products that are (d) received in time and (e) are an essential contribution to decision making |

| Expected Result 2: (Reduced Disaster Risk) - Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements |  |  |  |
| --- | --- | --- | --- |
| KO 2.1 | Multi-hazard early warning systems are implemented | KPI 2.1.1 | Number of NMHSs contributing to the implementation of multi-hazard early warning systems |
| KO 2.2 | National integrated flood management plans are developed | KPI 2.2.1 | Number of Members establishing flood management plans (not all met services responsible for hydrology; but within WMO mandate and PR responsibilities) |
|  |  | KPI 2.2.2 | Number of NMHSs participating in regional hydrological forecasting systems for transboundary river basins |
| KO 2.3 | Drought early warning systems are improved | KPI 2.3.1 | NMHSs and Regional Centres that issue drought early warnings |

| Expected Result 3: (Improved Data Processing, Modelling and Forecasting) - Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support ,in particular, reduced disaster risk and climate impact and adaptation strategies |  |  |  |
| --- | --- | --- | --- |
| KO 3.1 | Improved climate monitoring, long range forecasts and long-term projections | KPI 3.1.1 | Number of Members issuing: (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
|  |  | KPI 3.1.2 | Perceived quality of the issued: (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
|  |  | KPI 3.1.3 | Perceived timeliness of the issued: (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
| KO 3.2 | Climate information and prediction products for climate adaptation and risk management are improved | KPI 3.2.1 | Perceived quality of the products of WMO Regional Climate Centres used at the national level |
|  |  | KPI 3.2.2 | Number of Members operationally developing and disseminating climate products and information for national needs at basic, intermediate and advanced levels |
|  |  | KPI 3.2.3 | Perceived quality of the national climate information and products available in Member countries |
|  |  | KPI 3.2.4 | Number of Members providing targeted/ tailored climate information, products and services, through formal mechanisms including National Climate Outlook Forums, to support user requirements in their countries for adaptation and climate risk management in key socio-economic sectors |
| KO 3.3 | Hydrological information and products, including water resources, are improved | KPI 3.3.1 | Number of Members using a Quality Management Framework for Hydrology based on current guidance materials |
|  |  | KPI 3.3.2 | Number of regional hydrological databases developed in transboundary river basins |
| KO 3.4 | Drought information and prediction for risk management is improved | KPI 3.4.1 | NMHSs and Regional Centres issuing drought information and prediction |

| Expected Result 4: (Improved Observations and Data Exchange) - Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO |  |  |  |
| --- | --- | --- | --- |
| KO 4.1 | WMO Integrated Global Observing System implementation phase is completed | KPI 4.1.1 | Percentage of progress in achieving the key implementation tasks, milestones and deliverables specified by the WIGOS Implementation Plan (WIP) |
|  |  | KPI 4.1.2 | Increased availability of observations for users (as measured by several ratios) |
|  |  | KPE 4.1.3 | Number of partner organizations involved in WIGOS implementation |
| KO 4.2 | WMO information System is developed and implemented | KPI 4.2.1 | Progress in the implementation of WIS by NMHSs as measured by: (a) percentage of registered WIS centres that have been endorsed as WIS compliant; and (b) Number of NMHSs with improved observational data and products as a result of implementation of WIS functions |
|  |  | KPI 4.2.2 | Number of NMHSs whose data processing and management capabilities have enhanced as a result of implementation of WIS functions |
| KO 4.3 | Progress in implementing the Global Climate Observing System | KPI 4.3.1 | Percentage of progress in achieving the GCOS implementation plan |
| KO 4.4 | Data rescue and data management systems improved | KPI 4.4.1 | Number of NMHSs undertaking data rescue or being involved in regional collaborative data rescue initiatives such as MEDARE |
|  |  | KPI 4.4.2 | Number of Members implementing modern climate data management systems and/or climate monitoring systems |

| Expected Result 5: (Advance Targeted Research) - Enhanced capabilities of Members to contribute to and draw benefits from the global research capability for weather, climate, water and the related environmental science and technology development |  |  |  |
| --- | --- | --- | --- |
| KO 5.1 | Research in climate prediction/projection to improve the skills of seasonal, decadal and longer timescales is enhanced | KPI 5.1.1 | Number of new activities advancing climate research capacity at the global and regional level, especially for early career scientists and scientists from developing and LDC countries |
|  |  | KPI 5.1.2 | Number of early career scientists and scientists from developing and least developed countries that WCRP funded to participate in activities to advance climate research |
|  |  | KPI 5.1.3 | Degree of satisfaction among NMHSs with the skill of climate predictions |
| KO 5.2 | Research in the prediction of high-impact weather on time scales of hours to seasons is enhanced | KPI 5.2.1 | Number of total research projects (new, ongoing and completed) on operational products and services |
|  |  | KPI 5.2.2 | Number of Members whose operational products and services have improved as a result of WMO research projects |
|  |  | KPI 5.2.3 | Number of NMHSs in developing and least developed countries participating in regional and international research initiatives on high impact weather or severe weather forecasting demonstration projects |
| KO 5.3 | Atmospheric chemistry observations and assessment meet needs of environmental conventions and policy assessments | KPI 5.3.1 | Degree of Member satisfaction with the: (a) usefulness; and (b) timeliness of Global Atmospheric Chemistry Bulletins |
|  |  | KPI 5.3.2 | Degree of Member satisfaction with the usefulness of: (a) GAW measurement guidelines and reports; (b) Sand-and-Dust storm forecasting; and (c) the chemical weather activities of GURME |
| KO 5.4 | Seamless forecasts of weather, climate, water and the environment from days to seasons are developed in support of the GFCS | KPI 5.4.1 | Number of NMHSs participating in the integration of observations, research, modelling and analysis results to improve sub-seasonal to seasonal weather/climate projections and predictions |

| Expected Result 6: (Strengthened Capacity Development) - Enhanced capabilities of Members’ NMHSs, in particular, in developing and least developed countries and Small Island Developing States, to fulfil their mandates. |  |  |  |
| --- | --- | --- | --- |
| KO 6.1 | Visibility and relevance of NMHSs in national and regional development agendas is improved, particularly in developing and least developed countries | KPI 6.1.1 | Number of NMHSs with: (a) increased contribution to national policy setting; (b) improved awareness by users on types of services NMHSs can deliver; (c) improved user accessibility to forecasts and warnings; (d) improved timeliness of forecasts and warnings; and (e) increased accuracy of forecasts and warnings |
|  |  | KPI 6.1.2 | Number of NMHSs with: (a) increased contribution to regional policy setting; (b) improved awareness by regional users on types of services that can be provided by the centre; (c) improved regional user accessibility to forecasts and warnings; (d) improved timeliness of forecasts and warnings delivered from the Regional Centre; and (e) increased accuracy of forecasts and warnings delivered from the Regional Centre |
| KO 6.2 | Infrastructure and operational facilities of NMHSs and Regional Centres are improved, particularly in developing and least developed countries | KPI 6.2.1 | Number of NMHSs with improved infrastructure and operational facilities |
| KO 6.3 | Education and training development facilities at national and regional levels are improved, especially in developing and least developed countries | KPI 6.3.1 | Number of institutions providing education and training support for GFCS-related activities |
|  |  | KPI 6.3.2 | Degree to which Members are getting value for money from the WMO Fellowship Programme |
|  |  | KPI 6.3.3 | Degree of Member satisfaction with the Regional Training Centres (RTCs) in use |
| KO 6.4 | Capacities of NMHSs are enhanced through cooperation and partnerships with other national and regional organizations | KPI 6.4.1 | Development projects and activities funded through voluntary contributions |

| Expected Result 7: (Strengthened Partnerships) - New and strengthened partnerships and cooperation activities to improve NMHSs' performance in delivering services and to demonstrate the value of WMO contributions within the United Nations system, relevant regional organizations, international conventions and national strategies. |  |  |  |
| --- | --- | --- | --- |
| KO 7.1 | \WMO leadership and contribution in relevant UN system and other international partners' initiatives and programmes is improved | KPI 7.1.1 | Number of reports of WMO and its co-sponsored programmes submitted to UN and other international conventions, particularly the UNFCCC, UNCCD and UNCBD |
|  |  | KPI 7.1.2 | Number of contracts/cooperation agreements within which WMO is engaged with partners |
|  |  | KPI 7.1.3 | Number of NMHSs implementing projects with the UN and other international and/or regional organizations |
| KO 7.2 | Public, decision-makers and other stakeholders are increasingly aware of key WMO and NMHSs issues, activities and priorities through enhanced communication | KPI 7.2.1 | Uptake of WMO public information outputs as measured by: (a) number of unique visitors on the WMO website; (b) number of times WMO was mentioned in press articles; (c) number of Facebook fans; and (d) number of Twitter followers |
|  |  | KPI 7.2.2 | Degree to which NMHSs make use of WMO public information outputs |
|  |  | KPI 7.2.3 | Number of NMHSs that have provided training to senior managers and/or communication officers in media relations, social media or other aspects of communication |

| Expected Result 8: (Improved Efficiency and Effectiveness): Promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources. |  |  |  |
| --- | --- | --- | --- |
| KO 8.1 | Effective and efficient WMO Congress and EC | KPI 8.1.1 | Degree of Member satisfaction with documentation for Cg, EC and its working groups |
|  |  | KPI 8.1.2 | Degree of Member satisfaction with supporting services for Cg and EC (interpretation, conference activities and facilities) |
|  |  | KPI 8.1.3 | Decrease in the total cost of sessions held under similar conditions |
| KO 8.2 | An effective and efficient Organization | KPI 8.2.1 | Percentage of implemented accepted oversight recommendations for improved business effectiveness on the agreed deadline |
|  |  | KPI 8.2.2 | Unqualified opinion of the external auditor in the financial period |
|  |  | KPI 8.2.3 | Increase in the efficiency of fulfilling requirements for linguistic and publishing services |
|  |  | KPI 8.2.4 | Issuance of statements of internal control in the financial period |
| KO 8.3 | Effective and efficient constituent bodies (RAs and TCs) | KPI 8.3.1 | Degree of Member satisfaction with constituent body documentation |
|  |  | KPI 8.3.2 | Degree of Member satisfaction with constituent body supporting services (interpretation, conference services and facilities) |
|  |  | KPI 8.3.3 | Decrease in the total cost of constituent body sessions held under similar conditions |
| 8.4 | Gender equality across WMO | KPI 8.4.1 | Proportion of men/women in WMO constituent bodies |
|  |  | KPI 8.4.2 | Number of men/women granted WMO fellowship/number of total candidates |

Table 3: Risks that may influence the achievement of expected results and actions to mitigate them.

| Expected Results | Risk |  |  |  | Mitigation |
| --- | --- | --- | --- | --- | --- |
| ER 1: (Improved service quality and service delivery): Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warnings and services in response to users’ needs and to enable their use in decision-making by relevant societal sectors ER 2: (Reduced Disaster Risk) Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements | Lack of improvement in the availability of surface or space-based observations, production and dissemination systems essential for the provision of services. Members non-compliance with WMO and ICAO QMS and competencies standards, particularly those related to quality management, would compromise the quality of services and the role of NMHSs reducing the credibility of WMO and its Member’s NMHSs resulting to inability of NMHSs to service civil aviation, compete with other service providers and raise revenue from cost recovery. |  |  |  | WHYCOS initiative and HYCOS components. Linkage with GCOS. Continuous dialogue with those working in the space-based observation systems from a climate and hydrology perspective. QMF approach to service development and delivery through CCl, CAgM and CHy. Contribution to GFCS. Actions identified in the Operating Plan; Requirements reflected in deliverables and expected outcomes; Monitoring and coordination. Promote culture of compliance. Identify and fix deficiencies. Proactively develop standards and recommended practices for the delivery of other services. Develop adequate implementation guidance. Promote bilateral cooperation through “twinning” or “coaching”. Promote the sharing of experiences among NMHSs. Focused training on service delivery. Establish SD pilot projects. |
|  | The ICAO Aviation System Block Upgrades (ASBU) for Air Traffic Management (ATM) will lead to significant mid-to-long-term changes and impacts in the mode of aeronautical meteorological service delivery to a time horizon of 2028 and beyond and pose strong requirements to Members to adapt to the new models of service provision and compliance with new regulations and institutional arrangements resulting in stronger competition between service providers (including private entities) with potential impact on the role of NMHSs in serving international air navigation and negative effects on their overall mandate and the possibility to recover the cost for the aviation meteorological services. The weakness in succession planning, an aging workforce, loss of skilled personnel due to natural attrition coupled with inadequate resources to enhance human capacities and infrastructure of the NMHS. |  |  |  | Close collaboration with ICAO to contribute to development of new systems, services and regulatory frameworks. Participate in the development of adequate cost-recovery mechanisms for multi-national service provision models. Undertake systematic measures to ensure competitiveness of the NMHSs as aviation service providers. Facilitate fast uptake of science and technology achievements into operational practice in order to respond to the user demands. Establishment of RCCs, RCOFs and RTCc (Climate). CCl and CAgM training initiatives. Establishment of COMET – Hydrology courses on-line. Assistance to RTCs (Hydrology) in training courses. Training strategy for HWR. Training components of extrabudgetary funded projects. Implementing an integrated approach, including modernization, operational development, on-the-job training, etc. crossing all levels (international, regional and national), all disciplines (weather, climate, water, and environment related), and all major communities (the General Public, Transportation, Health, Agriculture & Food Security, DRR, Energy, Urban Sustainability etc.). |
| ER 3: (Improved Data Processing, Modelling and Forecasting) Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support, in particular, reduced disaster risk and climate impact and adaptation strategies ER 4: (Improved Observations and Data Exchange: Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO ER 5: (Advance Targeted Research) Enhanced capabilities of Members to contribute to and draw benefits from the global research capability for weather, climate, water and related environmental science and technology development | Inadequate resources to modernize optimize and sustain global observing systems, the underlying data processing, data management and high performance computing capacity. |  |  |  | Align the global research effort to the major needs of Members Demonstrate the benefits of the investments in the global research effort and observation networks aimed towards integrated, enhance and new services. Training to develop human resources capable of improving methods and efficiency of observing, processing and computing. WIGOS is creating a framework that will enable Members to gain synergies with other organizations to improve observing systems and their coverage at national, regional and global levels. WIS is enabling better access to and sharing of data and products across all programmes. |
| ER 6: (Strengthened Capacity Development) Enhanced capabilities of Members’ NMHSs, in particular, in developing and least developed countries and Small Island Developing States, to fulfil their mandates |  | Inadequate budgetary provisions to NMHS to implement and build capacity to operate essential infrastructure and provide services. |  |  | WMO assistance as identified in the WMO Capacity Development Strategy. QMF approach and guidance on management of climate and hydrological services. HYCOS Components. Contribution to GFCS. Building a targeted partnership (including cascading process) between advanced and least developed through effective integrated efforts provided by WMO Programmes, projects, and activities for CD. |
|  |  | The capacity of the WMO and its Members’ NMHSs to mobilize and effectively utilize resources from funding agencies to invest in weather, water and climate infrastructure and human resources. |  |  | WMO assistance as identified in the WMO Capacity Development Strategy especially in resource mobilization. Working closely with donors and delivering on funded projects. Preparation of project proposals with Member country input. Both WIGOS and WIS are providing clearly defined competencies and learning guides that will allow Members to ensure their staff have the required skills and to assist WMO training activities to ensure they are developing the necessary competencies in staff. WIGOS framework and WIS also address the budgetary and resource mobilization issues including providing clear standards and practices that can be used in specifying capacity building projects. Assist NMHSs to develop business plans consistent with WMO technical regulations and national requirements. |
| ER 7: (Strengthened Partnerships) New and strengthened partnerships and cooperation activities to improve NMHSs’ performance in delivering services and to demonstrate the value of WMO contributions within the United Nations system, relevant regional organizations, international conventions and national strategies |  |  | By missing opportunities to engage partners actively, there will be limitations in establishing institutional linkages needed for the implementation of DRR, GFCS, WIGOS and Research activities, together with sourcing additional funding to support shared initiatives and ability to engage users to develop and use user-oriented services. |  | Identifying the key partnerships to enter into. Attending selected research/ academic community meetings. Keeping contact with relevant TC members and Management Group members to identify new advances. Contribution to GFCS. Active systematic monitoring of existing and future agreements. Full implementation of the Communication strategy. Make maximal use of opportunities. Leverage available funding. Under each priority areas should be developed to monitor the performance in the effort of partnership for each TCs, RAs, and the Secretariat. |
| ER 8: (Improved Efficiency and Effectiveness) Promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources |  |  |  | Weaknesses in system of internal control that may compromise the reputation of the Organization. | Regular reviews of the system of internal control, including where necessary participation of external parties. |
|  |  |  |  | Interrupting operations at Secretariat and field offices. | Actions identified in the Business Continuity Plan. |
|  |  |  |  | Resources to sustain multilingual conference and publishing services. | Actions listed in the Risk Register and introduction in LCP of efficiency oriented new practices; updated Standing Instructions (Ch. 2, 3); respect schedule of constituent sessions as approved by Congress. |

## II.	PROGRAMME ACTIVITIES PLANNED AND FUNDED FOR IMPLEMENTATION IN 2016-2019

(in Swiss Francs)

| ER 2015 | Key Outcome 2015 | Major Programme | Constituent Body | Activity | 2016-2019 |
| --- | --- | --- | --- | --- | --- |
| 1 | 1.1 | AgMP | CAgM | Activities of CAgM ETs, TTs on Services | 159,000 |
| 1 | 1.1 | AgMP | CAgM | Activities of CAgM ETs, TTs on Science and Technology | 159,000 |
| 1 | 1.1 | AgMP | CAgM | CAgM session | 332,000 |
| 1 | 1.1 | AgMP | CAgM | Support to CAgM Technical Conference preceding CAgM-17 | 140,000 |
| 1 | 1.1 | AgMP | CAgM | Support to the president of CAgM | 40,000 |
| 1 | 1.1 | AgMP | CAgM | Support to regional association activities related to agrometeorology | 88,000 |
| 1 | 1.1 | AgMP | CAgM | Operating expenses for Agricultural Meteorology Programme | 20,000 |
| 1 |  | AgMP | CAgM | Publications and Reports of Agricultural Meteorology Division | 150,000 |
| 1 |  | AgMP | CAgM | Review and updates of Guide to Agricultural Meteorological Practices (WMO-No. 134) | 20,000 |
| 1 |  | AgMP | CAgM | Two Meetings of CAgM-Implementation Coordination Team (ICT) | 100,000 |
| 1 | 1.1 | AgMP | CAgM | Activities of CAgM ETs, TTs on Disasters, Climate Change and Agriculture | 159,000 |
| 1 | 1.1 | AgMP | CAgM | Activities of CAgM ETs, TTs on Capacity Development | 159,000 |
| 2 | 2.2 | HWRP | CHy | Development/Implementation of National Pilot Projects under WMO Flood Forecasting Initiative | 400,000 |
| 2 | 2.2 | HWRP | CHy | Implementation of the Strategy and Action plan of WMO's Flood Forecasting Initiative | 60,000 |
| 2 | 2.2 | HWRP | CHy | Helpdesk services and technology transfer in flood management (JPO) | 100,000 |
| 2 | 2.2 | HWRP | CHy | Guidance on and monitoring of the FFI through International Advisory Group (FFI-AG) | 80,000 |
| 2 |  | HWRP | CHy | CHy activities in hydrological forecasting | 45,000 |
| 3 | 3.2 | AgMP | CAgM | Meetings of CAgM-Management Group | 165,000 |
| 3 |  | WCSP/HWRP | N | CLW participation in regional association meetings | 36,000 |
| 3 | 3.3 | HWRP | CHy | Application of climate information for water managers | 50,000 |
| 3 | 3.3 | HWRP | CHy | Operating expenses of the Hydrology and Water Resources Branch (HWR) | 2,000 |
| 3 | 3.3 | HWRP | CHy | Operating expenses of the Hydrology and Water Resources Branch (HWR) | 146,000 |
| 3 | 3.3 | HWRP | CHy | Development of Technical Regulations and other Manuals as per the recommendation of CHy | 160,000 |
| 3 | 3.3 | HWRP | CHy | Evaluation of performance of hydrological instruments and techniques | 56,000 |
| 3 | 3.3 | HWRP | CHy | CHy activities – general | 60,000 |
| 3 |  | HWRP | CHy | CHy activities in QMF-H | 100,000 |
| 3 |  | HWRP | CHy | CHy activities in data Op&mgmt. | 50,000 |
| 3 |  | HWRP | CHy | CHy activities in WRA | 50,000 |
| 3 |  | HWRP | CHy | CHy activities in water, climate and risk mgmt. | 50,000 |
| 3 | 3.3 | HWRP | CHy | Development of new and support to the existing WHYCOS components | 120,000 |
| 3 | 3.3 | HWRP | CHy | Promote and support coordination among various WHYCOS components | 32,000 |
| 3 | 3.3 | HWRP | CHy | Guidance on and monitoring of the WHYCOS through International Advisory Group (WIAG) | 74,000 |
| 3 | 3.3 | HWRP | CHy | Publication of Manuals according to the QMF-Hydrology, including e-publication | 296,000 |
| 3 | 3.3 | HWRP | CHy | Meetings of the Advisory Working Group (AWG) (2013, 2014, 2015) | 148,000 |
| 3 | 3.3 | HWRP | CHy | Updating of HWR and CHy websites and support to INFOHYDRO | 40,000 |
| 3 | 3.3 | HWRP | CHy | Support to Regional Associations activities in HWR | 100,000 |
| 3 | 3.3 | HWRP | CHy | Support hydrological data exchange and data management activities including data rescue | 36,000 |
| 3 | 3.3 | HWRP | CHy | Support to global initiatives in HWR | 40,000 |
| 3 | 3.3 | HWRP | CHy | Support to president of CHy | 60,000 |
| 3 |  | HWRP | CHy | Participation in and support of Regional Working Groups in Hydrology | 156,000 |
| 3 | 3.3 | HWRP | CHy | Commission for Hydrology session (CHy) | 250,000 |
| 3 | 3.2 | WCSP | CCl | Development of guidance and best practices on use of global/regional climate products | 201,000 |
| 3 | 3.2 | WCSP | CCl | Development of Climate Services Toolkit | 165,000 |
| 3 | 3.2 | WCSP | CCl | CCl-CBS activities in support of Climate Services Information System | 146,000 |
| 3 | 3.2 | WCSP | CCl | Development of tools and guidance for user-targeted climate products and indices | 97,150 |
| 3 | 3.2 | WCSP | CCl | Commission for Climatology CCl-16 | 332,000 |
| 3 | 3.2 | WCSP | CCl | Commission for Climatology (CCl) activities | 301,000 |
| 3 | 3.2 | WCSP | CCl | Meetings of EC Working Group on Climate and Related Weather, Water and Environmental Matters | 128,700 |
| 3 | 3.2 | WCSP | CCl | Operating expenses of the Climate Prediction and Adaptation Branch (CLPA) | 100,000 |
| 3 | 3.2 | WCSP | CCl | Development of Global Seasonal Climate Update (GSCU) (consensus-based) | 90,000 |
| 3 |  | WCSP | CCl | Publications and Reports of Climate Coordination Activities Division | 20,000 |
| 3 |  | WCSP | CCl | Review and updates of Guide to Climatological Practices (WMO-No. 100) | 20,000 |
| 3 | 3.2 | WCSP | CCl | Support for user aspects of climate services through regional workshops and national and Regional Climate Outlook Forums | 130,000 |
| 3 | 3.2 | WCSP | CCl | Publications and Reports of World Climate Applications and Services Division | 80,000 |
| 3 | 3.2 | WCSP | CCl | Standardization of Regional Climate Center (RCC) product presentation and dissemination | 120,000 |
| 3 | 3.2 | WCSP | CCl | Support to Regional Climate Outlook Fora (RCOF) and national climate For a | 320,000 |
| 3 | 3.2 | WCSP | CCl | Support to president of CCl | 100,000 |
| 3 | 3.2 | WCSP | CCl | Support to joint CCl-WCRP activities on regional climate predictions and projections | 75,000 |
| 3 | 3.2 | WCSP | CCl | Meetings of CCl-Management Group | 165,000 |
| 3 | 3.2 | WCSP | CCl | Support to CCl Technical Conference preceding CCl | 140,000 |
| 3 | 3.2 | WCSP | CCl | Meetings of CCl Implementation Coordination Team on CSIS | 165,000 |
| 3 | 3.2 | WCSP | CCl | Support to regional association activities related to climate applications and services | 110,000 |
| 3 | 3.2 | WCSP | CCl | Regional Workshops on Climate Services for User Sectors | 110,000 |
| 3 |  | WCSP | CCl | Climate coordination activities including WCP partnerships | 80,000 |
| 6 | 6.2 | AgMP | CAgM | Roving Seminars for Farmers | 60,000 |
| 6 | 6.2 | AgMP | CAgM | Training Workshops on Agrometeorological Services | 30,000 |
| 6 | 6.2 | AgMP | CAgM | Assistance for WMO Regional Training Centers in Agrometeorology | 20,000 |
| 6 | 6.2 | HWRP | CHy | Regional/National Seminars/Workshop on Manuals of the QMF-Hydrology including development of promotional material | 180,000 |
| 6 | 6.2 | HWRP | CHy | Development of Training Proposals according to the WMO Strategy for Education and Training (E&T) in HWR | 50,000 |
| 6 | 6.2 | HWRP | CHy | Training Activities according to WMO Strategy for Education and Training (E&T) in HWR | 350,000 |
| 6 | 6.2 | HWRP | CHy | Support to Participants for Working Seminars, Technical Conferences, Courses in HWR | 32,000 |
| 6 | 6.2 | HWRP | CHy | Assistance for WMO Regional Training Centers in HWR | 40,000 |
| 6 |  | HWRP | CHy | Technical assistance in HWR | 80,000 |
| 6 | 6.2 | WCSP | CCl | Workshop on Operational Climate Prediction | 100,000 |
| 6 | 6.2 | WCSP | CCl | Development of climate curriculum modules for use in RTCs and national training programmes | 70,000 |
| 6 | 6.2 | WCSP | CCl | Training Activities on CSIS product generation | 278,100 |
| 6 | 6.3 | ETRP | EC Panel on ET | Distance Learning Courses according to Education and Training (E&T) strategy for Hydrology and Water Resources Programme | 60,000 |
| 6 | 6.2 | ETRP | EC Panel on ET | Roving seminars on weather, climate and farmers | 40,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Support to blended learning courses according to the Education and Training (E&T) Strategy for HWR | 53,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Agrometeorology | 80,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on climate forecasting and verification | 80,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on application and production of climate forecast products | 100,000 |
| 7 |  | AgMP | N | Support for AGM participation in UN agency activities | 20,000 |
| 7 | 7.1 | AgMP | CAgM | Participation in and contribution to meetings of the United Nations Convention to Combat Desertification (UNCCD) and Convention on Biodiversity (CBD) | 80,000 |
| 7 | 7.3 | WCSP/HWRP | N | COS Charges CLW | 620,000 |
| 7 | 7.1 | HWRP | CHy | Support to UN-Water activities | 32,000 |
| 7 | 7.1 | HWRP | CHy | Participation in Hydrology and Water Resources (HWR) meetings of UN bodies | 24,000 |
| 7 | 7.1 | HWRP | CHy | WMO/UNESCO Liaison Committee for Hydrology | 16,000 |
| 7 | 7.1 | HWRP | CHy | Co-sponsoring of activities in Hydrology and Water Resources (HWR) organized by NGOs and IGOs | 80,000 |
| 7 | 7.1 | WCSP | CCl | Development of Guidance Documents and Manuals for CSIS operations | 75,000 |
| 7 | 7.1 | WCSP | CCl | Participation in meetings of climate-related matters organized by other UN bodies and international agencies | 100,000 |
| 7 | 7.1 | WCSP | CCl | Participation in and contribution to UNFCCC meetings and conferences | 200,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the Regional Activities Coordination Office | 43,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Advisory services for manpower development of NMHSs | 40,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Coordination of ETR matters with UN and other international organizations | 28,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Coordination of Fellowships with UN and other international organizations | 28,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Education and Training (E&T) Symposium | 170,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Implementation of Fellowships for Refugees | 200,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Implementation of Long-term Fellowships | 2,000,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Implementation of Short-term Fellowships | 1,400,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Meeting of the EC Panel of Experts on Education and Training (E&T) | 334,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Operating Expenses of the Education and Training Office | 122,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Preparation and distribution of training publications to Members and Regional Training Centers (RTCs) | 260,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Production and exchange of training materials | 120,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Promoting and supporting distance and e-learning | 120,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Promoting school and Popular Education | 20,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Provision to training institutes of advisory and training services | 160,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Regional Training Seminars for National Trainers | 320,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Regional Training Seminars on capacity development | 53,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Support for ad hoc requests from LDCs to attend training events | 60,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Survey on/Determination of Member's training needs | 30,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Seminar on Curriculum Development to support high priority areas | 53,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Seminar on Human Resources Development Planning | 106,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Coordination meeting with RTCs and training institutes | 100,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Support to WMO Virtual Laboratory | 80,000 |
| 6 | 6.2 | LDC | N | Operating expenses of the LDC Programme | 90,000 |
| 6 | 6.4 | LDC | N | Regional Resource Mobilization Workshops | 80,000 |
| 6 | 6.2 | LDC | N | Regional Workshop for Asia | 20,000 |
| 6 | 6.2 | LDC | N | Regional Workshop for SIDS | 20,000 |
| 6 | 6.2 | LDC | N | Regional Workshop for South-West Pacific | 20,000 |
| 6 | 6.1 | LDC | N | Three National Workshops for Strategic Plan | 60,000 |
| 6 | 6.1 | LDC | N | Two LDC Coordination Meetings | 40,000 |
| 6 | 6.2 | LDC | N | Two Regional Workshops for Africa | 40,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 39,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 39,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 39,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 28,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 40,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 20,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 45,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 37,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 39,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 40,000 |
| 6 | 6.2 | RP | N | Advocacy Missions for Members & Regional Coordination | 40,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA I | 8,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA II | 8,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA III | 8,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA IV | 8,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA V | 8,000 |
| 6 | 6.1 | RP | N | Assistance to president of RA VI | 8,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA I | 4,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA VI | 4,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA V | 4,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA II | 4,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA IV | 4,000 |
| 6 | 6.1 | RP | N | Assistance to Regional Hydrological Advisors in RA III | 4,000 |
| 6 | 6.1 | RP | N | Common costs for DRA for centrally administered services | 680,000 |
| 6 | 6.1 | RP | N | Cost sharing with SREP for P staff support | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for E&S Africa, Nairobi | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for North and Central America, San Jose, Costa Rica | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for South America, Asuncion, Paraguay | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for SW Pacific | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for W-Africa, Abuja | 100,000 |
| 6 | 6.1 | RP | N | Expenses of the WMO Office for West Asia | 100,000 |
| 6 | 6.1 | RP | N | Fixed costs of the WMO Office in Abuja, Nigeria | 520,000 |
| 6 | 6.1 | RP | N | Fixed costs of the WMO Office in Nairobi, Kenya | 132,000 |
| 6 | 6.1 | RP | N | Fixed costs of the WMO Office in San Jose, Costa Rica | 72,000 |
| 6 | 6.1 | RP | N | Management Group of RA I | 33,000 |
| 6 | 6.1 | RP | N | Management Group of RA II | 33,000 |
| 6 | 6.1 | RP | N | Management Group of RA III | 33,000 |
| 6 | 6.1 | RP | N | Management Group of RA IV | 33,000 |
| 6 | 6.1 | RP | N | Management Group of RA V | 33,000 |
| 6 | 6.1 | RP | N | Management Group of RA VI | 36,000 |
| 6 | 6.2 | RP | EC Panel on ET | Meetings of the EC Working Group on Capacity Development | 50,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the DRA Department | 68,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the Regional Office for Africa (RAF) | 112,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the Regional Office for Asia & South-West Pacific (RAP) | 112,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the Regional Office for Europe (EUR) | 112,000 |
| 6 | 6.1 | RP | N | Operating Expenses of the Regional Office for the Americas (RAM) | 112,000 |
| 6 | 6.1 | RP | RA | Regional Association I | 165,000 |
| 6 | 6.1 | RP | RA | Regional Association II | 293,000 |
| 6 | 6.1 | RP | RA | Regional Association III | 95,000 |
| 6 | 6.1 | RP | RA | Regional Association IV | 129,000 |
| 6 | 6.1 | RP | RA | Regional Association V | 100,000 |
| 6 | 6.1 | RP | RA | Regional Association VI | 258,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA I | 35,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA II | 35,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA III | 35,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA IV | 35,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA V | 35,000 |
| 6 | 6.1 | RP | N | Regional Seminar in RA VI | 35,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA I | 74,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA II | 74,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA III | 74,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA IV | 74,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA V | 74,000 |
| 6 | 6.1 | RP | N | Regional Technical Conference in RA VI | 74,000 |
| 6 | 6.1 | RP | N | Support to regional presidents meeting | 20,000 |
| 6 | 6.1 | RP | N | UN Security Management System in the field | 160,000 |
| 6 | 6.1 | RP | N | Working Group on Tropical Cyclones of RA I | 50,000 |
| 6 | 6.1 | RP | N | Working Groups of RA VI | 100,000 |
| 6 | 6.1 | RP | N | Working Groups of RA I | 100,000 |
| 6 | 6.1 | RP | N | Working Groups of RA II | 100,000 |
| 6 | 6.1 | RP | N | Working Groups of RA III | 100,000 |
| 6 | 6.1 | RP | N | Working Groups of RA IV | 100,000 |
| 6 | 6.1 | RP | N | Working Groups of RA V | 100,000 |
| 6 | 6.1 | RP | N | Working Groups on Hurricanes of RA IV | 58,000 |
| 6 | 6.4 | RMDP | N | Management & Operation of VCP Programme | 40,000 |
| 6 | 6.2 | RMDP | N | Project Development: Negotiations with Donors, Development of Contribution Agreements; Management of Projects funded from Voluntary Contributions | 134,000 |
| 6 | 6.4 | RMDPP | N | Regional Symposia on Development Cooperation and Sensitizing Donors | 80,000 |
| 6 | 6.4 | RMDPP | N | Resource Mobilization Missions | 80,000 |
| 6 | 6.4 | RP | N | Support for the Country Profile Data base | 24,000 |
| 7 | 7.1 | RP | N | Participation in Meetings for Regional Coordination | 20,000 |
| 7 | 7.1 | Overall Coordination | N | Provision of WMO contribution to the United Nations system | 680,000 |
| 7 | 7.1 | Overall Coordination | N | Expenses of the WMO Liaison Office in New York | 360,000 |
| 7 | 7.1 | Overall Coordination | N | WMO/EUMETNET Joint Office in Brussels - WMO contribution Trust Fund | 200,000 |
| 7 | 7.2 | Overall Coordination | N | Production of WMO Bulletins (2 issues per year in E, F, R, S) + MeteoWorld (4 issues in E, F) | 400,000 |
| 7 | 7.2 | Overall Coordination | N | Celebration of World Meteorological Day (WMD) | 100,000 |
| 7 | 7.2 | Overall Coordination | N | Organization of press conferences, promotional events, exhibits, fairs, training sessions | 240,000 |
| 7 |  | Overall Coordination | N | Production and dissemination of press materials, brochures, information kits, audio-visual materials | 319,996 |
| 8 |  | Overall Coordination | N | Two meetings of the EC Advisory Panel of Experts on Gender Mainstreaming | 134,000 |
| 8 |  | Overall Coordination | N | Training of two trainers on gender equality and the empowerment of women | 10,000 |
| 8 |  | Overall Coordination | N | Four trainings for Secretariat staff on gender equality and the empowerment of women | 15,000 |
| 8 |  | Overall Coordination | N | Development of training materials and tools on gender equality and the empowerment of women | 15,000 |
| 7 |  | Overall Coordination | N | World Climate Conference 2019 | 200,000 |
| 8 | 8.1 | PMO | N | Congress | 1,600,000 |
| 8 | 8.1 | PMO | N | Three full sessions of EC | 1,860,000 |
| 8 | 8.1 | PMO | N | One short session of EC | 160,000 |
| 8 | 8.1 | PMO | N | Four FINAC sessions | 40,000 |
| 8 | 8.1 | PMO | N | Four full Bureau sessions | 200,000 |
| 8 | 8.1 | PMO | N | Four short Bureau sessions | 20,000 |
| 8 | 8.1 | PMO | N | Assistance to the President of WMO | 120,000 |
| 8 | 8.2 | PMO | N | Eight Audit Committee meetings | 208,000 |
| 8 | 8.2 | Overall Coordination | N | Election of Officers by correspondence + IMO prize | 80,000 |
| 8 | 8.1 | PMO | RA | Four Meetings of Presidents of TCs, Four mtgs of Presidents of RAs | 40,000 |
| 8 | 8.1 | Overall Coordination | N | Awarding IMO Prize | 48,000 |
| 8 | 8.2 | EM | N | Executive direction of the work of the Secretariat | 520,000 |
| 8 | 8.2 | EM | N | Operating Expenses of SGO, DSGO, ASGO, CER (volume-related costs and ICT services) | 660,000 |
| 4 | 4.3 | WCSP | CCl | WMO Contribution to GCOS | 630,100 |
| 4 | 4.3 | WCSP | CCl | ICT Charges to GCOS on OBS | 100,000 |
| 1 | GFCS.5 | GFCS | N | Costs related to ICT for the functioning of the Office | 60,000 |
| 1 | GFCS.1 | GFCS | N | Printing costs associated with GFCS materials | 60,000 |
| 1 | GFCS.1 | GFCS | N | Missions of staff and IBCS management committee members to advocate the GFCS at important meetings and events | 50,000 |
| 6 |  | GFCS |  | Missions of staff and IBCS management committee members to advocate the GFCS at important meetings and events | 250,000 |
| 6 | GFCS.1 | GFCS | N | Production of audio-visuals and publications | 300,000 |
| 6 | GFCS.1 | GFCS | N | Workshops to support pillars and priority areas | 1,609,000 |
| 8 | GFCS.1 | GFCS | N | Workshops to support pillars and priority areas | 41,000 |
| 8 | 8.2 | Internal Oversight | N | External Audit fees | 746,000 |
| 8 | 8.2 | Internal Oversight | N | WMO Contribution to the financing of JIU activities | 162,000 |
| 8 | 8.2 | Internal Oversight | N | ICT Charges | 100,000 |
| 8 | 8.2 | Internal Oversight | N | Operating Expenses of the Internal Oversight Office | 168,000 |
| 7 | 7.1 | WCSP | CCl | WMO Contribution to IPCC | 175,400 |
| 7 | 7.1 | WCSP | CCl | IPCC ICT & COS charges | 300,000 |
| 8 | 8.1 | Conference services | N | Conference services for meetings of IPCC, WCRP, GCOS and other extrabudgetary programmes | 44,000 |
| 8 | 8.2 | Language services and publications | N | Management of the LCP Department | 2,219,200 |
| 8 | 8.2 | Language services and publications | N | Documentation and translation services | 1,170,000 |
| 8 | 8.2 | Language services and publications | N | WMO Publications | 858,000 |
| 8 | 8.2 | Language services and publications | N | WMO Publications | 40,000 |
| 8 | 8.2 | Language services and publications | N | Standardized WMO branding and attractive designs | 282,000 |
| 8 | 8.2 | Language services and publications | N | Print shop management | 700,000 |
| 8 | 8.2 | Conference services | N | Conference services for external clients | 28,000 |
| 8 | 8.2 | Conference services | N | Management and maintenance of WMO Conference Centre | 142,000 |
| 8 | 8.2 | Language services and publications | N | Publications - distribution and management of stock | 198,000 |
| 8 |  | Conference services | N | Conference services for WMO meetings | 260,000 |
| 3 | 3.1 | WCSP | CBS | Climate Monitoring and Climate Watches | 406,000 |
| 3 | 3.1 | WCSP | CBS | Climate Data Management and Data Rescue | 400,000 |
| 3 | 3.1 | WCSP | CBS | Provision of the WMO Climate Statements and Reviews | 130,000 |
| 4 | 4.1 | SAT | CBS | Space weather activities coordination and integration | 80,000 |
| 4 | 4.1 | SAT | CBS | Cross-cutting coordination with satellite operators and international bodies | 100,000 |
| 4 | 4.1 | SAT | CBS | Rolling Requirements Review for space-based component of WIGOS | 30,000 |
| 4 | 4.1 | SAT | CBS | Satellite intercalibration (GSICS) for applications | 45,000 |
| 4 | 4.1 | SAT | CBS | Satellite data and product requirements for climate services | 40,000 |
| 4 | 4.1 | SAT | CBS | Space-based observing system vision, optimization and integration | 60,000 |
| 4 | 4.1 | SAT | CBS | Reporting to WMO constituent bodies and Consultative Meetings on Satellite Matters | 50,000 |
| 4 | 4.1 | SAT | CBS | Inter-regional data exchange support through NAEDEX and APSDEU meetings | 24,000 |
| 6 | 4.1 | SAT | CBS | Vlab training programme and focused training events | 60,000 |
| 4 | 4.1 | SAT | CBS | Gap analyses and impact studies for architecture for climate monitoring | 30,000 |
| 4 | 4.1 | SAT | CBS | Implementing new data dissemination strategy with advanced ICT opportunities | 40,000 |
| 4 | 4.1 | SAT | CBS | Advancing SCOPE efforts for Nowcasting, climate and hydrology products | 80,000 |
| 4 | 4.1 | SAT | CBS | Fostering application and product developments through international science groups | 40,000 |
| 4 | 4.1 | SAT | CBS | WIGOS Manual and Guide : Space component development (English Draft) | 10,000 |
| 4 | 4.1 | SAT | CBS | Support and advance Expert Team on Satellite Utilization and Products (ET-SUP) activities | 100,000 |
| 4 | 4.1 | SAT | CBS | Assessment and advocacy of socio-economic benefits of satellite programmes | 40,000 |
| 4 | 4.1 | SAT | CBS | Operating expenses (supplies, printing, translation) | 12,000 |
| 4 | 4.1 | WWW | CBS | CBS TECO (2014) | 80,000 |
| 4 | 4.1 | WWW | CBS | Organization of CBS-Ext. session | 230,000 |
| 4 | 4.1 | WWW | CBS | CBS Management meetings | 200,000 |
| 4 | 4.1 | WWW | CBS | Assistance to the president of CBS | 140,000 |
| 4 | 4.1 | WWW | CBS | Communication charges of the OBS Department | 120,000 |
| 4 | 4.1 | WWW | CBS | Advisory Services for WIGOS, WIS and publications | 300,000 |
| 4 | 4.1 | WWW | CBS | Operating expenses of the Office of the Director of the OBS Department | 177,000 |
| 4 | 4.1 | WWW | CBS | Operating expenses of the Office of the Director of the OBS Department | 23,000 |
| 4 | 4.1 | WWW | CBS | Office equipment of the OBS Department | 210,000 |
| 4 | 4.1 | WWW | CBS | Information Technology Charges (e-mail, data storage, internet access etc.) OBS | 760,000 |
| 4 | 4.1 | WWW | CCl | Support to the collaboration of CCl, CIMO and CBS MGs collaboration relevant activities | 120,000 |
| 4 | 4.1 | WWW | CBS | Participation of RA-WG Chairpersons to two CBS sessions | 80,000 |
| 4 | 4.1 | WWW | CBS | Organization of CBS session | 460,000 |
| 4 | 4.1 | WWW | CBS | CBS TECO | 100,000 |
| 4 |  | WIGOS | CBS | Coordination for Joint WIGOS/WIS implementation activities engaging relevant TCs | 160,000 |
| 4 |  | WIGOS | N | Coordination for regional WIGOS implementation | 260,000 |
| 4 |  | WIGOS | CBS | WIGOS Implementation - Global level | 366,000 |
| 4 |  | WIGOS | N | WIGOS Implementation - Regional level | 123,000 |
| 4 |  | WIGOS | CBS | WIGOS Implementation - National level | 111,000 |
| 4 | 4.1 | GCW | CBS | Development and implementation of the Observing component of the Global Cryosphere Watch (GCW-CryoNet) | 100,000 |
| 4 | 4.1 | GCW | CBS | Establishment of the GCW Project Office | 200,000 |
| 4 | 4.1 | GOS | RA | Support to the EC Panel on Polar Observation, Research and Services (related to observations) | 80,000 |
| 4 |  | GOS | CBS | CBS coordination for implementation and integration of observing systems | 510,000 |
| 4 |  | WIGOS | JCOMM | JCOMM contribution to WIGOS implementation | 80,000 |
| 4 | 4.1 | IMO | CIMO | Support to IMOP development in WIGOS implementation | 200,000 |
| 4 | 4.1 | IMO | CIMO | CIMO Management Meeting | 100,000 |
| 4 | 4.1 | IMO | CIMO | Support to CIMO Intercomparisons | 80,000 |
| 4 | 4.1 | IMO | CIMO | Two Meetings of the International Organizing Committees (IOCs) for intercomparisons | 145,000 |
| 4 | 4.1 | IMO | CIMO | Update of CIMO Guide and Manual (English draft only, no editing and translations) | 140,000 |
| 4 | 4.1 | IMO | CIMO | Meetings for CIMO high priority activities in support of WIGOS. | 115,000 |
| 4 | 4.1 | IMO | CIMO | Meetings of CIMO OPAG Standardization and Intercomparisons ETs | 100,000 |
| 4 | 4.1 | IMO | CIMO | Meetings of CIMO OPAG Rem-Sem and New Tech ETs | 60,000 |
| 4 | 4.1 | IMO | CIMO | Meetings of CIMO OPAG Capacity Building ETs | 65,000 |
| 4 | 4.1 | IMO | CIMO | Technical Conference on Instruments and Methods of Observations (TECO) | 60,000 |
| 4 | 4.1 | IMO | CIMO | Commission for Instruments and Methods of Observation | 362,000 |
| 4 | 4.1 | IMO | CIMO | CIMO TECO | 65,000 |
| 4 | 4.1 | IMO | CIMO | Support to the president of CIMO | 40,000 |
| 4 | 4.2 | WIS | CBS | Support to CBS-ISS | 60,000 |
| 4 | 4.2 | WIS | CBS | Maintain data representations | 180,000 |
| 4 | 4.2 | WIS | CBS | Extend and create data representations to support WMO priority activities | 176,800 |
| 4 | 4.2 | WIS | CBS | WIS developments in support of DRR | 25,600 |
| 4 | 4.2 | WIS | CBS | WIS Office Support | 160,000 |
| 4 | 4.2 | WIS | CBS | WIS Capacity Development | 120,000 |
| 4 | 4.2 | WIS | CBS | Development and implementation of WIS Centres | 321,600 |
| 4 | 4.2 | WIS | CBS | Development and implementation of WIS networks | 180,000 |
| 4 | 4.2 | WIS | CBS | WIS developments in support of WMO priority activities | 120,000 |
| 4 | 4.2 | WIS | CBS | Development and maintenance of WIS technical regulations | 94,000 |
| 4 | 4.2 | WIGOS | CBS | Radio frequency coordination | 350,600 |
| 4 | 4.2 | WIGOS | CBS | Maintain WIGOS Core Metadata representation | 120,000 |
| 4 | 4.1 | SAT | CBS | Regional requirements groups for satellite data access | 100,000 |
| 4 | 4.2 | WIS | CBS | Implement WIS monitoring systems | 180,000 |
| 4 |  | MMOP | CCl | Marine Climatology | 24,000 |
| 4 |  | WIGOS |  | Support to the operation of WIGOS Information Resource (WIR) | 120,000 |
| 4 |  | WIGOS |  | Development of WIGOS Regulatory Material - Phase I | 100,000 |
| 4 |  | WIGOS |  | Translation of WIGOS Regulatory Material - Phase II | 200,000 |
| 4 |  | WIGOS |  | Development of WIGOS Guide (best practices on WIGOS) | 80,000 |
| 4 |  | WIGOS |  | Organization of Expert Team on Satellite Systems (ET-SAT) | 100,000 |
| 4 |  | WIGOS |  | WIS Support to WIGOS Data Management and Policy | 70,000 |
| 4 |  | WIGOS |  | Consultancy on WIGOS Coordination and Communication | 60,000 |
| 4 |  | WIGOS |  | Consultancy on Radio Frequency Protection | 50,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Oceanographic Observations and Networks | 40,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Climate Monitoring and Watch Systems | 80,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Seminar on Instruments | 80,000 |
| 0 |  | Resource Management | N | Resource Management and Support | 80,000 |
| 0 |  | Resource Management | N | Missions and Training - BO | 20,000 |
| 0 |  | Resource Management | N | ITD Generic Travel and Training | 20,000 |
| 0 |  | Resource Management | N | Missions and Training - PTS | 20,000 |
| 0 |  | Resource Management | N | Missions and Training - FIN | 20,000 |
| 0 |  | Resource Management | N | Missions and Training - HRD | 20,000 |
| 0 |  | Resource Management | N | Joint Costs (excluding JIU and field security) | 600,000 |
| 0 |  | Resource Management | N | Other Expenditure (staff compensation fund) | 286,000 |
| 0 |  | Resource Management | N | Headquarter building (repayment of the loan) | 5,909,200 |
| 0 |  | Resource Management | N | Building maintenance and building insurance | 400,000 |
| 0 |  | Resource Management | N | Training for REM staff | 40,000 |
| 0 |  | Resource Management | N | Office Support - Budget Office | 35,000 |
| 0 |  | Resource Management | N | Office Support - FIN, MAMMUT, Fitch Ratings | 60,000 |
| 0 |  | Resource Management | N | Short-term and Compensation for Staff Association President | 360,000 |
| 0 |  | Resource Management | N | Maintenance of PWA software | 20,000 |
| 0 |  | Resource Management | N | Insurance (Willis) | 293,600 |
| 0 |  | Resource Management | N | Administration staff (classification consultant) | 6,400 |
| 0 |  | Resource Management | N | Insurance (Malicious Acts) | 14,000 |
| 0 |  | Resource Management | N | Mediation Services | 40,000 |
| 0 |  | Resource Management | N | Provision for unforeseen actuarial penalties (UNJSPF) | 200,000 |
| 0 |  | Resource Management | N | WMO General Training | 351,000 |
| 0 |  | Resource Management | N | WMO General Training | 49,000 |
| 0 |  | Resource Management | N | Travel and procurement processes of WMO (travel, temporary staff) | 25,000 |
| 0 |  | Resource Management | N | COS building and RC insurance | 948,000 |
| 0 |  | Resource Management | N | COS building security | 2,088,000 |
| 0 |  | Resource Management | N | COS vehicles maintenance and insurance | 60,000 |
| 0 |  | Resource Management | N | COS miscellaneous building running expenditure | 163,200 |
| 0 |  | Resource Management | N | COS building ordinary maintenance | 3,564,000 |
| 0 |  | Resource Management | N | COS building energy costs | 2,400,000 |
| 0 |  | Resource Management | N | COS building cleaning services | 602,000 |
| 0 |  | Resource Management | N | COS building cleaning services | 938,000 |
| 0 |  | Resource Management | N | COS building cleaning services | 260,000 |
| 0 |  | Resource Management | N | COS building extraordinary maintenance (incl. Planning costs) | 2,406,632 |
| 8 | 8.2 | Resource Management | N | Management and maintenance of WMO Conference Centre | 850,000 |
| 0 |  | Resource Management | N | ITD Maintenance, Operations and Enhancements - Oracle EBS | 2,060,000 |
| 0 |  | Resource Management | N | ITD Maintenance, Operations and Enhancements - Standard Applications and Services | 1,600,000 |
| 0 |  | Resource Management | N | ITD Maintenance, Operations and Enhancements - Dedicated Applications and Services | 160,000 |
| 0 |  | Resource Management | N | ITD Helpdesk Operations and Support | 1,040,000 |
| 0 |  | Resource Management | N | ITD Telecommunications and Network Connectivity | 1,200,000 |
| 0 |  | Resource Management | N | ITD Maintenance, Operations and Enhancements - Generic ICT Infrastructure | 1,120,000 |
| 0 |  | Resource Management | N | ITD ICT Security | 400,000 |
| 0 |  | Resource Management | N | ITD Library Support Services | 10,000 |
| 0 |  | Resource Management | N | ITD REM Sponsored Projects | 400,000 |
| 0 |  | Resource Management | N | ITD Extraordinary Infrastructure Maintenance / Upgrade | 100,000 |
| 0 |  | Resource Management | N | COS + ITD Charges | 1,780,000 |
| 5 | 5.2 | WWRP / GAW | CAS | Operating Expenses of the Atmospheric Research and Environment Branch (ARE) | 76,000 |
| 5 | 5.2 | WWRP / GAW | CAS | ICT charges ARE | 280,000 |
| 5 | 5.2 | WWRP / GAW | CAS | Atmospheric Research and Environment Branch International Activities | 100,000 |
| 5 | 5.2 | WWRP / GAW | CAS | Session of Commission for Atmospheric Sciences (CAS) | 196,558 |
| 5 |  |  | CAS | CAS Technical Conference | 70,000 |
| 5 | 5.2 | WWRP / GAW | CAS | CAS Management Group | 126,317 |
| 5 | 5.2 | WWRP / GAW | CAS | Assistance to the president of CAS | 65,000 |
| 5 | 5.2 | WWRP / GAW | CAS | Support to CAS representatives' attendance at meetings of other WMO Expert Groups | 34,400 |
| 5 | 5.2 | WWRP / GAW | CAS | WMO research awards | 6,880 |
| 5 | 5.2 | WWRP / GAW | CAS | Coordination of weather-climate activities through annual WWRP/WCRP WGNE Workshop | 80,000 |
| 5 | 5.2 | WWRP / GAW | CAS | Development of WMO contribution and role on Geoengineering through cooperation between CAS and WCRP | 68,800 |
| 5 | 5.2 | WWRP | CAS | Annual meetings of CAS Scientific Steering Committee on World Weather Research Programme (SSC WWRP) to review progress of the programme, initiate new projects and guide current and future efforts | 137,600 |
| 5 | 5.2 | WWRP | CAS | Data Assimilation and Observing Strategy Working Group, project and other technical meetings and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | Quadrennial International Symposium on Data Assimilation (2017) & Symposium Proceedings | 34,400 |
| 5 | 5.2 | WWRP | CAS | Predictability and Ensemble Forecast Working Group, project and other technical meetings and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | Biennial workshops on Predictability & Ensemble Forecasts (2016/2018) | 51,600 |
| 5 | 5.2 | WWRP | CAS | Societal and Economical Application working group, project and other technical meetings including collaboration with JONAS with PWS and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | Biennial Joint SERA/IRDR Workshops (2017/2019) | 51,600 |
| 5 | 5.5 | WWRP | CAS | Meeting on Tropical Meteorology Research Working Group, Cyclone and Monsoon panel, project and technical meetings and projects and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | Quadrennial International Workshops on Tropical Cyclones (2018) & publication of workshop proceedings | 34,400 |
| 5 | 5.2 | WWRP | CAS | Quadrennial International Workshop on Tropical Cyclone Landfall Processes (2017) & publication of workshop proceedings | 25,800 |
| 5 | 5.2 | WWRP | CAS | Quadrennial International Workshop on Monsoons (2017) & publication of workshop proceedings | 34,400 |
| 5 | 5.2 | WWRP | CAS | Biennial technical workshops on tropical cyclones/monsoons (with ETR and TCP) (2016/2018) | 34,400 |
| 5 | 5.2 | WWRP | CAS | Forecast verification research joint working group meeting, project and other technical meetings and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | International Verification Methods Workshop with Verification Tutorial Course (2017) (with ETP) | 34,400 |
| 5 | 5.2 | WWRP | CAS | Roving tutorial on Verification Methods (with ETP) | 12,900 |
| 5 | 5.2 | WWRP | CAS | Nowcasting and Mesoscale Weather Forecasting Research Working Group, project and other technical meetings and related publications | 92,600 |
| 5 | 5.2 | WWRP | CAS | Quadrennial International Symposium on Nowcasting and very short range forecasting with training workshop (2016) & publication of symposium proceedings | 34,400 |
| 5 | 5.4 | WWRP | CAS | Support for international coordination of three regional steering groups (Asia/Northern Africa-Middle East-Europe/Pan America) of the WMO Sand and Dust Storm Warning Advisory and Assessment System and related publications | 68,800 |
| 5 | 5.4 | WWRP | CAS | Transition research into operations thru the support to WWRP forecast demonstration/research & development projects | 68,800 |
| 5 | 5.4 | WWRP | CAS | Improve collaboration/cooperation with other relevant international research activities and bodies | 51,600 |
| 5 | 5.3 | GAW | CAS | Meetings of the CAS SSC on Environmental Pollution and Atmospheric Chemistry (EPAC) and publication of report | 100,000 |
| 5 |  | GAW | CAS | Meetings of SAGs and Expert Teams | 292,400 |
| 5 | 5.3 | GAW | CAS | Quadrennial GAW Symposium (2017) and GAW 30yr anniversary (2019) | 61,920 |
| 5 | 5.3 | GAW | CAS | GAW Implementation plan (2016-2023) activities: midterm, meetings, preparation of addendum and publication of report | 9,460 |
| 5 | 5.3 | GAW | CAS | Ozone and UV (QA/QC activities, technical meetings, publications and service delivery) | 79,120 |
| 5 |  | GAW | CAS | Ozone Quadrennial Symposium | 11,180 |
| 5 |  | GAW | CAS | Biennial Brewer Workshops | 22,360 |
| 5 | 5.3 | GAW | CAS | Aerosol research (QA/QC activities, technical meetings, publications and service delivery) | 80,000 |
| 5 | 5.3 | GAW | CAS | Greenhouse gas (QA/QC activities, technical meetings, publications and service delivery) | 80,000 |
| 5 |  | GAW | CAS | Biennial WMO/IAEA meetings on CO2 and other greenhouse gas measurement techniques | 30,960 |
| 5 |  | GAW | CAS | Support of WMO Round Robin Comparisons | 10,000 |
| 5 | 5.3 | GAW | CAS | Reactive gases & precipitation chemistry (QA/QC activities, technical meetings, publications and service delivery) | 120,000 |
| 5 |  | GAW | CAS | VOC expert meeting | 15,000 |
| 5 | 5.3 | GAW | CAS | Support for data management, data exchange and added products delivery related to atmospheric composition (support to data centers, NRT activities and data QA/QC | 79,120 |
| 5 | 5.3 | GAW | CAS | Technical meetings, capacity development, projects, assessments and publications for megacities and urban complexes | 60,000 |
| 5 |  | GAW | CAS | International Workshop on Air Quality Forecasting (IWAQFR) | 41,280 |
| 5 | 5.3 | GAW | CAS | Support for cross-cutting interdisciplinary research related to atmospheric composition (forest fires, biogenic fluxes, air pollution) through coordinated observations, development and support to forecast systems, technical meetings and integrated products and service delivery | 108,720 |
| 5 |  | GAW | CAS | Joint meetings with IGAC (IGAC Open Science Conference, Working Group, Interdisciplinary Biomass Burning Initiative) | 60,000 |
| 5 |  | GAW | CAS | Support of GESAMP activities | 40,000 |
| 5 | 5.3 | GAW | CAS | Support for international research and international conventions (the Vienna Convention, Montreal Protocol, CLRTAP, CCC, WMO/UNEP Ozone Assessment etc.) and support to international conferences | 34,400 |
| 5 |  | GAW | CAS | Annual TFMM meetings | 40,000 |
| 5 | 5.3 | GAW | CAS | Training and capacity development activities (4 per year) related to atmospheric composition (GAWTEC and other training activities) (with ETP) | 92,400 |
| 5 | 5.3 | GAW | CAS | Training and capacity development activities (4 per year) related to atmospheric composition (GAWTEC and other training activities) (with ETP) | 68,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Workshops on GAW measure & quality assurance | 40,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Workshop on Operational Monsoon Research and Forecast Issues | 20,000 |
| 8 | 8.2 | Overall Coordination | N | Operating Expenses of the Strategic Planning Office (SPO) | 4,000 |
| 8 | 8.2 | Overall Coordination | N | Information Technology Charges (e-mail, data storage, Internet access etc.) SPO | 80,000 |
| 8 | 8.2 | Overall Coordination | N | Review and update of WMO Strategic Plan, Operating Plan, M&E and ERM | 4,000 |
| 8 | 8.2 | Overall Coordination | N | Preparation/publication of WMO Strategic Plan | 26,000 |
| 8 | 8.2 | Overall Coordination | N | Preparation/publication of WMO Operating Plan | 32,000 |
| 8 | 8.2 | Overall Coordination | N | Ongoing strategic planning activities including support to Secretariat and WMO constituent bodies(Consultancy services) | 3,000 |
| 8 | 8.2 | Overall Coordination | N | Three meetings of the EC Working Group on WMO Strategic and Operational Planning and two meetings of the Task Group on Continuous improvement of WMO Processes and Practices | 196,000 |
| 8 | 8.2 | Overall Coordination | N | Development and implementation of Monitoring and Evaluation (M&E) System including preparing six-month progress reports, conducting surveys and reviewing publications on M&E System and Guide | 4,000 |
| 8 | 8.2 | Overall Coordination | N | Training of staff on strategic planning and monitoring and evaluation | 12,000 |
| 8 | 8.2 | Overall Coordination | N | Implementation of Enterprise Risk Management (ERM) including Training of Secretariat Staff and reviewing RM Policy and Framework | 8,000 |
| 8 | 8.2 | Overall Coordination | N | Support to Members of developing and least developed countries on strategic planning including preparation of guides on strategic planning | 10,000 |
| 8 | 8.2 | Overall Coordination | N | Office support, EM | 3,000 |
| 5 | 5.1 | WCRP | N | WMO contribution to JCRF | 1,200,000 |
| 3 |  | DPFS | CBS | Publications (Technical Regulations/Manual on the GDPFS, GDPFS guidance materials) | 160,000 |
| 2 |  | AMP | N | Planning and coordination activities, including integration and emergency assistance to NMHSs, in the Weather and Disaster Risk Reduction Services | 200,000 |
| 3 | 2.1 | DPFS | CBS | Further implementation of the 5 existing SWFDP regional projects and initiate the implementation of 4 new SWFDP regional projects | 200,000 |
| 3 |  | DPFS | CBS | Consolidate the SWFDP into Global Sustainable Operations, by Strengthening/Sustaining Operational Centres to Sustain and Increase the capacity of NMHSs to deliver relevant Services to the various user-sectors | 120,000 |
| 2 | 2.1 | DRR | N | Development of DRR knowledge (e.g. guidelines, standards, training modules) products for capacity development of WMO Members on hazard risk assessment, early warning systems and hazard risk financing with emphasis on alignment with the Post-2015 Framework on DRR. | 350,442 |
| 2 |  | MMOP | JCOMM | JCOMM Coordination for improved metocean services for Marine Environmental Emergency Responses | 70,000 |
| 1 | 6.2 | AeMP | CAeM | Workshops on climate change and aviation | 60,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Hurricane Forecasting | 160,000 |
| 2 | 2.1 | DRR | N | National and Regional implementation of holistic DRR capacity development and adaptation demonstration projects in the thematic areas of hazard risk assessment, early warning systems and hazard risk financing with emphasis on alignment with the Post-2015 Framework on DRR | 214,159 |
| 1 | 1.1 | AMP | N | Operating expenses and consultancy in the Weather and Disaster Risk Reduction Services Department | 123,000 |
| 1 | 1.2 | MMOP | JCOMM | Support for Developing Marine Forecasters Competence Requirements, and guidance material for marine meteorological services and training | 110,000 |
| 1 | 1.1 | MMOP | JCOMM | Nine JCOMM Expert Team Meetings on emerging issues | 285,000 |
| 2 | 2.1 | DRR | N | Coordination with and servicing of United Nations System and other partner organizations on DRR aspects | 175,221 |
| 2 | 2.1 | TCP | RA | Annual sessions of RA IV Hurricane Committee for its operational coordination and action programme | 280,000 |
| 3 | 2.1 | DPFS | CBS | Meetings of the Cross-Programmatic Steering Group for the SWFDP | 70,000 |
| 1 | 1.1 | MMOP | JCOMM | Meeting of the Joint WMO/IOC Technical Commission for Oceanography and Marine Meteorology (JCOMM) | 260,000 |
| 1 | 1.1 | AeMP | CAeM | CAeM-16 session and Technical Conference (3 session days, 3 days TECO) | 250,000 |
| 3 | 3.1 | DPFS | CBS | Workshops on the implementation of the operational sub-seasonal to seasonal forecasting, within the context of the GFCS/CSIS | 40,000 |
| 1 | 1.1 | PWS | CBS | Demonstration/pilot projects on the implementation of the WMO Strategy for Service Delivery | 100,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Seminar on PWS Delivery | 100,000 |
| 1 | 1.1 | PWS | CBS | Demonstration/pilot projects on the application of methodologies for the assessment of the socio-economic benefits of meteorological and hydrological services | 90,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Aeronautical meteorology | 80,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Course on Marine meteorology | 80,000 |
| 3 |  | ERA | CBS | Publications (ERA guidance materials and technical documents) | 50,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training Seminars on GDPFS | 70,000 |
| 3 |  | ERA | CBS | Workshops on the use and interpretation of products from RSMCs for Environmental Emergency Response (EER) | 60,000 |
| 1 | 1.1 | AMP | N | Operating Expenses and consultancy in the Weather and Disaster Risk Reduction Services Department | 83,000 |
| 1 |  | PWS | N | Pilot project(s) on impact-based forecasts and risk-based warnings for action-oriented forecast and warnings delivery | 116,814 |
| 2 |  | PWS | N | Pilot project on integrated urban weather and climate service (based on the results of the WWRP work) | 116,814 |
| 1 | 1.1 | PWS | CBS | WMO Forum on socio-economic impact of services | 50,000 |
| 1 |  | PWS | N | Meetings of the Executive Council Working Group on Service Delivery | 97,345 |
| 1 |  | PWS | CBS | Designing and implementing service delivery operational response systems (Technical structures, Competency building, Technical standards, Vulnerability-based warnings, SOPs etc.) | 55,000 |
| 1 | 1.1 | AeMP | CAeM | Development of guidance on meteorological service for other types of transport | 20,000 |
| 1 |  | MMOP |  | Publication (Manual on and Guide to Marine Meteorological Services) | 20,000 |
| 1 | 6.2 | AeMP | CAeM | Publications and web improvements | 20,000 |
| 2 | 2.1 | TCP | N | RA IV Workshop on Hurricane Forecasting and Public Weather Services (with PWS & ETR) | 155,000 |
| 2 |  | TCP | N | WMO Global Initiative for Tropical Cyclone Forecasting | 150,000 |
| 6 | 6.2 | DPFS | CBS | Co-sponsored training events with ECMWF, DWD, and NOAA/NCWCP | 140,000 |
| 6 | 6.2 | TCP | N | RA I Workshop on Tropical Cyclone Forecasting and Public Weather Services (with PWS) | 135,000 |
| 1 | 1.1 | AeMP | CAeM | ET/TT Team-building meetings, reporting and production meetings, several Teleconferences | 130,000 |
| 2 | 2.1 | TCP | RA | Biennial sessions of RA I Tropical Cyclone Committee for its operational coordination and action programme | 120,000 |
| 6 | 6.2 | ETRP | N | On-the-job training for TC forecasters | 120,000 |
| 2 | 2.1 | DRR | N | Major Conferences and Symposia on socio-economic benefits, DRR and the SWFDP | 200,000 |
| 1 | 1.1 | PWS | CBS | CBS/PWS Expert Team meetings | 114,000 |
| 6 | 6.3 | ETRP | EC Panel on ET | Training workshops on SWFDP | 40,000 |
| 2 | 2.1 | TCP | N | RA V Workshop on TC Forecasting and Public Weather Services (with PWS) | 105,000 |
| 2 | 2.1 | TCP | RA | Biennial sessions of RA V Tropical Cyclone Committee for its operational coordination and action programme | 100,000 |
| 1 | 1.2 | PWS | CBS | Meetings and workshops to implement guidelines on service delivery in megacities | 30,000 |
| 6 | 6.2 | AeMP | CAeM | Training workshops on ATM support | 95,000 |
| 2 | 2.1 | TCP | N | Implementation support to regional Storm Surge Watch Schemes (with JCOMM through MMOP) | 90,000 |
| 4 |  | WIGOS | CBS | Perform gap analysis, develop requirements and monitoring procedures for improving basic systems for efficient warning services | 20,000 |
| 2 |  | ERA | CBS | Pilot projects on the provision of forecasting products to assist humanitarian agencies (planning, preparedness and response) | 20,000 |
| 6 | 6.1 | RP | EC Panel on ET | Working Group on Tropical Cyclones of RA V | 50,000 |
| 2 | 2.1 | TCP | N | Annual sessions of Panel on Tropical Cyclones for implementation of its Coordinated Technical Plan | 80,000 |
| 2 |  | TCP | RA | Support for regional coordination of TC Committees | 80,000 |
| 6 | 6.2 | ETRP | JCOMM | Two training workshops for marine forecasters competences and service skills | 76,000 |
| 3 | 1.1 | DPFS | CBS | CBS Expert Team meetings on Operational Prediction from Sub-seasonal to Longer-time Scale, in support of the GFCS/CSIS | 70,000 |
| 1 | 1.1 | MMOP | JCOMM | JCOMM Management Committee | 69,000 |
| 1 | 1.1 | AeMP | CAeM | Developing joint standards and procedures with ICAO | 60,000 |
| 1 |  | AeMP | CAeM | Drafting of sub-regional cooperation agreement, cost recovery principles, user interaction, joint development and training activities | 60,000 |
| 1 | 1.1 | MMOP | JCOMM | Support to JCOMM co-presidents | 60,000 |
| 3 | 1.1 | DPFS | CBS | CBS Expert Team meetings on Operational Weather Forecasting Process and Support Service Delivery to the Public and Socio-Economic Sectors/Applications (PWS, AgM, AeM, MMO, TC) | 60,000 |
| 2 | 1.1 | ERA | CBS | Meetings of the CBS Expert Team on Emergency Response Activities (ERA) | 60,000 |
| 2 | 2.1 | TCP | N | Annual sessions of Typhoon Committee for implementation of its Strategic Plan | 60,000 |
| 1 |  | MMOP | JCOMM | Implementation support for WMO programmatic areas | 60,000 |
| 6 | 7.1 | AeMP | CAeM | Workshops on cooperation, compliance and cost recovery | 60,000 |
| 7 | 1.2 | MMOP | JCOMM | Interaction with marine stakeholders and partner organizations for user requirements | 60,000 |
| 2 | 1.1 | MMOP | JCOMM | Support for Steering Group of Coastal Inundation Forecasting Demonstration Project (CIFDP) | 58,000 |
| 1 | 1.2 | PWS | CBS | Technical Seminars on the implementation of the WMO Strategy for Service Delivery | 50,000 |
| 2 | 1.1 | PWS | CBS | Meetings and workshops to implement impact-based decision support services | 50,000 |
| 2 | 2.1 | TCP | N | Quadrennial International Workshop on Tropical Cyclone (with WWRP) | 50,000 |
| 2 |  | TCP | N | Technical support to operational TC forecasting with IT | 50,000 |
| 3 |  | ERA | CBS | Meetings of the CBS Task Team on Operational Procedures for Nuclear ERA | 50,000 |
| 1 |  | PWS | CBS | Joint capacity development events with TCP in service delivery related to tropical cyclones | 45,000 |
| 1 | 1.1 | AeMP | CAeM | CAeM Management Group meeting | 40,000 |
| 3 | 2.1 | DPFS | CBS | Secondment of NMHS experts to strengthen operational (GDPFS) centres, especially regional centres | 40,000 |
| 2 | 1.1 | ERA | CBS | Meetings of the CBS Task Team on Development of Operational Procedures for Non-Nuclear ERA | 40,000 |
| 2 | 2.1 | TCP | N | Quadrennial International Workshop on Tropical Cyclone Landfall processes (with WWRP) | 40,000 |
| 3 | 3.1 | DPFS | CBS | Meetings and projects for the implementation of Surface Forecast Verification | 40,000 |
| 3 |  | DPFS | CBS | Development of guidelines and implementation of projects on the use and propagation of NWP/EPS into High-Impact Weather (HIW) forecasting and hazard risk management | 40,000 |
| 6 |  | ETRP | CBS | Support to ETR Training Events in GDPFS and SWFDP | 40,000 |
| 1 | 7.1 | AeMP | CAeM | Support to VASAG | 40,000 |
| 1 | 1.1 | PWS | CBS | CBS Implementation Coordination Team meeting | 34,000 |
| 3 |  | DPFS | CBS | Functioning of the SWFDP Project Office | 32,000 |
| 1 | 1.1 | AeMP | CAeM | Support to president of CAeM | 30,000 |
| 6 |  | AeMP | CAeM | Support for implementation of qualification requirements | 30,000 |
| 1 | 1.1 | AeMP | CAeM | Targeted implementation support on request, gap analyses | 28,000 |
| 1 |  | AeMP | CAeM | Implementation support to Members developing ATM support and WXXM-based products | 25,000 |
| 1 |  | ETRP | CBS | Support by ETR to training events on PWS | 24,000 |
| 1 |  | PWS | CBS | Support to regional events, Working Groups and Task Teams of Regional Associations | 20,000 |
| 1 |  | PWS | CBS | PWS component in the further implementation of the existing SWFDP projects and initiation of the new SWFDP regional projects | 20,000 |
| 1 |  | PWS | CBS | Publication of guidance materials, proceedings and reports (PWS) | 20,000 |
| 2 | 1.1 | ERA | CBS | Development of guidelines on the use and interpretation of products from RSMCs for Environmental Emergency Response (EER) | 20,000 |
| 6 |  | RP | CBS | Support to Working Groups of Regional Associations and of Meteorological Groups within Regional Economic Bodies | 20,000 |
| 6 |  | ETRP | CBS | Support to ETR Training Events in ERA | 20,000 |
| 6 |  | TCP | N | Biennial technical workshops on tropical cyclones/monsoons (with WWRP & ETR) | 20,000 |
| 1 |  | PWS | CBS | Missions to implement CAP standard through the CAP Jump-start initiative | 15,000 |
| 2 |  | PWS | CBS | Guidance on delivering meteorological assistance to humanitarian agencies for interpretation of forecast products | 10,000 |
| 3 |  | DPFS | CBS | Development of operational arrangements with the GDPFS on the implementation of seamless weather and climate watch systems | 10,000 |
| 3 |  | DPFS | CBS | Development of guidelines and implementation of projects on the use and interpretation of blending remote-sensing data and NWP products for very short-range forecasting, including nowcasting, in support of AeM and multi-hazard Early Warning Systems (EWS) | 10,000 |
| 7 |  | ERA | CBS | Coordination with IAEA and other relevant international organizations (e.g. ICAO, WHO) on ERA aspects | 34,912 |
| 1 | 1.1 | ERA | CBS | Advisory services on emerging issues of Emergency Response Activities (ERA) | 17,456 |
| 1 | 1.1 | AMP | N | ICT Charges WDS | 488,763 |

## III.	TECHNICAL COMMISSIONS OPERATING PLANS

According to Resolution 38 (Cg-XVI), technical commissions are requested to develop their own Operating Plans in support of the implementation of the WMO Strategic Plan 2016-2019. EC requested technical commissions to finalize their operating plans by January 2016. Operating plans of the technical commissions that have been received are included hereunder.

### III.1	COMMISSION FOR INSTRUMENTS AND METHODS OF OBSERVATION (CIMO) OPERATING PLAN 2016-2019

| ER | Key Outcome | Deliverable | Programme | Technical Commission | Activity | Y2016 | Y2017 | Y2018 | Y2019 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | 4.1 | Report of SPICE Intercomparison | IMOP | CIMO | Intercomparison – SPICE | X |  |  |  |  |
| 4 | 4.1 | Report of IPC-XII - Traceability of ref. pyrheliometers | IMOP | CIMO | Intercomparison - IPC-XII | X |  |  |  |  |
| 4 | 4.1 | Report of infrared radiometer intercomparison | IMOP | CIMO | Intercomparison of infrared radiometers | X |  |  |  |  |
| 4 | 4.1 | Detailed plan for Intercomparison | IMOP | CIMO | Intercomparison feasibility study | X | X |  |  |  |
| 4 | 4.1 | Report of Intercomparison | IMOP | CIMO | Intercomparison |  | X | X | X |  |
| 4 | 4.1 | Reports on Completed Instrument Tests | IMOP | CIMO | Testbeds | X | X | X | X |  |
| 4 | 4.1 | IOM Reports | IMOP | CIMO | Capacity Building |  |  |  |  |  |
| 4 | 4.1 | Conference on Instruments & Methods of Obs. | IMOP | CIMO | TECO-2016 (Capacity building) | X |  |  |  |  |
| 4 | 4.1 | Instrument Exhibition (METEOREX-2016) | IMOP | CIMO | METEOREX-2016 | X |  |  |  |  |
| 4 | 4.1 | Conference on Instruments & Methods of Obs. | IMOP | CIMO | TECO-2018 (Capacity building) |  |  | X |  |  |
| 4 | 4.1 | Instrument Exhibition (METEOREX-2018) | IMOP | CIMO | METEOREX-2018 |  |  | X |  |  |
| 4 | 4.1 | Workshop on instrumentation (challenges faced in mountain stations or AWS) | IMOP | CIMO | Workshop (Capacity Building) |  | X |  |  |  |
| 4 | 4.1 | New web-based edition of ICA | IMOP | CIMO | Update of the International Cloud Atlas | X |  |  |  |  |

Note: This Operating Plan comes as a complement to the activities already listed in the Secretariat Operating Plan relevant to CIMO.

### III.2	COMMISSION FOR HYDROLOGY (CHy) OPERATING PLAN 2016-2019

| Expected Result 1 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warnings and services in response to users’ needs, and to enable their use in decision-making by relevant societal sectors. |  |  |  |  |  |  |  |  |
| Key Outcome 1.1 | Improved access to seamless weather, climate and water and related environmental products and services (e.g. warnings, forecasts and supporting information) |  |  |  |  |  |  | Source of funding |
| Key Performance Indicators | - Analyses showing the social and economic benefits of the improved services - NMHS with regular access to products provided by global and regional centres |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Update guidance on the application of the seamless prediction capabilities for delivery of water-related products (e.g. forecasts and warnings) | Guide and Manuals which are state-of-the-art | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Review and evaluate the advances in Numerical Weather Prediction (NWP) with respect to improved flood forecasting and warning services (e.g. through case studies) | Improved flood forecasting and warning services. | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |

| Expected Result 2 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements |  |  |  |  |  |  |  |  |
| Key Outcome 2.1 | Multi-hazard warning systems are implemented |  |  |  |  |  |  | Source of funding |
| Key Performance Indicators | - Increase in the number of NMHSs with multi-hazard warning systems - Number of NMHSs integrated into national emergency management systems - Developing country Members providing disaster risk reduction products and services |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Provide advice and support to the projects related to the Flash Flood Guidance System (FFGS) and PROHIMET taking account of other initiatives in the area | Informed decisions associated with CHy related flood activities (namely FFGS and PROHIMET) | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |
| Review and evaluate the developments associated with the Global Flood Alert System | Informed decisions associated with CHy related flood activities (namely GFAS) | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Provide guidance and advice on the use of hydrological models in collaboration with other related hazards, such as storm surges, cyclones, etc. | Improved multi-hazard warning capabilities of NMHSs | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |
| Review and revise the Strategy and Action Plan on the Flood Forecasting Initiative in line with recommendations from the FFI Advisory Group and evolving Member needs. | Refined and improved Strategy and Action plan for flood forecasting | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from |
| Prepare guidance material on the application and use of seasonal outlooks for water-related hazard forecasting and prediction | Technical report and workshops – increased capabilities in NMHSs | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |

| Key Outcome 2.2 | National integrated flood management plans are developed |  |  |  |  |  |  | Source of funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Performance Indicators | - Number of Members establishing flood management plans - Number of regional hydrological forecasting systems established in transboundary basins |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Review and update guidance material on Integrated Flood Management provided through the APFM, including responding to new and emerging requests. | Technical guidance material, workshops and knowledge management website | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |

| Key Outcome 2.3 | Drought early warning systems are improved |  |  |  |  |  |  | Source of funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Performance Indicators | - NMHSs and Regional Centres issuing drought early warnings - Satisfaction in drought early warning systems issued by NMHSs and Regional Centres |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Prepare guidelines for the development of drought early warnings of relevance to decision-making in the water sector. | Technical guidance and workshops – increased capabilities of NMHSs | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |

| Expected Result 3 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support in particular, reduced disaster risk and climate impact and adaptation strategies |  |  |  |  |  |  |  |  |
| Key Outcome 3.2 | Climate information and prediction products for climate adaptation and risk management are improved |  |  |  |  |  |  | Source of funding |
| Key Performance Indicators | - Number of operational Regional Climate Centres providing inputs for the National Climate Centres - Number of Members with formal NCCs, accessing global and regional products, using guidance materials and transmitting climate products for national needs - Number of Members interacting with users while providing climate services, through formal mechanisms including National Climate Outlook Forums, in support of adaptation and climate risk management in key socio-economic sectors - Members using best practices for climate adaptation and risk management in key socio-economic sectors |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Provide advice and guidance on relevant hydrological risk management issues related to climate variability and change | Informed decisions associated with CHy related risk management issues (floods and droughts) | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Continue to develop, in close cooperation with CAgM and CCl, activities to support hydrological drought prediction capabilities | Manual on Hydrological Drought Prediction. | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |
| Establish a network of hydrological stations that will show the impacts of climate variability and change in the data | Data from climate sensitive hydrological stations available and accessible | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Provide a component of the GFCS User Interface Platform for the water sector | Improved climate services meeting the needs of the water resources information users | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |

| Key Outcome 3.3 | Hydrological information and products, including water resources assessments, are improved |  |  |  |  |  |  | Source of funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Performance Indicators | - Number of Members having established a Quality Management Framework for Hydrology using current guidance materials for hydrology and water resources management - Number of regional hydrological databases developed in transboundary river basins |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Application of the guidance material on the definition and implementation of a Quality Management System (QMS) for NHSs | Improved capabilities of Members though guidance material and workshops | Quality Management Framework Hydrology | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Review of material for the Technical Regulations (WMO-No. 49); | Revised editions of the TRs | Quality Management Framework Hydrology | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Promulgate the results of the assessment of performance of flow measurement instruments and techniques against WMO standards based on the project proposal developed during the previous intersessional period | Improved capabilities of Members though guidance material and workshops | Quality Management Framework Hydrology | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Obtain international acceptance of standards, formats and protocols for data transfer | Assist in the implementation of agreed international data transfer standards | Data Operations and Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Monitoring advances and assist in the development of new technologies for Hydrometric Monitoring | Improved capabilities of Members though guidance material and workshops | Quality Management Framework Hydrology | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Conduct training and workshops using the Manual on Water Resources Assessment | Improved capabilities of members in Water Resources Assessment | Water Resources Assessment | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Monitor and report on the development of improved areal estimation of evaporation, evapotranspiration and soil moisture. | State-of-the-art report, including methodological approaches to assessment of basic moisture regime characteristics (evaporation, soil moisture). | Water Resources Assessment | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Monitor, report and prepare guidance material on the current status of network design and optimization, including the use of modelling | Efficient and effective monitoring systems – link to WIGOS | Water Resources Assessment | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Promote and distribute the Information Note on ecological flow requirements and ecological assessment, taking into account the activities of other groups | Report with proposals on elaboration of determination of ecological flow, adverse effects on water objects, maximum admissible impact on water objects and runoff withdrawal. Case-studies | Water Resources Assessment | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Promote capacity-building in the use of CHy Manuals, e.g. Manual on Low Flows, Manual on Flood Forecasting, etc. | Improved capabilities of Members though guidance material and workshops using material prepared by CHy. | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |
| Prepare guidance material on the potential use of the current capabilities in regional climate modelling (RCM) for water resources assessment and management | Document on the current capabilities in regional climate modelling (RCM) for water resources assessment and management | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Promote data rescue activities | Guidance available on data rescue for hydrological data | Data Operations and Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Promote, monitor, report and provide advice on the application of Resolution 25 (Cg-XIII) by Members and in particular in HYCOS projects | Results of previous survey evaluated. Recommendations and guidance prepared | Data Operations and Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Monitor, report and provide advice on the activities of the international data centres and address the international data requirements | Existing international data centres surveyed. Improved operation of International Data Centres. | Data Operations and Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |

| Expected Result 4 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO |  |  |  |  |  |  |  |  |
| Key Outcome 3.2 | Climate information and prediction products for climate adaptation and risk management are improved |  |  |  |  |  |  | Source of funding |
| Key Performance Indicators | - Number of operational Regional Climate Centres providing inputs for the National Climate Centres - Number of Members with formal NCCs, accessing global and regional products, using guidance materials and transmitting climate products for national needs - Number of Members interacting with users while providing climate services, through formal mechanisms including National Climate Outlook Forums, in support of adaptation and climate risk management in key socio-economic sectors - Members using best practices for climate adaptation and risk management in key socio-economic sectors |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC | 2016 | 2017 | 2018 | 2019 |  |
| Provide advice and guidance on relevant hydrological risk management issues related to climate variability and change | Informed decisions associated with CHy related risk management issues (floods and droughts) | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Continue to develop, in close cooperation with CAgM and CCl, activities to support hydrological drought prediction capabilities | Manual on hydrological drought prediction | Hydrological Forecasting and Prediction | CHy | X | X | X | X | In-kind contributions and support from Secretariat and extrabudgetary funds for target areas |
| Establish a network of hydrological stations that will show the impacts of climate variability and change in the data | Data from climate sensitive hydrological stations available and accessible | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |
| Provide a component of the GFCS User Interface Platform for the water sector | Improved climate services meeting the needs of the water resources information users. | Water, Climate and Risk Management | CHy | X | X | X | X | In-kind contributions and support from Secretariat |

### III.3	COMMISSION FOR ATMOSPHERIC SCIENCES (CAS) OPERATING PLAN 2016-2019

| Expected Result 5 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhanced capabilities of Members to contribute to and draw benefits from the global research capacity for weather, climate, water and the related environmental science and technology development |  |  |  |  |  |  |  |  |  |
| Key Outcome 5.2 | Research in the prediction of high-impact weather on time scales of hours to seasons is enhanced |  |  |  |  |  |  |  | Source of funding |
| Key Performance Indicators | - Increased research on operations products and services - Improvements in the number of internationally coordinated NMHS in developing and least developed countries contributing to relevant regional and international research initiatives, weather research initiatives and/or forecast demonstration projects completed |  |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC |  | 2016 | 2017 | 2018 | 2019 |  |
| Sub-Seasonal to Seasonal (S2S) prediction research project as a joint WWRP and WCRP initiative. Project duration: 5 years + 5 years based on assessment of progress, starting from 2014 | Improved predictive skill on the sub-seasonal to seasonal timescale based on the improved understanding of Earth-system processes that contribute to such skill. A fundamental contribution to the GFCS. Contributing towards DRR, Service Delivery and Capacity Development | WWRP, jointly with WCRP | CAS |  | X | X | X | X | S2S Trust Fund plus support by secretariat and International Coordination Office |
| Polar Prediction research Project (PPP) as the hours to seasonal timescale research contribution to GIPPS and conducted in close collaboration with the WCRP Polar Climate Predictability Initiative. Project duration:10 years starting from 2014 | Improved predictive skill in polar region and the improved understanding of links between polar and extra-polar weather. Contributing towards DRR, GFCS, Service Delivery and Capacity Development | WWRP in collaboration with WCRP | CAS |  | X | X | X | X | PPP Trust Fund plus support by secretariat and International Coordination Office |
| High Impact Weather (HIWeather) Research Project for forecasts covering hours to days and promoting the socio-economic applications of such predictions in key sectors. Project duration: 5 years starting from 2015 | Improved predictive skill of high impact weather events at high spatial and temporal resolutions focussing on priority applications including the urban environment, hydrological events. Contributing towards DRR, Service Delivery and Capacity Development | WWRP | CAS |  | X | X | X | X | HIWeather Trust Fund plus support by secretariat and International Coordination Office |
| Improving the understanding and modelling of water related processes in the atmosphere and its impact on hydrology as a key ingredient in DRR and resource management. Ongoing. | Enhanced focus on water-related processes and impacts in the projects and activities of WWRP. Research Development and Forecast Demonstration Projects (RDPs/FDPs) focussing on weather-water related phenomena | WWRP | CAS in cooperation with CHy and CBS |  | X | X | X | X | Regular budget to ensure coordination with WMO |
| Key Outcome 5.3 | Atmospheric chemistry observations and assessment meet needs of environmental conventions and policy assessments |  |  |  |  |  |  |  | Target |
| Key Performance Indicators | - Regular bulletins on global atmospheric chemistry are provided to environmental conventions and policy assessments - Number of technical reports, measurement guidelines and scientific analyses linking atmospheric chemistry to weather, climate, water and the environment |  |  |  |  |  |  |  |  |
| Activities | Deliverables | Programme | TC |  | 2016 | 2017 | 2018 | 2019 |  |
| Research to support services for Megacities and large urban complexes linking weather, climate, water and related environmental phenomena. A cross-cutting initiative. Project duration: 10 years starting 2014 | Improved urban observations, data assimilation and predictive skill tailored for the urban environment and in of support policy, planning, routine decisions and risk management. Contributing towards DRR, GFCS, WIGOS/WIS, Service Delivery and Capacity Development | GAW, WWRP in collaboration with PWS, DRR, WCRP, GFCS | CAS in cooperation with CBS |  | X | X | X | X | Megacity trust plus Secretariat support and coordination |
| Integrated Greenhouse Gas Information System to support policy and provide regionally relevant information on sources and sinks. Project Duration: 10 years starting 2015 | Improved GHG observations, data assimilation and modelling of the carbon cycle as an independent, science-based input to support policy and operational decisions on Greenhouse gas mitigation strategies and their effectiveness. Contributing towards GFCS, WIGIS/WIS, Service Delivery and Capacity Development | GAW | CAS |  | X | X | X | X | Regular budget to ensure coordination within WMO and with partners |
| Research to support informed decisions and policy advice on geoengineering. Duration 5 years starting 2014 | Informed role for WMO regarding geoengineering, a UN-wide position and framework and knowledge gaps addressed through research | GAW, WWRP, WCRP | CAS |  | X | X | X |  | Regular budget to ensure coordination within WMO and with partners |
| Establishment of an integrated global aerosol observation system in support of weather, climate, air quality and health applications Duration: 10 years starting 2016 | Improved aerosol observations and data assimilation process for aerosols in support of improved weather, climate and air quality forecasts as well as health applications | GAW in collaboration with WWRP WGNE | CAS |  | X | X | X | X | Regular budget to initiate, provide guidance and coordinate Member initiatives on aerosol observations |

## IV.	REGIONAL ASSOCIATIONS OPERATING PLANS

According to Resolution 38 (Cg-XVI), regional associations are requested to develop their own Operating Plans in support of the implementation of the WMO Strategic Plan 2016-2019. EC requested regional associations to finalize their Operating Plans by January 2016. Operating Plans of regional associations that have been received are included hereunder.

### IV.1	REGIONAL ASSOCIATION II (ASIA)

EXPECTED RESULTS, KEY OUTCOMES AND KEY PERFORMANCE INDICATORS

| Expected Result 1: Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warning and services in response to users' needs, and to enable their use in decision-making by relevant societal sectors |  |  |  |
| --- | --- | --- | --- |
| KO 1.1 | Improved access to seamless weather , climate, water, and related environmental products and services (e.g. warnings , forecasts and supporting information) | KPI 1.1.1 | Number of Members demonstrating quantitative measurements of the socio-economic benefits of their products and services |
|  |  | KPI 1.1.2 | Percentage of NMHSs with regular access to products provided by global and regional centres |
| KO 1.2 | Delivery of weather , climate , water and related environmental products and services to users' communities is improved | KPI 1.2.1 | Number of NMHSs expressing user satisfaction with the: (a) availability, (b) reliability and (c) range of products that are (d) received in time and (e) are an essential contribution to decision-making |

Expected/ add on Deliverables/Activities in RA II 2016-2019 SOP

1.	Promotion and strengthening of the principle of free and unrestricted international exchange of data and products among Members, particularly in meeting the requirements of regional and sub-regional programmes related to RCCs/GFCS & DCPCs.

2.	Improved provision of agrometeorological services to the user community by promoting practical applications of technological advances in the agrometeorology domain.

| Expected Result 2: Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements |  |  |  |
| --- | --- | --- | --- |
| KO 2.1 | Multi-hazard early warning systems are implemented | KPI 2.1.1 | Number of NMHSs contributing to the implementation of multi-hazard early warning systems |
| KO 2.2 | National integrated flood management plans are developed | KPI 2.2.1 | Number of Members establishing flood management plans |
|  |  | KPI 2.2.2 | Number of NMHSs participating in regional hydrological forecasting systems for transboundary river basins |
| KO 2.3 | Drought early warning systems are improved | KPI 2.3.1 | NMHSs and Regional Centres that issue drought early warnings |

Expected/add on Deliverables/Activities in RA II 2016-2019 SOP

1.	Strengthening Marine METAREAs in RA II under the framework of WMO/JCOMMIGMDSS.

2.	Developing/enhancing capacity to provide consistent levels of met/ocean information and drift information in the event of a range of marine environmental incidents including:

(a)	Spills of oil and other noxious substances;

(b)	Accidents related to objects;

(c)	Radioactive material discharges in marine and coastal zones;

(d)	Other environmental hazards e.g. harmful algal blooms.

3.	Strengthening links with disaster managers.

4.	Measurement of changes in river flow in snow/glacier-fed rivers to assess the effect of climate change and climate variability.

5.	Issuance of flood, flash and urban flood warnings, landslide/debris flow warnings and constantly improving upon them.

| Expected Result 3: Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support in particular, reduced disaster risk and climate impact and adaptation strategies |  |  |  |
| --- | --- | --- | --- |
| KO 3.1 | Improved climate monitoring long range forecasts and long-term projections | KPI 3.1.1 | Number of Members issuing: (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
|  |  | KPI 3.1.2 | Perceived quality of the issued: (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
|  |  | KPI 3.1.3 | Perceived timeliness of the issued (a) monthly predictions; (b) seasonal predictions; (c) climate watch bulletins; and (d) long-term projections |
| KO 3.2 | Climate information and prediction products for climate adaptation and risk management are improved | KPI 3.2.1 | Perceived quality of the products of WMO Regional Climate Centres used at the national level |
|  |  | KPI 3.2.2 | Number of Members operationally developing and disseminating climate products and information for national needs at basic, intermediate and advanced levels |
|  |  | KPI 3.2.3 | Perceived quality of the national climate information and products available in Member countries |
|  |  | KPI 3.2.4 | Number of Members providing targeted/tailored climate information, products and services, through formal mechanisms including National Climate Outlook Forums, to support user requirements in their countries for adaptation and climate risk management in key socio-economic sectors |
| KO 3.3 | Hydrological information and products, including water resources, are improved | KPI 3.3.1 | Number of Members using a Quality Management Framework for Hydrology based on current guidance materials |
|  |  | KPI 3.3.2 | Number of regional hydrological databases developed in transboundary river basins |
| KO 3.4 | Drought information and prediction for risk management is improved | KPI 3.4.1 | NMHSs an Regional Centres issuing drought information and prediction |

- Provision of monthly and seasonal climate prediction: (K.O)

- Hydrological information and products, including water resource assessments are to be improved in RA II (K.O)

Expected/add on Deliverables/Activities in RA II 2016-2019 SOP

1.	Marine observations and providing data to support global and regional climate studies, including participation in GLOSS (Global Sea Level Observing System) to monitor long-term sea level changes associated with global warming.

2.	Enhanced capability in climate observations.

3.	Percentage of marine met service providers making marine observations and providing data to support global and regional climate models.

4.	Establishment of subregional RCOFS in South East Asia and South West & West Asia.

5.	Adoption of innovative agrometeorological adaptation strategies in face of climate variability and climate change.

| Expected Result 4: Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO |  |  |  |
| --- | --- | --- | --- |
| KO 4.1 | WMO Integrated Global Observing System implementation phase is completed | KPI 4.1.1 | Percentage of progress in achieving the key implementation tasks, milestones and deliverables specified by the WIGOS Implementation Plan (WIP) |
|  |  | KPI 4.1.2 | Increased availability of observations for users (as measured by several ratios) |
| KO 4.2 | WMO information System is developed and implemented | KPI 4.2.1 | Progress in the implementation of WIS by NMHSs as measured by: (a) percentage of registered WIS centres that have been endorsed as WIS compliant; and (b) number of NMHSs with improved observational data and products as a result of implementation of WIS functions |
|  |  | KPI 4.2.2 | Number of NMHSs whose data processing and management capabilities have enhanced as a result of implementation of WIS functions |
| KO 4.3 | Progress in implementing the Global Climate Observing System | KPI 4.3.1 | Percentage of progress in achieving the GCOS Implementation Plan |
| KO 4.4 | Data rescue and data management systems improved | KPI 4.4.1 | Number of NMHSs undertaking data rescue or being involved in regional collaborative data rescue initiatives such as MEDARE |
|  |  | KPI 4.4.2 | Number of Members implementing modern climate data management systems and/or climate monitoring systems |

Establishment of one or two RICs at least with basic capabilities to cover West Asia & SW Asia WIGOS Projects similar to East Asia & South East Asia

1.	Integration of surfaced-based remote sensing observation in West/South-west Asia and South East Asia possibly two inter-regional projects in West Asia with Region VI and one subregional project in GCC countries.

2.	Capacity-building in Radar techniques in West/South West Asia (similar to above).

3.	Further improvement on capacity in use of satellite data products and facilitation of training datasets and tool boxes.

4.	Implementation of DCPCs in Marine, GAW and AMDAR areas.

5.	Enhanced capacity of RMTN circuits with the required bandwidth to receive and disseminate satellite and NWP products.

Analysis of implementation status of RMTN depicts that more than 90% circuits are running at speed <:  64 kbps. For effective implementation of WIS.it was recommended in the Meeting of WMO RA II Working Group on WMO Integrated Observing System and WMO Information System (WG-IOS./WIS), Seoul. Republic of Korea. 30 November – 7 December 2011 that the circuits may be upgraded to 512 kbps because new sets of data like satellite and NWP products have significant contribution for operation critical activities and 512 kbps would help timely delivery of various sets of data to end users in minimal time.

  - less than 64kbps

64 .bps

12SI<bps to less than

51:!kbps

•5 1::?kbps to less than 1Mt:ps

16%	•More tl1an & equal to

tMbps

However.at present only 26% of total circuits operate at speed 2 512 kbps. Therefore there is a need to push NMHSs for upgrade of circuits.

The number of circuits at each speed as of September 2012 (Revised categories since 2011)

Moreover.certain RMTN circuits like Karachi - Tashkent and Kabul -Tashkent are not logical networks and there is no c

Moreover certain RMTN circuits like Karachi-Tashkent and Kabul – Tashkent are not logical networks and there is no chance of their revival in coming time.

| Expected Result 5: Enhanced capabilities of Members to contribute to and draw benefits from the global research capacity for weather, climate, water and the related environmental science and technology development |  |  |  |
| --- | --- | --- | --- |
| KO 5.1 | Research in climate prediction/projection to improve the skills of seasonal, decadal and longer timescales is enhanced | KPI 5.1.1 | Number of new activities advancing climate research capacity at the global and regional level, especially for early career scientists and scientists from developing and LDC countries |
|  |  | KPI 5.1.2 | Number of early career scientists and scientists from developing and least developed countries that WCRP funded to participate in activities to advance climate research |
|  |  | KPI 5.1.3 | Degree of satisfaction among NMHSs with the skill of climate predictions |
| KO 5.2 | Research in the prediction of high-impact weather on time scales of hours to seasons is enhanced | KPI 5.2.1 | Number of total research projects (new, ongoing and completed) on operational products and services |
|  |  | KPI 5.2.2 | Number of Members whose operational products and services have improved as a result of WMO research projects |
|  |  | KPI 5.2.3 | Number of NMHSs in developing and least developed countries participating in regional and international research initiatives on high impact weather or severe weather forecasting demonstration projects |
| KO 5.3 | Atmospheric chemistry observations and assessment meet needs of environmental conventions and policy assessments | KPI 5.3.1 | Degree of Member satisfaction with the: (a) usefulness; and (b) timeliness of Global Atmospheric Chemistry Bulletins |
|  |  | KPI 5.3.2 | Degree of Member satisfaction with the usefulness of: (a) GAW measurement guidelines and reports; (b) Sand-and-Dust storm forecasting; and (c) the chemical weather activities of GURME |
| KO 5.4 | Seamless forecasts of weather, climate, water and the environment from days to seasons are developed in support of the GFCS | KPI 5.4.1 | Number of NMHSs participating in the integration of observations, research, modelling and analysis results to improve sub-seasonal to seasonal weather/climate projections and predictions |

1.	Atmospheric chemistry observations and assessment meet needs of environmental conventions and policy assessments.

2.	Maintenance/enhancement of Global Atmospheric Watch (GAW) stations in the Region.

| Expected Result 6: Enhanced capabilities of NMHSs, in particular in developing and least developed countries and Small Island developing States, to fulfill their mandates |  |  |  |
| --- | --- | --- | --- |
| KO 6.1 | Visibility and relevance of NMHSs in national and regional development agendas is improved, particularly in developing and least developed countries | KPI 6.1.1 | Number of NMHSs with: (a) increased contribution to national policy setting ; (b) improved awareness by users on types of services NMHSs can deliver; (c) improved user accessibility to forecasts and warnings; (d) improved timeliness of forecasts and warnings; and (e) increased accuracy of forecasts and warnings |
|  |  | KPI 6.1.2 | Number of NMHSs with: (a) increased contribution to regional policy setting; (b) improved awareness by regional users on types of services that can be provided by the centre; (c) improved regional user accessibility to forecasts and warnings; (d) improved timeliness of forecasts and warnings delivered from the Regional Centre; and (e) increased accuracy of forecasts and warnings delivered from the Regional Centre |
| KO 6.2 | Infrastructure and operational .facilities of NMHSs and Regional Centres are improved, particularly in developing and least developed countries | KPI 6.2.1 | Number of NMHSs with improved infrastructure and operational facilities |
| KO 6.3 | Education and training development facilities at national and regional levels are improved, especially in developing and least developed countries | KPI 6.3.1 | Number of institutions providing education and training support for GFCS related activities |
|  |  | KPI 6.3.2 | Degree to which Members are getting value for money from the WMO Fellowship Programme |
|  |  | KPI 6.3.3 | Degree of Member satisfaction with the Regional Training Centres (RTCs) in use |
| KO 6.4 | Capacities of NMHSs are enhanced through cooperation and partnerships with other national and regional organizations | KPI 6.4.1 | Development projects and activities funded through voluntary contributions |

  - 6.2 Infrastructure and operational facilities of NMHSs and regional centers are improved, particularly in developing and least developed countries.

1.	Improve data availability and quality of observing in RA II especially in West/South West Asia and South & South East Asia

The recent organizational developments in the field of air traffic managements and regulations in some regions amongst that controversial proposal for AeM service provision are to be open for competition. Should this proposal be implemented by them, there will be cascading impacts in our Region. To this effect, in addition to the new/ICAO driven requirement of QMS, Competencies etc., the center providing aviation or marine service should possess some prerequisites. The technical commission should develop some guidelines similar to RSBN & RBCN Networks for Aviation and Marine Centers also.

For Ex : For an aviation center:

    - The center should be WIS compliant.

    - Equipped with Operational Weather Radar.

    - Satellite data reception capability of every 15 minutes.

    - Should satisfy the requirement defined for High Res NWP & Nowcasting capability according to the OSCAR database.

| Expected Result 7: New and strengthened partnerships and cooperation activities to improve NMHSs' performance in delivering services and to demonstrate the value of WMO contributions within the United Nations system, relevant regional organizations, international conventions and national strategies |  |  |  |
| --- | --- | --- | --- |
| KO 7.1 | WMO leadership and contribution in relevant UN system and other international partners' initiatives and programmes is improved | KPI 7.1.1 | Number of reports of WMO and its co- sponsored programmes submitted to UN and other international conventions , particularly the UNFCCC, UNCCD and UNCBD |
|  |  | KPI 7.1.2 | Number of contracts/cooperation agreements within which WMO is engaged with partners |
|  |  | KPI 7.1.3 | Number of NMHSs implementing projects with the UN and other international and/or regional organizations |
| KO 7.2 | Public, decision-makers and other stakeholders are increasingly aware of key WMO and NMHSs issues, activities and priorities through enhanced communication | KPI 7.2.1 | Uptake of WMO public information outputs as measured by: (a) number of unique visitors on the WMO website; (b) number of times WMO was mentioned in press articles; (c) number of Facebook fans; and (d) number of Twitter followers |
|  |  | KPI 7.2.2 | Degree to which NMHSs make use of WMO public information outputs |
|  |  | KPI 7.2.3 | Number of NMHSs that have provided training to senior managers and/or communication officers in media relations, social media or other aspects of communication |

| Expected Result 8: Promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources |  |  |  |
| --- | --- | --- | --- |
| KO 8.1 | Effective and efficient WMO Congress and EC | KPI 8.1.1 | Degree of Member satisfaction with documentation for Cg, EC and its working groups |
|  |  | KPI 8.1.2 | Degree of Member satisfaction with supporting services for Cg and EC (interpretation , conference activities and facilities) |
|  |  | KPI 8.1.3 | Decrease in the total cost of sessions held under similar conditions |
| KO 8.2 | An effective and efficient Organization | KPI 8.2.1 | Percentage of implemented accepted oversight recommendations for improved business effectiveness on the agreed deadline |
|  |  | KPI 8.2.2 | Unqualified opinion of the external auditor in the financial period |
|  |  | KPI 8.2.3 | Increase in the efficiency of fulfilling requirements for linguistic and publishing services |
|  |  | KPI 8.2.4 | Issuance of statements of internal control in the financial period |
| KO 8.3 | Effective and efficient constituent bodies (RAs and TCs) | KPI 8.3.1 | Degree of Member satisfaction with constituent body documentation |
|  |  | KPI 8.3.2 | Degree of Members satisfaction with constituent body supporting services (interpretation, conference services and facilities) |
|  |  | KPI 8.3.3 | Decrease in the total cost of constituent body sessions held under similar conditions |
| 8.4 | Gender equity across WMO | 8.4.1 | Proportion of men/women in WMO constituent bodies |
|  |  | 8.4.2 | Number of men/women granted WMO fellowship/number of total candidates |

Increase in EC seats for RA II is crucial in achieving all Expected Results

ANNEX

PROGRAMMATIC FOCUS TO ACHIEVE EXPECTED RESULTS

1.	Background

The main priorities and focus on the achievement of Expected Results are defined in the WMO Strategic Plan and related decisions and the directions of the Seventeenth World Meteorological Congress (Geneva, 25 May-12 June 2015). The priorities for the Organization are as listed in Table 1.

WMO carries out its work through scientific and technical programmes: namely, the World Weather Watch (WWW), World Climate Programme (WCP), Hydrology and Water Resources Programme (HWRP), Education and Training Programme (ETRP), Voluntary Cooperation Programme (VCP), Regional Programme (RP), Disaster Risk Reduction (DRR) Programme, WMO Space Programme (WMOSP), Aeronautical Meteorology Programme (AeMP), Agricultural Meteorology Programme (AgMP), Marine Meteorology and Oceanography Programme (MMOP), Public Weather Services (PWS) Programme, Tropical Cyclone Programme (TCP), World Climate Research Programme (WCRP), World Weather Research Programme (WWRP), Global Atmosphere Watch (GAW) Programme, WMO Quality Management Framework, Information and Public Affairs Programme, and WMO Programme for the Least Developed Countries. These scientific and technical programmes are designed to assist all Members in providing, and benefiting from, a wide range of meteorological and hydrological services and to address the current and emerging challenges associated with weather, climate, water and related environmental conditions.

The programmes are based on the concept and experience that mutual benefits are gained from cooperative use of the pool of knowledge that has been, and is still being, created by worldwide sharing of meteorological, hydrological and related environmental observations, data and information among Members. WMO Programmes facilitate cost-effective and efficient support to provision of weather, climate, water and related environmental services by all Members. In addition to the scientific and technical programmes are the Executive Management and the Language, Conference and Publishing Services Department (LCP) that ensure efficient operation of the Programmes. The programmes, constituent bodies and departments contributing to each expected result are indicated against each activity.

2.1	Expected Result 1 (ER 1): Improved service quality and service delivery

IV.2  REGIONAL ASSOCIATION II (ASIA)

| Priorities for RA II |  |  |
| --- | --- | --- |
| Priorities in 2012-2015 |  | Priorities in 2016-2019 |
| Implementation of the WIS/WIGOS and necessary improvement of the GTS |  | Integration of surfaced based remote sensing observation in west south west Asia (WIGOS linked to DRR) |
| Sustainable capacity development including human resources development |  | Capacity building in Radar techniques in west south west Asia. (WIGOS linked to DRR) |
| Implementation of the GFCS in support of agriculture and food security; water; health; and disaster risk reduction, as well as energy and other sectors, through ,but not limited to enhancement and operation of the RA II RCC network and RCOFs |  | Improve data availability and quality of observing in west south west Asia.(WIGOS) |
| Climate services to address the slow-onset impacts of climate variability and climate change |  | Further improvement on capacity in use of satellite data products and facilitation of training datasets and tool boxes. (WIGOS) |
| Establishment of a region-wide multi-hazard early warning system for disaster risk reduction |  | Strengthening Met Areas in RA II and strengthening Aviation centers with the requirement defined for High RES NWP & Now casting capability according to the OSCAR data base and establishment of sub-regional wide muti hazard early warning system (DRR) |
| Implementation of aeronautical meteorological services enhancements in coordination with CAeM and upgrading of service delivery capacity in other application areas including marine meteorological services |  | Establishment of sub-regional RCOFS in South East Asia and South West Asia. (GFCS) |
| Implementation of the WMO flood forecasting initiative, water resources assessment and regional exchange of hydrological data and information; and |  | Adoption of innovative agrometeorological adaptation strategies in face of climate variability and climate change (GFCS) |
| Reduction of risks and impacts of region specific hazards caused by sand and dust storms, thunderstorms and associated extreme weather events |  | % of marine met service providers making marine observations and providing data to support global and regional climate models.(GFCS) |
|  |  | Atmospheric chemistry observations and assessment meet needs of environmental conventions and policy assessments.(GFCS) |
|  |  | Developing/enhancing capacity to provide a consistent levels of met ocean information and drift information in the event of a range of marine environmental incidents including: - Spills of oil and other noxions substance. - Accidents related to objects. - Radioactive material discharges in marine and coastal zones. - Other environmental hazards e.g. harmful algal blooms. (DRR) |

Enhanced capabilities of Members to deliver and improve access to high-quality weather, climate, water and related environmental predictions, information, warnings and services in response to users’ needs and to enable their use in decision-making by relevant societal sectors.

2.1.1	Improved service quality and service delivery will be achieved through the implementation of the Organization-wide Implementation Plan of the Strategy for Service Delivery applied to a number of sectors. Air and marine transport are critical enablers of global trade and economic development. Increasing density in air and marine transport with reduced tolerance for error require continuous improvement. WMO will continue to highlight the necessity to ensure compliance with international standards and promote coherent, seamless and accurate warnings of hazardous weather in collaboration with relevant national organizations (e.g. Civil Aviation Authorities) and international organizations (i.e. the International Civil Aviation Organization - ICAO and International Maritime Organization - IMO). The Agricultural Meteorological Programme will refocus its existing activities to meet the growing demands of users for more targeted weather and climate services.

WMO contributes to the enhancement of the capabilities of Members to deliver high-quality information and services in many ways with a focus on the following key client groups:

  - The general public (through the Public Weather Services Programme);

  - The emergency management sector (through the Disaster Risk Reduction Programme);

  - The aviation industry (through the Aeronautical Meteorology Programme);

  - The marine sector (through the Marine Meteorology and Oceanography Programme);

  - The water sector (through the Hydrology and Water Resources Programme); and

  - The agriculture sector (through the Agricultural Meteorology Programme).

    - The focus during the period 2016-2019 will be on:

- Improving the ability of NMHSs to meet International Civil Aviation Organization (ICAO) requirements by: (i) accelerating the implementation of ICAO/WMO competency standards and Quality Management Systems (QMS); (ii) addressing the emerging needs and challenges associated with the global air navigation plan; and (iii) strengthening cost recovery frameworks;

- Implementing climate services under the GFCS particularly for countries that lack them by: (i) establishing regional climate centres; (ii) identifying user requirements for climate products; and (iii) developing the Climate Services Information System (CSIS);

- Facilitating the sharing of techniques and procedures in support of civil protection, the media and weather-sensitive economic sectors;

- Guiding and assisting Members to maintain their Quality Management Systems (QMS), ensure the competence of aeronautical meteorological personnel by enhancing the current assessment methodologies, increase the available on-line training modules mapped to the competence requirements, and proper documentation personnel assessments;

- Improving the monitoring and issuance of warnings on storm surges, droughts, floods  and coastal inundation;

- Proactively prepare the regulatory basis and methodological support for NMHSs to establish Quality Management System and competencies for personnel serving marine transportation in anticipation of a formal requirement by the IMO;

- Promoting the application of the science of meteorology, climatology, hydrology and related technology to improve products and services through engagement in demonstration projects and other collaborative activities;

- Enhancing Members’ capacity to deliver services by promoting and supporting research into the social and economic impacts of weather services;

- Collaborating with Members to prepare the regulatory basis and methodological support for  NMHSs to establish Quality Management System and competencies for personnel serving hydrological institutions;

- Training staff, particularly from NMHSs in the developing and Least Developed Countries (LDCs), to meet competency requirements for personnel engaged in service delivery;

- Strengthening sub-regional cooperation in AeM;

- Regular review and update of technical regulations and guidance on marine meteorological services

- Assisting NMHSs to assess and demonstrate the benefits of hydrometeorological services;

and

- Implementing the Organization-wide Implementation Plan of the Strategy for Service Delivery.

2.2	Expected Result 2 (ER 2): Reduced Disaster Risk

Enhanced capabilities of Members to reduce risks and potential impacts of hazards caused by weather, climate, water and related environmental elements.

2.2.1	Disaster risk reduction is a key priority for all governments. NMHSs are an integral component of multi-hazard national emergency management systems and work with relevant sectors to develop products and information to support decision-making related to environmental threats. WMO is committed to providing guidance to Members on the provision of authoritative meteorological and hydrological information and advisories, through the Common Alerting Protocol and the Register of Alerting Authorities.

The focus during the period 2016-2019 will be on:

- Improving the effectiveness of high quality impact-based forecasts and multi-hazard early warnings of high impact meteorological, hydrological and related environmental hazards, thereby contributing to international efforts on disaster risk reduction, resilience and prevention;

- Strengthening institutional capacities of NMHSs and networks of specialized centres, such as Regional Specialized Meteorological Centres (RSMCs) and Regional Climate Centres (RCCs), designed to mitigate the threat of natural disasters;

- Facilitating disaster risk analysis and the development of national multi-hazard early warning systems through institutional partnerships to ensure that services are provided and used in a cost effective, systematic and sustainable manner;

- Improving forecasts and warnings using the available best science and technology;

- Improving access to the products and services from the leading global numerical weather prediction centres and to training forecasters in their use, and in verification of their effectiveness through projects such as the Severe Weather Forecast Demonstration Project (SWFDP);

- Ensuring that forecasts and warnings are available to all that need them, and are understood by all those who need to use them in their decision-making;

- Increasing the ability of NMHSs to deliver an effective warning service;

- Emphasizing the need for overall system effectiveness including collection of relevant meteorological data, analyzing the data and preparing accurate forecasts and warnings, delivering timely information to all relevant decisions-makers and to the emergency services organizations;

- Enhancing the uptake of integrated flood and drought management approaches at the national level;

- Working with the insurance industry to develop new products that would assist communities that are highly exposed to extreme weather to insure against possible financial impacts;

- Analyzing extreme climate events, together with climate change scenarios and local conditions, to determine the best disaster risk reduction strategies by involving stakeholders such as disaster risk reduction experts, emergency services managers, climate change scientists, national and local government decision-makers, landholders and economists;

- Improving infrastructure and staff capability of NMHSs in the least developed and developing countries through partnerships with the UN and other international institutions such as the World Bank, regional development banks and UNDP; and

- Enhancing linkage between NMHSs and the broader disaster management community, including UN partners, NGO agencies and the private sector.

2.3	Expected Result 3 (ER 3): Improved Data Processing, Modelling and Forecasting Enhanced capabilities of Members to produce better weather, climate, water and related environmental information, predictions and warnings to support, in particular, reduced disaster risk and climate impact and adaptation strategies.

    - Improved Data Processing and Forecasting emphasizes the need to effectively translate the benefits derived from research into operational products and services toward the needs of, inter alia, agriculture, water and health, and disaster risk reduction. Investments in high performance computing, and data assimilation will allow for more accurate, effective and timely predictions from NMHSs and existing specialized centres.

    - The focus during the period 2016-2019 will be on:

- Continuous improvements in weather prediction by employing improved numerical weather prediction models, including Ensemble Prediction Systems, leading to higher accuracy in forecasts and warnings of high impact weather such as tropical storms, heavy precipitation events or strong winds;

- Continued support to Severe Weather Forecast Demonstration Projects, with the aim of making them operational, as a cost-effective means for testing high resolution models and a practical approach for strengthening capacities through technology transfer;

- Improving climate projections through the implementation of the Global Framework for Climate Services (GFCS) in particular the Climate Services Information System and the User Interface Platform;

- Designing products and services that would promote the delivery of accurate, timely and effective information about climate (past, present and future) to serve complex decision-making across a wide range of climate-sensitive activities and enterprises particularly as relates to the four priority areas of the GFCS, namely disaster risk reduction, water, health and agriculture;

- Strengthening operational (GDPFS) centres, especially regional centres;

- Operational implementation of the GFCS/CSIS;

- Improving water services to support improvements in water resource management, by promoting open access to high quality hydrological data, raising awareness of the range of available hydrological techniques by practitioners and promoting the deployment of effective improved in-situ instrumentation and remote sensing capabilities, such as radar installations and satellites;

- Ensuring that Members have sufficient numbers of competent, capable and skilled human resources to undertake the work required in hydrology and water resources;

- Assisting NMHSs to provide better agrometeorological services to the agricultural community;

- Working with Members to put more agrometeorological data and products on WIS;

- Capacity development through roving seminars, training at RTCs and interactions with other WMO and partner-based capacity-building initiatives;

- Assisting NHSs to develop and maintain relevant infrastructure and human resources for providing data and products with an emphasis on implementing a Quality Management Framework-Hydrology (QMF-H) approach;

- Promoting effective use of hydrological data and information in support of sustainable socio-economic development through linkages with GFCS observational requirements;

- Promoting the World Hydrological Cycle Observing System (WHYCOS) project with emphasis on the use of the hydrological data collected to meet specific purposes and the development of related hydrological products and services;

- Facilitating the rational development and operation of NHSs including staff education and training, increasing public awareness of the importance of hydrological activities, and providing support through technical cooperation activities; and

- Developing guidance materials to assist NHSs in implementing institutional improvements, and building their capacity to assess the economic and social benefits of the services.

2.4	Expected Result 4 (ER 4): Improved Observations and Data Exchange

Enhanced capabilities of Members to access, develop, implement and use integrated and interoperable Earth- and space-based observation systems for weather, climate and hydrological observations, as well as related environmental and space weather observations, based on world standards set by WMO.

    - Improved Observations and Data Exchange addresses the development and improvements in three systems: the WMO Integrated Global Observing System, WMO Information System and WMO’s contribution to the Global Climate Observing System. These programmes support the observational requirements of all WMO Programmes as well as the GFCS, GEOSS, the IPCC and Members’ obligations under a number of international conventions such as, inter alia, the UNFCCC, the UNCCD and the Vienna Convention for the Protection of the Ozone Layer.

    - The focus during the period 2016-2019 will be on:

- Completing the implementation of the WIGOS/WIS to address the observational requirements of all WMO Programmes and partners;

- Assisting Members in the integrated design and standardized operation of national and regional observing systems that support the service delivery objectives;

- Members access to practical guidance and tools for designating, planning and operating integrated observing systems and networks that addresses global standards and support national requirements for weather, climate and water services and information;

- Promoting sound data and metadata management as an essential process for transforming observational data into useful products and services;

- Further development of data discovery, access and retrieval services for all weather, climate, water and related data produced by centres and Members;

- Implementing pilot projects to demonstrate the value of increased cooperation and dialogue between NMSs and NHSs for enhancing hydrological forecast capabilities;

- Improving the HelpDesk for Integrated Flood Management (IFM HelpDesk);

- Improving the efficiency and effectiveness of data and information systems;

- Exploring opportunities for higher integration among observing systems that span domains (e.g., ocean, atmosphere, land) and science disciplines, and that combine in situ observation with remote sensing;

- Addressing standardization of instrument measurements, methods of observation, and end-product quality assurance;

- Enhancing the collection and availability of critical data needed to monitor and predict aspects of the environment, including hazards;

- Improving the quality, traceability and consistency of observations, leading to better products and services;

- Facilitating optimal design of observing networks and their flexibility to incorporate new observing systems;

- Improving the coordination, standardization and evaluation by WMO Members of their national observing networks;

- Improving climate observations for the three domains, namely the Atmosphere, Ocean Land through the co-sponsored GCOS.

2.5	Expected Result 5 (ER 5): Advance Targeted Research

Enhanced capabilities of Members to contribute to and draw benefits from the global research capability for weather, climate, water and related environmental science and technology development.

2.5.1	Research underpins improvements in the prediction of weather, climate, water and related environmental conditions by enhancing our understanding of changes in weather, climate, the hydrological cycle and the chemical composition of the troposphere and stratosphere. This expected result will be pursued through partnerships with national scientific institutions and international organizations such as ICSU and UNESCO, amongst others. The achievements will have a significant contribution to developing user-relevant and user-friendly services for the public, disaster management, economic (marine, aviation) and support the GFCS Pillar on Research, Modelling and Prediction.

    - The focus for the period 2016-2019 will be on:

- Research on high-impact weather on time scales of hours to weeks with specific attention being given to the first few days;

- Improving user-oriented sub-seasonal to seasonal predictions to increase forecast skill on the sub-seasonal to seasonal timescales to inform management decisions, particularly in agriculture and food security, water, disaster risk reduction, energy and health

(c)	Advancing the Subseasonal to Seasonal (S2S) Prediction Project;

(d)	Improving operational meteorological and hydrological monitoring and prediction services in polar and high mountain regions and beyond by: (i) operationalizing the Global Cryosphere Watch (GCW); (ii) better understanding the implications of changes in these regions on the global weather and climate patters, ;and (iii) advancing the Polar Prediction under the Global Integrated Polar Prediction System (GIPPS);

(e)	Advancing services for megacity and large urban complexes to assist societies in urban areas to improve their quality of life, their effective use of resources and to reduce vulnerabilities to impacts of high impact events;

(f)	Improving flood and drought predictions to increase forecast skill on different spatial and time scales to support decision-making in agriculture and food security, water resource management, disaster risk reduction, energy and health sectors;

(g)	Improving early detection and warning of tropical cyclones, floods, draughts, coastal inundation, heat waves, disease outbreaks, and poor air quality, including the waxing and waning of monsoon precipitation;

(h)	Improving flood and drought predictions to increase forecast skill on different spatial and time scales to support decision-making in agriculture and food security, water resource management, disaster risk reduction, energy and health sectors;

(i)	Conducting conferences, workshops, and/or symposiums to engage Members and enhance their awareness on potential benefits of advances in science;

(j)	Identifying and supporting new directions for weather, climate and atmospheric chemistry research to support climate services and assessments, and to meet the needs of the NMHSs and other users of weather, climate and environmental information;

(k)	Accelerating improvements in prediction skill of high-impact weather and in the utilization of weather products to address these events;

(l)	Conducting specialized training on GAW to enhance the capacity of station operators to make high quality GAW observations;

(m)	Assessing GAW observational methods for atmospheric aerosols, developing appropriate quality assurance system and performing process based studies, within the context of WIGOS and WIS;

(n)	Developing new verification techniques focusing on the needs of users across the time and spatial scales applicable to both the weather and climate communities; and

(o)	Enhancing collaboration between CCl and WCRP to work towards constant improvement of climate products and services, especially in the area of climate prediction on seasonal and decadal scales, and also on climate change projections and downscaling.

2.6	Expected Result 6 (ER 6): Strengthened Capacity Development

Enhanced capabilities of Members’ NMHSs, in particular, in developing and least developed countries and Small Island Developing States, to fulfil their mandates.

    - Capacity Development focuses on the need to improve the infrastructure operated by NMHS and develop their institutional and human resources capacity. By achieving this result, the WMO is able to enhance capabilities in the provision of improved weather, water and climate observations and services to support disaster risk reduction, water resource management, sustainable agriculture, and better health outcomes. A major emphasis will be on establishing climate services in those countries and territories in which basic climate services are lacking.

    - The focus for the period 2016-2019 will be on:

- Enhancing the capacity of NMHSs to deliver on their mission by assisting with human resource development, technical and institutional capacities and improved infrastructure, particularly in developing, least developed and small island developing states;

- Implementing WMO Strategy on Capacity Development to empower NMHS institutions and assist them in building effective communication with governments, policy- and decision-makers, and development partners to expand the number of strategic partnerships;

- Scientific, technical and project management training to promote a culture of compliance with international standards and recommended practices;

- Training in agrometeorology and roving seminars for farmers and NMHSs staff to develop climate information, products and services;

- Training and fellowships on observing and information system;

- Training and fellowships on climate and hydrology;

- Capacity Development in AeM, ERA, GDPFS, SWFDP, and TC Forecasting and Warnings;

- Review and implementation of technical regulations and practices;

- Strengthening marine meteorological services and impact-based forecasting;

- Increasing capacity of NMHSs and Regional Centres, especially in developing and least developed countries, to develop and apply weather-, climate- and water-related information and products to support climate change adaptation in their countries;

- Support to GFCS implementation;

- Assessing and addressing Members training needs, including, professional training and development, technical training, project development and management training;

- Increasing assistance for training through WMO Fellowships Programme and other mechanisms;

- Support to educational institutions in the development and application of their curricula and their scientific and technological skills;

- Fostering, as appropriate, regional, sub-regional and national cooperation and institutional framework towards improving weather, water and climate observing and monitoring infrastructure and operational facilities of NMHSs and Regional Centres, particularly in developing and least developed countries;

- Enhancing resource mobilization in support of capacity development;

- Increasing capacity through human resources development in NMHSs to support climate change adaptation in their countries by providing more sustainable training mechanisms;

- Promoting the application of climate information, such as seasonal outlooks, for adaptation to climate change and variability;

- Encouraging capacity development through RCCs, RCOFs and the associated user forums;

- Developing and disseminating a toolkit to support climate services training activities; and

- Continued implementation of Severe Weather Forecast Demonstration Projects (SWFDPs).

2.7	Expected Result 7 (ER 7): Strengthened Partnerships

New and strengthened partnerships and cooperation activities to improve NMHSs’ performance in delivering services and to demonstrate the value of WMO contributions within the United Nations system, relevant regional organizations, international conventions and national strategies.

2.7.1	Partnerships will focus on opportunities for cooperation on the priorities outlined in the plan without compromising relationships that support other areas of WMO’s mandate. WMO will foster enhanced partnerships with co-sponsors of WCRP, GCOS and the IPCC to achieve shared interests. WMO will improve NMHSs’ performance in delivering services as authoritative sources of weather, water and climate services and demonstrate the value of its contribution to the broader agenda of the United Nations, particularly to sustainable development, climate change mitigation and adaptation, gender equality, human rights and rule of law.

    - In the period 2016-2019 WMO will focus on:

- Monitoring partnerships to establish their continued relevance and effectiveness;

- Exploring concrete ways for furthering collaborations with the economic sector through UN Global Compact, the World Economic Forum and the World Business Council for Sustainable Development;

- Consolidating relationships with its partners using the GFCS mechanisms, e.g. the Inter-Agency Coordination Group (ICG) and the Partner Advisory Committee (PAC) together with the Intergovernmental Board on Climate Services (IBCS);

- Contributing to the implementation and follow-up processes of major international programmes of action (for example, on disaster risk reduction, on adaptation, on LDCs, capacity development and on women);

- Monitoring jointly sponsored programmes or bodies, such as IPCC, WCRP and GCOS, through specific agreements with relevant partners (for example, UNESCO-IOC, ICSU, UNEP);

- Developing outreach, in particular on the Internet, using collaborative platforms as well as social media to enhance weather, climate and water knowledge base in a demand-driven and user-oriented perspective;

- Promoting the contribution of operational hydrology and water-related climate services to integrated water resources management at the basin/catchment scale around the world;

- Implementing the Associated Programme on Flood Management (APFM) and the Integrated Drought Management in collaboration with the Global Water Partnership (GWP), the United Nations Convention to Combat Desertification (UNCCD) and the Food and Agricultural Organization (FAO);

- Assisting countries to establish and implement National Drought Policies, based on sound scientific understanding and guidance;

- Supporting countries to apply the Integrated Flood Management concept and providing guidance and advice on flood plain management actions;

- Developing and implementing ISO quality assurance standards for the management of both air and maritime operations;

- Developing and maintaining strategic partnerships with UN agencies such as UNDP, UNISDR, UNEP-FI, WFP, international and regional development agencies and banks, regional socio-economic groupings, humanitarian community, and the private sector associations in areas such as risk transfer (e.g., insurance, reinsurance) that assist NMHSs to better undertake their national roles in disaster risk reduction;

- Assisting developing countries to build their risk reduction capability;

- Assisting NMHS to establish partnerships with Disaster risk Management Agencies, and various socio-economic sectors affected by natural hazards such as agriculture, energy, water resource management, finance and planning, as well as statistical bureaus collecting loss and damage data with emergency management organizations so as to promote closer relationships between these organizations and the NMHSs;

- Supporting the Group on Earth Observations (GEO) process and contributing to the implementation of the Global Earth Observation System of Systems (GEOSS) to the extent possible within the WMO mandate;

- Publishing WMO Bulletin twice a year in English, French, Russian and Spanish;

- Implementing IPA Strategy;

- Implementing gender mainstreaming activities; and

- Continued support to IPCC.

2.8	Expected Result 8 (ER 8): Improved Efficiency and Effectiveness

Promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources.

2.8.1	Improved Effective and Efficient Organization seeks to ensure robust oversight of the programmes and financial management of the Organization and accountability to Members. This includes developing a coherent Strategic Plan, Operating Plan, Results-based Budget and a Monitoring and Evaluation system that integrates activities of all parts of the Organization, including governing and constituent bodies, and the Secretariat. High quality, affordable language, conference and publishing services will be provided to WMO Members through the production of publications and the delivery of conference services in an appropriate number of working languages as defined by Congress to facilitate decision-making. WMO will also continue to implement risk management as an integral part of its system of internal control and results-based management, and promote Quality Management Systems in NMHSs and within the WMO Secretariat for efficient and effective use of resources.

The focus in 2016-2019 will be on:

- Conducting a strategic review of WMO structures, operating arrangements and budgeting practices focusing on the effectiveness of constituent body activities and the Secretariat arrangements;

- Improving the efficiency and effectiveness of governing and constituent bodies;

- Promoting open and transparent business processes, efficient and effective use of resources, and equitable treatment of all parties;

- Enhancing the efficiency of the WMO Secretariat and fostering climate-friendly operations;

- Ensuring the integrity of WMO management systems;

- Improving the connection between the Organization’s strategic priorities and initiatives, programmes and budget, through results-based management systems and practices;

- Conducting a comprehensive review of structures, programmes and priorities and implementing the relevant findings;

- Promoting gender equality and empowerment of women across the Organization and NMHSs;

- Promoting the culture of compliance with WMO regulations and standards, and fostering the rule of law;

- Improving support services, a key factor in efficient functioning of constituent bodies, by providing for translation, interpretation, and meeting planning functions;

- Improving the efficiency, effectiveness and transparency of the programmatic and financial management of the Organization to allow an appropriate level of management and financial control;

- Continued implementation of ERM and WMO RBM, based on WMO SP, WMO OP, Results-based Budget (RBB), WMO M&E, WMO Risk Management Policy and WMO Risk Management Framework, to increase the confidence and commitment of Members in supporting the Organization;

- Providing guidance on strategic planning to developing and least developed countries;

- Engaging in UN initiatives promoted by the CEB to heighten its standards in domains such as the greening of the Organization and the development of quality assurance;

- Increased involvement of internal oversight (either of assurance or a consulting nature) in governance, risk management, and control;

- Providing high quality and affordable language, conference and publishing services;

- Improving linguistic and publications services;

- Providing high-quality conference, procurement, travel and common services; implementing WMO Policy on Gender Mainstreaming and the incorporation of gender aspects in relevant programmes and activities; and

- Supporting the implementation of GFCS activities.

# List of Acronyms and Abbreviations

ADM		Advanced Dissemination Method

AEM		Aeronautical Meteorology Division

AeMP		Aeronautical Meteorology Programme

AG		Advisory Group

AgM		Agricultural Meteorology Division

AgMP		Agricultural Meteorology Programme

AMDAR		Aircraft Meteorological Data Relay

AMMA		African Monsoon Multidisciplinary Analysis

APSDEU		Asia-Pacific Satellite Data Exchange and Utilization Meeting

ASG		Assistant Secretary-General (WMO)

BIPM		Bureau International des Poids et Mesures

BSH		Basic Systems in Hydrology

CAeM		Commission for Aeronautical Meteorology

CAgM		Commission for Agricultural Meteorology

CAS		Commission for Atmospheric Sciences

CBH		Capacity Building in Hydrology

CBS		Commission for Basic Systems

CCA		Climate Coordination Activities

CCl		Commission for Climatology

CDMS		Climate Data Base Management System

CEOP		Coordinated Enhanced Observing Period

CEOS		Committee on Earth Observation Satellites

CER		Cabinet and External Relations (Department, WMO)

Cg		WMO Congress

CGMS		Coordination Group for Meteorological Satellites

CHy		Commission for Hydrology

CIMO		Commission for Instruments and Methods of Observation

CLIPS		Climate Information and Prediction Services

CLW		Climate and Water (Department, WMO)

CLIVAR		Climate variability and predictability study (WCRP)

COP		Conference of the Parties

COPUOS		United Nations Committee on the Peaceful Uses of Outer Space

CWI		Programme on Cooperation in Water-related Issues

DRA		Development and Regional Activities (Department, WMO)

DRR		Disaster Risk Reduction Programme

DSG		Deputy Secretary-General

EC		Executive Council (WMO)

EPAC		Environmental Pollution and Atmospheric Chemistry

ERA		Emergency Response Activities

ESCAP		Economic and Social Commission for Asia and the Pacific (UN)

ET		Expert Team

ETRP		Education and Training Programme

FAH		Programme on Forecasting and Applications Hydrology

FAO		Food and Agriculture Organization of the United Nations

GAW		Global Atmosphere Watch

GCN		GLOSS (Global Sea-Level Observing System) Core Network

GCOS		Global Climate Observing System

GDPS		Global Data-processing System

GEO		Group on Earth Observations

GEOSS		Global Earth Observation System of Systems

GEWEX		Global Energy and Water Cycle Experiment (WCRP)

GMDSS		Global Maritime Distress and Safety System

GOOS		Global Ocean Observing System

GOS		Global Observing System

GSICS		Global Space-based Inter-calibration System

GTN-H		Global Terrestrial Network-Hydrology

GTOS		Global Terrestrial Observing System

GTS		Global Telecommunication System

GUAN		GCOS (Global Climate Observing System) Upper-Air Network

HFA		Hyogo Framework for Action

HFW		Hydrological Forecasting for Water Resources Management

HNRC		HOMS National Reference Centres

HOMS		Hydrological Operational Multipurpose System

HYCOS		Hydrological Cycle Observing System (component of WHYCOS)

HWRP		Hydrology and Water Resources Programme

IACRNA		Inter-Agency Committee on Response to Nuclear Accidents

IAEA		International Atomic Energy Agency

IASC		International Arctic Science Committee

ICAO		International Civil Aviation Organization

ICSU		International Council for Science

ICT		Implementation/Coordination Team

IFRC		International Federation of Red Cross and Red Crescent Societies

IGACO		Integrated Global Atmospheric Chemistry Observations (strategy)

IGDDS		Integrated Global Data Dissemination Service

IGOS		Integrated Global Observing Strategy

IGWCO		Integrated Global Water Cycle Observations

IMOP		Instruments and Methods of Observation Programme

IOC		Intergovernmental Oceanographic Commission (UNESCO)

IOO		Internal Oversight Office

IPCC		Intergovernmental Panel on Climate Change (WMO/UNEP)

IPM		Informal Planning Meeting

IPWG		International Precipitation Working Group

IPY		International Polar Year

IRI		International Research Institute for Climate and Society

IROWG		International Radio-Occultation Working Group

ISCU		International Council for Science

ISDR		International Strategy for Disaster Reduction

ISO		International Organization for Standardization

ISS		Information Systems and Services

ITWG		International A-TOVS Working Group

IWRM		Integrated Water Resources Management

JCOMM		Joint WMO/IOC Technical Commission for Oceanography and Marine Meteorology

JSC		Joint Scientific Committee (WCRP)

LC		Legal Counsel

LDC		Least Developed Country

LCP		Language, Conference and Publishing Services (Department, WMO)

MDG		Millennium Development Goal

MG		Management Group

MMOP		Marine Meteorology and Oceanography Programme

MPERSS		Marine Pollution Emergency Response Support System

NAEDEX		North America-Europe Data Exchange meeting

NGO		Non-governmental organization

NHS		National Hydrological Service

NMC		National Meteorological Centre

NMHS		National Meteorological and Hydrological Service

NMS		National Meteorological or Hydrometeorological Service

NWP		Numerical Weather Prediction

OBS		Observing and Information Systems (Department, WMO)

OC		Overall Coordination of WMO Scientific and Technical Programmes

OCHA		United Nations Office for the Coordination of Humanitarian Affairs

OPAG		Open Programme Area Group

PMO		Policy Making Organs (WMO)

PPR		Programme Performance Report

PR		Permanent Representative

PWS		Public Weather Services Division

PWSP		Public Weather Services Programme

QMF		Quality Management Framework

RA		Regional Association

R&D		Research and Development

REM		Resource Management (Department, WMO)

RICs		Regional Instrument Centre

RMDP		Resource Mobilization and Development Partnerships

RP		Regional Programme

RRCs		Regional Radiation Centre

RSMC		Regional Specialized Meteorological Centre

RTC		Regional Training Centre

SBSTA		Subsidiary Body for Scientific and Technological Advice (UNFCCC)

SCHOTI		Standing Conference of Heads of Meteorological Training Institutions

SFCG		Space Frequency Coordination Group

SG		Secretary-General

SIDS		Small Island Developing State

SOP		Secretariat Operating Plan

SP		Strategic Plan

SSA		System Support Activity

TC		Technical Commission

TCP		Tropical Cyclone Programme

TCOP		Technical Cooperation Programme

TECO		Technical Conference on Meteorological and Environmental Instruments and Methods of Observation

TF		Trust Fund

TFSP		Task Force on Seasonal Prediction

THORPEX		Hemispheric Observing System Research and Predictability Experiment

TMT		Training Management Team

TOR		Terms of Reference

UN		United Nations

UNCBD		United Nations Convention on Biological Diversity

UNCCD		United Nations Convention to Combat Desertification

UNDP		United Nations Development Programme

UNEP		United Nations Environment Programme

UNESCO		United Nations Educational, Scientific and Cultural Organization

UNFCCC		United Nations Framework Convention on Climate Change

UNOOSA		United Nations Office for Outer Space Affairs

UNICEF		United Nations Children’s Fund

UNOSAT		United Nations Institute for Training and Research Operational Programme on Satellite Applications

UNWTO		United Nations World Trade Organization

VACS		Variability of the African Climate Systems

VCP		Voluntary Cooperation Programme

VL		Virtual Laboratory

WAFS		World Area Forecast System

WAMIS		World Agrometeorological Information Service

WB		World Bank

WCAC		World Climate Applications and CLIP (Division, WMO)

WCASP		World Climate Applications and Services Programme

WCDMP		World Climate Data and Monitoring Programme

WCP		World Climate Programme

WCRIP		World Climate Assessment and Response Strategies Programme

WCRP		World Climate Research Programme

WDM		WWW Data Management

WG		Working Group

WGNE		Working Group on Numerical Experimentation

WG-PIW		Working Group on Planning and Implementation of the WWW

WHYCOS		World Hydrological Cycle Observing System

WIGOS		WMO Integrated Global Observing System

WIS		WMO Information System

WMC		World Meteorological Centre

WMO		World Meteorological Organization

WMOSP		WMO Space Programme

WOAP		WCRP Observation and Assimilation Panel

WFP		World Food Programme

WRC		World Radiation Centre

WRI		Programme on Water-related Issues

WSSD		World Summit on Sustainable Development

WWRP		World Weather Research Programme

WWW		World Weather Watch

__________

* 	In MS Word 2007 or 2003, go to “View” > “Document Map”.  In MS Word 2010, go to “View” > “Navigation Pane”.  
In MS Word on a Mac, go to “View” > “Navigation Pane”, select “Document Map” in the drop-down list on the left.