| World Meteorological Organization Commission for Basic Systems Management Group, seventeenth Session Geneva, 27 February - 1 March 2017 | [CBS-MG-17]/Doc. 4.4 |
| --- | --- |
|  | Submitted by: G. Fleming 20.Feb.2017 DRAFT 2 |

# Proposed Membership of the OPAG-PWSD teams

# and their work plans

### SUMMARY

This document provides proposals from the OPAG PWSD Chair, Gerald Fleming (Ireland), and co-Chair, Dmitry Kiktev (Russian Federation) concerning (i) the membership of the OPAG-PWSD Expert Teams and (ii) their work plans.

### DECISIONS/ACTIONS REQUIRED:

The Management Group is invited to decide on the following:

- Membership of the OPAG-PWSD Teams

- Work plans of the OPAG-PWSD Teams

### REFERENCES:

- Approved documents of CBS-16, and particularly document CBS-16-d05-10(1)-CBS-WORKING-STRUCTURE-approved_en.docx

### ANNEXES:

- Proposed membership of the OPAG-PWSD teams

- Proposed work plans of the OPAG-PWSD teams

# __________

## Annex 1

### Proposed membership of the OPAG-PWSD Expert Teams

| Team | Name | Country | Role |
| --- | --- | --- | --- |
| ICT-PWSD | FLEMING | Ireland | Chairperson |
| ICT-PWSD | KIKTEV | Russian Fed. | Co-Chairperson |
| ICT-PWSD | LANG | United Kingdom | Chair ET-SPII |
| ICT-PWSD | JACKS | United States of America | Chair ET-IMPACT |
| ICT-PWSD | MILTON | Canada | Coordinator |
| ICT-PWSD | CACIC | Croatia | Coordinator |
| ET-SPII | LANG | United Kingdom | Chairperson |
| ET-SPII | LI | China | Co-Chairperson |
| ET-SPII | TANAKA | Japan | Core Member |
| ET-SPII | CHEN | Hong Kong China | Core Member |
| ET-SPII | HAGEDORN | Germany | Core Member |
| ET-SPII | RYAN | Ireland | Core Member |
| ET-SPII | MORGAN | Australia | Core Member |
| ET-SPII | KOCH | United States of America | Core Member |
| ET-SPII | DUDLEY | Canada | Core Member |
| ET-SPII | SABAI | Morocco | Core Member |
| ET-SPII | PORTILLO | Spain | Core Member |
| ET-SPII | LIU | China | Associate Member |
| ET-IMPACT | JACKS | United States of America | Chairperson |
| ET-IMPACT | LEE | Hong Kong, China | Co-Chairperson |
| ET-IMPACT | MILTON | Canada | Core Member |
| ET-IMPACT | DAVIES | United Kingdom | Core Member |
| ET-IMPACT | CHEN | China | Core Member |
| ET-IMPACT | WANG | China | Core Member |
| ET-IMPACT | HONORÉ | France | Core Member |
| ET-IMPACT | GOOLAUP | Mauritius | Core Member |
| ET-IMPACT | NOBLE | New Zealand | Core Member |
| ET-IMPACT | CERRUDO | Argentina | Core Member |
| C-CF | MILTON | Canada | Coordinator |
| C-RAL | CACIC | Croatia | Coordinator |

__________

### Annex 2

### PROPOSED WORK PLANS OF THE OPAG-PWSD EXPERT TEAMS AND COORDINATORS

### FOR THE COMING CBS INTER-SESSIONAL PERIOD 2017-2020

ICT/PWS Team Deliverables and Action sheets for the intersessional period 2014/2016

(Updated FEB 2017)

|  | Deliverable 1 (TOR a): Noting the publication of the “WMO Strategy for Service Delivery and its Implementation Plan”, ensure that actions relevant to PWS are carried out |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Initiating the discussion on the re-alignment of the OPAG with the elements of Service Delivery | All ICT Members |  | 6 June 2014 |  | Done |  | Done |  |
| 2. | Review and finalize draft TORs to reflect the re-alignment in 1 above | All ICT/PWS Members |  | Forthcoming ET Meetings |  |  |  | To be Done |  |
| 3. | Present the draft TORs to CBS-16 | OPAG Chair and Secretariat |  | 2016 |  |  |  | To be Done |  |
|  | Deliverable 2 (TOR c): Establish contact with relevant people in other CBS OPAGs, Commissions, etc., as required |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Contact Chairpersons of OPACE III/IV to explore possible collaboration | Chairperson |  | June 2012 |  | Closed |  | Closed |  |
| 2. | Contact representatives of CHy to explore possible collaboration | Chairperson |  | June 2012 |  | Closed |  | Closed |  |
|  | Deliverable 3 (TORs c and d): Facilitate the development of one or a number of “one-stop-shops” for the provision of advice and assistance to the Humanitarian Response Community |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Finalize the Report of the ICTT and circulate as required | Chairperson/TT |  | End-2012 |  | Completed |  | Completed |  |
| 2. | Prepare an inventory of data and products that are currently available and can be used by Humanitarian Response agencies | Chairperson/TT and WMO Secretariat |  | End-2012 |  | Undertaken through the work of the new CBS TT |  | Completed ?? |  |
| 3. | Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | WMO Secretariat |  | End-2012 |  | Completed |  | Completed |  |
| 4. | Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of National PWS Focal Points as a resource in the context of national operations of Humanitarian Response agencies | Chairperson/TT and WMO Secretariat |  | End-2012 |  | PWS will organize the work of interpretation of climate outlooks of major global centre(s) for the use by Humanitarian agencies. |  | Ongoing / underway |  |
|  | Deliverable 4 (TOR e): Promote the concept of NMHSs as the Single Official Voice at times of severe/high-impact weather |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Make use of the new “WMO Register of Alerting Authorities” to promote and embed the SOV concept | Chairperson/OPAG and WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 2. | Designate an Expert Advisor to assist with the implementation of CAP at NMHSs and to promote registration of Members in the “WMO Register of Alerting Authorities” | ICT Members/ WMO Secretariat |  | May 2012 |  | Completed |  | Completed |  |
| 3. | Ensure inclusion of this principle in all relevant PWS documents | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
|  | Deliverable 5 (TOR f): Detailed feedback from recipients of targetted PWS activities, such as SWFDP, Learning-Through-Doing (LTD) Projects, training, etc. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Organize the collection and analysis of feedback from training participants and PRs | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 2. | Collate information flowing back from the feedback mechanisms built into the SWFDP and publish on the PWS Website | Co-Chairperson/OPAG and WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 3. | Organize the reception of bi-annual reports from Members participating in LTD Projects (through Focal Points where possible) and publish on the PWS Website | WMO Secretariat |  | Ongoing |  | Completed |  | Completed |  |
|  | Deliverable 6 (TOR g): Develop a Competency Framework for PWS Forecasting and Activities. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Draft a Competency Framework relevant to PWS Forecasters and circulate to all ICT Members, ETR Representatives, etc. | Chairperson |  | May 2012 |  | Completed |  | Completed |  |
| 2. | Review draft and provide feedback to WMO Secretariat/ Chairperson | All ICT Members |  | July 2012 |  | Completed |  | Completed |  |
| 3. | Finalize PWS Competency Framework for CBS-Ext.(2014) | WMO Secretariat/ Chairperson |  | September 2014 |  | Completed |  | Completed |  |
|  | Deliverable 7 (TOR h): Develop materials on the Social and Economic Benefits of NMHSs as decided by the RA VI (Europe) Task Team and the World Bank Project. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Compile and carry out comparative analysis of the impact of the services provided by NMHSs through socio-economic benefits studies | RA VI TT on socio-economic benefits/ World Bank |  | Mid- to end-2012 |  | Ongoing development through the joint WMO/World Bank publication |  | Completed |  |
| 2. | Improve methodologies in SEB studies through concurrent field testing and training as part of specific demonstration/pilot projects as well as on-going NMHSs’ investment programmes | World Bank/ WMO Secretariat |  | End-2012 through 2013 |  | Ongoing development through the joint WMO/World Bank publication |  | Completed |  |
| 3. | Disseminate an authoritative joint WMO-World Bank guidance document | WMO Secreatiat/ World Bank |  | December 2014 |  | Will be disseminated upon publication |  | Completed |  |
|  | Deliverable 8 (TOR i): Future activities as a follow-up to WENS |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Finalize “Concept Note” developed in Shanghai in November 2011 regarding the follow-up activities to WENS | Dr Tang Xu |  | End-2012 |  | Completed |  | Completed |  |
| 2. | Implement follow-up activities as defined in the “Concept Note” | Persons as defined in the “Concept Note” |  | Mid-2013 |  | Closed |  | Closed |  |
| 3. | Prepare publications, etc., as outlined in Section 12 of the WENS Final Report | Shanghai Meteorological Service (SMS) |  | End-2012 |  | Closed |  | Closed |  |
|  | Deliverable 9 (TOR i): Guidelines for Meteorological Support to Olympic Games. |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Review current draft and bring it up-to-date, include the Beijing and Vancouver Games, then provide to IOC and other sporting organizations as appropriate, and publish on PWS Webpage |  | Chairperson ET/SPI/ WMO Secretariat |  | September 2014 |  | Chair ET/SPII to follow-up |  | Ongoing |
|  | Deliverable 10 (TOR j): Strengthen the involvement of the NMHSs’ PWS Focal Points with the work of the OPAG and of the PWS Programme |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Update the list of National PWS Focal Points periodically |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 2. | Request PRs to appoint National PWS Focal Points in Member countries where none are, as yet, identified |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 3. | Carry out a regular survey of the work of the National PWS Focal Points in relation to PWS functions and publish the results |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 4. | Keep National PWS Focal Points fully involved and informed in the activities of the PWS Programme and of the OPAG |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
|  | Deliverable 11 (TOR j): Market and promote the availability and use of PWS material among the NMHS/PWS Community |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Periodically review statistics on the hits and usage of PWS pages on the WMO Website |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 2. | Continue to implement strategies for increasing the ease of access to PWS pages through Google and other search engines |  | WMO Secretariat |  | Ongoing |  | Done |  | Ongoing |

Public Weather Services (PWS) Expert Team on Meeting User Needs in Reducing the Impact of Hydrometeorological Hazards (CBS/OPAG-PWS ET/DPM) AND THE TASK TEAM ON IMPACT OF MULTI-HAZARD PREDICTION AND COMMUNICATION (TT/IMPACT)

(SHANGHAI, CHINA, 27 JUNE-1 JULY 2016)

Team Deliverables

| (Item 6.0)Building on the WMO Guidelines on Multi-hazard Impact-Based Forecast and Warning Services (WMO No. 1150), develop an implementation strategy which describes next actionable steps and evolution Deliverable 1: A stakeholder workshop to plan and design the implementation plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Action(s): |  | Responsible Member(s): | Due Date: | Status: |
| 1. | Identify and contact the stakeholders: DRM rep, Media, Business sector, e.g., utilities, health, transport etc, social science, GFDRR (WBG), and the team members |  | Haleh and Paul | End July 2016 |  |
| 2. | Organize the workshop |  | Haleh | 7-11 (week), Geneva |  |
| 3. | Report to CBS |  |  | End November 2016 |  |
| 4. | Publish the guidance material |  | Haleh and all | End 2017 |  |
| Agneda item 6.1:Training and competencies in impact-based forecasting and warning services Deliverable 2: |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Review of the PWS competecy Framework to identify gaps in the area of IBF | Jennifer Paul |  | End July 2016 |  |
| 2. | Identify existing training materials supporting the development of competencies | Jennifer All |  | End October 2016 |  |
| 3. | At the Workshop review all material on competency and training | Jennifer All |  | End of Workshop |  |
| Agneda item 6.2: Verification and evaluation of benefits of impact-based forecasts and warnings to social and economic sectors Deliverable 3 : Prepare a template based on items identified by the team (Appendix) |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Prepare the template for presentation at the workshop | Paul Jeff |  | End October 2016 |  |
| Agenda item 6.4 : Development/strengthening of relationships with partners, in particular disaster management agencies Deliverable 4: |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Prepare a poster or paper for presentation at CBS | Albrecht Baode Paul |  | Mid November 2016 |  |
| Agenda item 6.5 :Targeted thresholds for users (to be linked to verification item) Deliverable 5: A Framework (template) for cataloguing impact thresholds |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Draft to be developed for inclusion into the implementation plan | Eli To be reviewed by all |  | July 2017 |  |
| Agenda item 6.7 : Science and technology requirements to support impact-based forecasting and warning services Deliverable 6: Keep track of requirements from modellers and research |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Establish initial contacts with relevant TCs, NMHSs and WMO Programmes to make sure requirements are collected and taken into consideration (HiWeather, forecasting) | Haleh All |  | End October 2016 |  |

PUBLIC WEATHER SERVICES EXPERT TEAM ON SERVICES AND PRODUCTS InnovaTION AND IMPROVEMENT(cbs/opag-pws ET-SPIi)

Team Deliverables

(Exeter, UK, 11-15 July 2016)

| DELIVERABLE 1: PUBLISH GUIDANCE ON THE ADOPTION OF A SERVICE-DRIVEN APPROACH TO DEVELOPMENT OF NOWCAST SYSTEMS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actions: | Responsible Member(s): |  | Due Date: |  | Status: |
| 1. | Finalise guidance developed for members at different levels of capability to assist in applying a service driven approach to the development of nowcast systems. | Lead: WL |  | 30/8/16 |  | Done |
| 2. | Circulate final report to all WMO Members, specific groups, organisations involved in development of nowcasting services. | HK |  | 31/12/16 |  | Done |
| DELIVERABLE 2: COORDINATE WITH ET-IMPACT TO DEVELOP GUIDANCE ON USING AND COMMUNICATING UNCERTAINTY IN IMPACT-BASED FORECASTING |  |  |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: |  | Status: |  |
| 1. | Assemble examples and best practice of applying uncertainty information for use in impact-based forecasting, for example translation of percentage probabilities into scenarios for use in decision making for emergency planning and response. | WL | 31/3/17 |  | Ongoing |  |
| 2. | Contribute to ET-IMPACT enhanced guidelines on impact-based forecasting | WL/Chair ET-IMPACT | 31/9/17 |  | Ongoing |  |
| DELIVERABLE 3: ENHANCEMENT OF WWIS AND SWIC WEBSITES |  |  |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: |  | Status: |  |
| 1. | (a) Discuss with ECMWF in acquiring ENS data for use in WWIS forecast compilation; (b) Write to selected PRs requesting forecast of 5-days at least and the use of ECMWF ENS data to fill the gaps otherwise; (c) Develop and launch the revamped WWIS website with observational data with responsive design (d) Develop and launch the revamped MyWorldWeather app for the WWIS (e) Incorporate in WWIS CAP-based warnings currently available on the public domain f) Check availability of CAP/XML warnings from Philippinnes, Meteoalarm, JMA (g) Revamp the SWIC website to incorporate CAP-based warnings (h) Gather information on the status of the development of WMO Alert-hub by NOAA (contact Mr Paese, NOAA/NESDIS) | - AC - HK - AC - AC - AC - HK/WL/YT - AC - JG | - 30/9/16 - 31/12/16 - 31/3/17 - 30/6/17 - 31/12/17 - 30/8/16 - 30/6/18 h) 30/8/16 |  | Ongoing |  |

| DELIVERABLE 4: UTILISATION OF ‘BIG DATA’ FOR MONITORING, IMPACT ASSESSMENT AND DECISION-MAKING IN PWS DELIVERY |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Collect and share (with TT below), through individual contacts, examples of different approaches to use of crowdsourced observations, impacts and behavioural data amongst NMHSs. | AC to lead, all contribute | 31/10/16 | Done |
| 2. | Investigate and propose possible experts as potential members of a Task Team. (AC member) | All | ASAP | Done |
| 3. | Create Task Team from subject-matter experts to study and propose a strategy for PWS in utilisation of Big Data. | Chair ET/SPII | 31/10/16 | Done |
| 4. | Task Team to report on the results of its work to ET/SPII | TT | 30/8/17 | Ongoing |
| DELIVERABLE 5: EXPLOITING PUBLIC/PRIVATE PARTNERSHIPS FOR PUBLIC WEATHER SERVICE DELIVERY |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Create Task Team to work with relevant bodies on formulating a strategy for PWS exploitation of Public Private Partnerships (PPPs), and influence ‘rules of engagement’ for PPPs as proposed by EC 68. | Chair ET/SPII | 30/9/16 | Done |
| 2. | Task Team to report on the results of its work to ET/SPII. |  | 30/4/17 | Ongoing |
| 3. | ET to investigate and propose possible experts and potential members of the Task Team. | All | Asap | Done |
| DELIVERABLE 6: IMPROVING PWS DELIVERY THROUGH LINKING WITH OPAG-DPFS |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1 | Formalise liaison between OPAG-PWS ICT (through Chair ET/SPII) and OPAG-DPFS ICT through identification of a focal point in each team. | Chair ET-SPII | 31/7/16 | Done |
| 2 | Formally contact Chair OPAG DPFS to engage OPAG-PWS in the process of revision of GDPFS Manual by revewing the revised version and providing relevant content. | Chair ET/SPII | 31/7/16 | Done |

Responsible Team Member Key:

Armstrong Y.C. Cheng (AC)

John L. Guiney (JG)

Haleh Kootval (HK)

William J. Lang (WL)

Yoshiro Tanaka (YT)

Eugene Vasilyev (EV)

_____________