| World Meteorological Organization Commission for Basic Systems Management Group, seventeenth Session Geneva, 27 February - 1 March 2017 | [CBS-MG-17]/Doc. 4.1 |
| --- | --- |
|  | Submitted by: Anthony Rea 17.Feb.2017 DRAFT 1 |

# Proposed Membership of the OPAG-IOS teams

# and their work plans

### SUMMARY

This document provides proposal from the OPAG IOS Chair, Anthony Rea (Australia), and co-Chair, Jochen Dibbern (Germany) concerning (i) the membership of the OPAG-IOS Expert Teams and (ii) their work plans.

### DECISIONS/ACTIONS REQUIRED:

The Management Group is invited to decide on the following:

- Membership of the OPAG-IOS Teams

- Work plans of the OPAG-IOS Teams

### REFERENCES:

- Approved documents of CBS-16, and particularly document CBS-16-d05-10(1)-CBS-WORKING-STRUCTURE-approved_en.docx

### ANNEXES:

- Proposed membership of the OPAG-IOS teams

- Proposed work plans of the OPAG-IOS teams

# __________

## Annex 1

### Proposed membership of the OPAG-IOS Expert Teams

| Team | Name | Country | Role |
| --- | --- | --- | --- |
| ICT-IOS | REA | Australia | Chair |
| ICT-IOS | DIBBERN | Germany | Co-chair |
| ICT-IOS | MICHELSON | Canada | Core member |
| ICT-IOS | ANDERSON | ECMWF | Core member |
| ICT-IOS | ENGLISH | ECMWF | Core member |
| ICT-IOS | ALLAIX | France | Core member |
| ICT-IOS | PARK | Korea, Rep | Co-coordinator |
| ICT-IOS | GOLDSTRAW | United Kingdom | Core member |
| ICT-IOS | TURTON | United Kingdom | Associate member |
| ICT-IOS | BOUKABARA | United States | Associate member |
| ICT-IOS | KAYE | United States | Core member |
| ICT-IOS | MARSHALL | United States | Core member |
| IPET-OSDE | ANDERSSON | ECMWF | Chairperson |
| IPET-OSDE | KLINK | Germany | Co-chairperson |
| IPET-OSDE | LI | China | Core member |
| IPET-OSDE | FAHMY | Egypt | Core member |
| IPET-OSDE | MUNRO | EUMETSAT | Associate member |
| IPET-OSDE | SATO | Japan | Core member |
| IPET-OSDE | PARK | Korea, Rep | Core member |
| IPET-OSDE | LARSEN | SAON | Associate member |
| IPET-OSDE | EYRE | United Kingdom | Core member |
| IPET-OSDE | GOLDSTRAW | United Kingdom | Core member |
| IPET-OSDE | BOUKABARA | United States | Associate member |
| IPET-OSDE | MARSHALL | United States | Associate member |
| IPET-OSDE | MA | China | Associate member |
| IPET-SUP | ENGLISH | ECMWF | Chairperson |
| IPET-SUP | FANG | China | Co-Chairperson |
| IPET-SUP | DIOP KANE | Senegal | Core member |
| IPET-SUP | DONOHO | USA | Core member |
| IPET-SUP | JANG | Korea, Rep | Core member |
| IPET-SUP | OMORI | Japan | Core member |
| IPET-SUP | MACHADO | Brazil | Core member |
| IPET-SUP | ADRIYANTO | Indonesia | Core member |
| IPET-SUP | KEOGH | United Kingdom | Core member |
| IPET-SUP | ECKMAN | United Sates | Associate member |
| IPET-SUP | WANNOP | EUMETSAT | Associate member |
| IPET-SUP | TBD |  | Associate member |
| IPET-SUP | HOLLMANN | Germany | Associate member |
| IPET-SUP | TBD |  | Associate member |
| ET-SAT | KAYE | United States | Chairperson |
| ET-SAT | KIM | Korea, Rep | Co-Chairperson |
| ET-SAT | KROUPNIK | Canada | Core member |
| ET-SAT | LU | China | Core member |
| ET-SAT | PETITEVILLE | ESA | Core member |
| ET-SAT | BOJKOV | EUMETSAT | Core member |
| ET-SAT | ALBERT | Germany | Core member |
| ET-SAT | YOSHIDA | Japan | Core member |
| ET-SAT | KUNIMATSU | Japan | Core member |
| ET-SAT | OKI | Japan | Core member |
| ET-SAT | USPENSKIY | Russia | Core member |
| ET-SAT | BOUKABARA | USA | Core member |
| ET-SAT | TBD | India |  |
| ET-SAT | TBD | France |  |
| ET-ABO | MARSHALL | United States | Chairperson |
| ET-ABO | MOUHTADI | Morocco | Vice-chair |
| ET-ABO | RIVABEN | Argentina | Core member |
| ET-ABO | BODY | Australia | Core member |
| ET-ABO | CERQUEIRA | Brazil | Associate member |
| ET-ABO | CAO | China | Associate member |
| ET-ABO | BESSON | France | Associate member |
| ET-ABO | HOFF | Germany | Associate member |
| ET-ABO | FORD | HMEI | Associate member |
| ET-ABO | HENDRICKS | HMEI | Associate member |
| ET-ABO | JACOBS | HMEI | Associate member |
| ET-ABO | LEE | Hong Kong, China | Core member |
| ET-ABO | SONNABEND | IATA | Associate member |
| ET-ABO | HALSEY | ICAO | Associate member |
| ET-ABO | KUMAGAI | Japan | Core member |
| ET-ABO | GROOTERS | Netherlands | Core member |
| ET-ABO | VAN DER MEULEN | Netherlands | Associate member |
| ET-ABO | PELACHO | Spain | Associate member |
| ET-ABO | STRINGER | United Kingdom | Core member |
| ET-ABO | TYSON | United Kingdom | Associate member |
| ET-ABO | FARRAR | United States | Associate member |
| ET-ABO | STRAHAN | United States | Associate member |
| ET-ABO | ILBOUDO | Senegal | Associate member |
| ET-ABO | MOSETLHO | South Africa | Associate member |
| ET-SBO | GOLDSTRAW | United Kingdom | Chairperson |
| ET-SBO | PEI | China | Co-Chairperson |
| ET-SBO | MONNIK | Australia | Core member |
| ET-SBO | LUCAS | Brazil | Associate member |
| ET-SBO | TORRES | Chile | Core member |
| ET-SBO | GUO | China | Associate member |
| ET-SBO | ABDALLAH | Egypt | Associate member |
| ET-SBO | HUUSKONEN | Finland | Core member |
| ET-SBO | KLEINERT | Germany | Core member |
| ET-SBO | MAERZ | Germany | Associate member |
| ET-SBO | HAYASHI | Japan | Associate member |
| ET-SBO | IRIE | Japan | Associate member |
| ET-SBO | OTA | Japan | Associate member |
| ET-SBO | KARANJA | Kenya | Core member |
| ET-SBO | CHO | Korea, Rep | Associate member |
| ET-SBO | NOUNI | Morocco | Associate member |
| ET-SBO | HASHMI | Pakistan | Associate member |
| ET-SBO | KATS | Russian Fed. | Associate member |
| ET-SBO | RUFFIEUX | Switzerland | Core member |
| ET-SBO | INGLEBY | United Kingdom | Associate member |
| ET-SBO | OAKLEY | United Kingdom | Core member |
| ET-SBO | SCHMITT | United States | Associate member |
| ET-SBO | SZYNBORSKI | United States | Associate member |
| SG-RFC | ALLAIX | France | Chairperson |
| SG-RFC | FRANC | United States | Co-Chairperson |
| SG-RFC | HETTRICK | Australia | Core member |
| SG-RFC | HODGE | Australia | Associate member |
| SG-RFC | SANTOS | Brazil | Core member |
| SG-RFC | FOURNIER | Canada | Associate pending replacement nomination |
| SG-RFC | ZHANG | China | Core member |
| SG-RFC | NIE | China | Associate member |
| SG-RFC | FAHMY | Egypt | Associate member |
| SG-RFC | MARELLI | ESA | Associate member |
| SG-RFC | TRISTANT | EUMETNET | Core member |
| SG-RFC | DREIS | EUMETSAT | Core member |
| SG-RFC | MOHR | Germany | Associate member |
| SG-RFC | POOL | HMEI | Associate member |
| SG-RFC | SALMIVAARA | HMEI | Associate member |
| SG-RFC | NOZDRIN | ITU | Core member |
| SG-RFC | KAJIWARA | Japan | Associate member |
| SG-RFC | KARANJA | Kenya | Core member |
| SG-RFC | CHOI | Korea, Rep | Core member ? |
| SG-RFC | AZAROV | Russian Fed. | Associate member |
| SG-RFC | DASHKOV | Russian Fed. | TBD |
| SG-RFC | USPENSKY | Russian Fed. | TBD |
| SG-RFC | GORBE | South Sudan | Associate member |
| SG-RFC | HERVO | Switzerland | Core member |
| SG-RFC | PETSUWAN | Thailand | Associate member |
| SG-RFC | BEWLEY | United Kingdom | Core member |
| SG-RFC | METZNER | United States | Associate member |
| SG-RFC | GIBSON | United States | Interested expert |
| SG-RFC | HUNEYCUTT | United States | Interested expert |
| SG-RFC | LECK | United States | Interested expert |
| SG-RFC | VON DEAK | United States | Associate member |
| C-SEIS | BOUKABARA | United States | Co-coordinator |
| C-SEIS | PARK | Korea, Rep | Co-coordinator |
| C-MAR | TURTON | Jonathan | Co-ordinator |

__________

### Annex 2

### PROPOSED WORK PLANS OF THE OPAG-IOS EXPERT TEAMS AND COORDINATORS

### FOR THE COMING CBS INTER-SESSIONAL PERIOD 2017-2020

- Updated Work Plan with status for the Inter Programme Expert Team on Observing System Design and Evolution (IPET-OSDE) FOR THE PERIOD 2012-2016

(Workplan as decided by IPET-OSDE-1, April 2014; status of tasks as of 16 April 2016)

| Id | Priority | Objective | Outcome | Deliverable | Activity | Leader | Due | Other ETs | Effort | Status Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | To contribute to the implementation of WIGOS, including WIGOS Manual, and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by Congress XVI, and then ICG-WIGOS | Relevant WIP activities addressed | Meeting | Chairperson IPET-OSDE | Ongoing | ICG-WIGOS, IPET-WIFI |  | OND Principles included in WIGOS Manual OND Guidance addressing the Principles almost complete Vision 2040 Space well developed and reviewed at IPET-OSDE-2 Vision 2040 Surface preparation initiated at IPET-OSDE-2 |
| 2 | 1 | Survey and collate user requirements for observations for WMO and WMO-sponsored programmes | Review and update WMO database of observational user requirements, through Points of Contact for application areas. | OSCAR/ Requirements up-to-date | Review by FPs | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; PoCs regularly contacted for updates |
| 3 | 1 | Survey and collate observing systems capabilities for surface-based and space-based systems that are components or candidate components of WIGOS | Review and update WMO database of observing system capabilities, in collaboration with other OPAG IOS ETs and other Technical Commissions as appropriate. | OSCAR/Space & OSCAR/Surface up to date | Review by Members (coordination via NFPs) | Chairperson IPET-OSDE | Ongoing / Annual review | ICT-IOS, ET-ABO, ET-SBO, ICG-WIGOS/TT-WMD |  | Ongoing for space-based, and recorded in OSCAR/Space. Ongoing for surface-based through new developments with OSCAR/Surface, to be used when operational in 2016 |
| 4 | 1 | Maintain Rolling Review of Requirements (RRR) for observations in several application areas, using subject area experts, including appropriate liaison with Technical Commissions and programmes and co-sponsored programmes (e.g. CAS, JCOMM, CAeM, CAgM, CHy, CCl, GCOS, GFCS, and GCW) | Continue RRR process for the listed application areas and expand to new areas as required: review and update as necessary Statements of Guidance on the extent to which present/ planned observing system capabilities meet user requirements, through Points of Contact on application areas. | Statements of Guidance for all Application Areas | Application Area Contact Points; Meeting | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; some SoG reviewed. Overall review done by IPET-OSDE-1 and IPET-OSDE-2. Some updates to user requirements and SoGs made during the period. |
| 5 | 1 | Prepare and maintain reviews of observation impact studies undertaken by NWP centres and provide information for consideration by IPET-OSDE and OPAG-IOS | Rapporteurs on Impact Studies and NWP experts, review results of impact studies relevant to the evolution of observing systems. Organize and hold next NWP Impact Studies Workshop in 2016. | Findings of impact studies | Impact studies | Rapporteurs on Scientific Evaluation of Impact Studies undertaken by NWP Centres | 2016: workshop |  |  | Report of the 5th NWP “Impact” workshop (Sedona, 2012) published. Ongoing: recent findings, and proposals for new impact studies discussed at IPET-OSDE1 and approved by CBS Ext.(2014). Preparations well advanced for 6th workshop (Shanghai, May 2016) |
| 6 | 1 | Promote CBS activities in support of GCOS goals | Review the implications of the progress on the GCOS Implementation Plan for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCOS | Meeting | Rapporteur on GCOS matters | 2013 2016 |  |  | Ongoing interactions between IPET-OSDE Chairperson and GCOS. |
| 7 | 1 | Promote CBS activities in support of GFCS goals | Review the implications of the GFCS IP for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GFCS | Meeting | Chairperson IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE1. GCOS/GFCS interaction encouraged. |
| 8 | 1 | Promote CBS activities in support of GCW goals | Review the implications for the activities of CBS of the GCW developments, including the GCW Implementation Strategy, and the Cryosphere theme report for the IGOS partnership. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCW | Meeting | Chairperson IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE-1 and IPET-OSDE-2. CBS CWP submitted to the AOS1. |
| 9 | 1 | Monitor progress and actions by Members and partner Organizations per the approved Implementation Plan for the Evolution of the Global Observing Systems (EGOS-IP), fully responding to the “Vision for the GOS in 2025”,and promote activities in support of progress | Seek feedback from National Focal Points, Expert Teams, relevant Technical Commissions, and other groups on the implementation of EGOS-IP, and keep the EGOS-IP progress report up to date. Initiate and monitor activities which promote progress. | EGOS-IP progress report | Survey with FPs, TCs; meeting | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing. Feedback against the new EGOS-IP requested to the NFPs for 2013, 2014 and 2015. 2013 input reviewed at IPET-OSDE-1. 2014 and 2015 input reviewed by IPET-OSDE-2. New feedback by EGOS-IP action “owners” reviewed by IPET-OSDE-2. |
| 10 | 1 | Propose guidance regarding observing system network design principles | Draft guidance document on network design (to be further discussed at IPET-OSDE-1 in 2014) | Guidance document on network design | Meeting | Chairperson IPET-OSDE | End 2013 2014 |  |  | 2 workshops organized in Nov. 2013 and Feb. 2015. OND Principles approved with WIGOS Manual. Draft OND guidance almost complete. |

- Work Plan for the Sub-Group on Radio-Frequency Coordination (SG-RFC) for the period 2012-2015

| Id | Priority | Objective | Outcome | Deliverable(s) | Activity | Leader | Due | Other ETs | Effort |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Represent WMOs needs at ITU WRC-12. | Radio Regulations ensure WMO observing and communications systems have uninterrupted access to necessary frequencies | WMO Position Paper on WRC-12 Agenda. | Support to secretariat representation at WRC-12 | Chairperson | Jan/Feb 2012 |  |  |
| 2 | 1 | WRC-15 | Radio Regulations ensure WMO observing and communications systems have uninterrupted access to necessary frequencies | WMO Position Paper on WRC-15 Agenda. | - Representation at Conference Preparations meetings for WRC-15 - Preparation of a preliminary position paper on WRC-15 agenda, maintain and update for final submission to WRC-15. - Organization of studies and submission of contributions supporting the WMO position at ITU-R Working Parties involved) - Participation in ITU-R study groups and JTG - Representation of WMO at ITU-R Regional Organizations meetings. | Chairperson | Various times throughout the period. WRC-15 scheduled for Nov 2015 |  |  |
| 3 | 1 | Monitor and address Spectrum issues related to meteorological and Earth exploration applications/systems | Present and future meteorological and related needs for spectrum are met |  | - Participation in ITU-R study groups and working parties. - Participate in national activities in support of ITU-R processes. | - Chairperson - Focal points (See Attachment 1) | On-going | - ICT-IOS, - ET-WISC, - ET-CTS - CIMO |  |
| 4 | 2 | Establishment of a WMO Strategy on radio-frequency protection for meteorology and related environmental | Improved ability of NMHSs to ensure national spectrum policies incorporate meteorological and related needs for spectrum | Strategy paper for consideration of EC-65 | - Preparation of draft strategy - Review by SG-RFC and submission to CBS - Consideration by EC-65 | - Secretariat - Chairperson - Secretariat | EC-65 |  |  |
| 5 | 2 | Establishment of a guide for NMHS on participation in radio frequency coordination processes | Improved ability of NMHSs to participate in national and international spectrum policy and management processes | Guide to Participation in Radio-frequency Coordination (WMO-No. 1159) | - Prepare draft guide, - Review by SG-RFC - Review by CBS - Review by Cg-17 - Publish | - Secretariat - Chairperson - Secretariat | EC-65 |  |  |
| 6 | 2 | Monitor ITU-R regional organization activities and represent WMO issues where possible | Regional organizations decisions take into account WMO needs | Regional organization representation for WMO | - Bring to the attention of SG-RFC any regional issues affecting WMO and vice versa | - Focal points, see attachment 3 | Ongoing |  |  |
| 7 | 2 | Cooperation with other organizational entities such as GEO, SFCG, CGMS | WMO needs are taken into consideration of other environmental related activities | Participation and representation of WMO | - Bring to the attention of SG-RFC any issues from other earth observations related organizations affecting WMO and vice versa | - Focal points, see attachment 2 | Ongoing |  |  |

- DRAFT Work Plan for the Expert Team on Surface-Based Observing Systems (ET-SBO) for the period 2017 – 2020 (Version 0.1)

(Generated at ICT-IOS-9 April 2016)

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Helping WIGOS Succeed Agreed ToR: Contribute to the implementation of WIGOS by undertaking those tasks assigned to it by the OPAG IOS Chairperson as part of the WIGOS pre-operational phase priority activities. Notes: ToR Changes made by CBS-MG and supported by ET. Activities will support the 5 priority areas for WIGOS defined by Congress. | Address relevant items of WIGOS Pre-Operational Phase Activities assigned to ET-SBO, details to be forthcoming during work plan period, see individual task sheets for more detail. | Ongoing | Co-ordination Lead: Chairperson ET-SBO for overall delivery with lead and contributors for each task identified |  |  |
| 1.1 |  | Detailed tasks | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 2. | Improving Technical Documents Draft ToR: Develop and update relevant elements of the WIGOS Regulatory and Guidance materials, including the Manual and the Guide to the GOS and incorporating WIGOS data quality monitoring system recommendations. Notes: Changes proposed to ToR to remove specific reference to technologies in the ToR. | Review and update the technical regulations and associated guidance material. Priority technologies to be defined early in new intersessional period but will definitely include Radiosonde and will likely include lightning detection systems & GNSS systems. | In time for WIGOS approvals mechanism | Task Lead: TBD Task Contributors: TBD |  |  |
| 2.1 |  | Update the Radiosonde regulatory material currently recorded in the Manual on the GOS WMO No.544 and Guide to the GOS WMO No. 488 | Draft material generated 2017 and passed to WIGOS EB in 2018 | Task Lead: TBD Task Contributors: TBD |  | 30 working days to be assigned to this task. |
| 2.2 |  | Other tasks to be identified | TBD | Task Lead: TBD Task Contributors: TBD |  | Likely to include a review of lightning detection systems and GNSS based measurement systems |
| 3. | Status of Implementation # Draft ToR: Monitor and assess the status of operational and planned surface-based observing systems and ensure this is adequately described in OSCAR/Surface and associated observational metadata databases. Notes: Minor modification of ToR to reflect the use of OSCAR/Surface as the official source of observational metadata. | Establish and implement a review mechanism to enable regular assessment of the status of the ET-SBO technology implementation, as described in OSCAR/Surface can be reported against assigned EGOS-IP Actions | Ongoing / Annual review | Task Lead: TBD Task Contributors: TBD |  | 60 days provisionally allocated to this action. |
| 3.1 |  | Make recommendations to OSCAR/Surface ‘maintenance and development’ team for the further enhancement of OSCAR/Surface to improve its functionality | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 3.2 |  | Further tasks to be confirmed | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 4. | Meeting User Requirements Agreed ToR: In collaboration with IPET-OSDE, assess the contribution of current and planned SBO systems to meeting user requirements for all Application Areas; Notes: No change to ToR. | Provide expert input and reports to IPET-OSDE on the suitability of each observing system in meeting each Application areas requirement | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 4.1 |  | # Contribute to the evolutionary development of the Vision for the GOS, being led by IPET-OSDE | 2017 and | Task Lead: TBD Task Contributors: TBD |  |  |
| 5. | Delivering the EGOS-IP # Draft ToR: Facilitate the delivery of those EGOS-IP actions identified as priorities by OPAG-IOS, including the identification as appropriate of the technical support required for project implementation plans, including guidance materials, technical specifications and project documentation for resource mobilization activities; # Notes: ToR now includes new CBS-MG ToR 8 | Identify EGOS-IP Actions for ET-SBO as lead co-ordination body. |  | Co-ordination Lead: TBD |  |  |
| 5.1 |  | # Co-ordinate delivery of EGOS-IP Action G10 – Optimizing the global radiosonde schedule See EGOS-IP G10 for details. | Ongoing | Task Lead: (Tim Oakley) Task Contributors: (RongKang Yang) |  | # Significant consultation with RAs, TCs etc. needed. |
| 5.2 |  | Other actions to be identified. | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 6. | Promoting Best Practice # Agreed ToR: Monitor the status of operational networks of SBO systems, promote best practice among WMO Members and provide advice on operational matters; Note: No change to ToR from previous inter-sessional period. | # Establish an improved source for technical advice documents “The SBO Portal” as part of the WIGOS Information Resource. Populate Portal with national best practice documents. Respond to requests for advice from members | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 6.1 |  | Specific tasks to be included at a later date. | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 8. | Reporting Progress to ICT-IOS # Agreed ToR: Provide advice and support to the Chairperson of OPAG-IOS on the implementation of the WIGOS pre-operational phase priority activities. Note: This is the reporting mechanism | # Deliver progress reports and recommendations for changes to operating practices, technical documents and guidance to ICT-IOS during inter-sessional period. | 2018 and 2020 | Task Lead: Chairperson ET-SBO |  |  |
| 8.1 |  | Deliver contribution to ICT-IOS-10. | April 2018 (tbc) | # Chairperson ET-SBO with review of report by all members. |  |  |

- CBS EXPERT TEAM ON AIRCRAFT-BASED OBSERVING SYSTEMS (ET-ABO) WORK PLAN FOR THE PERIOD 2017-2020

(Version D4, July 2016 - Based on Terms of Reference Proposed by ICT-IOS-9, April 2016)

| ToR | Task | Deliverable/Activity | Comment |
| --- | --- | --- | --- |
| (a) Under the direction of the Chairperson of the OPAG-IOS, undertake tasks and provide advice on and support for the implementation of the WIGOS framework and the priority activities of the WIGOS pre-operational phase. | - Provide representation to relevant IGC-WIGOS work groups, including the TT-WMD and TT-WRM - Contribute to OSCAR/Surface development & implementation. - Contribute to WIGOS ABO regulatory and guidance development. | - Representation at meetings and input to work programs of work groups - Contribution to OSCAR/Surface ABO metadata development - Publication and maintenance of the Guide to Aircraft-Based Observations. | Ongoing from previous inter-sessional period. |
| (b) In collaboration with the CIMO Expert Team on Aircraft-based Observations, manage and coordinate the Aircraft Based Observations (ABO) programme, including the development and implementation of the ET-ABO work plan and the budget for the corresponding expenditure of the AMDAR Trust Fund in line with its ToR. | - Hold two sessions of ET-ABO with a possible joint session held with ET-AO. - Harmonize annual work plan and budget for ET-ABO with ET-AO annual work plan and budget. - Maintain the ABOP Strategy and Implementation Plan. | - Final report of sessions - Progress with work program - Work plans and budgets - Maintained ABOP Strategy and Implementation Plan (A-SIP). | Ongoing from previous inter-sessional period. |
| (c) Provide technical and scientific resources in support of further development of the Aircraft Based Observing System, assist in ABO training and outreach activities and contribute to the CIMO ET-AO Activities. | - Assist in the development and coordination of regional and national ABO programmes. - Undertake regional workshops on ABO/AMDAR. - Contribute to national and regional ABO & AMDAR development projects. - Under the WMO/EUMETNET MoU, collaborate with E-AMDAR on regional and global development of AMDAR. - Promote ABO and AMDAR to relevant aviation bodies. - Promote ABO and AMDAR through the AMDAR newsletter. - Maintain and enhance the COMET AMDAR Learning module. | - Development of ABOP Regional Implementation Plans. - Establishment of RA ABO work groups. - Two regional workshops held annually. - Employ part-time ABOP Development Officer under E-AMDAR Program. - Establishment of AMDAR programmes in Kenya, Ethiopia and Morocco. - Two projects with FLYHT for trial of the AFIRS system in regions I and V. - Expanded operational use of WMO AMDAR Onboard Software for B777. - Attendance at and reports from AEEC Data-Link User Forum meetings bi-annually. - Two volumes annually of the WMO AMDAR Observing System Newsletter. - Possible update of the COMET AMDAR Learning Module focussing on data use. | Ongoing from previous inter-sessional period. |
| (d) Oversee and assist in the maintenance, enhancement and optimization of the Aircraft Based Observing System, including the AMDAR observing system, in line with the requirements of Members and the recommendations and actions of the EGOS-IP. | - Liaise with ICAO on data management of ICAO aircraft observations, including input to the ICAO Met. Panel. - Work with national and regional programmes to optimize ABO reporting and coverage. | - Establishment of WAFC authorized regional ABO data processing centres. - Improved QC of AIREP and ADS-C aircraft observations. - Ongoing supplementary AMDAR data provision, particularly focussed on Region I. | Ongoing from previous inter-sessional period. |
| (e) Coordinate the development and maintenance of the ABO quality monitoring system as a component of the WIGOS Data Quality Monitoring System. | - Establish the ABO Global Data Centre (GDC-ABO). - Enhance data monitoring and QC in collaboration with monitoring and lead center. | - Agreement with NOAA on operation of GDC-ABO. - GDC-ABO operational. - Enhanced functions of GDC-ABO. - Introduce daily monitoring and reporting by Lead Centre for ABO. | Ongoing from previous inter-sessional period. |
| (f) Coordinate with and report to the work groups of CBS and other Technical Commissions as appropriate and relevant to the ET-ABO work plan and as directed by the Chairperson of the OPAG-IOS. | - Represent ABO and contribute to the activities of CBS/IPET-OSDE. | - Representative attendance at IPET-OSDE sessions. | Ongoing from previous inter-sessional period. |
| (g) Provide advice and support to the Chairperson of OPAG-IOS, and report on all activities relevant to its Terms of Reference. | - Report to sessions of ICT-IOS. | - Representative of ET-ABO to attend and provide report to ICT-IOS sessions. | Ongoing from previous inter-sessional period. |

- PROposed Expert Team on Satellite Systems (ET-SAT) Work PROGRAMME for the period 2016-2019 (LAST UPDATE: 29 FEB 2016)

(this work plan is to be presented to the OPAG-IOS Chairperson, then updated by the Team to assign responsibilities, deadlines, and indicate status)

| No. | Task (ToR) | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Assess and document, in the framework of the WMO Rolling Review of Requirements, the actual and planned capabilities of operational and R&D satellites constituting the space-based component of WIGOS and their adequacy to meet the WMO requirements for satellite data and products. This will be achieved in considering the information provided by participating agencies as well as the outcome of CGMS and CEOS, including e.g. the progress of CEOS constellations; the feedback from WMO should be communicated to CGMS and CEOS. | Guide the development and maintenance of OSCAR/Space Serve as beta-testing group of OSCAR/Space version 2.0 Perform gap analyses (i) in the CGMS baseline, (ii) against the Vision of the GOS/ WIGOS space-based component systems, to inform WMO Members on a regular basis Perform gap analyses in areas of specific or evolving interest to WMO, such as hydrology, atmospheric composition, space weather | Continuous 1 April – 31 May 2016 | ET-SAT and WMO Secretariat | WMO Secretariat to release OSCAR/Space Version 2.0 in May 2016 Options for long-term maintenance of OSCAR/ Space under development |  |
| 2 | Provide technical advice on implementation of integrated satellite observing systems | Guide the development of the Vision of the WIGOS space-based component systems in 2040, in coordination with IPET-OSDE; Support WMO information needs on satellite systems, including CBS and WMO Programme guidance material (e.g., Manual on WIGOS) | Continuous until late 2018, as required Continuous | ET-SAT and WMO SP Secretariat | Developed first draft of Vision, for discussion by CM-13 and IPET-SUP-2 (Jan/Feb 2016) |  |
| 3 | Assess progress of R&D and demonstration satellite systems, and identify opportunities and/or problem areas concerning satellite technology and plans | Present and discuss novel sensor, mission or space technology concepts and their potential utility to WMO Discuss radio frequency issues and highlight them to the SG-RFC as appropriate Keep abreast of developments regarding private operators of basic satellite systems, and provide guidance to WMO | 2016 onwards | ET-SAT and WMO SP Secretariat |  |  |
| 4 | Coordinate with IPET-SUP and other relevant CBS teams on satellite related matters | Joint session on Vision 2040 and OSCAR/Space Version 2.0 in 2017 | 3-7 April 2017 (tentative) |  |  |  |

- New proposed Work Plan for the Inter Programme Expert Team on Satellite Utilization and Products for the period 2016-2019

| No. | Task (ToR) | Deliverable/Activity | Due | Responsible | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Monitor the progress of satellite data availability and use by WMO Members, related issues and expectations, with the aim to publish findings and recommendations in a WMO document | Quadrennial survey Analysis of responses Findings and recommendations Advice to Regional Associations on follow-up actions WMO document for publication Next survey | Feb 2016 Apr 2016 Apr 2016 Sep 2016 Jan 2017 2020 | WMO SP Secretariat and IPET-SUP | Survey carried out in the period 8 Feb – 15 Mar 2016; More than 400 responses received |
| 2 | Provide advice and support to the development and implementation of WIGOS, from a satellite user's perspective and coordinate with ET-SAT and IPET-OSDE on the evolution of the space-based component of Global Observing Systems; | Contribute to the evolving EGOS IP, the Manual on the GOS, WIGOS Regulatory Material, the Vision for the WIGOS component systems 2040, and the WIGOS IP Support WMO Programmes (both operational and research) in their satellite data and product-related needs, with focus on marine meteorology and oceanography, climate, hydrology, and atmospheric composition | As required Continuous | IPET - SUP and WMO SP Secretariat | IPET-SUP provided input to the initial Vision for the WIGOS space-based components in 2040 |
| 3 | Initiate and promote activities to improve the availability of operational and R&D satellite data according to user needs, monitor these activities in close coordination with the relevant working groups, regional associations and with WIS activities | Promote the development and maintenance of Regional Satellite Data Requirements Groups and satellite data requirements in all Regions, as appropriate Promote activities to advance the Satellite Data Dissemination Strategy: - Information and guidance - Data requirements - Enhancing data availability - Description and Registration - Dissemination and User Access Encourage and assist Regional Satellite Data Requirements Coordination Groups in carrying out Region-based user surveys | 2016 onwards | IPET - SUP and WMO SP Secretariat, with assistance from Int'l WGs IGDDS and RARS implementation groups | Regional Groups active in RA I, II, III/IV Development of progress indicators ongoing, including for DBNet Ongoing |
| 4 | Review present and future R&D satellite data and products including their availability and potential applications, and provide advice with a view of increased utilization by WMO Members; | Review of relevance and availability of R&D satellite data, based on global/regional requirements; Strengthen interaction with R&D agencies in the area of altimetry, soil moisture, precipitation, and climate Make recommendations for improved availability, information and training, especially for developing countries Collect case studies to demonstrate the value of satellite data for hydrological applications | Ongoing 2017 | IPET - SUP and WMO SP Secretariat | Participation in relevant fora, focus WMO survey on these topics and interaction with CEOS as appropriate |
| 5 | Review, and assist in addressing, the needs of WMO Members and regional associations for information regarding satellite capabilities and in particular access to and utilization of satellite data and products; | Maintain OSCAR/Space and a list of satellite data access points, processing and analysis software tools on WMO webpage Support activities to achieve user readiness for the new generation of meteorological satellites, including the development of guidelines for users and satellite operators | 2016/2 (continued yearly) | IPET - SUP and WMO SP Secretariat | Best practices for achieving user readiness (Reference User Readiness Project) published; Next-generation of OSCAR/ Space, Product Access Guide and SATURN online |
| 6 | Promote development and harmonization of satellite data and products responding to WMO Members’ needs, and develop and update relevant elements of the WIGOS regulatory and guidance materials, including the Manual and the Guide to the GOS and the WIGOS quality data monitoring system | Provide guidance to Sustained Co-ordinated Processing of Environmental Satellite Data (SCOPE) for Climate Monitoring as a key contribution to the architecture for climate monitoring from space. Continue to develop and promote the SCOPE-Nowcasting, initiative and support the work of the coordinating group. Collaborate with WIGOS, WIS and CGMS on developing data format and metadata standards, as well as procedures for monitoring satellite data availability and quality Promote the exploitation of commonalities of instruments on the new meteorological satellites in generation of product and training material | 2016-2018 | IPET - SUP and WMO SP Secretariat, SCOPE-CM Executive Panel, and SCOPE-Nowcasting Coordination Group | SCOPE-CM IP under review Four Pilot Projects in progress |
| 7 | Keep under review the needs of WMO Members for training in satellite meteorology and related fields, and engage with the Management Group of the Virtual Laboratory for Education and Training in Satellite Meteorology (VLab) to address these needs, towards full utilization of satellite data from operational and R&D satellites, in accordance with the 2015–2019 Virtual Laboratory Training Strategy; | Regular reviews of the VLab status, activities and plans (training resources, courses, meetings, newsletters); Support existing VLab CoEs and the establishment of new ones; Provide guidance to meet users' needs, especially from less developed Members and for the next generation of satellites; Explore training partnerships Contribution to training resource development | Continuous activity | VLMG, WMO SP Office and IPET-SUP | VLab 2015-2019 strategy updated Events on user preparedness planned Joint COSPAR/VLab training event on space weather planned for August 2016 |
| 8 | Holding joint and/or overlapping meetings with ET-SAT as appropriate, to facilitate interaction between users and providers of satellite systems, data and products | Plan for joint session of ET-SAT and IPET-SUP in 2017 | 2017/4 | WMO SP Office |  |
| 9 | Coordinate with ET-SAT with a view to making recommendations and receiving input on matters, such as the exchange, management, and archiving of satellite data and products, radio frequency utilization, as well as education and training and other appropriate capacity-building measures related to the use of satellite data in all WMO Programmes, including support to resource mobilization activities; | As above Exchange meeting reports Engage with ET-SAT on specific issues as required, such as developing the Vision for WIGOS space-based component systems in 2040 | Ongoing | WMO SP Office, IPET-SUP Chairperson |  |
| 10 | Coordinate with WMO Technical Commissions and Programmes, including co-sponsored Programmes, activities related to satellite utilization and products, through ex-officio membership on the Team | Increase engagement with WMO Technical Commissions, including JCOMM, CCl and CHy Develop and implement communications strategy | Ongoing 2015/4 | IPET-SUP Chairperson and WMO SP Office IPET-SUP Chairperson |  |

_____________