| OPAG ISS Operating Plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Activities | Deliverable/Activity | Due | Responsible | OPAG-ISS Tasks |
| OPAG-ISS01 | WIS monitoring | Implement WIS monitoring at GISCs Extend standardization to DCPC and NC data flow and availability, and report on traffic associated with programmes, eg emergency messages (Tsunami) through WIS. | Q2 2016, Q4 2017 Q2 2018 | OPAG ISS | ET-WISC01 ET-CTS07 |
| OPAG-ISS02 | WIS implementation at national level | Training and capacity development based on competencies coordinated by RA working groups and GISCs Improve regulatory materials and guidelines | Q2 2018 Q2 2016, Q2 2018 | OPAG ISS | ET-WISC09, 10 IPET-CM02, 03, 08 |
| OPAG-ISS03 | WIS operation | Procedure to ensure the consistency and completeness of Metadata catalogue. Mechanism to ensure that GISC cache contain all global data exchanged during the past 24h Recommendation for the implementation of data policies management Procedure to ensure the efficient exchange of information through the WIS network Procedures for intra-GISCs communication in case of events such as: scheduled updates, maintenance work Recommended GISC-GISC backup procedures Contribute to SATCOM | Q4 2018 Q4 2018 Q2 2018 Q4 2018 Q4 2017 Q4 2017 Ongoing | OPAG ISS | ET-WISC03, 04, 05, 07, 08 ET-CTS09 IPET-CM07 |
| OPAG-ISS04 | WIS usability | Harmonisation of user interface to help user to find data from any GISCs Harmonization of user registration parameters Improve WIS discovery metadata | Q2 2018 Q4 2017 Q2 2016, Q2 2018 | OPAG ISS | IPET-DD01, 02 ET-WISC02, 06 |
| OPAG-ISS05 | Centres compliance | Finalise certification of candidate WIS centres Undertake re-certification of WIS centres Review and refine WIS certification requirement Generalise centres certification process to cover other Commissions and Programmes Provide guidance and training on audit certification Coordinate other centres certification Monitor compliance on information exchange | Q4 2017 Q2 2019 Q4 2017 Q4 2017 Q4 2018 Ongoing Ongoing | OPAG ISS | ET-WISC11, ET-CAC01, 02,03,04,05 IPET-CM05, 06, 09 |
| OPAG-ISS06 | WIS security | Implement WIS security incident response process Updated version of the guide on IT security and the guide on VPN via the Internet | Q2 2016, Q2 2018 Q2 2016, Q2 2018 | OPAG ISS | ET-CTS03, 04, 05 |
| OPAG-ISS07 | WIS strategy and evolution | Consolidate WIS 2.0 stakeholder requirements Develop the implementation plan for WIS 2.0 Partnership with TC, RAs and external organisation, eg GEO, ICAO, IOC Investigate technical, management and financial options for establishing WIS 2.0 Monitor and explore new technologies and emerging data issues and prototype and pilot where applicable | Q4 2017 Q4 2018 Ongoing |  | ET-CTS01, 02, 06, 08 ET-WISC09, 10 TT-eWIS01, 02 |
| OPAG-ISS08 | Effective information management | Review available information management practices and develop appropriate standards and practices in information management Incorporate standards and practices for information management under WIS Part C Update to WIS competencies in the area of information management Review, maintain and develop WMO data representations and supporting vocabularies, together with associated guidance Review, maintain and develop WIS Discovery metadata, together with associated guidance | Q4 2017 Q4 2018 Q4 2018 Fast track: Bi-annually; In session:, Q4 2016, Q4 2018 Fast track: Bi-annually; In session:, Q4 2016, Q4 2018 |  | TT-IM01, 02, 03 IPET-CM01, 04, 05, 07, 08 IPET-DD03, 04 |