ANNEX IV

APPROVED WORK PLANS OF THE CBS TEAMS

1.	OPAG IOS

- Updated Work Plan with status for the Inter Programme Expert Team on Observing System Design and Evolution (IPET-OSDE) FOR THE PERIOD 2012-2016

(Workplan as decided by IPET-OSDE-1, April 2014; status of tasks as of 16 April 2016)

| Id | Priority | Objective | Outcome | Deliverable | Activity | Leader | Due | Other ETs | Effort | Status Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | To contribute to the implementation of WIGOS, including WIGOS Manual, and provide relevant advice and support to the chairperson of ICT-IOS | Address relevant items of WIGOS Implementation Activities agreed by Congress XVI, and then ICG-WIGOS | Relevant WIP activities addressed | Meeting | Chairperson IPET-OSDE | Ongoing | ICG-WIGOS, IPET-WIFI |  | OND Principles included in WIGOS Manual OND Guidance addressing the Principles almost complete Vision 2040 Space well developed and reviewed at IPET-OSDE-2 Vision 2040 Surface preparation initiated at IPET-OSDE-2 |
| 2 | 1 | Survey and collate user requirements for observations for WMO and WMO-sponsored programmes | Review and update WMO database of observational user requirements, through Points of Contact for application areas. | OSCAR/ Requirements up-to-date | Review by FPs | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; PoCs regularly contacted for updates |
| 3 | 1 | Survey and collate observing systems capabilities for surface-based and space-based systems that are components or candidate components of WIGOS | Review and update WMO database of observing system capabilities, in collaboration with other OPAG IOS ETs and other Technical Commissions as appropriate. | OSCAR/Space & OSCAR/Surface up to date | Review by Members (coordination via NFPs) | Chairperson IPET-OSDE | Ongoing / Annual review | ICT-IOS, ET-ABO, ET-SBO, ICG-WIGOS/TT-WMD |  | Ongoing for space-based, and recorded in OSCAR/Space. Ongoing for surface-based through new developments with OSCAR/Surface, to be used when operational in 2016 |
| 4 | 1 | Maintain Rolling Review of Requirements (RRR) for observations in several application areas, using subject area experts, including appropriate liaison with Technical Commissions and programmes and co-sponsored programmes (e.g. CAS, JCOMM, CAeM, CAgM, CHy, CCl, GCOS, GFCS, and GCW) | Continue RRR process for the listed application areas and expand to new areas as required: review and update as necessary Statements of Guidance on the extent to which present/ planned observing system capabilities meet user requirements, through Points of Contact on application areas. | Statements of Guidance for all Application Areas | Application Area Contact Points; Meeting | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing; some SoG reviewed. Overall review done by IPET-OSDE-1 and IPET-OSDE-2. Some updates to user requirements and SoGs made during the period. |
| 5 | 1 | Prepare and maintain reviews of observation impact studies undertaken by NWP centres and provide information for consideration by IPET-OSDE and OPAG-IOS | Rapporteurs on Impact Studies and NWP experts, review results of impact studies relevant to the evolution of observing systems. Organize and hold next NWP Impact Studies Workshop in 2016. | Findings of impact studies | Impact studies | Rapporteurs on Scientific Evaluation of Impact Studies undertaken by NWP Centres | 2016: workshop |  |  | Report of the 5th NWP “Impact” workshop (Sedona, 2012) published. Ongoing: recent findings, and proposals for new impact studies discussed at IPET-OSDE1 and approved by CBS Ext.(2014). Preparations well advanced for 6th workshop (Shanghai, May 2016) |
| 6 | 1 | Promote CBS activities in support of GCOS goals | Review the implications of the progress on the GCOS Implementation Plan for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCOS | Meeting | Rapporteur on GCOS matters | 2013 2016 |  |  | Ongoing interactions between IPET-OSDE Chairperson and GCOS. |
| 7 | 1 | Promote CBS activities in support of GFCS goals | Review the implications of the GFCS IP for the activities of CBS. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GFCS | Meeting | Chairperson IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE1. GCOS/GFCS interaction encouraged. |
| 8 | 1 | Promote CBS activities in support of GCW goals | Review the implications for the activities of CBS of the GCW developments, including the GCW Implementation Strategy, and the Cryosphere theme report for the IGOS partnership. Bring relevant issues to the attention of the IPET-OSDE | RRR consistent with GCW | Meeting | Chairperson IPET-OSDE | 2016 |  |  | Relevant activities reviewed at IPET-OSDE-1 and IPET-OSDE-2. CBS CWP submitted to the AOS1. |
| 9 | 1 | Monitor progress and actions by Members and partner Organizations per the approved Implementation Plan for the Evolution of the Global Observing Systems (EGOS-IP), fully responding to the “Vision for the GOS in 2025”,and promote activities in support of progress | Seek feedback from National Focal Points, Expert Teams, relevant Technical Commissions, and other groups on the implementation of EGOS-IP, and keep the EGOS-IP progress report up to date. Initiate and monitor activities which promote progress. | EGOS-IP progress report | Survey with FPs, TCs; meeting | Chairperson IPET-OSDE | Ongoing / Annual review |  |  | Ongoing. Feedback against the new EGOS-IP requested to the NFPs for 2013, 2014 and 2015. 2013 input reviewed at IPET-OSDE-1. 2014 and 2015 input reviewed by IPET-OSDE-2. New feedback by EGOS-IP action “owners” reviewed by IPET-OSDE-2. |
| 10 | 1 | Propose guidance regarding observing system network design principles | Draft guidance document on network design (to be further discussed at IPET-OSDE-1 in 2014) | Guidance document on network design | Meeting | Chairperson IPET-OSDE | End 2013 2014 |  |  | 2 workshops organized in Nov. 2013 and Feb. 2015. OND Principles approved with WIGOS Manual. Draft OND guidance almost complete. |

- Work Plan for the Sub-Group on Radio-Frequency Coordination (SG-RFC) for the period 2012-2015

| Id | Priority | Objective | Outcome | Deliverable(s) | Activity | Leader | Due | Other ETs | Effort |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Represent WMOs needs at ITU WRC-12. | Radio Regulations ensure WMO observing and communications systems have uninterrupted access to necessary frequencies | WMO Position Paper on WRC-12 Agenda. | Support to secretariat representation at WRC-12 | Chairperson | Jan/Feb 2012 |  |  |
| 2 | 1 | WRC-15 | Radio Regulations ensure WMO observing and communications systems have uninterrupted access to necessary frequencies | WMO Position Paper on WRC-15 Agenda. | - Representation at Conference Preparations meetings for WRC-15 - Preparation of a preliminary position paper on WRC-15 agenda, maintain and update for final submission to WRC-15. - Organization of studies and submission of contributions supporting the WMO position at ITU-R Working Parties involved) - Participation in ITU-R study groups and JTG - Representation of WMO at ITU-R Regional Organizations meetings. | Chairperson | Various times throughout the period. WRC-15 scheduled for Nov 2015 |  |  |
| 3 | 1 | Monitor and address Spectrum issues related to meteorological and Earth exploration applications/systems | Present and future meteorological and related needs for spectrum are met |  | - Participation in ITU-R study groups and working parties. - Participate in national activities in support of ITU-R processes. | - Chairperson - Focal points (See Attachment 1) | On-going | - ICT-IOS, - ET-WISC, - ET-CTS - CIMO |  |
| 4 | 2 | Establishment of a WMO Strategy on radio-frequency protection for meteorology and related environmental | Improved ability of NMHSs to ensure national spectrum policies incorporate meteorological and related needs for spectrum | Strategy paper for consideration of EC-65 | - Preparation of draft strategy - Review by SG-RFC and submission to CBS - Consideration by EC-65 | - Secretariat - Chairperson - Secretariat | EC-65 |  |  |
| 5 | 2 | Establishment of a guide for NMHS on participation in radio frequency coordination processes | Improved ability of NMHSs to participate in national and international spectrum policy and management processes | Guide to Participation in Radio-frequency Coordination (WMO-No. 1159) | - Prepare draft guide, - Review by SG-RFC - Review by CBS - Review by Cg-17 - Publish | - Secretariat - Chairperson - Secretariat | EC-65 |  |  |
| 6 | 2 | Monitor ITU-R regional organization activities and represent WMO issues where possible | Regional organizations decisions take into account WMO needs | Regional organization representation for WMO | - Bring to the attention of SG-RFC any regional issues affecting WMO and vice versa | - Focal points, see attachment 3 | Ongoing |  |  |
| 7 | 2 | Cooperation with other organizational entities such as GEO, SFCG, CGMS | WMO needs are taken into consideration of other environmental related activities | Participation and representation of WMO | - Bring to the attention of SG-RFC any issues from other earth observations related organizations affecting WMO and vice versa | - Focal points, see attachment 2 | Ongoing |  |  |

- DRAFT Work Plan for the Expert Team on Surface-Based Observing Systems (ET-SBO) for the period 2017 – 2020 (Version 0.1)

(Generated at ICT-IOS-9 April 2016)

| No. | Task | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Helping WIGOS Succeed Agreed ToR: Contribute to the implementation of WIGOS by undertaking those tasks assigned to it by the OPAG IOS Chairperson as part of the WIGOS pre-operational phase priority activities. Notes: ToR Changes made by CBS-MG and supported by ET. Activities will support the 5 priority areas for WIGOS defined by Congress. | Address relevant items of WIGOS Pre-Operational Phase Activities assigned to ET-SBO, details to be forthcoming during work plan period, see individual task sheets for more detail. | Ongoing | Co-ordination Lead: Chairperson ET-SBO for overall delivery with lead and contributors for each task identified |  |  |
| 1.1 |  | Detailed tasks | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 2. | Improving Technical Documents Draft ToR: Develop and update relevant elements of the WIGOS Regulatory and Guidance materials, including the Manual and the Guide to the GOS and incorporating WIGOS data quality monitoring system recommendations. Notes: Changes proposed to ToR to remove specific reference to technologies in the ToR. | Review and update the technical regulations and associated guidance material. Priority technologies to be defined early in new intersessional period but will definitely include Radiosonde and will likely include lightning detection systems & GNSS systems. | In time for WIGOS approvals mechanism | Task Lead: TBD Task Contributors: TBD |  |  |
| 2.1 |  | Update the Radiosonde regulatory material currently recorded in the Manual on the GOS WMO No.544 and Guide to the GOS WMO No. 488 | Draft material generated 2017 and passed to WIGOS EB in 2018 | Task Lead: TBD Task Contributors: TBD |  | 30 working days to be assigned to this task. |
| 2.2 |  | Other tasks to be identified | TBD | Task Lead: TBD Task Contributors: TBD |  | Likely to include a review of lightning detection systems and GNSS based measurement systems |
| 3. | Status of Implementation # Draft ToR: Monitor and assess the status of operational and planned surface-based observing systems and ensure this is adequately described in OSCAR/Surface and associated observational metadata databases. Notes: Minor modification of ToR to reflect the use of OSCAR/Surface as the official source of observational metadata. | Establish and implement a review mechanism to enable regular assessment of the status of the ET-SBO technology implementation, as described in OSCAR/Surface can be reported against assigned EGOS-IP Actions | Ongoing / Annual review | Task Lead: TBD Task Contributors: TBD |  | 60 days provisionally allocated to this action. |
| 3.1 |  | Make recommendations to OSCAR/Surface ‘maintenance and development’ team for the further enhancement of OSCAR/Surface to improve its functionality | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 3.2 |  | Further tasks to be confirmed | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 4. | Meeting User Requirements Agreed ToR: In collaboration with IPET-OSDE, assess the contribution of current and planned SBO systems to meeting user requirements for all Application Areas; Notes: No change to ToR. | Provide expert input and reports to IPET-OSDE on the suitability of each observing system in meeting each Application areas requirement | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 4.1 |  | # Contribute to the evolutionary development of the Vision for the GOS, being led by IPET-OSDE | 2017 and | Task Lead: TBD Task Contributors: TBD |  |  |
| 5. | Delivering the EGOS-IP # Draft ToR: Facilitate the delivery of those EGOS-IP actions identified as priorities by OPAG-IOS, including the identification as appropriate of the technical support required for project implementation plans, including guidance materials, technical specifications and project documentation for resource mobilization activities; # Notes: ToR now includes new CBS-MG ToR 8 | Identify EGOS-IP Actions for ET-SBO as lead co-ordination body. |  | Co-ordination Lead: TBD |  |  |
| 5.1 |  | # Co-ordinate delivery of EGOS-IP Action G10 – Optimizing the global radiosonde schedule See EGOS-IP G10 for details. | Ongoing | Task Lead: (Tim Oakley) Task Contributors: (RongKang Yang) |  | # Significant consultation with RAs, TCs etc. needed. |
| 5.2 |  | Other actions to be identified. | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 6. | Promoting Best Practice # Agreed ToR: Monitor the status of operational networks of SBO systems, promote best practice among WMO Members and provide advice on operational matters; Note: No change to ToR from previous inter-sessional period. | # Establish an improved source for technical advice documents “The SBO Portal” as part of the WIGOS Information Resource. Populate Portal with national best practice documents. Respond to requests for advice from members | Ongoing | Task Lead: TBD Task Contributors: TBD |  |  |
| 6.1 |  | Specific tasks to be included at a later date. | TBD | Task Lead: TBD Task Contributors: TBD |  |  |
| 8. | Reporting Progress to ICT-IOS # Agreed ToR: Provide advice and support to the Chairperson of OPAG-IOS on the implementation of the WIGOS pre-operational phase priority activities. Note: This is the reporting mechanism | # Deliver progress reports and recommendations for changes to operating practices, technical documents and guidance to ICT-IOS during inter-sessional period. | 2018 and 2020 | Task Lead: Chairperson ET-SBO |  |  |
| 8.1 |  | Deliver contribution to ICT-IOS-10. | April 2018 (tbc) | # Chairperson ET-SBO with review of report by all members. |  |  |

- CBS EXPERT TEAM ON AIRCRAFT-BASED OBSERVING SYSTEMS (ET-ABO) WORK PLAN FOR THE PERIOD 2017-2020

(Version D4, July 2016 - Based on Terms of Reference Proposed by ICT-IOS-9, April 2016)

| ToR | Task | Deliverable/Activity | Comment |
| --- | --- | --- | --- |
| (a) Under the direction of the Chairperson of the OPAG-IOS, undertake tasks and provide advice on and support for the implementation of the WIGOS framework and the priority activities of the WIGOS pre-operational phase. | - Provide representation to relevant IGC-WIGOS work groups, including the TT-WMD and TT-WRM - Contribute to OSCAR/Surface development & implementation. - Contribute to WIGOS ABO regulatory and guidance development. | - Representation at meetings and input to work programs of work groups - Contribution to OSCAR/Surface ABO metadata development - Publication and maintenance of the Guide to Aircraft-Based Observations. | Ongoing from previous inter-sessional period. |
| (b) In collaboration with the CIMO Expert Team on Aircraft-based Observations, manage and coordinate the Aircraft Based Observations (ABO) programme, including the development and implementation of the ET-ABO work plan and the budget for the corresponding expenditure of the AMDAR Trust Fund in line with its ToR. | - Hold two sessions of ET-ABO with a possible joint session held with ET-AO. - Harmonize annual work plan and budget for ET-ABO with ET-AO annual work plan and budget. - Maintain the ABOP Strategy and Implementation Plan. | - Final report of sessions - Progress with work program - Work plans and budgets - Maintained ABOP Strategy and Implementation Plan (A-SIP). | Ongoing from previous inter-sessional period. |
| (c) Provide technical and scientific resources in support of further development of the Aircraft Based Observing System, assist in ABO training and outreach activities and contribute to the CIMO ET-AO Activities. | - Assist in the development and coordination of regional and national ABO programmes. - Undertake regional workshops on ABO/AMDAR. - Contribute to national and regional ABO & AMDAR development projects. - Under the WMO/EUMETNET MoU, collaborate with E-AMDAR on regional and global development of AMDAR. - Promote ABO and AMDAR to relevant aviation bodies. - Promote ABO and AMDAR through the AMDAR newsletter. - Maintain and enhance the COMET AMDAR Learning module. | - Development of ABOP Regional Implementation Plans. - Establishment of RA ABO work groups. - Two regional workshops held annually. - Employ part-time ABOP Development Officer under E-AMDAR Program. - Establishment of AMDAR programmes in Kenya, Ethiopia and Morocco. - Two projects with FLYHT for trial of the AFIRS system in regions I and V. - Expanded operational use of WMO AMDAR Onboard Software for B777. - Attendance at and reports from AEEC Data-Link User Forum meetings bi-annually. - Two volumes annually of the WMO AMDAR Observing System Newsletter. - Possible update of the COMET AMDAR Learning Module focussing on data use. | Ongoing from previous inter-sessional period. |
| (d) Oversee and assist in the maintenance, enhancement and optimization of the Aircraft Based Observing System, including the AMDAR observing system, in line with the requirements of Members and the recommendations and actions of the EGOS-IP. | - Liaise with ICAO on data management of ICAO aircraft observations, including input to the ICAO Met. Panel. - Work with national and regional programmes to optimize ABO reporting and coverage. | - Establishment of WAFC authorized regional ABO data processing centres. - Improved QC of AIREP and ADS-C aircraft observations. - Ongoing supplementary AMDAR data provision, particularly focussed on Region I. | Ongoing from previous inter-sessional period. |
| (e) Coordinate the development and maintenance of the ABO quality monitoring system as a component of the WIGOS Data Quality Monitoring System. | - Establish the ABO Global Data Centre (GDC-ABO). - Enhance data monitoring and QC in collaboration with monitoring and lead center. | - Agreement with NOAA on operation of GDC-ABO. - GDC-ABO operational. - Enhanced functions of GDC-ABO. - Introduce daily monitoring and reporting by Lead Centre for ABO. | Ongoing from previous inter-sessional period. |
| (f) Coordinate with and report to the work groups of CBS and other Technical Commissions as appropriate and relevant to the ET-ABO work plan and as directed by the Chairperson of the OPAG-IOS. | - Represent ABO and contribute to the activities of CBS/IPET-OSDE. | - Representative attendance at IPET-OSDE sessions. | Ongoing from previous inter-sessional period. |
| (g) Provide advice and support to the Chairperson of OPAG-IOS, and report on all activities relevant to its Terms of Reference. | - Report to sessions of ICT-IOS. | - Representative of ET-ABO to attend and provide report to ICT-IOS sessions. | Ongoing from previous inter-sessional period. |

- PROposed Expert Team on Satellite Systems (ET-SAT) Work PROGRAMME for the period 2016-2019 (LAST UPDATE: 29 FEB 2016)

(this work plan is to be presented to the OPAG-IOS Chairperson, then updated by the Team to assign responsibilities, deadlines, and indicate status)

| No. | Task (ToR) | Deliverable/Activity | Due | Responsible | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Assess and document, in the framework of the WMO Rolling Review of Requirements, the actual and planned capabilities of operational and R&D satellites constituting the space-based component of WIGOS and their adequacy to meet the WMO requirements for satellite data and products. This will be achieved in considering the information provided by participating agencies as well as the outcome of CGMS and CEOS, including e.g. the progress of CEOS constellations; the feedback from WMO should be communicated to CGMS and CEOS. | Guide the development and maintenance of OSCAR/Space Serve as beta-testing group of OSCAR/Space version 2.0 Perform gap analyses (i) in the CGMS baseline, (ii) against the Vision of the GOS/ WIGOS space-based component systems, to inform WMO Members on a regular basis Perform gap analyses in areas of specific or evolving interest to WMO, such as hydrology, atmospheric composition, space weather | Continuous 1 April – 31 May 2016 | ET-SAT and WMO Secretariat | WMO Secretariat to release OSCAR/Space Version 2.0 in May 2016 Options for long-term maintenance of OSCAR/ Space under development |  |
| 2 | Provide technical advice on implementation of integrated satellite observing systems | Guide the development of the Vision of the WIGOS space-based component systems in 2040, in coordination with IPET-OSDE; Support WMO information needs on satellite systems, including CBS and WMO Programme guidance material (e.g., Manual on WIGOS) | Continuous until late 2018, as required Continuous | ET-SAT and WMO SP Secretariat | Developed first draft of Vision, for discussion by CM-13 and IPET-SUP-2 (Jan/Feb 2016) |  |
| 3 | Assess progress of R&D and demonstration satellite systems, and identify opportunities and/or problem areas concerning satellite technology and plans | Present and discuss novel sensor, mission or space technology concepts and their potential utility to WMO Discuss radio frequency issues and highlight them to the SG-RFC as appropriate Keep abreast of developments regarding private operators of basic satellite systems, and provide guidance to WMO | 2016 onwards | ET-SAT and WMO SP Secretariat |  |  |
| 4 | Coordinate with IPET-SUP and other relevant CBS teams on satellite related matters | Joint session on Vision 2040 and OSCAR/Space Version 2.0 in 2017 | 3-7 April 2017 (tentative) |  |  |  |

- New proposed Work Plan for the Inter Programme Expert Team on Satellite Utilization and Products for the period 2016-2019

| No. | Task (ToR) | Deliverable/Activity | Due | Responsible | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Monitor the progress of satellite data availability and use by WMO Members, related issues and expectations, with the aim to publish findings and recommendations in a WMO document | Quadrennial survey Analysis of responses Findings and recommendations Advice to Regional Associations on follow-up actions WMO document for publication Next survey | Feb 2016 Apr 2016 Apr 2016 Sep 2016 Jan 2017 2020 | WMO SP Secretariat and IPET-SUP | Survey carried out in the period 8 Feb – 15 Mar 2016; More than 400 responses received |
| 2 | Provide advice and support to the development and implementation of WIGOS, from a satellite user's perspective and coordinate with ET-SAT and IPET-OSDE on the evolution of the space-based component of Global Observing Systems; | Contribute to the evolving EGOS IP, the Manual on the GOS, WIGOS Regulatory Material, the Vision for the WIGOS component systems 2040, and the WIGOS IP Support WMO Programmes (both operational and research) in their satellite data and product-related needs, with focus on marine meteorology and oceanography, climate, hydrology, and atmospheric composition | As required Continuous | IPET - SUP and WMO SP Secretariat | IPET-SUP provided input to the initial Vision for the WIGOS space-based components in 2040 |
| 3 | Initiate and promote activities to improve the availability of operational and R&D satellite data according to user needs, monitor these activities in close coordination with the relevant working groups, regional associations and with WIS activities | Promote the development and maintenance of Regional Satellite Data Requirements Groups and satellite data requirements in all Regions, as appropriate Promote activities to advance the Satellite Data Dissemination Strategy: - Information and guidance - Data requirements - Enhancing data availability - Description and Registration - Dissemination and User Access Encourage and assist Regional Satellite Data Requirements Coordination Groups in carrying out Region-based user surveys | 2016 onwards | IPET - SUP and WMO SP Secretariat, with assistance from Int'l WGs IGDDS and RARS implementation groups | Regional Groups active in RA I, II, III/IV Development of progress indicators ongoing, including for DBNet Ongoing |
| 4 | Review present and future R&D satellite data and products including their availability and potential applications, and provide advice with a view of increased utilization by WMO Members; | Review of relevance and availability of R&D satellite data, based on global/regional requirements; Strengthen interaction with R&D agencies in the area of altimetry, soil moisture, precipitation, and climate Make recommendations for improved availability, information and training, especially for developing countries Collect case studies to demonstrate the value of satellite data for hydrological applications | Ongoing 2017 | IPET - SUP and WMO SP Secretariat | Participation in relevant fora, focus WMO survey on these topics and interaction with CEOS as appropriate |
| 5 | Review, and assist in addressing, the needs of WMO Members and regional associations for information regarding satellite capabilities and in particular access to and utilization of satellite data and products; | Maintain OSCAR/Space and a list of satellite data access points, processing and analysis software tools on WMO webpage Support activities to achieve user readiness for the new generation of meteorological satellites, including the development of guidelines for users and satellite operators | 2016/2 (continued yearly) | IPET - SUP and WMO SP Secretariat | Best practices for achieving user readiness (Reference User Readiness Project) published; Next-generation of OSCAR/ Space, Product Access Guide and SATURN online |
| 6 | Promote development and harmonization of satellite data and products responding to WMO Members’ needs, and develop and update relevant elements of the WIGOS regulatory and guidance materials, including the Manual and the Guide to the GOS and the WIGOS quality data monitoring system | Provide guidance to Sustained Co-ordinated Processing of Environmental Satellite Data (SCOPE) for Climate Monitoring as a key contribution to the architecture for climate monitoring from space. Continue to develop and promote the SCOPE-Nowcasting, initiative and support the work of the coordinating group. Collaborate with WIGOS, WIS and CGMS on developing data format and metadata standards, as well as procedures for monitoring satellite data availability and quality Promote the exploitation of commonalities of instruments on the new meteorological satellites in generation of product and training material | 2016-2018 | IPET - SUP and WMO SP Secretariat, SCOPE-CM Executive Panel, and SCOPE-Nowcasting Coordination Group | SCOPE-CM IP under review Four Pilot Projects in progress |
| 7 | Keep under review the needs of WMO Members for training in satellite meteorology and related fields, and engage with the Management Group of the Virtual Laboratory for Education and Training in Satellite Meteorology (VLab) to address these needs, towards full utilization of satellite data from operational and R&D satellites, in accordance with the 2015–2019 Virtual Laboratory Training Strategy; | Regular reviews of the VLab status, activities and plans (training resources, courses, meetings, newsletters); Support existing VLab CoEs and the establishment of new ones; Provide guidance to meet users' needs, especially from less developed Members and for the next generation of satellites; Explore training partnerships Contribution to training resource development | Continuous activity | VLMG, WMO SP Office and IPET-SUP | VLab 2015-2019 strategy updated Events on user preparedness planned Joint COSPAR/VLab training event on space weather planned for August 2016 |
| 8 | Holding joint and/or overlapping meetings with ET-SAT as appropriate, to facilitate interaction between users and providers of satellite systems, data and products | Plan for joint session of ET-SAT and IPET-SUP in 2017 | 2017/4 | WMO SP Office |  |
| 9 | Coordinate with ET-SAT with a view to making recommendations and receiving input on matters, such as the exchange, management, and archiving of satellite data and products, radio frequency utilization, as well as education and training and other appropriate capacity-building measures related to the use of satellite data in all WMO Programmes, including support to resource mobilization activities; | As above Exchange meeting reports Engage with ET-SAT on specific issues as required, such as developing the Vision for WIGOS space-based component systems in 2040 | Ongoing | WMO SP Office, IPET-SUP Chairperson |  |
| 10 | Coordinate with WMO Technical Commissions and Programmes, including co-sponsored Programmes, activities related to satellite utilization and products, through ex-officio membership on the Team | Increase engagement with WMO Technical Commissions, including JCOMM, CCl and CHy Develop and implement communications strategy | Ongoing 2015/4 | IPET-SUP Chairperson and WMO SP Office IPET-SUP Chairperson |  |

2.	OPAG ISS

| OPAG ISS Work Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| No. | Task | Deliverable/Activity | Due | Responsible |
| ET-WISC01 | Review, further develop and oversee routine WIS monitoring activities | Pilot implementation of WIS monitoring in the operational WIS centres. Proposals on monitoring the time of transmission of emergency messages (Tsunami) through WIS. | Q4 2017 | ET-WISC |
| ET-WISC02 | Harmonization of user interface. | Proposals on the harmonization of user interface functionality to help user find data from any GISCs and improve user experience | Q2 2018 | ET-WISC |
| ET-WISC03 | Improvement of metadata catalogue consistency | Procedure to ensure the consistency and completeness of Metadata catalogue at each GISC | Q4 2018 | ET-WISC |
| ET-WISC04 | Improvement of 24h cache completeness | Mechanism to ensure that GISC cache contain all global data exchanged during the past 24h | Q2 2018 | ET-WISC |
| ET-WISC05 | Implementation of data policies management | Recommendation for Data policies management | Q2 2018 | ET-WISC |
| ET-WISC06 | Harmonization of user registration parameters | Standard WIS authentication and authorization design and candidate implementation solutions. | Q4 2017 | ET-WISC |
| ET-WISC07 | Operational GISCs communication. | Procedures for intra-GISCs communication in case of events such as: scheduled updates, maintenance work, changes in the set WIS-GISC-XXX if members/ organization are added or removed | Q4 2017 | ET-WISC |
| ET-WISC08 | GISC backup procedures | Recommended GISC-GISC backup procedures | Q4 2017 | ET-WISC |
| ET-WISC09 | Review and develop the Manual on WIS (WMO-No 1060), the Guide to WIS (WMO No 1061) and associated informal guidance to better meet the needs of Members, | Proposals on the amendments for the Manual on WIS (WMO-No 1060), the Guide to WIS (WMO No 1061) and associated informal guidance. | Ad hoc | ET-WISC |
| ET-WISC10 | Review WIS competencies related to WIS centre operations and associated training and learning guides, | Proposals on the amendments for WIS competencies. | Ad hoc | ET-WISC |
| ET-CTS01 | WMO IPv6 Initiative | Questionnaire on IPv6 Analysis of the survey Recommendation on potential follow-up activities (eg training) | Q1-2018 and Q1-2020 | ET-CTS (O.Gorwits, I.Glaser) |
| ET-CTS02.1 | Cache in and through the cloud – Phase 1 in collaboration with TT-eWIS | Report on technical, management and financial options for establishing a cloud solution to facilitate the exchange between the GISCs | Q4-2017 | ET-CTS (R.Giraud) |
| ET-CTS02.2 | Cache in and through the cloud – Phase 2 implementation in collaboration with TT-eWIS | Implement the cloud solution to facilitate the exchange between the GISCs | Q2-2020 | ET-CTS |
| ET-CTS03 | Review of the guide on IT security (Publication WMO 1115) | Updated version of the WMO 1115 document | Q1-2018 and Q1-2020 | ET-CTS |
| ET-CTS04 | Review of the guide on VPN via the Internet (Publication WMO 1116) | Updated version of the WMO 1116 document | Q1-2018 and Q1-2020 | ET-CTS |
| ET-CTS05 | WIS emergency security response strategy | Implementation of the proposed security strategy | Q4-2017 | ET-CTS |
| ET-CTS06 | Monitor technological evolution in the area of responsibility such as - Internet of Things and slow speed network (LORA, SIGFOX…) - BigData and Cloud technologies | Reports related experience within members and if required initiate experiments | Q1-2018 and Q1-2020 | ET-CTS |
| ET-CTS07 | Contribute to the WIS Monitoring activity | Propose or assess proposal regarding monitoring solutions for the WIS | Ongoing | ET-CTS |
| ET-CTS08 | Contribute to task GD-11 (Activities for GEOSS) | Technical evaluation of solution such as eduGAIN | Ongoing | Chair of ET-CTS |
| ET-CTS09 | Contribute to SATCOM Forum | Support the organisation of the SATCOM forum and reports to CBS | Ongoing | Chair of ET-CTS |
| IPET-CM01 | Review and maintain the Table Driven Code Forms by defining descriptors, common sequences, data templates and the regulations supporting these, including data representation of regional practices, so they meet the requirements of all Members, WMO Programmes and other concerned international organizations, such as ICAO | Proposed updates to the Manual on Codes for adoption via Fast-track and adoption between CBS sessions | Semi-annually | IPET-CM |
| IPET-CM02 | Review and update guidance to Members and technical commissions on data representation, including national practices, and invite, coordinate and assist Members to validate modified or new data representations |  | Ad-hoc | IPET-CM |
| IPET-CM03 | Review and maintain the Manual on Codes (WMO-No. 306) and associated reference and guidance material as required within the range of responsibilities, and publish these in suitable electronic formats for human and automated use, including codes.wmo.int. | Support to WMO’s publishing of the Manual on Codes Mature version of GRIB Edition 3 based upon the experimental version to be adopted at CBS in 2016 Experimental version of BUFR Edition 5 | Annual CBS 2020 CBS 2020 | IPET-CM |
| IPET-CM04 | Review and develop procedures and guidance to enable the interoperability of metadata and data between WMO standards and formats used within other communities, such as NetCDF, using the WMO Logical Data Model as a tool to achieve this |  | Ad-hoc | IPET-CM |
| IPET-CM05 | Monitor conformance of data exchanged within the WIS and metadata records published to the WIS DAR catalogue with WMO data representation standards for utility and conformance with the guidance and WMO Core Metadata Profile, and develop action plans, including capacity-building, to address issues identified by monitoring |  | Continuous | IPET-CM |
| IPET-CM06 | Monitor progress towards and coordinate actions to implement migration to Table Driven Codes Forms | Annual review of migration status per regional association and of consolidate monitoring status Consolidated review of global migration status based on routine WWW monitoring Advice to Members in support of migration activities Training (to trainers) on table driven code forms | Annually Annually Ad-hoc Ad-hoc | IPET-CM |
| IPET-CM07 | Review and maintain the data designators in abbreviated headings in Manual on the GTS (WMO-No. 386) | Proposed updates to the Manual on the GTS for adoption via Fast-track | Annually | IPET-CM |
| IPET-CM08 | Contribute to the maintenance of WIS competencies related to use of codes and associated training and learning guides and facilitate training | Training material | Annual training attached to IPET meeting | IPET-CM |
| IPET-CM09 | Assist WIGOS Data Quality Monitoring System (WDQMS) in understanding and dealing with erroneous BUFR messages as they are identified by WDQMS | Response to issues as identified | Ad-hoc | IPET-CM |
| IPET-DD01 | Improve relevance of WIS Discovery metadata | WIS users are able to find information on data and services: - User-centred analysis of effectiveness of GISC catalogue search interface - Guidance for GISC/DCPC providers on search interface design - Guidance for metadata authors including assessment of ‘metadata granularity’ - Guidance for metadata tool developers - Guidance on making WIS metadata records discoverable via industry search engines Periodical monitoring of metadata quality in WIS DAR catalogue - Procedures for metadata quality monitoring- including tracking ‘missing’ metadata - Metadata catalogue monitoring tool(s) | Q2 2018 monthly | IPET-DD |
| IPET-DD02 | WMO Core Metadata Profile (WCMP) compatible with community best practice | Releases of WCMP amended to accommodate needs of Members and Programmes (fast-track) Assessment of value to be realised from migration of WCMP to ISO 19115-1:2014 & ISO/TS 19115-3:2016 | Biannual | IPET-DD |
| IPET-DD03 | Extend WMO data model(s) to address additional WMO information exchange requirements | Updates to WIGOS MD Application Schema in support of OSCAR implementation Updates to IWXXM in support of ICAO Annex 3 Amendments 78 and 79 and ICAO SWIM Application Schema (and associated code form) to encode climate station metadata and climate data streams Updated Guidelines on data modelling (reflecting changes to METCE etc.) Guidance regarding use of model-driven code forms available to Members |  | IPET-DD |
| IPET-DD04 | Publish standard vocabularies in support of WMO information exchange requirements | Consistent terminology Definitions and language translations added to WMO Codes Registry WMO data models (e.g. METCE, OPM, IWXXM, WIGOS MD) published as ontology resources within WMO Codes Registry |  | IPET-DD |
| ET-CAC01 | Establish an overall adapted audit process | Prepare new audit cycle and applicable principles....but in view of being generic enough to allow an extrapolation to other areas Define distinct criteria (maturity levels) and metrics that allow a proper assignment to a level | Q4 2017 | ET-CAC |
| ET-CAC02 | Run GISCs certification process | Second round of GISCs audit | Q2 2019 | ET-CAC |
| ET-CAC03 | Coordinate DCPCs and NCs certification | Co-ordinate the certification of NCs and DCPCs | Ad-hoc | ET-CAC |
| TT-IM01 | review available information management practices and develop appropriate standards and practices in information management | Workshop on best practices in information management Guidelines on standards and best practices in information management | Q4 2017 | TT-IM |
| TT-IM02 | incorporate standards and practices for information management under WIS Part C | updated Manual on WIS and Guide to the WIS tacking into account standard in information management | Q4 2018 | TT-IM |
| TT-IM03 | Update to WIS competencies in the area of information management | Proposals on the amendments for WIS competencies related to information management Proposal for training and learning guides | Q4 2018 | TT-IM |
| TT-eWIS01 | Consolidate WIS 2.0 stakeholder requirements | Consolidated stakeholder requirements | Q4 2017 | TT-eWIS |
| TT-eWIS02 | Develop the implementation plan for WIS 2.0 | implementation plan schedule and key deliverables Organisation proposal and associated costs Risk analysis | Q4 2018 | TT-eWIS |

3.	OPAG DPFS

OPAG DPFS KEY OBJECTIVES, MILESTONES AND RECOMMENDATIONS TO CBS-16

| OPAG – DPFS Key Objectives |  |  |  |
| --- | --- | --- | --- |
| 1. Implementation of the revised Manual of the GDPFS (WMO-No. 485) 2. Working with the Steering Group on Seamless GDPFS to develop a Strategy for the future GDPFS 3. Evolution of the GDPFS to facilitate implementation of impact-based forecasting and risk-based warnings |  |  |  |
| Expert Teams | Activities | Milestones |  |
| ICT-DPFS and all ETs | - Implementation of new Manual of GDPFS - Rolling review of user requirements - Cascading forecast process and seamless approach - Review of guidelines on meteorological site assessment of NPP (used to be TN-170) | - 2018 - (S/GDPFS) - (S/GDPFS) - 2018 |  |
| ET-OWFPS | - Use of additional observation types for verification - Develop strategy to exchange of EPS products and guidelines on post-processing (incl. calibration of model output) - Implications throughout forecast chain for high-resolution NWP including data assimilation - Building on existing GDPFS to respond to user requirements (SG-S/GDPFS, ET-IMPACT) for impact-based forecasting and risk-based warnings (in staged approach) | - 2019 - 2020 - 2018 - Wait for requirements |  |
| IPET-OPSLS | - Workshops on Operational Climate Prediction - Guidelines on procedures for generating regional seasonal forecasts - Implementation of sub-seasonal forecasts, including establishment of sub-seasonal GPCs and possibly of an associated lead center. - Designation of LC-NTCP - Develop revised strategies for verification exchange, including for LC-LRFMME multi-model products, real-time verification and support to GSCU - To support emerging requirements of Polar RCCs, revisit the mandatory and highly recommended data requirements for GPCs able to provide forecast information relevant to Polar regions, and revise GPDFS as necessary - Develop mechanisms for WGSIP and S2S project communities to provide feedback on LC-LRFMME products, and access GPC data to advance research efforts. (2018) - Review applications for new GPC candidates for WMO designation and update LC-LRFMME products by incorporating newly designated GPCs in the the multi-model forecast product. | - 2018 - 2018 - 2019 - 2017 - 2018 - 2018 - 2018 - (2017-2018...we are expecting a formal application from DWD to seek formal GPC designation) |  |
| ET-ERA | - Migration from fax to e-mail distribution of RSMC products - Develop and test new products as well as Ensemble and Transfer Coefficient Matrix (TCM) methods for atmospheric transport and dispersion modelling - Continue to develop non-nuclear ERA - Guidelines on usage of non-nuclear ERA products | - 2019 - 2019 - 2019 - 2018 |  |
| SG-SWFDP | - Develop a project summary book after 10-year activities - Expand SWFDP to cover more regions - Support to existing subprojects to Phase IV - Integration with other initiatives such as FFGS | - 2018 - 2019 - 2019 - 2019 |  |
| TT-HUM | - Designation of Centres for operational support to Humanitarian Agencies - Contribute to the development of Global MeteoAlarm System | - 2018 - ???? |  |
| TT-CentreAudit | - Develop the efficient and effective procedure for regular audit of the GDPFS Centres’ compliance - Review WMO Technical Report on GDPFS and NWP Research in consideration with the revision of the Manual and the proposed audit procedure, and propose a revised reporting mechanism using CPDB. | - 2017 - 2018 |  |
| TT-Guide | - Renew the Guide on GDPFS (WMO-No.305) in line with the new revised Manual on GDPFS(WMO-No.485) | - 2019 |  |

4.	OPAG PWSD

ICT/PWS Team Deliverables and Action sheets for the intersessional period 2014/2016

(Updated FEB 2017)

|  | Deliverable 1 (TOR a): Noting the publication of the “WMO Strategy for Service Delivery and its Implementation Plan”, ensure that actions relevant to PWS are carried out |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Initiating the discussion on the re-alignment of the OPAG with the elements of Service Delivery | All ICT Members |  | 6 June 2014 |  | Done |  | Done |  |
| 2. | Review and finalize draft TORs to reflect the re-alignment in 1 above | All ICT/PWS Members |  | Forthcoming ET Meetings |  |  |  | To be Done |  |
| 3. | Present the draft TORs to CBS-16 | OPAG Chair and Secretariat |  | 2016 |  |  |  | To be Done |  |
|  | Deliverable 2 (TOR c): Establish contact with relevant people in other CBS OPAGs, Commissions, etc., as required |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Contact Chairpersons of OPACE III/IV to explore possible collaboration | Chairperson |  | June 2012 |  | Closed |  | Closed |  |
| 2. | Contact representatives of CHy to explore possible collaboration | Chairperson |  | June 2012 |  | Closed |  | Closed |  |
|  | Deliverable 3 (TORs c and d): Facilitate the development of one or a number of “one-stop-shops” for the provision of advice and assistance to the Humanitarian Response Community |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Finalize the Report of the ICTT and circulate as required | Chairperson/TT |  | End-2012 |  | Completed |  | Completed |  |
| 2. | Prepare an inventory of data and products that are currently available and can be used by Humanitarian Response agencies | Chairperson/TT and WMO Secretariat |  | End-2012 |  | Undertaken through the work of the new CBS TT |  | Completed ?? |  |
| 3. | Compile a listing of PWS-based resources relevant to point 1 above and communicate this to Secretariat DPFS, to include basic warnings, basic public forecasts, SWIC, WWIS, etc. | WMO Secretariat |  | End-2012 |  | Completed |  | Completed |  |
| 4. | Investigate the use of the delivery structure of WMO (RSMCs, RCCs, etc.) and the network of National PWS Focal Points as a resource in the context of national operations of Humanitarian Response agencies | Chairperson/TT and WMO Secretariat |  | End-2012 |  | PWS will organize the work of interpretation of climate outlooks of major global centre(s) for the use by Humanitarian agencies. |  | Ongoing / underway |  |
|  | Deliverable 4 (TOR e): Promote the concept of NMHSs as the Single Official Voice at times of severe/high-impact weather |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Make use of the new “WMO Register of Alerting Authorities” to promote and embed the SOV concept | Chairperson/OPAG and WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 2. | Designate an Expert Advisor to assist with the implementation of CAP at NMHSs and to promote registration of Members in the “WMO Register of Alerting Authorities” | ICT Members/ WMO Secretariat |  | May 2012 |  | Completed |  | Completed |  |
| 3. | Ensure inclusion of this principle in all relevant PWS documents | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
|  | Deliverable 5 (TOR f): Detailed feedback from recipients of targetted PWS activities, such as SWFDP, Learning-Through-Doing (LTD) Projects, training, etc. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Organize the collection and analysis of feedback from training participants and PRs | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 2. | Collate information flowing back from the feedback mechanisms built into the SWFDP and publish on the PWS Website | Co-Chairperson/OPAG and WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |  |
| 3. | Organize the reception of bi-annual reports from Members participating in LTD Projects (through Focal Points where possible) and publish on the PWS Website | WMO Secretariat |  | Ongoing |  | Completed |  | Completed |  |
|  | Deliverable 6 (TOR g): Develop a Competency Framework for PWS Forecasting and Activities. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Draft a Competency Framework relevant to PWS Forecasters and circulate to all ICT Members, ETR Representatives, etc. | Chairperson |  | May 2012 |  | Completed |  | Completed |  |
| 2. | Review draft and provide feedback to WMO Secretariat/ Chairperson | All ICT Members |  | July 2012 |  | Completed |  | Completed |  |
| 3. | Finalize PWS Competency Framework for CBS-Ext.(2014) | WMO Secretariat/ Chairperson |  | September 2014 |  | Completed |  | Completed |  |
|  | Deliverable 7 (TOR h): Develop materials on the Social and Economic Benefits of NMHSs as decided by the RA VI (Europe) Task Team and the World Bank Project. |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Compile and carry out comparative analysis of the impact of the services provided by NMHSs through socio-economic benefits studies | RA VI TT on socio-economic benefits/ World Bank |  | Mid- to end-2012 |  | Ongoing development through the joint WMO/World Bank publication |  | Completed |  |
| 2. | Improve methodologies in SEB studies through concurrent field testing and training as part of specific demonstration/pilot projects as well as on-going NMHSs’ investment programmes | World Bank/ WMO Secretariat |  | End-2012 through 2013 |  | Ongoing development through the joint WMO/World Bank publication |  | Completed |  |
| 3. | Disseminate an authoritative joint WMO-World Bank guidance document | WMO Secreatiat/ World Bank |  | December 2014 |  | Will be disseminated upon publication |  | Completed |  |
|  | Deliverable 8 (TOR i): Future activities as a follow-up to WENS |  |  |  |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |  |
| 1. | Finalize “Concept Note” developed in Shanghai in November 2011 regarding the follow-up activities to WENS | Dr Tang Xu |  | End-2012 |  | Completed |  | Completed |  |
| 2. | Implement follow-up activities as defined in the “Concept Note” | Persons as defined in the “Concept Note” |  | Mid-2013 |  | Closed |  | Closed |  |
| 3. | Prepare publications, etc., as outlined in Section 12 of the WENS Final Report | Shanghai Meteorological Service (SMS) |  | End-2012 |  | Closed |  | Closed |  |
|  | Deliverable 9 (TOR i): Guidelines for Meteorological Support to Olympic Games. |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Review current draft and bring it up-to-date, include the Beijing and Vancouver Games, then provide to IOC and other sporting organizations as appropriate, and publish on PWS Webpage |  | Chairperson ET/SPI/ WMO Secretariat |  | September 2014 |  | Chair ET/SPII to follow-up |  | Ongoing |
|  | Deliverable 10 (TOR j): Strengthen the involvement of the NMHSs’ PWS Focal Points with the work of the OPAG and of the PWS Programme |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Update the list of National PWS Focal Points periodically |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 2. | Request PRs to appoint National PWS Focal Points in Member countries where none are, as yet, identified |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 3. | Carry out a regular survey of the work of the National PWS Focal Points in relation to PWS functions and publish the results |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 4. | Keep National PWS Focal Points fully involved and informed in the activities of the PWS Programme and of the OPAG |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
|  | Deliverable 11 (TOR j): Market and promote the availability and use of PWS material among the NMHS/PWS Community |  |  |  |  |  |  |  |  |
|  | Action(s): |  | Responsible Member(s): |  | Due Date: |  | Status 2014: |  | Status 2016: |
| 1. | Periodically review statistics on the hits and usage of PWS pages on the WMO Website |  | WMO Secretariat |  | Ongoing |  | Ongoing |  | Ongoing |
| 2. | Continue to implement strategies for increasing the ease of access to PWS pages through Google and other search engines |  | WMO Secretariat |  | Ongoing |  | Done |  | Ongoing |

Public Weather Services (PWS) Expert Team on Meeting User Needs in Reducing the Impact of Hydrometeorological Hazards (CBS/OPAG-PWS ET/DPM) AND THE TASK TEAM ON IMPACT OF MULTI-HAZARD PREDICTION AND COMMUNICATION (TT/IMPACT)

(SHANGHAI, CHINA, 27 JUNE-1 JULY 2016)

Team Deliverables

| (Item 6.0)Building on the WMO Guidelines on Multi-hazard Impact-Based Forecast and Warning Services (WMO No. 1150), develop an implementation strategy which describes next actionable steps and evolution Deliverable 1: A stakeholder workshop to plan and design the implementation plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Action(s): |  | Responsible Member(s): | Due Date: | Status: |
| 1. | Identify and contact the stakeholders: DRM rep, Media, Business sector, e.g., utilities, health, transport etc, social science, GFDRR (WBG), and the team members |  | Haleh and Paul | End July 2016 |  |
| 2. | Organize the workshop |  | Haleh | 7-11 (week), Geneva |  |
| 3. | Report to CBS |  |  | End November 2016 |  |
| 4. | Publish the guidance material |  | Haleh and all | End 2017 |  |
| Agneda item 6.1:Training and competencies in impact-based forecasting and warning services Deliverable 2: |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Review of the PWS competecy Framework to identify gaps in the area of IBF | Jennifer Paul |  | End July 2016 |  |
| 2. | Identify existing training materials supporting the development of competencies | Jennifer All |  | End October 2016 |  |
| 3. | At the Workshop review all material on competency and training | Jennifer All |  | End of Workshop |  |
| Agneda item 6.2: Verification and evaluation of benefits of impact-based forecasts and warnings to social and economic sectors Deliverable 3 : Prepare a template based on items identified by the team (Appendix) |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Prepare the template for presentation at the workshop | Paul Jeff |  | End October 2016 |  |
| Agenda item 6.4 : Development/strengthening of relationships with partners, in particular disaster management agencies Deliverable 4: |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Prepare a poster or paper for presentation at CBS | Albrecht Baode Paul |  | Mid November 2016 |  |
| Agenda item 6.5 :Targeted thresholds for users (to be linked to verification item) Deliverable 5: A Framework (template) for cataloguing impact thresholds |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Draft to be developed for inclusion into the implementation plan | Eli To be reviewed by all |  | July 2017 |  |
| Agenda item 6.7 : Science and technology requirements to support impact-based forecasting and warning services Deliverable 6: Keep track of requirements from modellers and research |  |  |  |  |  |
|  | Action(s): | Responsible Member(s): |  | Due Date: | Status: |
| 1. | Establish initial contacts with relevant TCs, NMHSs and WMO Programmes to make sure requirements are collected and taken into consideration (HiWeather, forecasting) | Haleh All |  | End October 2016 |  |

PUBLIC WEATHER SERVICES EXPERT TEAM ON SERVICES AND PRODUCTS InnovaTION AND IMPROVEMENT(cbs/opag-pws ET-SPIi)

Team Deliverables

(Exeter, UK, 11-15 July 2016)

| DELIVERABLE 1: PUBLISH GUIDANCE ON THE ADOPTION OF A SERVICE-DRIVEN APPROACH TO DEVELOPMENT OF NOWCAST SYSTEMS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Actions: | Responsible Member(s): |  | Due Date: |  | Status: |
| 1. | Finalise guidance developed for members at different levels of capability to assist in applying a service driven approach to the development of nowcast systems. | Lead: WL |  | 30/8/16 |  | Done |
| 2. | Circulate final report to all WMO Members, specific groups, organisations involved in development of nowcasting services. | HK |  | 31/12/16 |  | Done |
| DELIVERABLE 2: COORDINATE WITH ET-IMPACT TO DEVELOP GUIDANCE ON USING AND COMMUNICATING UNCERTAINTY IN IMPACT-BASED FORECASTING |  |  |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: |  | Status: |  |
| 1. | Assemble examples and best practice of applying uncertainty information for use in impact-based forecasting, for example translation of percentage probabilities into scenarios for use in decision making for emergency planning and response. | WL | 31/3/17 |  | Ongoing |  |
| 2. | Contribute to ET-IMPACT enhanced guidelines on impact-based forecasting | WL/Chair ET-IMPACT | 31/9/17 |  | Ongoing |  |
| DELIVERABLE 3: ENHANCEMENT OF WWIS AND SWIC WEBSITES |  |  |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: |  | Status: |  |
| 1. | (a) Discuss with ECMWF in acquiring ENS data for use in WWIS forecast compilation; (b) Write to selected PRs requesting forecast of 5-days at least and the use of ECMWF ENS data to fill the gaps otherwise; (c) Develop and launch the revamped WWIS website with observational data with responsive design (d) Develop and launch the revamped MyWorldWeather app for the WWIS (e) Incorporate in WWIS CAP-based warnings currently available on the public domain f) Check availability of CAP/XML warnings from Philippinnes, Meteoalarm, JMA (g) Revamp the SWIC website to incorporate CAP-based warnings (h) Gather information on the status of the development of WMO Alert-hub by NOAA (contact Mr Paese, NOAA/NESDIS) | - AC - HK - AC - AC - AC - HK/WL/YT - AC - JG | - 30/9/16 - 31/12/16 - 31/3/17 - 30/6/17 - 31/12/17 - 30/8/16 - 30/6/18 h) 30/8/16 |  | Ongoing |  |

| DELIVERABLE 4: UTILISATION OF ‘BIG DATA’ FOR MONITORING, IMPACT ASSESSMENT AND DECISION-MAKING IN PWS DELIVERY |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Collect and share (with TT below), through individual contacts, examples of different approaches to use of crowdsourced observations, impacts and behavioural data amongst NMHSs. | AC to lead, all contribute | 31/10/16 | Done |
| 2. | Investigate and propose possible experts as potential members of a Task Team. (AC member) | All | ASAP | Done |
| 3. | Create Task Team from subject-matter experts to study and propose a strategy for PWS in utilisation of Big Data. | Chair ET/SPII | 31/10/16 | Done |
| 4. | Task Team to report on the results of its work to ET/SPII | TT | 30/8/17 | Ongoing |
| DELIVERABLE 5: EXPLOITING PUBLIC/PRIVATE PARTNERSHIPS FOR PUBLIC WEATHER SERVICE DELIVERY |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1. | Create Task Team to work with relevant bodies on formulating a strategy for PWS exploitation of Public Private Partnerships (PPPs), and influence ‘rules of engagement’ for PPPs as proposed by EC 68. | Chair ET/SPII | 30/9/16 | Done |
| 2. | Task Team to report on the results of its work to ET/SPII. |  | 30/4/17 | Ongoing |
| 3. | ET to investigate and propose possible experts and potential members of the Task Team. | All | Asap | Done |
| DELIVERABLE 6: IMPROVING PWS DELIVERY THROUGH LINKING WITH OPAG-DPFS |  |  |  |  |
|  | Actions: | Responsible Member(s): | Due Date: | Status: |
| 1 | Formalise liaison between OPAG-PWS ICT (through Chair ET/SPII) and OPAG-DPFS ICT through identification of a focal point in each team. | Chair ET-SPII | 31/7/16 | Done |
| 2 | Formally contact Chair OPAG DPFS to engage OPAG-PWS in the process of revision of GDPFS Manual by revewing the revised version and providing relevant content. | Chair ET/SPII | 31/7/16 | Done |

Responsible Team Member Key:

Armstrong Y.C. Cheng (AC)

John L. Guiney (JG)

Haleh Kootval (HK)

William J. Lang (WL)

Yoshiro Tanaka (YT)

Eugene Vasilyev (EV)

____________