## Slide 1: OPAG DPFS

## Slide 2: DPFS Recommended Decisions to EC-70
Endorsement of S-GDPFS IP Incl establishing the Project Office
SWFDP
  Accelerate Res 13 Cg-17 implementation
  Establishment of a Trust Funds
  Future Strategy for SWFDP based on overall assessment
Guide to GDPFS (WMO-No. 305) Outlines
Amendments to Tech Regs
  JCOMM
  Designation of New Centres (Nowcasting, WMCS, Svr Wx)
  CHy*
Inf doc – GDPFS/CSIS Integration (provided CBS-MG approval)
GMAS … Fred?

## Slide 3
March 2018 |  | 
9 | Draft v1.0 of the IP ready and distributed to EC SG on S/GDPFS and setting up of a teleconference to obtain their feedback | Done
9-26 | Preparation for TECO/CBS MG | Done
26-29 | Discussion at TECO/CBS | Done
April 2018 |  | 
13 | Feedback from TECO participants and SG on S-GDPFS and others | 
25 April | Draft2 of IP completed | 
May 2018 |  | 
5 | Submission of EC-70 Doc | 
June 2018 |  | 
20-29 | Executive Council 70 - Incl Side event | 
29 - | Lobbying for and securing pilot projects | 
 | Assessment of pilots projects | 
 | Update of IP | 
June 2019 | Congress | 
 | Submission for Congress approval | 
Timeline - S-GDPFS IP