## Draft time table for IWXXM 3.1 and associated work plan

| Date | Event | Work packages/owners |
| --- | --- | --- |
| September 2017 | Last opportunity for changes in requirements | WG-MIE |
| 15 November 2017 | 2.1.1 released (issued for WMO approval procedure) | Top priority Documentation (Foreman); codes.wmo.int entries (Hedley); schematron rules (TOP ABV, BLW, TAF CAVOK rule) (Choy); Second priority examples (more than one message in collect, edit to remove observable properties sub-paths) (Braeckel); TAC to XML guidance update (Braeckel); Third priority codes registry validation tool. (Hedley) . |
| Early December 2017 | Issue document describing intended contents of 3.0 (including simplification, compatibility, Amd 78) and expected time table. |  |
| mid-December 2017 | First draft Amd 78 received | Halsey to provide initial contents of document being prepared for ANC. |
|  | … work on development |  |
| March 2018 | Approval of iwxxm 2.1.1 by President WMO |  |
| 1 April 2018 | Test version (IWXXM 3.0 RC1) available for testing |  |
| …feedback from users |  |  |
| May 2018 | iwxxm 2.1.1 becomes “operational” |  |
| 1st September 2018 (optional release) | IWXXM 3.0RC2 schema available for draft amendments to Manual on Codes |  |
| ….feedback from users | … creation of formal documentation | Secretariat with support from team |
| 1st December 2018 | Formal approval procedure initiated for IWXXM 3.0 RC3. | Includes: schemas schematrons examples Manual on Codes Wiki codes.wmo.int entries |
| ….intergovernmental feedback |  |  |
| March 2019 | Conclusion of formal approval procedure and (subject to the approval). Final IWXXM 3.0 schemas available on the web with draft documentation |  |
| May 2019 | IWXXM 3.0 released |  |
| Nov 2019 | IWXXM 3.0 operational (Amd 78 implementation date) |  |